## Sheet1
EVENT RISK MITIGATION ASSESSMENT FORM
EVENT ID | EVENT NAME | [6 empty] | EVENT MANAGER | ASSESSED BY | ASSESSMENT DATE
| WAI TRI 2021 | [8 empty] | 2021-05-22 11:45
EVENT DESCRIPTION | [8 empty] | APPROVED BY | APPROVAL DATE
Run, Cycle and Swim event
Rate Likelihood and Impact Levels on a scale of 1 to 5 | [5 empty] | ––––––– DO NOT ALTER –––––––
REF ID | HAZARD DESCRIPTION | CONSEQUENCE | IMPACT DESCRIPTION Time, Cost, Performance | PROBABILITY | IMPACT | SCORE | RISK LEVEL | CURRENT RISK MITIGATION AND CONTROL MEASURES |  |  | STATUS | COMPLETION DATE | LEVEL |  |  | RATING MATRIX |  |  |  |  | RATING_NO | RATING_NAME
| Enviroment - Weather | [11 empty] | 1 | LIKELIHOOD | 5 | 5 | 10 | 15 | 20 | 25 | 1 | MINOR | Use safety equipment/clothing/substance to protect against and minimise harm
| Sun | Sunburn, heat stroke, dehydration |  | 2 | 1 | 2 | MINOR | [5 empty] | 2 |  | 4 | 4 | 8 | 12 | 16 | 20 | 2 | MINOR | Use safety equipment/clothing/substance to protect against and minimise harm
| Wind |  |  | 2 | 1 | 2 | MINOR | [5 empty] | 3 |  | 3 | 3 | 6 | 9 | 12 | 15 | 3 | MINOR | Use safety equipment/clothing/substance to protect against and minimise harm
| Rain |  |  | 2 | 1 | 2 | MINOR | [5 empty] | 4 |  | 2 | 2 | 4 | 6 | 8 | 10 | 4 | MODERATE | Limit exposure, adhere to procedures and H&S rules. Erect warnings, provide training, re-eveluate risk score
| Snow |  |  | 3 | 1 | 3 | MINOR | [5 empty] | 5 |  | 1 | 1 | 2 | 3 | 4 | 5 | 5 | MODERATE | Limit exposure, adhere to procedures and H&S rules. Erect warnings, provide training, re-eveluate risk score
| Enviroment - Venue | [14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | MODERATE | Limit exposure, adhere to procedures and H&S rules. Erect warnings, provide training, re-eveluate risk score
| Flat Ground Risks |  |  | 1 | 1 | 1 | MINOR | [7 empty] | RATING MATRIX 5 4 3 2 1: IMPACT | 7 | MODERATE | Limit exposure, adhere to procedures and H&S rules. Erect warnings, provide training, re-eveluate risk score
| Uneven Ground Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 8 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Sealed Vehicle Carriage Way Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 9 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Water Channels/Kerbing Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 10 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Concrete Pavement Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 11 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Unsealed Vehicle Carraige Way Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 12 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Grassed Area Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 13 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Ungrassed Area Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 14 | HIGH | Isolate hazard, erect barriers, fences or other control measures to mitigate, re-eveluate risk score
| Trees, Shrubs, High Vegetation Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 15 | CRITICAL | Substitute hazard for less hazardous thing, substance or work practice, re-evaluate risk score
| Gardens and Surround Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 16 | CRITICAL | Substitute hazard for less hazardous thing, substance or work practice, re-evaluate risk score
| Fixed Sports Equipment Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 17 | CRITICAL | Substitute hazard for less hazardous thing, substance or work practice, re-evaluate risk score
| Raised stage Risks |  |  | 3 | 2 | 6 | MODERATE | [13 empty] | 18 | CRITICAL | Substitute hazard for less hazardous thing, substance or work practice, re-evaluate risk score
| Trailer Risks |  |  | 3 | 2 | 6 | MODERATE | [13 empty] | 19 | CRITICAL | Substitute hazard for less hazardous thing, substance or work practice, re-evaluate risk score
| Rescue Helicopter Pad Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 20 | CRITICAL | Substitute hazard for less hazardous thing, substance or work practice, re-evaluate risk score
| Bridge Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 21 | EXTREME | Stop, remove sources of harm, re-evalute risk score before proceeding
| Fence Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 22 | EXTREME | Stop, remove sources of harm, re-evalute risk score before proceeding
| Open Waterway Risks |  |  | 5 | 2 | 10 | HIGH | [13 empty] | 23 | EXTREME | Stop, remove sources of harm, re-evalute risk score before proceeding
| Building Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 24 | EXTREME | Stop, remove sources of harm, re-evalute risk score before proceeding
| Marquee/Tent Risks |  |  | 3 | 1 | 3 | MINOR | [13 empty] | 25 | EXTREME | Stop, remove sources of harm, re-evalute risk score before proceeding
| Raised Inspection Cover Risks |  |  | 3 | 2 | 6 | MODERATE
TRAFFIC
| Entry/Egress |  |  | 3 | 1 | 3 | MINOR
| Parking |  |  | 3 | 1 | 3 | MINOR | [15 empty] | Nil intervention required
| Throughout Venue/Courses |  |  | 3 | 1 | 3 | MINOR | [15 empty] | Basic intervention/care required
| Emergencies Vehicles |  |  | 3 | 1 | 3 | MINOR | [15 empty] | Intermediate intervention/care required, re-evacuate
| UTILITIES | [21 empty] | Advance intervention/care required, re-evacuate
| Electricity Direct Current (DC) |  |  | 3 | 1 | 3 | MINOR | [15 empty] | Specialist intervention, multi reposnse, secure scene
| Electricity Alternate Current (AC) |  |  | 3 | 1 | 3 | MINOR
| Extension Cords/Multi Boxes Inside |  |  | 3 | 1 | 3 | MINOR
| Extension Cords/Multi Boxes Outside |  |  | 3 | 1 | 3 | MINOR
| Portable Generators |  |  | 3 | 1 | 3 | MINOR
| Water Supply |  |  | 1 | 1 | 1 | MINOR
| Cooking/BBQ Facilities |  |  | 2 | 1 | 2 | MINOR
| Vendors |  |  | 2 | 1 | 2 | MINOR
| Music/Public Address System |  |  | 2 | 1 | 2 | MINOR
| Security |  |  | 2 | 1 | 2 | MINOR
| First Aid |  |  | 2 | 1 | 2 | MINOR
| Waste Management |  |  | 2 | 1 | 2 | MINOR
| Amusement Devices/Equipment |  |  | 1 | 1 | 1 | MINOR
CROWD MANAGEMENT
| Wayfinding Optimisation |  |  | 3 | 2 | 6 | MODERATE
| Queue Management |  |  | 3 | 2 | 6 | MODERATE
| Temporary Closures |  |  | 3 | 1 | 3 | MINOR
| Rapid Deployment |  |  | 2 | 1 | 2 | MINOR
| Visitor Flow Management |  |  | 3 | 1 | 3 | MINOR
| Lost Person |  |  | 3 | 2 | 6 | MODERATE
EVACUATIONS
| Fire Alarm |  |  | 1 | 1 | 1 | MINOR
| Earthquake |  |  | 1 | 1 | 1 | MINOR
| Flooding |  |  | 1 | 1 | 1 | MINOR
| Bomb Threat |  |  | 1 | 1 | 1 | MINOR
| Violent Person |  |  | 1 | 1 | 1 | MINOR
EMERGENCY SERVICES
| Fire |  |  | 1 | 1 | 1 | MINOR
| Police |  |  | 1 | 1 | 1 | MINOR
| Ambulance |  |  | 1 | 1 | 1 | MINOR
| Hospital |  |  | 1 | 1 | 1 | MINOR
HAZARDOUS SUBSTANCES
| Petrol |  |  | 3 | 2 | 6 | MODERATE
| Deisel |  |  | 2 | 1 | 2 | MINOR
| LPG |  |  | 3 | 2 | 6 | MODERATE
| Solvents |  |  | 2 | 1 | 2 | MINOR
| Cleaning Products |  |  | 2 | 1 | 2 | MINOR
CONSUMED/TAKEN SUBSTANCES
| Alcohol - Visitor Supplied |  |  | 2 | 1 | 2 | MINOR
| Drugs - Visitor Supplied |  |  | 2 | 1 | 2 | MINOR
| Fungai |  |  | 1 | 1 | 1 | MINOR
FOOD/BEVERAGES
| Preperation |  |  | 2 | 1 | 2 | MINOR
| Cooking |  |  | 3 | 1 | 3 | MINOR
| Cross Contamination |  |  | 3 | 2 | 6 | MODERATE
| Allergens |  |  | 3 | 3 | 9 | HIGH
STAFFING
| Volunteers |  |  | 2 | 1 | 2 | MINOR
| First Aiders |  |  | 2 | 1 | 2 | MINOR
TRIATHLON
| Run |  |  | 3 | 1 | 3 | MINOR
| Cycle |  |  | 3 | 2 | 6 | MODERATE
| Swim |  |  | 3 | 2 | 6 | MODERATE
INJURY MECHANISIM
| Trip/Fall |  |  | 3 | 2 | 6 | MODERATE
| Collision - Running |  |  | 1 | 1 | 1 | MINOR
| Collision - Cycling |  |  | 3 | 2 | 6 | MODERATE
| Collision - Pedestrian Vs. Vehicle |  |  | 2 | 1 | 2 | MINOR
| Collision - Cycle Vs. Vehicle |  |  | 2 | 1 | 2 | MINOR
| Collision - Vehicle Vs. Vehicle |  |  | 2 | 1 | 2 | MINOR
| Collision - Tree |  |  | 1 | 1 | 1 | MINOR
| Collison - Bridge |  |  | 1 | 1 | 1 | MINOR
| Collision - Fences |  |  | 1 | 1 | 1 | MINOR
| Collision - Animals |  |  | 1 | 1 | 1 | MINOR
| Electrocution |  |  | 3 | 2 | 6 | MODERATE
| Poisioning |  |  | 3 | 2 | 6 | MODERATE
| Drowning |  |  | 3 | 2 | 6 | MODERATE
| Choking |  |  | 3 | 2 | 6 | MODERATE
| Medical Event |  |  | 3 | 3 | 9 | HIGH
| Death |  |  | 1 | 2 | 2 | MINOR
INJURIES
| Skin Irritations |  |  | 3 | 1 | 3 | MINOR
| Abrasions |  |  | 3 | 1 | 3 | MINOR
| Contusions |  |  | 3 | 1 | 3 | MINOR
| Open Wounds |  |  | 3 | 3 | 9 | HIGH
| Sprains/Strains |  |  | 3 | 3 | 9 | HIGH
| Dislocations |  |  | 3 | 3 | 9 | HIGH
| Fractures |  |  | 3 | 3 | 9 | HIGH
| Spinal Injuries |  |  | 2 | 2 | 4 | MODERATE
| Faints |  |  | 3 | 1 | 3 | MINOR
| Strokes |  |  | 3 | 2 | 6 | MODERATE
| Heat Exhaustion |  |  | 2 | 2 | 4 | MODERATE
| Pnuemonia |  |  | 2 | 1 | 2 | MINOR
| Diabetic Emergencies |  |  | 3 | 3 | 9 | HIGH
| Fitting |  |  | 3 | 3 | 9 | HIGH
| Animal Bites |  |  | 3 | 3 | 9 | HIGH
| Anaphalaxis |  |  | 3 | 3 | 9 | HIGH
| Drowning |  |  | 3 | 2 | 6 | MODERATE
| Degloving |  |  | 3 | 2 | 6 | MODERATE
| Overdose |  |  | 2 | 2 | 4 | MODERATE
| Respiratory |  |  | 3 | 3 | 9 | HIGH
| Heart Attack |  |  | 3 | 2 | 6 | MODERATE
| Cardiac Arrest |  |  | 3 | 3 | 9 | HIGH
| Burns |  |  | 3 | 2 | 6 | MODERATE
| Foriegn Objects - Eyes |  |  | 3 | 2 | 6 | MODERATE
| Loss of Limb |  |  | 2 | 2 | 4 | MODERATE
| Impaled |  |  | 1 | 2 | 2 | MINOR