## Forecast Input
Zone | Project Manager | Site Manager | LDP Name | Gang Leader | Ref No | Namex (Triio Works Order) | Street | Town | County | Namex (Local Authority) | PON Number | PON Diameter | Diameter 2 | Tier | Diameter Type | PON Material | Method | Pressure | Pon Category | Pol Concat | Ofgem | Max. Risk Score | Max. Budgeted Units (A) | Contract Output | Pure MR2 | PON Type | DELIVERY_POT | Start Date | End Date | Q3 | Q4 | Total | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | Column1 | Diameter | Pressure | Policies | Tiers | Material | Category | Month |  | 2021-10-03 | 2021-10-10 | 2021-10-17 | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881467 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 6"-7" | 11 | 68.52 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | -11.4 | 0 | -11.4 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | -0.95 | [15 empty] | CI/SIDI LP 6"-7" | 6"-7" | LP | Policy | T1 | DI | CI/SIDI LP 6"-7" |  | CI/SI/DI LP <=3" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881468 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 6"-7" | 6 | 44.53 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 44.52 | 0 | 44.52 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | [15 empty] | CI/SI/DI LP 6"-7" | 6"-7" | LP | Policy | T1 | SI | CI/SI/DI LP 6"-7" |  | CI/SI/DI LP 4"-5" | 5017.315 | 6678.545 | 6436.615 | 6628.895 | 6598.29 | 6176.0643 | 6563.9043 | 6759.7843 | 7018.8843 | 6971.0976 | 6480.6176 | 5748.2676 | 0 | 0 | 6558.62 | 7933.12 | 7992.15 | 7376.08 | 6892.87 | 7436.81 | 8020.83 | 7172.98 | 6724.45 | 5812.25 | 5563.11 | 5257.6 | 5342.14
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881472 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 6"-7" | 21 | 78.02 | MR1 | N | T1 SEED |  | 44424 | 44547 | 3 | 0 | 3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [15 empty] | CI/SI/DI LP 6"-7" | 6"-7" | LP | Policy | T1 | CI | CI/SI/DI LP 6"-7" |  | CI/SI/DI LP 6"-7" | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881473 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 6"-7" | 6 | 158.17 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 130.2 | 0 | 130.2 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | 10.85 | [15 empty] | CI/SI/DI LP 6"-7" | 6"-7" | LP | Policy | T1 | CI | CI/SI/DI LP 6"-7" |  | CI/SI/DI LP 8" | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881478 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 6"-7" | 3 | 47.92 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 47.88 | 0 | 47.88 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | [15 empty] | CI/SI/DI LP 6"-7" | 6"-7" | LP | Policy | T1 | SI | CI/SI/DI LP 6"-7" |  | LMPS | 27.44 | 110.94 | 170.44 | 170.44 | 165.5 | 230.94 | 235.46 | 250.2 | 308.57 | 308.57 | 308.57 | 254.39 | 0 | 0 | 254.39 | 254.39 | 254.39 | 254.39 | 254.39 | 248.68 | 248.68 | 248.68 | 248.68 | 248.68 | 248.68 | 248.68 | 221.24
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881480 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 8" | 8 | 143.64 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 143.64 | 0 | 143.64 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | 11.97 | [15 empty] | CI/SI/DI LP 8" | 8" | LP | Policy | T1 | DI | CI/SI/DI LP 8" |  | T2A | 189.48 | 189.48 | 189.48 | 249.22 | 168.84 | 168.84 | 168.84 | 106.96 | 47.22 | 47.22 | 47.22 | 47.22 | 0 | 0 | 0 | 0 | 0 | 0 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 0 | 39.5
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 636124532 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 1.9 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 2.04 | 0 | 2.04 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5" |  | T2B | 0 | 0.59 | 0.59 | 0.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.85 | 96.85 | 96.85 | 96.85 | 96.85 | 96.85 | 96.85
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 636124533 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 2.88 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 2.88 | 0 | 2.88 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5" |  | 2" ST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 636124534 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 2.4 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 2.4 | 0 | 2.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5" |  | ST LP <=3" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.39 | 5.39 | 5.39 | 5.39 | 5.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 220000309151 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 5.71 | MR1 | N | T1 SECONDARY |  | 44424 | 44547 | 5.76 | 0 | 5.76 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5" |  | ST LP 4"-5" | 275.41 | 325.34 | 408.37 | 443.82 | 395.26 | 346.57 | 245.43 | 343.97 | 353.67 | 288.21 | 352.54 | 282.85 | 0 | 0 | 117.95 | 205.26 | 119.92 | 115.55 | 270.61 | 184.66 | 185.45 | 175.79 | 163.1 | 133.21 | 133.53 | 215.73 | 139.87
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Abel Cruz | IMGA223199 | WO-0760383 | NETHER STREET | LONDON | BARNET | Barnet London Borough Council | 510881479 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 33.73 | MR1 | N | T1 CONNECTED |  | 44424 | 44547 | 33.72 | 0 | 33.72 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5" |  | ST LP 6"-7" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Herbie Thomas | DPF | Abel Cruz | IMGA223200 | WO-0760952 | HOLDERS HILL ROAD | LONDON | BARNET | Barnet London Borough Council | 510993438 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 109.78 | MR1 | N | T1 SECONDARY |  | 44565 | 44648 | 0 | 109.72 | 109.72 | [14 empty] | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | 8.44 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5" |  | ST LP 8" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CMO East 1 | Michael Solomon | Herbie Thomas | DPF | Abel Cruz | IMGA223200 | WO-0760952 | HOLDERS HILL ROAD | LONDON | BARNET | Barnet London Borough Council | 510993439 | 2 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 0 | 63.46 | MR1 | N | T1 CONNECTED |  | 44565 | 44648 | 0 | 63.44 | 63.44 | [14 empty] | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | 4.88 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5" |  | Total | 5540.415 | 7335.665 | 7236.265 | 7523.735 | 7358.66 | 6953.1843 | 7244.4043 | 7491.6843 | 7759.1143 | 7645.8676 | 7219.7176 | 6363.4976 | 0 | 0 | 6936.35 | 8398.16 | 8371.85 | 7751.41 | 7446.03 | 7892.92 | 8574.58 | 7717.07 | 7255.85 | 6313.76 | 6064.94 | 5818.86 | 5839.6
CMO East 1 | Michael Solomon | Herbie Thomas | DPF | Abel Cruz | IMGA223200 | WO-0760953 | THORNFIELD AVENUE | LONDON | BARNET | Barnet London Borough Council | 510924864 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 119.35 | MR1 | N | T1 SECONDARY |  | 44565 | 44648 | 0 | 119.34 | 119.34 | [14 empty] | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | 9.18 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Herbie Thomas | DPF | Abel Cruz | IMGA223200 | WO-0760953 | THORNFIELD AVENUE | LONDON | BARNET | Barnet London Borough Council | 510924865 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 112.49 | MR1 | N | T1 SECONDARY |  | 44565 | 44648 | 0 | 112.45 | 112.45 | [14 empty] | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | 8.65 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Aurel Hoxhaj | IMGA223204 | WO-0760918 | HAMPSTEAD WAY | LONDON | BARNET | Barnet London Borough Council | 510844898 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 203.72 | MR1 | N | T1 SECONDARY |  | 44571 | 44603 | 0 | 203.7 | 203.7 | [15 empty] | 40.74 | 40.74 | 40.74 | 40.74 | 40.74 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Aurel Hoxhaj | IMGA223204 | WO-0760919 | MEADWAY | LONDON | BARNET | Barnet London Borough Council | 634049039 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 13.78 | MR1 | N | T1 SECONDARY |  | 44571 | 44603 | 0 | 13.8 | 13.8 | [15 empty] | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Aurel Hoxhaj | IMGA223206 | WO-0761330 | WELLGARTH ROAD | LONDON | BARNET | Barnet London Borough Council | 510934163 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 27.52 | MR1 | N | T1 SECONDARY |  | 44606 | 44652 | 0 | 27.51 | 27.51 | [20 empty] | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Aurel Hoxhaj | IMGA223206 | WO-0761331 | MORLAND CLOSE | LONDON | BARNET | Barnet London Borough Council | 510879085 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 127.35 | MR1 | N | T1 SECONDARY |  | 44606 | 44652 | 0 | 127.33 | 127.33 | [20 empty] | 18.19 | 18.19 | 18.19 | 18.19 | 18.19 | 18.19 | 18.19 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Aurel Hoxhaj | IMGA223206 | WO-0761332 | HAMPSTEAD WAY | LONDON | BARNET | Barnet London Borough Council | 220000799420 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 233.57 | MR1 | N | T1 SECONDARY |  | 44606 | 44652 | 0 | 233.59 | 233.59 | [20 empty] | 33.37 | 33.37 | 33.37 | 33.37 | 33.37 | 33.37 | 33.37 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223250 | WO-0761531 | MONKHAMS AVENUE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510878293 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 528.24 | MR1 | N | T1 SECONDARY |  | 44438 | 44533 | 528.2 | 0 | 528.2 | 52.82 | 52.82 | 52.82 | 52.82 | 52.82 | 52.82 | 52.82 | 52.82 | 52.82 | 52.82 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223250 | WO-0761531 | MONKHAMS AVENUE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510878294 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 61.78 | MR1 | N | T1 SECONDARY |  | 44438 | 44533 | -0.3 | 0 | -0.3 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223250 | WO-0761531 | MONKHAMS AVENUE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510878296 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 83.98 | MR1 | N | T1 SECONDARY |  | 44438 | 44533 | -13 | 0 | -13 | -1.3 | -1.3 | -1.3 | -1.3 | -1.3 | -1.3 | -1.3 | -1.3 | -1.3 | -1.3 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223250 | WO-0761532 | HUTTON CLOSE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510855769 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 54.35 | MR1 | N | T1 SECONDARY |  | 44438 | 44533 | 4.3 | 0 | 4.3 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223250 | WO-0761533 | PARK AVENUE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510889420 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 272.12 | MR1 | N | T1 SECONDARY |  | 44438 | 44533 | 272.2 | 0 | 272.2 | 27.22 | 27.22 | 27.22 | 27.22 | 27.22 | 27.22 | 27.22 | 27.22 | 27.22 | 27.22 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223250 | WO-0761534 | THE GREEN | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220001384707 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 136.63 | MR1 | N | T1 SECONDARY |  | 44438 | 44533 | 136.6 | 0 | 136.6 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | LDP Blank | Charlie Clark | IMGA223374 | WO-0762222 | LECHMERE APPROACH | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220000178908 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 40 | 55.52 | MR1 | N | T1 CBA |  | 44536 | 44540 | 55.52 | 0 | 55.52 | [10 empty] | 55.52 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | LDP Blank | Charlie Clark | IMGA223374 | WO-0762221 | LECHMERE AVENUE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510864862 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 34.6 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 34.6 | 0 | 34.6 | [11 empty] | 34.6 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223237 | WO-0759612 | NEW NORTH ROAD | ILFORD | REDBRIDGE | Redbridge London Borough Council | 510881967 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 318.4 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 318.4 | 318.4 | [14 empty] | 79.6 | 79.6 | 79.6 | 79.6 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223237 | WO-0759612 | NEW NORTH ROAD | ILFORD | REDBRIDGE | Redbridge London Borough Council | 631356389 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 20.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 20.68 | 20.68 | [14 empty] | 5.17 | 5.17 | 5.17 | 5.17 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223237 | WO-0759612 | NEW NORTH ROAD | ILFORD | REDBRIDGE | Redbridge London Borough Council | 634947550 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 72.42 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44565 | 44589 | 0 | 72.44 | 72.44 | [14 empty] | 18.11 | 18.11 | 18.11 | 18.11 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223237 | WO-0759612 | NEW NORTH ROAD | ILFORD | REDBRIDGE | Redbridge London Borough Council | 220000652675 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 12.03 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 12.04 | 12.04 | [14 empty] | 3.01 | 3.01 | 3.01 | 3.01 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223237 | WO-0759612 | NEW NORTH ROAD | ILFORD | REDBRIDGE | Redbridge London Borough Council | 220001236441 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 87 | 7.65 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 7.64 | 7.64 | [14 empty] | 1.91 | 1.91 | 1.91 | 1.91 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Charlie Clark | IMGA223237 | WO-0759612 | NEW NORTH ROAD | ILFORD | REDBRIDGE | Redbridge London Borough Council | 220001744410 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 48.45 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 48.44 | 48.44 | [14 empty] | 12.11 | 12.11 | 12.11 | 12.11 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761520 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885420 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 221.74 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 221.76 | 221.76 | [14 empty] | 27.72 | 27.72 | 27.72 | 27.72 | 27.72 | 27.72 | 27.72 | 27.72 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761520 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885421 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 101.43 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 101.44 | 101.44 | [14 empty] | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761520 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885430 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 152.39 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 152.4 | 152.4 | [14 empty] | 19.05 | 19.05 | 19.05 | 19.05 | 19.05 | 19.05 | 19.05 | 19.05 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761520 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 628485847 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 71.35 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 71.36 | 71.36 | [14 empty] | 8.92 | 8.92 | 8.92 | 8.92 | 8.92 | 8.92 | 8.92 | 8.92 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761520 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 628485850 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 5.95 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 5.92 | 5.92 | [14 empty] | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761520 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 632992835 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 1.11 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 1.12 | 1.12 | [14 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761521 | OAK HILL CRESCENT | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 632992834 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 1.13 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 1.12 | 1.12 | [14 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223294 | WO-0761522 | HOLLY CRESCENT | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510853534 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 192.04 | MR1 | N | T1 SECONDARY |  | 44565 | 44613 | 0 | 192.08 | 192.08 | [14 empty] | 24.01 | 24.01 | 24.01 | 24.01 | 24.01 | 24.01 | 24.01 | 24.01 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223295 | WO-0759648 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885422 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 35.02 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 35.04 | 35.04 | [21 empty] | 5.84 | 5.84 | 5.84 | 5.84 | 5.84 | 5.84 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223295 | WO-0759648 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885423 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 43.39 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 43.38 | 43.38 | [21 empty] | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223295 | WO-0759648 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885428 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 375.19 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 375.18 | 375.18 | [21 empty] | 62.53 | 62.53 | 62.53 | 62.53 | 62.53 | 62.53 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223295 | WO-0759648 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 628485848 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 34.26 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 34.26 | 34.26 | [21 empty] | 5.71 | 5.71 | 5.71 | 5.71 | 5.71 | 5.71 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223295 | WO-0759648 | OAK HILL | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 628485849 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 178.5 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 178.5 | 178.5 | [21 empty] | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | TBA - Lon | Forefront | Charlie Clark | IMGA223295 | WO-0759649 | OAK HILL GARDENS | WOODFORD GREEN | WALTHAM FOREST | Waltham Forest London Borough Council | 510885450 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 56.36 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 56.34 | 56.34 | [21 empty] | 9.39 | 9.39 | 9.39 | 9.39 | 9.39 | 9.39 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK |  |  |  | 510947267 | 100 |  | T1 | mm | DI |  | LP | Policy | T1Policy | 4"-5" |  | 40.68 | MR1 | N | T1 SECONDARY |  | 44326 | 44505 | 40.56 | 0 | 40.56 | 6.76 | 6.76 | 6.76 | 6.76 | 6.76 | 6.76 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 510947263 | 100 |  | T1 | mm | CI |  | LP | Policy | T1Policy | 4"-5" | 222 | 20 | MR1 | N | T1 PAST |  | 44326 | 44505 | -141.96 | 0 | -141.96 | -23.66 | -23.66 | -23.66 | -23.66 | -23.66 | -23.66 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 510947263 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 222 | 194 | MR1 | N | T1 PAST |  | 44326 | 44505 | 193.98 | 0 | 193.98 | 32.33 | 32.33 | 32.33 | 32.33 | 32.33 | 32.33 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 510947264 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 51 | 44.88 | MR1 | N | T1 SECONDARY |  | 44326 | 44505 | 45 | 0 | 45 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK |  |  |  | 510947268 | 50 |  | T1 | mm | ST |  | LP | Non policy | T1Non policy | 4"-5" |  | 27.51 | MR1 | N | T1 CONNECTED |  | 44326 | 44505 | 27.54 | 0 | 27.54 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 510947269 | 50 |  | T1 | mm | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 22.72 | MR1 | N | T1 CONNECTED |  | 44326 | 44505 | 22.62 | 0 | 22.62 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 510947270 | 50 |  | T1 | mm | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 17.26 | MR1 | N | T1 CONNECTED |  | 44326 | 44505 | 17.16 | 0 | 17.16 | 2.86 | 2.86 | 2.86 | 2.86 | 2.86 | 2.86 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 510947271 | 50 |  | T1 | mm | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 19.41 | MR1 | N | T1 CONNECTED |  | 44326 | 44505 | 19.5 | 0 | 19.5 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221002 | WO-0759885 | WEST HILL PARK | LONDON | CAMDEN | Camden Council | 622166902 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 14.43 | MR1 | N | T1 CONNECTED |  | 44326 | 44505 | 14.58 | 0 | 14.58 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Colin Grant | IMGA223296 | WO-0759715 | PRITCHARDS ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510895905 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 114 | 261.3 | MR1 | N | T1 SECONDARY |  | 44508 | 44582 | 166.25 | 71.25 | 237.5 | [6 empty] | 23.75 | 23.75 | 23.75 | 31.6667 | 31.6667 | 31.6667 |  |  | 23.75 | 23.75 | 23.75 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Colin Grant | IMGA223296 | WO-0759715 | PRITCHARDS ROAD | LONDON | TOWER HAMLETS | Hackney London Borough Council | 510895915 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 50 | 194.31 | MR1 | N | T1 SECONDARY |  | 44508 | 44582 | 123.62 | 52.98 | 176.6 | [6 empty] | 17.66 | 17.66 | 17.66 | 23.5467 | 23.5467 | 23.5467 |  |  | 17.66 | 17.66 | 17.66 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Drew Corrigan | Terra Firma | Colin Grant | IMGA221010 | WO-0760018 | AINSWORTH WAY | LONDON | CAMDEN | Camden Council | 510912607 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 47 | 303.1 | MR1 | N | T1 PAST |  | 44585 | 44645 | 0 | 303.12 | 303.12 | [17 empty] | 33.68 | 33.68 | 33.68 | 33.68 | 33.68 | 33.68 | 33.68 | 33.68 | 33.68 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Herbie Thomas | DPF | Colin Grantham | IMGA223307 | WO-0760010 | COLNEY HATCH LANE | LONDON | HARINGEY | Haringey Council | 510813133 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 274.68 | MR1 | N | T1 SECONDARY |  | 44494 | 44554 | 274.68 | 0 | 274.68 |  |  |  |  | 30.52 | 30.52 | 30.52 | 30.52 | 30.52 | 40.6933 | 40.6933 | 40.6933 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761266 | ARTHUR ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510783524 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 120.62 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 3.63 | 0 | 3.63 | 1.21 | 1.21 | 1.21 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761266 | ARTHUR ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510783525 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 41.89 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 0.93 | 0 | 0.93 | 0.31 | 0.31 | 0.31 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761267 | CHARLES ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510805937 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 122.75 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 16.71 | 0 | 16.71 | 5.57 | 5.57 | 5.57 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761268 | CLARISSA ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510810638 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 176.39 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | -43.59 | 0 | -43.59 | -14.53 | -14.53 | -14.53 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761269 | EDGAR ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510825696 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 70.86 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 20.88 | 0 | 20.88 | 6.96 | 6.96 | 6.96 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761269 | EDGAR ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510825697 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 112.63 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 112.65 | 0 | 112.65 | 37.55 | 37.55 | 37.55 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761270 | EDITH ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510825944 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 82.2 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 18.24 | 0 | 18.24 | 6.08 | 6.08 | 6.08 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223246 | WO-0761271 | EVA ROAD | ROMFORD | REDBRIDGE | Redbridge London Borough Council | 510829145 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 106.45 | MR1 | N | T1 SECONDARY |  | 44431 | 44484 | 0.48 | 0 | 0.48 | 0.16 | 0.16 | 0.16 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223248 | WO-0761624 | RODING LANE NORTH | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510915725 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 545.13 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44487 | 44547 | 545.13 | 0 | 545.13 |  |  |  | 60.57 | 60.57 | 60.57 | 60.57 | 60.57 | 60.57 | 60.57 | 60.57 | 60.57 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223248 | WO-0761624 | RODING LANE NORTH | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510915731 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 22.21 | MR1 | N | T1 SECONDARY |  | 44487 | 44547 | 22.23 | 0 | 22.23 |  |  |  | 2.47 | 2.47 | 2.47 | 2.47 | 2.47 | 2.47 | 2.47 | 2.47 | 2.47 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223248 | WO-0761624 | RODING LANE NORTH | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220001232473 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 9.46 | MR1 | N | T1 SECONDARY |  | 44487 | 44547 | 9.45 | 0 | 9.45 |  |  |  | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223248 | WO-0761625 | KENSINGTON DRIVE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220001383904 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 13.08 | MR1 | N | T1 SECONDARY |  | 44487 | 44547 | 13.05 | 0 | 13.05 |  |  |  | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | 1.45 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223248 | WO-0761626 | PORTMAN DRIVE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220001245043 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 1.82 | MR1 | N | T1 SEED |  | 44487 | 44547 | 1.8 | 0 | 1.8 |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223227 | WO-0761227 | ALDBOROUGH ROAD SOUTH | ILFORD | REDBRIDGE | Redbridge London Borough Council | 220001609211 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 104.28 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 104.28 | 104.28 | [14 empty] | 26.07 | 26.07 | 26.07 | 26.07 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223227 | WO-0761228 | DOWNSHALL AVENUE | ILFORD | REDBRIDGE | Redbridge London Borough Council | 510822652 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 326.92 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 326.92 | 326.92 | [14 empty] | 81.73 | 81.73 | 81.73 | 81.73 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223227 | WO-0761229 | LEICESTER GARDENS | ILFORD | REDBRIDGE | Redbridge London Borough Council | 510865078 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 188.12 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 188.12 | 188.12 | [14 empty] | 47.03 | 47.03 | 47.03 | 47.03 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223249 | WO-0761893 | THE GLADE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 603468054 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 122.57 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 122.58 | 122.58 | [14 empty] | 20.43 | 20.43 | 20.43 | 20.43 | 20.43 | 20.43 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223249 | WO-0761893 | THE GLADE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220001745075 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 46.4 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 46.38 | 46.38 | [14 empty] | 7.73 | 7.73 | 7.73 | 7.73 | 7.73 | 7.73 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223249 | WO-0761894 | HIGH ROAD | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510850260 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 83.59 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 83.58 | 83.58 | [14 empty] | 13.93 | 13.93 | 13.93 | 13.93 | 13.93 | 13.93 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223249 | WO-0761894 | HIGH ROAD | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 220001745081 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 56.07 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 56.1 | 56.1 | [14 empty] | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | 9.35 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223249 | WO-0761895 | BURLINGTON PLACE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 510799906 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 98.44 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 98.46 | 98.46 | [14 empty] | 16.41 | 16.41 | 16.41 | 16.41 | 16.41 | 16.41 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Steve Edwards | Vic Roxborough | MURRAY | Darren Hailstone | IMGA223249 | WO-0761895 | BURLINGTON PLACE | WOODFORD GREEN | REDBRIDGE | Redbridge London Borough Council | 606527779 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 5.63 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 5.64 | 5.64 | [14 empty] | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | 0.94 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Dean Joseph | IMGA223192 | WO-0761405 | HIGHVIEW GARDENS | EDGWARE | BARNET | Barnet London Borough Council | 510943986 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 457.06 | MR1 | N | T1 SECONDARY |  | 44431 | 44589 | 256.36 | 78.88 | 335.24 | 19.72 | 19.72 | 19.72 | 19.72 | 19.72 | 19.72 | 19.72 | 19.72 | 19.72 | 26.2933 | 26.2933 | 26.2933 |  |  | 19.72 | 19.72 | 19.72 | 19.72 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Dean Joseph | IMGA223192 | WO-0761405 | HIGHVIEW GARDENS | EDGWARE | BARNET | Barnet London Borough Council | 510943987 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 43.6 | MR1 | N | T1 SECONDARY |  | 44431 | 44589 | 31.59 | 9.72 | 41.31 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 3.24 | 3.24 | 3.24 |  |  | 2.43 | 2.43 | 2.43 | 2.43 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223208 | WO-0761720 | TEMPLE FORTUNE LANE | LONDON | BARNET | Barnet London Borough Council | 510921257 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 332.58 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 257.52 | 0 | 257.52 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | 21.46 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223208 | WO-0761720 | TEMPLE FORTUNE LANE | LONDON | BARNET | Barnet London Borough Council | 632873905 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 1 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 1.08 | 0 | 1.08 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223208 | WO-0761720 | TEMPLE FORTUNE LANE | LONDON | BARNET | Barnet London Borough Council | 633791780 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 1.04 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 1.08 | 0 | 1.08 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223208 | WO-0761720 | TEMPLE FORTUNE LANE | LONDON | BARNET | Barnet London Borough Council | 633792141 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 3.23 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 3.36 | 0 | 3.36 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223208 | WO-0761721 | HOOP LANE | LONDON | BARNET | Barnet London Borough Council | 220001759612 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.51 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 2.52 | 0 | 2.52 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223205 | WO-0760263 | HOOP LANE | LONDON | BARNET | Barnet London Borough Council | 510854291 | 12 |  | T2 | Inch | DI | Open Cut | LP | Policy | T2Policy | 10"-12" | 118 | 298.68 | MR2 | N | T2 PAST |  | 44487 | 44519 | 298.7 | 0 | 298.7 |  |  |  | 59.74 | 59.74 | 59.74 | 59.74 | 59.74 | [19 empty] | T2A | 10"-12" | LP | Policy | T2 | DI | T2A
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223193 | WO-0761879 | BROCKLEY HILL |  |  |  | 510940583 | 8 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 145.39 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 145.34 | 145.34 | [14 empty] | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | 11.18 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223193 | WO-0761879 | BROCKLEY HILL | STANMORE | BARNET | Barnet London Borough Council | 510797491 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 1325.81 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 1325.87 | 1325.87 | [14 empty] | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | 101.99 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223193 | WO-0761880 | NUTT GROVE | LONDON | BARNET | Barnet London Borough Council | 510994852 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 163.49 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 163.54 | 163.54 | [14 empty] | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | 12.58 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223193 | WO-0761881 | JULIUS CAESAR WAY | STANMORE | HARROW | Barnet London Borough Council | 612821694 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 54.65 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 54.6 | 54.6 | [14 empty] | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | Eamon McQuad | IMGA223193 | WO-0761879 | BROCKLEY HILL | STANMORE | BARNET | Barnet London Borough Council | 510996775 | 4 |  | T1 | Inch | CI | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 0 | 96.69 | MR1 | N | T1 CONNECTED |  | 44565 | 44652 | 0 | 96.72 | 96.72 | [14 empty] | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | 7.44 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Non policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Ioan Iusco | IMGA223328 | WO-0759598 | MACE STREET | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510871372 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 58.57 | MR1 | N | T1 SECONDARY |  | 44480 | 44498 | 58.56 | 0 | 58.56 |  |  | 19.52 | 19.52 | 19.52 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Ioan Iusco | IMGA223328 | WO-0759598 | MACE STREET | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510871374 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 24 | 25.59 | MR1 | N | T1 SECONDARY |  | 44480 | 44498 | 25.59 | 0 | 25.59 |  |  | 8.53 | 8.53 | 8.53 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Ioan Iusco | IMGA223319 | WO-0760101 | EXMOUTH STREET | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510829617 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 218 | 72.3 | MR1 | N | T1 PAST |  | 44494 | 44505 | 72.3 | 0 | 72.3 |  |  |  |  | 36.15 | 36.15 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Ioan Iusco | IMGA223321 | WO-0759764 | STEBONDALE STREET | LONDON | TOWER HAMLETS | Tower Hamlets Council | 220000376260 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 128 | 29.05 | MR1 | N | T1 PAST |  | 44501 | 44512 | 29.06 | 0 | 29.06 | [5 empty] | 14.53 | 14.53 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | James Turner | IMGA223215 | WO-0760046 | DANIEL PLACE | LONDON | BARNET | Barnet London Borough Council | 510819381 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 154.84 | MR1 | N | T1 SECONDARY |  | 44452 | 44505 | 74.88 | 0 | 74.88 | 12.48 | 12.48 | 12.48 | 12.48 | 12.48 | 12.48 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | James Turner | IMGA223191 | WO-0759665 | ORANGE HILL ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510887267 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 254 | 37.67 | MR1 | N | T1 PAST |  | 44508 | 44547 | 37.68 | 0 | 37.68 | [6 empty] | 6.28 | 6.28 | 6.28 | 6.28 | 6.28 | 6.28 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | James Turner | IMGA223191 | WO-0759665 | ORANGE HILL ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510943940 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 45.04 | MR1 | N | T1 SEED |  | 44508 | 44547 | 45.06 | 0 | 45.06 | [6 empty] | 7.51 | 7.51 | 7.51 | 7.51 | 7.51 | 7.51 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | James Turner | IMGA223191 | WO-0765818 | DEANSBROOK ROAD |  |  |  | 510943941 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" | 32 | 144.88 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 144.9 | 0 | 144.9 | [6 empty] | 24.15 | 24.15 | 24.15 | 24.15 | 24.15 | 24.15 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | DPF | James Turner | IMGA223406 | WO-0764515 | GOLDERS WAY | LONDON | BARNET | Barnet London Borough Council | 510838411 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 0 | 63.62 | MR1 | N | T1 CONNECTED |  | 44565 | 44589 | 0 | 63.64 | 63.64 | [14 empty] | 15.91 | 15.91 | 15.91 | 15.91 | [9 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Mark Clee | IMGA223301 | WO-0759761 | SOUTHWOLD ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510914113 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 114.96 | MR1 | N | T1 SECONDARY |  | 44452 | 44498 | 114.95 | 0 | 114.95 | 22.99 | 22.99 | 22.99 | 22.99 | 22.99 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Mark Clee | IMGA223301 | WO-0759761 | SOUTHWOLD ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510914117 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 59.11 | MR1 | N | T1 SECONDARY |  | 44452 | 44498 | 59.1 | 0 | 59.1 | 11.82 | 11.82 | 11.82 | 11.82 | 11.82 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Mark Clee | IMGA223301 | WO-0759761 | SOUTHWOLD ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510914118 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 49.52 | MR1 | N | T1 SECONDARY |  | 44452 | 44498 | 49.5 | 0 | 49.5 | 9.9 | 9.9 | 9.9 | 9.9 | 9.9 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Mark Clee | IMGA223301 | WO-0759761 | SOUTHWOLD ROAD | LONDON | HACKNEY | Hackney London Borough Council | 606401053 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 42.29 | MR1 | N | T1 SECONDARY |  | 44452 | 44498 | 42.3 | 0 | 42.3 | 8.46 | 8.46 | 8.46 | 8.46 | 8.46 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Mark Clee | IMGA223301 | WO-0759761 | SOUTHWOLD ROAD | LONDON | HACKNEY | Hackney London Borough Council | 220001342129 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 89.29 | MR1 | N | T1 SECONDARY |  | 44452 | 44498 | 89.3 | 0 | 89.3 | 17.86 | 17.86 | 17.86 | 17.86 | 17.86 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Mark Clee | IMGA223301 | WO-0759761 | SOUTHWOLD ROAD | LONDON | HACKNEY | Hackney London Borough Council | 220001342183 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 4.86 | MR1 | N | T1 SECONDARY |  | 44452 | 44498 | 4.85 | 0 | 4.85 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223212 | WO-0760340 | NEW BRENT STREET |  |  |  | 510881765 | 6 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 93.11 | MR1 | N | T1 SECONDARY |  | 44410 | 44484 | 8.07 | 0 | 8.07 | 2.69 | 2.69 | 2.69 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223212 | WO-0760340 | NEW BRENT STREET | LONDON | BARNET | Barnet London Borough Council | 606693079 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 8.75 | MR1 | N | T1 SECONDARY |  | 44410 | 44484 | 2.79 | 0 | 2.79 | 0.93 | 0.93 | 0.93 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223212 | WO-0760341 | EATON ROAD | LONDON | BARNET | Barnet London Borough Council | 510870133 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 423 | 174.23 | MR1 | N | T1 PAST |  | 44410 | 44484 | 29.25 | 0 | 29.25 | 9.75 | 9.75 | 9.75 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761272 | ALEXANDRA GROVE | LONDON | BARNET | Barnet London Borough Council | 510780661 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 225.9 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 127.66 | 88.38 | 216.04 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 13.0933 | 13.0933 | 13.0933 |  |  | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 | 9.82 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761272 | ALEXANDRA GROVE | LONDON | BARNET | Barnet London Borough Council | 510780662 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 53.44 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 30.16 | 20.88 | 51.04 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 3.0933 | 3.0933 | 3.0933 |  |  | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761272 | ALEXANDRA GROVE | LONDON | BARNET | Barnet London Borough Council | 510780663 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 178.07 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 100.62 | 69.66 | 170.28 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 10.32 | 10.32 | 10.32 |  |  | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 | 7.74 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761272 | ALEXANDRA GROVE | LONDON | BARNET | Barnet London Borough Council | 510780664 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 253.45 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 143.26 | 99.18 | 242.44 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 14.6933 | 14.6933 | 14.6933 |  |  | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 | 11.02 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761272 | ALEXANDRA GROVE | LONDON | BARNET | Barnet London Borough Council | 621242248 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 3.78 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 2.08 | 1.44 | 3.52 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.21333 | 0.21333 | 0.21333 |  |  | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761272 | ALEXANDRA GROVE | LONDON | BARNET | Barnet London Borough Council | 631691573 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 2.22 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 1.3 | 0.9 | 2.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.13333 | 0.13333 | 0.13333 |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761273 | THYRA GROVE | LONDON | BARNET | Barnet London Borough Council | 510925353 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 116.94 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 66.04 | 45.72 | 111.76 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 6.7733 | 6.7733 | 6.7733 |  |  | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 | 5.08 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Pat Caulfield | IMGA223194 | WO-0761273 | THYRA GROVE | LONDON | BARNET | Barnet London Borough Council | 510925354 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 56.99 | MR1 | N | T1 SECONDARY |  | 44466 | 44624 | 32.24 | 22.32 | 54.56 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 3.3067 | 3.3067 | 3.3067 |  |  | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223334 | WO-0761261 | FAIRFOOT ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510829929 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 83 | 96.62 | MR1 | N | T1 PAST |  | 44473 | 44547 | 96.58 | 0 | 96.58 |  | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223334 | WO-0761261 | FAIRFOOT ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510829930 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 254 | 160.24 | MR1 | N | T1 PAST |  | 44473 | 44547 | 160.27 | 0 | 160.27 |  | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | 14.57 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223334 | WO-0761262 | CANTRELL ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510861634 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 32.35 | MR1 | N | T1 SECONDARY |  | 44473 | 44547 | 32.34 | 0 | 32.34 |  | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | 2.94 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223334 | WO-0761263 | SPANBY ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510914231 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 37 | 88.47 | MR1 | N | T1 SECONDARY |  | 44473 | 44547 | 88.44 | 0 | 88.44 |  | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | 8.04 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223324 | WO-0759727 | SALMON LANE | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510907945 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 116.06 | MR1 | N | T1 SECONDARY |  | 44515 | 44540 | 116.08 | 0 | 116.08 | [7 empty] | 29.02 | 29.02 | 29.02 | 29.02 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223326 | WO-0759979 | CABLE STREET | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510800839 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 115 | 13.69 | MR1 | N | T1 SEED |  | 44536 | 44540 | 13.69 | 0 | 13.69 | [10 empty] | 13.69 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223335 | WO-0759716 | ROUNTON ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510903745 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 61 | 85.33 | MR1 | N | T1 PAST |  | 44565 | 44578 | 0 | 85.32 | 85.32 | [14 empty] | 28.44 | 28.44 | 28.44 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223335 | WO-0759716 | ROUNTON ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 634699931 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 70 | 0.46 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 0.45 | 0.45 | [14 empty] | 0.15 | 0.15 | 0.15 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223327 | WO-0760223 | ROBINSON ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510901798 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 105.41 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 105.4 | 105.4 | [14 empty] | 21.08 | 21.08 | 21.08 | 21.08 | 21.08 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223327 | WO-0760224 | APPROACH ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510782439 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 120.88 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 120.9 | 120.9 | [14 empty] | 24.18 | 24.18 | 24.18 | 24.18 | 24.18 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Pawel Kulczewski | IMGA223330 | WO-0759661 | OLD BETHNAL GREEN ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510886313 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 109.71 | MR1 | N | T1 SECONDARY |  | 44599 | 44610 | 0 | 109.72 | 109.72 | [19 empty] | 54.86 | 54.86 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Pawel Kulczewski | IMGA223332 | WO-0759968 | BRUCE ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 220000434381 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 22.91 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44606 | 44638 | 0 | 22.9 | 22.9 | [20 empty] | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Pawel Kulczewski | IMGA223332 | WO-0759968 | BRUCE ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 220000434383 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 20.23 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44606 | 44638 | 0 | 20.25 | 20.25 | [20 empty] | 4.05 | 4.05 | 4.05 | 4.05 | 4.05 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Pawel Kulczewski | IMGA223332 | WO-0759968 | BRUCE ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 220000434435 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 31 | 90.36 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44606 | 44638 | 0 | 90.35 | 90.35 | [20 empty] | 18.07 | 18.07 | 18.07 | 18.07 | 18.07 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Pawel Kulczewski | IMGA223332 | WO-0759968 | BRUCE ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 220000223230 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 6 | 3.95 | MR1 | N | T1 CONNECTED |  | 44606 | 44638 | 0 | 3.95 | 3.95 | [20 empty] | 0.79 | 0.79 | 0.79 | 0.79 | 0.79 |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761698 | BRENT PARK ROAD | LONDON | BARNET | Barnet London Borough Council | 220001255900 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 2.56 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 2.52 | 0 | 2.52 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761699 | DALLAS ROAD | LONDON | BARNET | Barnet London Borough Council | 510819006 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 354.24 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 62.16 | 0 | 62.16 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | 5.18 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761699 | DALLAS ROAD | LONDON | BARNET | Barnet London Borough Council | 510819007 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 68.18 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 68.16 | 0 | 68.16 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761699 | DALLAS ROAD | LONDON | BARNET | Barnet London Borough Council | 220001444976 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.92 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | -1.2 | 0 | -1.2 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761700 | LAYFIELD ROAD | LONDON | BARNET | Barnet London Borough Council | 510864454 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 71.71 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 71.64 | 0 | 71.64 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761700 | LAYFIELD ROAD | LONDON | BARNET | Barnet London Borough Council | 510864455 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 257 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 257.04 | 0 | 257.04 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761700 | LAYFIELD ROAD | LONDON | BARNET | Barnet London Borough Council | 220001500718 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 195 | 1.57 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 1.56 | 0 | 1.56 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761700 | LAYFIELD ROAD | LONDON | BARNET | Barnet London Borough Council | 220001500729 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 195 | 0.75 | MR1 | N | T1 SECONDARY |  | 44417 | 44547 | 0.72 | 0 | 0.72 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761701 | PARK ROAD | LONDON | BARNET | Barnet London Borough Council | 510889813 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 5 | 22.56 | MR1 | N | T1 CONNECTED |  | 44417 | 44547 | 0.6 | 0 | 0.6 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | DPF | Romeo Zhuka | IMGA223214 | WO-0761701 | PARK ROAD | LONDON | BARNET | Barnet London Borough Council | 510889843 | 200 |  | T1 | mm | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 18.02 | MR1 | N | T1 CONNECTED |  | 44417 | 44547 | -1.92 | 0 | -1.92 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | -0.16 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765097 | MILLFIELD ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510877572 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 51.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 51.74 | 51.74 | [14 empty] | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765097 | MILLFIELD ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510877573 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 323.01 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 323.05 | 323.05 | [14 empty] | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | 24.85 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765097 | MILLFIELD ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510877574 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 13.51 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 13.52 | 13.52 | [14 empty] | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | 1.04 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765098 | PLAYFIELD ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510893376 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 47.32 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 47.32 | 47.32 | [14 empty] | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765098 | PLAYFIELD ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510893379 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 100.72 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 100.75 | 100.75 | [14 empty] | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | 7.75 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765098 | PLAYFIELD ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510893383 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 7.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 7.67 | 7.67 | [14 empty] | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765099 | ST ALPHAGE WALK FOOTPATH ACCESS TO NO4-8 EVENS NO13-21 ODDS | EDGWARE | BARNET | Barnet London Borough Council | 220000477581 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 114.37 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 114.4 | 114.4 | [14 empty] | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | 8.8 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Peter Rattigan | LDP Blank | Romeo Zhuka | IMGA223416 | WO-0765100 | GASKARTH ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510943316 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 42 | 229.73 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 229.71 | 229.71 | [14 empty] | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | 17.67 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765059 | GARRATT ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510943306 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 157.5 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 97.5 | 97.5 | [14 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765059 | GARRATT ROAD | EDGWARE | BARNET | Barnet London Borough Council | 510943307 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 37.63 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 23.27 | 23.27 | [14 empty] | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | 1.79 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765060 | ELMER GARDENS | EDGWARE | BARNET | Barnet London Borough Council | 510945091 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 160.5 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 99.32 | 99.32 | [14 empty] | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | 7.64 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765061 | FAIRFIELD CRESCENT | EDGWARE | BARNET | Barnet London Borough Council | 510945052 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 332.83 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 206.05 | 206.05 | [14 empty] | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | 15.85 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765061 | FAIRFIELD CRESCENT | EDGWARE | BARNET | Barnet London Borough Council | 510945053 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 121.81 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 75.4 | 75.4 | [14 empty] | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765061 | FAIRFIELD CRESCENT | EDGWARE | BARNET | Barnet London Borough Council | 510945054 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 91.93 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 56.94 | 56.94 | [14 empty] | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765062 | FAIRFIELD AVENUE | EDGWARE | BARNET | Barnet London Borough Council | 510945048 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 228.52 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 141.44 | 141.44 | [14 empty] | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | 10.88 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | Paul Cafferkey | LDP Blank | Romeo Zhuka | IMGA223418 | WO-0765063 | PARKFIELD CLOSE | EDGWARE | BARNET | Barnet London Borough Council | 510944240 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 96.33 | MR1 | N | T1 SECONDARY |  | 44565 | 44708 | 0 | 59.67 | 59.67 | [14 empty] | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223304 | WO-0761213 | WINSTON ROAD | LONDON | HACKNEY | Hackney London Borough Council | 220001280427 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 42 | 130.39 | MR1 | N | T1 SECONDARY |  | 44410 | 44547 | 130.44 | 0 | 130.44 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | 10.87 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223304 | WO-0761214 | ALBION ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510780084 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 526.7 | MR1 | N | T1 SECONDARY |  | 44410 | 44547 | 512.76 | 0 | 512.76 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | 42.73 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223303 | WO-0761298 | BANBURY ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510786390 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 42.54 | MR1 | N | T1 SECONDARY |  | 44466 | 44477 | 42.54 | 0 | 42.54 | 21.27 | 21.27 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223303 | WO-0761299 | GROOMBRIDGE ROAD | LONDON | HACKNEY | Hackney London Borough Council | 510842281 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 68.04 | MR1 | N | T1 SECONDARY |  | 44466 | 44477 | 68.04 | 0 | 68.04 | 34.02 | 34.02 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223320 | WO-0761479 | ABBOTT ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510778326 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 65.55 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 65.56 | 0 | 65.56 |  | 16.39 | 16.39 | 16.39 | 16.39 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223320 | WO-0761480 | NAIRN STREET | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510880820 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 37 | 143.2 | MR1 | N | T1 PAST |  | 44473 | 44498 | 143.2 | 0 | 143.2 |  | 35.8 | 35.8 | 35.8 | 35.8 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765091 | JENKINS ROAD | LONDON | NEWHAM | Newham London Borough Council | 510857167 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 333.51 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 333.45 | 333.45 | [14 empty] | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | 25.65 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765092 | PORT CRESCENT | LONDON | NEWHAM | Newham London Borough Council | 510894089 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 40.47 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 40.43 | 40.43 | [14 empty] | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | 3.11 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765093 | PALMER ROAD | LONDON | NEWHAM | Newham London Borough Council | 510889081 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 62 | 338.03 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 338 | 338 | [14 empty] | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765094 | HOLBORN ROAD | LONDON | NEWHAM | Newham London Borough Council | 510853153 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 229.6 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 229.58 | 229.58 | [14 empty] | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | 17.66 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765094 | HOLBORN ROAD | LONDON | NEWHAM | Newham London Borough Council | 510853158 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 121.86 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 121.81 | 121.81 | [14 empty] | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765095 | ALLIANCE ROAD | LONDON | NEWHAM | Newham London Borough Council | 510781134 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 25.75 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 25.74 | 25.74 | [14 empty] | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | 1.98 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765095 | ALLIANCE ROAD | LONDON | NEWHAM | Newham London Borough Council | 510781135 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 50.57 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 50.57 | 50.57 | [14 empty] | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765095 | ALLIANCE ROAD | LONDON | NEWHAM | Newham London Borough Council | 510781136 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 25.27 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 25.22 | 25.22 | [14 empty] | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | 1.94 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | LDP Blank | Slavec Rutkowski | IMGA223415 | WO-0765096 | WESTPORT ROAD | LONDON | NEWHAM | Newham London Borough Council | 510936131 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 124.36 | MR1 | N | T1 SECONDARY |  | 44565 | 44652 | 0 | 124.41 | 124.41 | [14 empty] | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | 9.57 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223331 | WO-0761784 | THREE MILL LANE | LONDON | NEWHAM | Tower Hamlets Council | 510925182 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 38 | 114.18 | MR1 | N | T1 SECONDARY |  | 44592 | 44631 | 0 | 114.18 | 114.18 | [18 empty] | 19.03 | 19.03 | 19.03 | 19.03 | 19.03 | 19.03 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223331 | WO-0761785 | HANCOCK ROAD | LONDON | TOWER HAMLETS | Tower Hamlets Council | 510845041 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 78.85 | MR1 | N | T1 SECONDARY |  | 44592 | 44631 | 0 | 78.84 | 78.84 | [18 empty] | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 1 | Michael Solomon | James Cox | Terra Firma | Slavec Rutkowski | IMGA223331 | WO-0763152 | THREE MILL LANE | LONDON | TOWER HAMLETS |  | 510925180 | 200 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 189.49 | MR2 | N | T1 PAST |  | 44592 | 44631 | 0 | 189.48 | 189.48 | [18 empty] | 31.58 | 31.58 | 31.58 | 31.58 | 31.58 | 31.58 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760429 | WEST MALLING WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959394 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 32.75 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 32.76 | 0 | 32.76 |  | 5.46 | 5.46 | 5.46 | 5.46 | 5.46 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760429 | WEST MALLING WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959395 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 32.88 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 32.88 | 0 | 32.88 |  | 5.48 | 5.48 | 5.48 | 5.48 | 5.48 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760429 | WEST MALLING WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959399 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 161.23 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 161.22 | 0 | 161.22 |  | 26.87 | 26.87 | 26.87 | 26.87 | 26.87 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760429 | WEST MALLING WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959400 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 29.96 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 29.94 | 0 | 29.94 |  | 4.99 | 4.99 | 4.99 | 4.99 | 4.99 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760429 | WEST MALLING WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959401 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 16.11 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 16.08 | 0 | 16.08 |  | 2.68 | 2.68 | 2.68 | 2.68 | 2.68 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760429 | WEST MALLING WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 220001693953 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 68.16 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 68.16 | 0 | 68.16 |  | 11.36 | 11.36 | 11.36 | 11.36 | 11.36 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760430 | DETLING CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510946324 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 54.98 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 54.96 | 0 | 54.96 |  | 9.16 | 9.16 | 9.16 | 9.16 | 9.16 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760430 | DETLING CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510946325 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 24.95 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 24.9 | 0 | 24.9 |  | 4.15 | 4.15 | 4.15 | 4.15 | 4.15 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760431 | NORTHOLT WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959391 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 69.93 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 69.96 | 0 | 69.96 |  | 11.66 | 11.66 | 11.66 | 11.66 | 11.66 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760431 | NORTHOLT WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 220001605270 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 5 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 4.98 | 0 | 4.98 |  | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Andrew Clements | IMGA223345 | WO-0760431 | NORTHOLT WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 220001605272 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 77.15 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 77.16 | 0 | 77.16 |  | 12.86 | 12.86 | 12.86 | 12.86 | 12.86 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761664 | DUXFORD CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510823927 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 10.26 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 10.25 | 0 | 10.25 | [6 empty] | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761664 | DUXFORD CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510823928 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 12.94 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 12.95 | 0 | 12.95 | [6 empty] | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761664 | DUXFORD CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510823929 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 23.34 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 23.35 | 0 | 23.35 | [6 empty] | 4.67 | 4.67 | 4.67 | 4.67 | 4.67 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761664 | DUXFORD CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510823931 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 48.85 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 48.85 | 0 | 48.85 | [6 empty] | 9.77 | 9.77 | 9.77 | 9.77 | 9.77 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761665 | TANGMERE CRESCENT | HORNCHURCH | HAVERING | Havering London Borough Council | 510920737 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 28.87 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 28.85 | 0 | 28.85 | [6 empty] | 5.77 | 5.77 | 5.77 | 5.77 | 5.77 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761665 | TANGMERE CRESCENT | HORNCHURCH | HAVERING | Havering London Borough Council | 510920738 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 52.38 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 52.4 | 0 | 52.4 | [6 empty] | 10.48 | 10.48 | 10.48 | 10.48 | 10.48 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761666 | STANSTED CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510916171 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 125.56 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 125.55 | 0 | 125.55 | [6 empty] | 25.11 | 25.11 | 25.11 | 25.11 | 25.11 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223346 | WO-0761666 | STANSTED CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510916172 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 107.4 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 107.4 | 0 | 107.4 | [6 empty] | 21.48 | 21.48 | 21.48 | 21.48 | 21.48 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760194 | NORTHOLT WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959387 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 48.82 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 48.82 | 0 | 48.82 | [11 empty] | 48.82 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760194 | NORTHOLT WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510959388 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 30.99 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 30.99 | 0 | 30.99 | [11 empty] | 30.99 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760195 | HAWKINGE WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510847314 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 20.24 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 20.25 | 20.25 | [14 empty] | 4.05 | 4.05 | 4.05 | 4.05 | 4.05 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760195 | HAWKINGE WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510847315 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 100.29 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 100.3 | 100.3 | [14 empty] | 20.06 | 20.06 | 20.06 | 20.06 | 20.06 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760195 | HAWKINGE WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510847316 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 69 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 69 | 69 | [14 empty] | 13.8 | 13.8 | 13.8 | 13.8 | 13.8 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760195 | HAWKINGE WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510847317 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 94.02 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 94 | 94 | [14 empty] | 18.8 | 18.8 | 18.8 | 18.8 | 18.8 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760195 | HAWKINGE WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510847318 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 43.45 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 43.45 | 43.45 | [14 empty] | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223347 | WO-0760195 | HAWKINGE WAY | HORNCHURCH | HAVERING | Havering London Borough Council | 510847319 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 49.42 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 49.4 | 49.4 | [14 empty] | 9.88 | 9.88 | 9.88 | 9.88 | 9.88 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761535 | ASHVALE DRIVE | UPMINSTER | HAVERING | Havering London Borough Council | 510784438 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 65.89 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 65.92 | 65.92 | [19 empty] | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761535 | ASHVALE DRIVE | UPMINSTER | HAVERING | Havering London Borough Council | 510784439 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 33.84 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 33.84 | 33.84 | [19 empty] | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761536 | ASHVALE GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 510784441 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 66 | 271.52 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 271.52 | 271.52 | [19 empty] | 33.94 | 33.94 | 33.94 | 33.94 | 33.94 | 33.94 | 33.94 | 33.94 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761537 | JUDITH ANNE COURT | UPMINSTER | HAVERING | Havering London Borough Council | 510857749 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 22.4 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 22.4 | 22.4 | [19 empty] | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761537 | JUDITH ANNE COURT | UPMINSTER | HAVERING | Havering London Borough Council | 510857750 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 43.67 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 43.68 | 43.68 | [19 empty] | 5.46 | 5.46 | 5.46 | 5.46 | 5.46 | 5.46 | 5.46 | 5.46 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761538 | ST MARYS LANE | UPMINSTER | HAVERING | Havering London Borough Council | 510857748 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 63.84 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 63.84 | 63.84 | [19 empty] | 7.98 | 7.98 | 7.98 | 7.98 | 7.98 | 7.98 | 7.98 | 7.98 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761539 | WESTBURY TERRACE | UPMINSTER | HAVERING | Havering London Borough Council | 510954644 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 63.47 | MR1 | N | T1 SECONDARY |  | 44599 | 44652 | 0 | 63.44 | 63.44 | [19 empty] | 7.93 | 7.93 | 7.93 | 7.93 | 7.93 | 7.93 | 7.93 | 7.93 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761535 | ASHVALE DRIVE | UPMINSTER | HAVERING | Havering London Borough Council | 510784440 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 37.72 | MR1 | N | T1 CONNECTED |  | 44599 | 44652 | 0 | 37.76 | 37.76 | [19 empty] | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Andrew Clements | IMGA223360 | WO-0761536 | ASHVALE GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 510784442 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 23.96 | MR1 | N | T1 CONNECTED |  | 44599 | 44652 | 0 | 24 | 24 | [19 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760933 | LONGTAIL | BILLERICAY | ESSEX | Basildon Borough Council | 510869481 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 178.27 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | -0.77 | 0 | -0.77 | -0.11 | -0.11 | -0.11 | -0.11 | -0.11 | -0.11 | -0.11 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760934 | DUNFANE | BILLERICAY | ESSEX | Basildon Borough Council | 510823550 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 82.67 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 3.5 | 0 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760935 | HOLLYFORD | BILLERICAY | ESSEX | Basildon Borough Council | 510853922 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 88.22 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 88.2 | 0 | 88.2 | 12.6 | 12.6 | 12.6 | 12.6 | 12.6 | 12.6 | 12.6 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760935 | HOLLYFORD | BILLERICAY | ESSEX | Basildon Borough Council | 510853923 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 62.16 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 0.07 | 0 | 0.07 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760935 | HOLLYFORD | BILLERICAY | ESSEX | Basildon Borough Council | 510853924 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 119.21 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 119.07 | 0 | 119.07 | 17.01 | 17.01 | 17.01 | 17.01 | 17.01 | 17.01 | 17.01 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760935 | HOLLYFORD | BILLERICAY | ESSEX | Basildon Borough Council | 601835492 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 2.68 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 2.73 | 0 | 2.73 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760936 | MERCER ROAD | BILLERICAY | ESSEX | Basildon Borough Council | 510958321 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 79.7 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | -0.21 | 0 | -0.21 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760936 | MERCER ROAD | BILLERICAY | ESSEX | Basildon Borough Council | 510958323 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 19.92 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | -0.21 | 0 | -0.21 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | -0.03 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760936 | MERCER ROAD | BILLERICAY | ESSEX | Basildon Borough Council | 510958938 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 16.18 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 16.17 | 0 | 16.17 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | 2.31 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760937 | TALISMAN WALK | BILLERICAY | ESSEX | Basildon Borough Council | 510920612 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 108.55 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 108.57 | 0 | 108.57 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760939 | BRIDLEWAY | BILLERICAY | ESSEX | Basildon Borough Council | 510796601 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 28.41 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 28.49 | 0 | 28.49 | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760939 | BRIDLEWAY | BILLERICAY | ESSEX | Basildon Borough Council | 510958324 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 15.12 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 14.98 | 0 | 14.98 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | 2.14 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760940 | FOXHUNTER WALK | BILLERICAY | ESSEX | Basildon Borough Council | 510834277 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 149.68 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | -29.33 | 0 | -29.33 | -4.19 | -4.19 | -4.19 | -4.19 | -4.19 | -4.19 | -4.19 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760940 | FOXHUNTER WALK | BILLERICAY | ESSEX | Basildon Borough Council | 510837493 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 35.96 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 2.03 | 0 | 2.03 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Ashley Sheppard | IMGA223004 | WO-0760941 | DOUBLET MEWS | BILLERICAY | ESSEX | Basildon Borough Council | 510946186 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 118.32 | MR1 | N | T1 SECONDARY |  | 44305 | 44512 | 0.21 | 0 | 0.21 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223266 | WO-0760456 | CHURCH LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510809127 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 433.98 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 433.98 | 0 | 433.98 |  |  |  | 72.33 | 72.33 | 72.33 | 72.33 | 72.33 | 72.33 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223266 | WO-0760456 | CHURCH LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 606690508 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 2.3 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 2.28 | 0 | 2.28 |  |  |  | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223266 | WO-0760457 | CARROLL HILL | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 220000526184 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 61.96 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 61.98 | 0 | 61.98 |  |  |  | 10.33 | 10.33 | 10.33 | 10.33 | 10.33 | 10.33 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223266 | WO-0760458 | WELLFIELDS | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 220001897409 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 8.33 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 8.34 | 0 | 8.34 |  |  |  | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | 1.39 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223266 | WO-0760456 | CHURCH LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 637656835 | 1 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 11.02 | MR1 | N | T1 CONNECTED |  | 44487 | 44526 | 11.04 | 0 | 11.04 |  |  |  | 1.84 | 1.84 | 1.84 | 1.84 | 1.84 | 1.84 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223262 | WO-0759958 | WOODSIDE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510941554 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 7.34 | MR1 | N | T1 SECONDARY |  | 44529 | 44540 | 7.34 | 0 | 7.34 | [9 empty] | 3.67 | 3.67 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223262 | WO-0759958 | WOODSIDE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510941555 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 161.38 | MR1 | N | T1 SECONDARY |  | 44529 | 44540 | 161.38 | 0 | 161.38 | [9 empty] | 80.69 | 80.69 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223264 | WO-0760075 | DOVES COTTAGE |  |  | Epping Forest District Council (Lower) | 510973379 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 42.07 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 42.07 | 0 | 42.07 | [11 empty] | 42.07 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223268 | WO-0759607 | MARJORAMS AVENUE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510873615 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 100.29 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 100.3 | 100.3 | [14 empty] | 50.15 | 50.15 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223268 | WO-0759607 | MARJORAMS AVENUE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 604791473 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 2.21 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 2.22 | 2.22 | [14 empty] | 1.11 | 1.11 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223267 | WO-0761350 | ST JOHNS ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510906520 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 79.88 | MR1 | N | T1 SECONDARY |  | 44578 | 44589 | 0 | 79.88 | 79.88 | [16 empty] | 39.94 | 39.94 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223267 | WO-0761351 | GRASMERE CLOSE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510838816 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 104.74 | MR1 | N | T1 SECONDARY |  | 44578 | 44589 | 0 | 104.74 | 104.74 | [16 empty] | 52.37 | 52.37 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223269 | WO-0759744 | SHAFTESBURY | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510967906 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 159 | 131.71 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 131.72 | 131.72 | [18 empty] | 65.86 | 65.86 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223269 | WO-0759744 | SHAFTESBURY | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510967907 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 29.63 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 29.64 | 29.64 | [18 empty] | 14.82 | 14.82 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223269 | WO-0759744 | SHAFTESBURY | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510967908 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 30.74 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 30.74 | 30.74 | [18 empty] | 15.37 | 15.37 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223259 | WO-0761282 | FOREST SIDE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510833641 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 123.89 | MR1 | N | T1 SECONDARY |  | 44606 | 44624 | 0 | 123.9 | 123.9 | [20 empty] | 41.3 | 41.3 | 41.3 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Barry Gardner | IMGA223259 | WO-0761283 | HIGH ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510850164 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 105.91 | MR1 | N | T1 SECONDARY |  | 44606 | 44624 | 0 | 105.9 | 105.9 | [20 empty] | 35.3 | 35.3 | 35.3 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764546 | LYNNETT ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510870969 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 180.19 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 180.2 | 0 | 180.2 | 36.04 | 36.04 | 36.04 | 36.04 | 36.04 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764546 | LYNNETT ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510870970 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 40.12 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 40.15 | 0 | 40.15 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764546 | LYNNETT ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510870971 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 12.15 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 12.1 | 0 | 12.1 | 2.42 | 2.42 | 2.42 | 2.42 | 2.42 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764546 | LYNNETT ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510870972 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 14.4 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 14.4 | 0 | 14.4 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764546 | LYNNETT ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510870973 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 43.94 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 43.9 | 0 | 43.9 | 8.78 | 8.78 | 8.78 | 8.78 | 8.78 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764547 | DAVID ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510819711 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 139.64 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 139.6 | 0 | 139.6 | 27.92 | 27.92 | 27.92 | 27.92 | 27.92 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764548 | LYMINGTON ROAD |  |  |  | side street | 100 |  | T1 | mm | DI |  | LP | Policy | T1Policy | 4"-5" |  | 1.9 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | -0.05 | 0 | -0.05 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764548 | LYMINGTON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510870802 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 544.45 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 14.8 | 0 | 14.8 | 2.96 | 2.96 | 2.96 | 2.96 | 2.96 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764549 | FRESHWATER ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510834687 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 272.47 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 272.45 | 0 | 272.45 | 54.49 | 54.49 | 54.49 | 54.49 | 54.49 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764549 | FRESHWATER ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001679319 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 0.5 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 0.55 | 0 | 0.55 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764549 | FRESHWATER ROAD | DAGENHAM | REDBRIDGE | Barking and Dagenham London Borough Council | 510800132 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 21.28 | MR1 | N | T1 SECONDARY |  | 44424 | 44498 | 21.25 | 0 | 21.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223170 | WO-0764549 | FRESHWATER ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 607377428 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 2 | 7.13 | MR1 | N | T1 CONNECTED |  | 44424 | 44498 | 7.15 | 0 | 7.15 | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 | [22 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760420 | TURNAGE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510927490 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 24 | 329.74 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 329.77 | 0 | 329.77 | [5 empty] | 47.11 | 47.11 | 47.11 | 47.11 | 47.11 | 47.11 | 47.11 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760420 | TURNAGE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000676703 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 14.55 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 14.56 | 0 | 14.56 | [5 empty] | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760421 | JOAN ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510857368 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 12.26 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 12.25 | 0 | 12.25 | [5 empty] | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760421 | JOAN ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510857369 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 39.14 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 39.13 | 0 | 39.13 | [5 empty] | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760421 | JOAN ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510857370 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 158.69 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 158.69 | 0 | 158.69 | [5 empty] | 22.67 | 22.67 | 22.67 | 22.67 | 22.67 | 22.67 | 22.67 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760422 | GRAFTON GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510839578 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 13.13 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 13.16 | 0 | 13.16 | [5 empty] | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | 1.88 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760422 | GRAFTON GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510839579 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 60.18 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 60.2 | 0 | 60.2 | [5 empty] | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760422 | GRAFTON GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510839580 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 15.91 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 15.89 | 0 | 15.89 | [5 empty] | 2.27 | 2.27 | 2.27 | 2.27 | 2.27 | 2.27 | 2.27 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760422 | GRAFTON GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510839581 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 61.05 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 61.04 | 0 | 61.04 | [5 empty] | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760423 | GRAFTON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510839610 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 170.73 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 170.73 | 0 | 170.73 | [5 empty] | 24.39 | 24.39 | 24.39 | 24.39 | 24.39 | 24.39 | 24.39 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760423 | GRAFTON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510839611 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 34.41 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 34.44 | 0 | 34.44 | [5 empty] | 4.92 | 4.92 | 4.92 | 4.92 | 4.92 | 4.92 | 4.92 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760424 | JOAN GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510857366 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 73.54 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 73.57 | 0 | 73.57 | [5 empty] | 10.51 | 10.51 | 10.51 | 10.51 | 10.51 | 10.51 | 10.51 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223171 | WO-0760424 | JOAN GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510857367 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 39.76 | MR1 | N | T1 SECONDARY |  | 44501 | 44547 | 39.76 | 0 | 39.76 | [5 empty] | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223173 | WO-0761641 | WHALEBONE LANE SOUTH | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 629969013 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 3.11 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 3.12 | 3.12 | [14 empty] | 0.78 | 0.78 | 0.78 | 0.78 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223173 | WO-0761641 | WHALEBONE LANE SOUTH | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000389326 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 244.4 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 244.4 | 244.4 | [14 empty] | 61.1 | 61.1 | 61.1 | 61.1 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223173 | WO-0761642 | PURLAND CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510896219 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 29 | 154.23 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 154.24 | 154.24 | [14 empty] | 38.56 | 38.56 | 38.56 | 38.56 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223173 | WO-0761642 | PURLAND CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510896220 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 119.06 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 119.08 | 119.08 | [14 empty] | 29.77 | 29.77 | 29.77 | 29.77 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510899953 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 11.64 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 9.54 | 9.54 | [18 empty] | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510899955 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 621.2 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 508.23 | 508.23 | [18 empty] | 56.47 | 56.47 | 56.47 | 56.47 | 56.47 | 56.47 | 56.47 | 56.47 | 56.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510899958 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 111.73 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 91.44 | 91.44 | [18 empty] | 10.16 | 10.16 | 10.16 | 10.16 | 10.16 | 10.16 | 10.16 | 10.16 | 10.16 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510899966 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 754.98 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 617.67 | 617.67 | [18 empty] | 68.63 | 68.63 | 68.63 | 68.63 | 68.63 | 68.63 | 68.63 | 68.63 | 68.63 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000243842 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 3.76 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 3.06 | 3.06 | [18 empty] | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000321118 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 2.85 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 2.34 | 2.34 | [18 empty] | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760384 | REEDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000351537 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 7.72 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 6.3 | 6.3 | [18 empty] | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760385 | ROGERS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001644829 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 112.25 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 91.8 | 91.8 | [18 empty] | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | 10.2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Billy Linwood | IMGA223164 | WO-0760386 | STERRY ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510917353 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 9.93 | MR1 | N | T1 SECONDARY |  | 44592 | 44666 | 0 | 8.1 | 8.1 | [18 empty] | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | Forefront | Bradley Bell | IMGA223381 | WO-0762160 | CHURCH STREET | BILLERICAY | ESSEX | Basildon Borough Council | 510809859 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 5872 | 234.64 | MR1 | N | T1 PAST |  | 44473 | 44505 | 234.65 | 0 | 234.65 |  | 46.93 | 46.93 | 46.93 | 46.93 | 46.93 | [21 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Forefront | Bradley Bell | IMGA223381 | WO-0762160 | CHURCH STREET | BILLERICAY | ESSEX | Basildon Borough Council | 604162885 | 2 |  | T1 | Inch | ST | Above Ground | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 13.64 | MR1 | N | T1 CONNECTED |  | 44473 | 44505 | 13.65 | 0 | 13.65 |  | 2.73 | 2.73 | 2.73 | 2.73 | 2.73 | [21 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Bradley Bell | IMGA223385 | WO-0762255 | ROBERT WAY | WICKFORD | ESSEX | Basildon Borough Council | 510901698 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 3080 | 265.27 | MR1 | N | T1 PAST |  | 44508 | 44540 | 265.25 | 0 | 265.25 | [6 empty] | 53.05 | 53.05 | 53.05 | 53.05 | 53.05 | [16 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Bradley Bell | IMGA223385 | WO-0762255 | ROBERT WAY | WICKFORD | ESSEX | Basildon Borough Council | 510901704 | 6 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 118 | 3.52 | MR1 | N | T1 CONNECTED |  | 44508 | 44540 | 3.5 | 0 | 3.5 | [6 empty] | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | [16 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Bradley Bell | IMGA223385 | WO-0762255 | ROBERT WAY | WICKFORD | ESSEX | Basildon Borough Council | 606440307 | 6 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 347 | 2.13 | MR1 | N | T1 CONNECTED |  | 44508 | 44540 | 2.15 | 0 | 2.15 | [6 empty] | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | [16 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761618 | BALLARDS ROAD |  |  |  | side street | 8 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 1.4 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.04 | 0 | 0.04 | 0.04 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761618 | BALLARDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510786224 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 715.38 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 7.48 | 0 | 7.48 | 7.48 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761618 | BALLARDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510786246 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 2.88 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 1.38 | 0 | 1.38 | 1.38 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761618 | BALLARDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000775595 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 20 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.04 | 0 | 0.04 | 0.04 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761618 | BALLARDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000776470 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 6.8 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.04 | 0 | 0.04 | 0.04 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761618 | BALLARDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000813466 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 30.54 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.06 | 0 | 0.06 | 0.06 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761619 | RIDGEWELL CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510786198 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 14 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.04 | 0 | 0.04 | 0.04 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761619 | RIDGEWELL CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901018 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 33 | 121.88 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 1.12 | 0 | 1.12 | 1.12 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761619 | RIDGEWELL CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901019 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 90.5 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | -0.02 | 0 | -0.02 | -0.02 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761619 | RIDGEWELL CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901020 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 55 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | -0.04 | 0 | -0.04 | -0.04 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761619 | RIDGEWELL CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901022 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 32.5 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.02 | 0 | 0.02 | 0.02 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223165 | WO-0761620 | OVAL ROAD NORTH | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510888230 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1.52 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.04 | 0 | 0.04 | 0.04 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223166 | WO-0759726 | CHURCH LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510786226 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 262.26 | MR1 | N | T1 SECONDARY |  | 44459 | 44477 | 262.26 | 0 | 262.26 | 131.13 | 131.13 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761287 | FRIZLANDS LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510834886 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 228.69 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 228.7 | 0 | 228.7 |  |  | 45.74 | 45.74 | 45.74 | 45.74 | 45.74 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761287 | FRIZLANDS LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510834888 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 351.92 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 351.9 | 0 | 351.9 |  |  | 70.38 | 70.38 | 70.38 | 70.38 | 70.38 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761287 | FRIZLANDS LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 606686753 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 2.13 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 2.15 | 0 | 2.15 |  |  | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761288 | RUSHOLME AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000034039 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 19.78 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 19.8 | 0 | 19.8 |  |  | 3.96 | 3.96 | 3.96 | 3.96 | 3.96 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761288 | RUSHOLME AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001292456 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 49.25 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 49.25 | 0 | 49.25 |  |  | 9.85 | 9.85 | 9.85 | 9.85 | 9.85 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761289 | LISTOWEL ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510867230 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 142.04 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 142.05 | 0 | 142.05 |  |  | 28.41 | 28.41 | 28.41 | 28.41 | 28.41 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761290 | CRESCENT ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001279400 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 2.38 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 2.4 | 0 | 2.4 |  |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223157 | WO-0761291 | LAWRENCE CRESCENT | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 629756195 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 0.96 | MR1 | N | T1 SECONDARY |  | 44480 | 44512 | 0.95 | 0 | 0.95 |  |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510956368 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 285.26 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 285.25 | 0 | 285.25 | [7 empty] | 57.05 | 57.05 | 57.05 | 57.05 | 57.05 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510956370 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 144.25 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 144.25 | 0 | 144.25 | [7 empty] | 28.85 | 28.85 | 28.85 | 28.85 | 28.85 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510956375 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 144.35 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 144.35 | 0 | 144.35 | [7 empty] | 28.87 | 28.87 | 28.87 | 28.87 | 28.87 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510956376 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 7.57 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 7.55 | 0 | 7.55 | [7 empty] | 1.51 | 1.51 | 1.51 | 1.51 | 1.51 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 606673050 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 2.64 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 2.65 | 0 | 2.65 | [7 empty] | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001572633 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 7.06 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 7.05 | 0 | 7.05 | [7 empty] | 1.41 | 1.41 | 1.41 | 1.41 | 1.41 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761683 | OXLOW LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001572884 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 15.9 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 15.9 | 0 | 15.9 | [7 empty] | 3.18 | 3.18 | 3.18 | 3.18 | 3.18 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761681 | ROBINSON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901802 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 220.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 220.68 | 220.68 | [14 empty] | 73.56 | 73.56 | 73.56 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761681 | ROBINSON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 606621685 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 4.39 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 4.38 | 4.38 | [14 empty] | 1.46 | 1.46 | 1.46 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223161 | WO-0761682 | STERRY ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901803 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 74.3 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 74.31 | 74.31 | [14 empty] | 24.77 | 24.77 | 24.77 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510855075 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 3.98 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 4 | 4 | [17 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510880235 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 14.72 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 14.7 | 14.7 | [17 empty] | 1.47 | 1.47 | 1.47 | 1.47 | 1.47 | 1.47 | 1.47 | 1.47 | 1.47 | 1.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510880237 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 565.45 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 565.5 | 565.5 | [17 empty] | 56.55 | 56.55 | 56.55 | 56.55 | 56.55 | 56.55 | 56.55 | 56.55 | 56.55 | 56.55 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510880238 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 168.42 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 168.4 | 168.4 | [17 empty] | 16.84 | 16.84 | 16.84 | 16.84 | 16.84 | 16.84 | 16.84 | 16.84 | 16.84 | 16.84 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510880239 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 95.02 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 95 | 95 | [17 empty] | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510880240 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 124.11 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 124.1 | 124.1 | [17 empty] | 12.41 | 12.41 | 12.41 | 12.41 | 12.41 | 12.41 | 12.41 | 12.41 | 12.41 | 12.41 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510880241 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 38.87 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 38.9 | 38.9 | [17 empty] | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | 3.89 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 606807594 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 2.02 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 2 | 2 | [17 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001619969 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 1 | 1 | [17 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760381 | MOVERS LANE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001786149 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 10.95 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 11 | 11 | [17 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Dan Beard | IMGA223148 | WO-0760382 | ST JOHNS ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510906495 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 181.7 | MR1 | N | T1 SECONDARY |  | 44585 | 44652 | 0 | 181.7 | 181.7 | [17 empty] | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510916970 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 23.88 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 12.96 | 8.64 | 21.6 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 |  |  | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | 1.08 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510924785 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 23.6 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 12.84 | 8.56 | 21.4 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 |  |  | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510924786 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 36 | 887.44 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 484.08 | 322.72 | 806.8 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 |  |  | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | 40.34 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510924788 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 19.21 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 10.56 | 7.04 | 17.6 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 |  |  | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | 0.88 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510924794 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 221 | 413 | MR1 | N | T1 PAST |  | 44382 | 44617 | 104.28 | 69.52 | 173.8 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 |  |  | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | 8.69 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510924795 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 465.31 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 0.24 | 0.16 | 0.4 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761771 | THORNDON AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510924796 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 8 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 4.44 | 2.96 | 7.4 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 |  |  | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | 0.37 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761772 | CADOGAN AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510800902 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 325.73 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | -5.04 | -3.36 | -8.4 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 |  |  | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | -0.42 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Dan Marsh | IMGA223088 | WO-0761772 | CADOGAN AVENUE | WEST HORNDON | ESSEX | Brentwood Borough Council | 510800903 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 128 | 285.33 | MR1 | N | T1 SECONDARY |  | 44382 | 44617 | 5.04 | 3.36 | 8.4 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 |  |  | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762166 | LABURNUM AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510958469 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 65.24 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 12.5 | 16.25 | 28.75 |  |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |  |  | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762166 | LABURNUM AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510958470 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 334.13 | MR1 | N | T1 CBA |  | 44487 | 44844 | 64.3 | 83.59 | 147.89 |  |  | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 |  |  | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | 6.43 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762166 | LABURNUM AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510958471 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 106.33 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 20.4 | 26.52 | 46.92 |  |  | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 |  |  | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762167 | LILAC AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510866092 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 521 | 323.01 | MR1 | N | T1 PAST |  | 44487 | 44844 | 62.1 | 80.73 | 142.83 |  |  | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 |  |  | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | 6.21 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762167 | LILAC AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 220001635021 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 8.85 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 1.7 | 2.21 | 3.91 |  |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 |  |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762168 | LAUREL AVENUE |  |  |  | 510864090 | 4 |  | T1 | Inch | ST |  | MP | Non-Policy | T1Non-Policy | 4"-5" |  | 79.44 | MR2 | Y | T1 ENM CANDIDATE |  | 44487 | 44844 | 15.3 | 19.89 | 35.19 |  |  | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 |  |  | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | 1.53 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762168 | LAUREL AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 220001636021 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 4.1 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 0.8 | 1.04 | 1.84 |  |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 |  |  | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762169 | ALMOND AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510781288 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 119.61 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 23 | 29.9 | 52.9 |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0762170 | DEIRDRE AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 220001368360 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 420.49 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 80.9 | 105.17 | 186.07 |  |  | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 |  |  | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | 8.09 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0765827 | ST PETERS TERRACE |  |  |  | 220001368364 | 4 |  | T1 | Inch | ST |  | MP | Non-Policy | T1Non-Policy | 4"-5" |  | 121.39 | MR1 | N | T1 ENM CANDIDATE |  | 44487 | 44844 | 23.3 | 30.29 | 53.59 |  |  | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 |  |  | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | 2.33 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dan Parish | IMGA223387 | WO-0765828 | LONDON ROAD |  |  |  | 220001368359 | 2 |  | T1 | Inch | ST |  | MP | Non-Policy | T1Non-Policy | 4"-5" |  | 89.51 | MR1 | N | T1 ENM CANDIDATE |  | 44487 | 44844 | 17.2 | 22.36 | 39.56 |  |  | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 |  |  | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | 1.72 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Dean Wilder | IMGA223059 | WO-0761076 | TILLINGHAM WAY |  |  |  | side street | 100 |  | T1 | mm | DI |  | LP | Policy | T1Policy | 4"-5" |  | 8 | MR1 | N | T1 SECONDARY |  | 44291 | 44505 | 0.06 | 0 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Dean Wilder | IMGA223059 | WO-0761076 | TILLINGHAM WAY | RAYLEIGH | ESSEX | Rochford District Council | 510970456 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 42 | 257.1 | MR1 | N | T1 SECONDARY |  | 44291 | 44505 | 45 | 0 | 45 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Dean Wilder | IMGA223059 | WO-0761077 | FYFIELD PATH | RAYLEIGH | ESSEX | Rochford District Council | 510970457 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 177 | 138.89 | MR1 | N | T1 SECONDARY |  | 44291 | 44505 | 14.88 | 0 | 14.88 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Dean Wilder | IMGA223059 | WO-0761078 | BARDFIELD WAY | RAYLEIGH | ESSEX | Rochford District Council | 510955673 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 97.68 | MR1 | N | T1 SECONDARY |  | 44291 | 44505 | 21.66 | 0 | 21.66 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | 3.61 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Dean Wilder | IMGA223059 | WO-0761078 | BARDFIELD WAY | RAYLEIGH | ESSEX | Rochford District Council | 510955675 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 268.59 | MR1 | N | T1 SECONDARY |  | 44291 | 44505 | 203.28 | 0 | 203.28 | 33.88 | 33.88 | 33.88 | 33.88 | 33.88 | 33.88 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dean Wilder | IMGA223392 | WO-0762210 | HETZAND ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510849333 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 66.64 | MR1 | N | T1 CBA |  | 44501 | 44512 | 66.64 | 0 | 66.64 | [5 empty] | 33.32 | 33.32 | [20 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 510913651 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 8598 | 466.23 | MR1 | N | T1 PAST |  | 44515 | 44547 | 233.1 | 0 | 233.1 | [7 empty] | 46.62 | 46.62 | 46.62 | 46.62 | 46.62 | [15 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606441393 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 347 | 2.14 | MR1 | N | T1 CONNECTED |  | 44515 | 44547 | 1.05 | 0 | 1.05 | [7 empty] | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [15 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606455077 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 2.53 | MR1 | N | T1 CONNECTED |  | 44515 | 44547 | 1.25 | 0 | 1.25 | [7 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [15 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606456496 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 5.09 | MR1 | N | T1 CONNECTED |  | 44515 | 44547 | 2.55 | 0 | 2.55 | [7 empty] | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | [15 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606468744 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 4.71 | MR1 | N | T1 CONNECTED |  | 44515 | 44547 | 2.35 | 0 | 2.35 | [7 empty] | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | [15 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 510913651 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 8598 | 466.23 | MR1 | N | T1 PAST |  | 44565 | 44596 | 0 | 233.1 | 233.1 | [14 empty] | 46.62 | 46.62 | 46.62 | 46.62 | 46.62 | [8 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606441393 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 347 | 2.14 | MR1 | N | T1 CONNECTED |  | 44565 | 44596 | 0 | 1.05 | 1.05 | [14 empty] | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [8 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606455077 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 2.53 | MR1 | N | T1 CONNECTED |  | 44565 | 44596 | 0 | 1.25 | 1.25 | [14 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606456496 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 5.09 | MR1 | N | T1 CONNECTED |  | 44565 | 44596 | 0 | 2.55 | 2.55 | [14 empty] | 0.51 | 0.51 | 0.51 | 0.51 | 0.51 | [8 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Dean Wilder | IMGA223399 | WO-0762261 | SOUTHEND ROAD | HOCKLEY | ESSEX | Rochford District Council | 606468744 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 4.71 | MR1 | N | T1 CONNECTED |  | 44565 | 44596 | 0 | 2.35 | 2.35 | [14 empty] | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | [8 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dean Wilder | IMGA223391 | WO-0762226 | LONDON ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510868723 | 6 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 3067 | 227.7 | MR1 | N | T1 PAST |  | 44599 | 44680 | 0 | 151.84 | 151.84 | [19 empty] | 18.98 | 18.98 | 18.98 | 18.98 | 18.98 | 18.98 | 18.98 | 18.98 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dean Wilder | IMGA223391 | WO-0762226 | LONDON ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510868732 | 6 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 461 | 3.63 | MR1 | N | T1 CONNECTED |  | 44599 | 44680 | 0 | 2.4 | 2.4 | [19 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dean Wilder | IMGA223391 | WO-0762226 | LONDON ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 606484247 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 84 | 4.07 | MR1 | N | T1 CONNECTED |  | 44599 | 44680 | 0 | 2.72 | 2.72 | [19 empty] | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Dean Wilder | IMGA223391 | WO-0762226 | LONDON ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 622460522 | 6 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 874 | 0.64 | MR1 | N | T1 CONNECTED |  | 44599 | 44680 | 0 | 0.4 | 0.4 | [19 empty] | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762178 | MARGARITE WAY | WICKFORD | ESSEX | Basildon Borough Council | 510873463 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 196.5 | MR1 | N | T1 CBA |  | 44487 | 44844 | 37.8 | 49.14 | 86.94 |  |  | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 |  |  | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | 3.78 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762179 | LOUVAINE AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 629609987 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 12.4 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 2.4 | 3.12 | 5.52 |  |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 |  |  | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762179 | LOUVAINE AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 220001368358 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 564 | 307.61 | MR1 | N | T1 PAST |  | 44487 | 44844 | 59.2 | 76.96 | 136.16 |  |  | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 |  |  | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | 5.92 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762180 | ELIZABETH DRIVE | WICKFORD | ESSEX | Basildon Borough Council | 510826603 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 466.04 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 89.6 | 116.48 | 206.08 |  |  | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 |  |  | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762181 | VICTORIA CRESCENT |  |  | Basildon Borough Council | 629609990 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 126.83 | MR1 | N | T1 CBA |  | 44487 | 44844 | 24.4 | 31.72 | 56.12 |  |  | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 |  |  | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762182 | VICTORIA AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510964802 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 147.42 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 28.4 | 36.92 | 65.32 |  |  | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 |  |  | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | 2.84 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762182 | VICTORIA AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 510964803 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 122.8 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 23.6 | 30.68 | 54.28 |  |  | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 |  |  | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | 2.36 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762182 | VICTORIA AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 606455054 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 2.53 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 0.5 | 0.65 | 1.15 |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Gerrard O'Day | IMGA223390 | WO-0762182 | VICTORIA AVENUE | WICKFORD | ESSEX | Basildon Borough Council | 220001368361 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 139 | 39.72 | MR1 | N | T1 CONNECTED |  | 44487 | 44844 | 7.6 | 9.88 | 17.48 |  |  | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 |  |  | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223071 | WO-0761678 | MARCUS AVENUE | THORPE BAY | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220000658606 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 14.68 | MR1 | N | T1 SECONDARY |  | 44438 | 44477 | 14.7 | 0 | 14.7 | 7.35 | 7.35 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223071 | WO-0761679 | ST JAMES AVENUE | THORPE BAY | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220000655285 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 21.65 | MR1 | N | T1 SECONDARY |  | 44438 | 44477 | 21.66 | 0 | 21.66 | 10.83 | 10.83 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223071 | WO-0761680 | STATION ROAD | THORPE BAY | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510916934 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 252.09 | MR1 | N | T1 SECONDARY |  | 44438 | 44477 | 59.82 | 0 | 59.82 | 29.91 | 29.91 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223055 | WO-0760145 | GROVE ROAD | RAYLEIGH | ESSEX | Rochford District Council | 510842906 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 405 | 99.48 | MR1 | N | T1 PAST |  | 44480 | 44498 | 99.48 | 0 | 99.48 |  |  | 33.16 | 33.16 | 33.16 | [22 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223055 | WO-0760145 | GROVE ROAD | RAYLEIGH | ESSEX | Rochford District Council | 635804310 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 331 | 36.4 | MR1 | N | T1 PAST |  | 44480 | 44498 | 36.39 | 0 | 36.39 |  |  | 12.13 | 12.13 | 12.13 | [22 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223060 | WO-0761658 | SOMERSET AVENUE | ROCHFORD | ESSEX | Rochford District Council | 510912714 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 35.07 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 35.1 | 0 | 35.1 | [5 empty] | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223060 | WO-0761658 | SOMERSET AVENUE | ROCHFORD | ESSEX | Rochford District Council | 510912715 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 389.69 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 389.7 | 0 | 389.7 | [5 empty] | 64.95 | 64.95 | 64.95 | 64.95 | 64.95 | 64.95 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223060 | WO-0761658 | SOMERSET AVENUE | ROCHFORD | ESSEX | Rochford District Council | 220000593911 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 1.02 | 0 | 1.02 | [5 empty] | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223060 | WO-0761659 | PERCY COTTIS ROAD | ROCHFORD | ESSEX | Rochford District Council | 220000657283 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 81.36 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 81.36 | 0 | 81.36 | [5 empty] | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 | 13.56 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223060 | WO-0761660 | THE DRIVE | ROCHFORD | ESSEX | Rochford District Council | 220000693520 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 4.69 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 4.68 | 0 | 4.68 | [5 empty] | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783797 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 30.26 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 21.84 | 21.84 | [14 empty] | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | 1.68 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783798 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 16.5 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 11.96 | 11.96 | [14 empty] | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783799 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 33.02 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 23.79 | 23.79 | [14 empty] | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783802 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 71.84 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 51.87 | 51.87 | [14 empty] | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783803 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 40.53 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 29.25 | 29.25 | [14 empty] | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783804 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 44.03 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 31.85 | 31.85 | [14 empty] | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783805 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 85.62 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 61.88 | 61.88 | [14 empty] | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | 4.76 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783806 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 112.94 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 81.51 | 81.51 | [14 empty] | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783807 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 142.18 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 102.7 | 102.7 | [14 empty] | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | 7.9 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783808 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 82.79 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 59.8 | 59.8 | [14 empty] | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783809 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 32.63 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 23.53 | 23.53 | [14 empty] | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | 1.81 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761507 | ASHANTI CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783810 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 77.29 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 55.77 | 55.77 | [14 empty] | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | 4.29 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783813 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 54.02 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 39 | 39 | [14 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824051 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 33.38 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 24.05 | 24.05 | [14 empty] | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | 1.85 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824052 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 78.66 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 56.81 | 56.81 | [14 empty] | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824053 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 37.76 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 27.3 | 27.3 | [14 empty] | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824054 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 31.26 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 22.62 | 22.62 | [14 empty] | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | 1.74 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824055 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 22.98 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 16.64 | 16.64 | [14 empty] | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824056 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 72.41 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 52.26 | 52.26 | [14 empty] | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | 4.02 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761508 | EAGLE WAY | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510824070 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 26.27 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 18.98 | 18.98 | [14 empty] | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | HArry Winter | IMGA223063 | WO-0761509 | ELM ROAD | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510783811 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 151.45 | MR1 | N | T1 SECONDARY |  | 44565 | 44687 | 0 | 109.33 | 109.33 | [14 empty] | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Ioan Iusco | IMGA223049 | WO-0759618 | ASSANDUNE CLOSE | ASHINGDON | ESSEX | Rochford District Council | 510784589 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 80.88 | MR1 | N | T1 SECONDARY |  | 44445 | 44484 | 80.88 | 0 | 80.88 | 26.96 | 26.96 | 26.96 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Ioan Iusco | IMGA223049 | WO-0759619 | NEWTON HALL GARDENS | ASHINGDON | ESSEX | Rochford District Council | 510882847 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 68.56 | MR1 | N | T1 SECONDARY |  | 44445 | 44484 | -0.42 | 0 | -0.42 | -0.14 | -0.14 | -0.14 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Ioan Iusco | IMGA223049 | WO-0759619 | NEWTON HALL GARDENS | ASHINGDON | ESSEX | Rochford District Council | 510882849 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 142.29 | MR1 | N | T1 SECONDARY |  | 44445 | 44484 | 120.33 | 0 | 120.33 | 40.11 | 40.11 | 40.11 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Ioan Iusco | IMGA223049 | WO-0759619 | NEWTON HALL GARDENS | ASHINGDON | ESSEX | Rochford District Council | 510882848 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 8 | 75.05 | MR1 | N | T1 CONNECTED |  | 44445 | 44484 | 0.06 | 0 | 0.06 | 0.02 | 0.02 | 0.02 | [24 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Ioan Iusco | IMGA223049 | WO-0759619 | NEWTON HALL GARDENS | ASHINGDON | ESSEX | Rochford District Council | 602801208 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 18 | 3.4 | MR1 | N | T1 CONNECTED |  | 44445 | 44484 | 3.42 | 0 | 3.42 | 1.14 | 1.14 | 1.14 | [24 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Ioan Iusco | IMGA223049 | WO-0759619 | NEWTON HALL GARDENS | ASHINGDON | ESSEX | Rochford District Council | 607100683 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 4.73 | MR1 | N | T1 CONNECTED |  | 44445 | 44484 | 4.74 | 0 | 4.74 | 1.58 | 1.58 | 1.58 | [24 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835565 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 199.84 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 199.87 | 0 | 199.87 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | 18.17 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835566 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" |  | 95.95 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 95.92 | 0 | 95.92 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835567 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 46.48 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 46.53 | 0 | 46.53 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | 4.23 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835573 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 134.37 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 134.42 | 0 | 134.42 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | 12.22 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835577 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 54.75 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 54.78 | 0 | 54.78 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | 4.98 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835579 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 176.49 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 176.44 | 0 | 176.44 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | 16.04 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761303 | SYLVAN CLOSE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510920267 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 76.07 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 76.12 | 0 | 76.12 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | 6.92 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761303 | SYLVAN CLOSE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510920268 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 24.42 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 24.42 | 0 | 24.42 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | 2.22 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761304 | CLEVELAND ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 220001264902 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 12.19 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 12.21 | 0 | 12.21 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761305 | GRAFTON ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 220001222909 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 5.84 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 5.83 | 0 | 5.83 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761306 | LEIGH ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 220001229185 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.67 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 2.64 | 0 | 2.64 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761307 | ASHINGDALE CLOSE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835566 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 95.95 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 95.92 | 0 | 95.92 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | 8.72 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761308 | MEYNELL AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 220001203486 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 2.24 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 2.2 | 0 | 2.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761309 | MARINE APPROACH | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 220001212300 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 2.89 | MR1 | N | T1 SECONDARY |  | 44466 | 44540 | 2.86 | 0 | 2.86 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223138 | WO-0761302 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510935684 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 21.9 | MR1 | N | T1 GD1 ENM |  | 44466 | 44540 | 21.89 | 0 | 21.89 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | 1.99 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761215 | OAK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510885503 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 80.44 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 80.48 | 80.48 | [14 empty] | 10.06 | 10.06 | 10.06 | 10.06 | 10.06 | 10.06 | 10.06 | 10.06 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761216 | HAWTHORN ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510847397 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 100.55 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 100.56 | 100.56 | [14 empty] | 12.57 | 12.57 | 12.57 | 12.57 | 12.57 | 12.57 | 12.57 | 12.57 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761217 | ELM ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510827173 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 171.32 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 171.36 | 171.36 | [14 empty] | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | 21.42 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761218 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835569 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 96.2 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 96.24 | 96.24 | [14 empty] | 12.03 | 12.03 | 12.03 | 12.03 | 12.03 | 12.03 | 12.03 | 12.03 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761218 | FURTHERWICK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510835570 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 32.57 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 32.56 | 32.56 | [14 empty] | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | 4.07 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761219 | THE PARKWAY | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510923796 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 50.19 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 50.16 | 50.16 | [14 empty] | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | 6.27 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761219 | THE PARKWAY | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510923797 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 81.17 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 81.2 | 81.2 | [14 empty] | 10.15 | 10.15 | 10.15 | 10.15 | 10.15 | 10.15 | 10.15 | 10.15 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223137 | WO-0761220 | BLACKTHORNE ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510792657 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 90.7 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 90.72 | 90.72 | [14 empty] | 11.34 | 11.34 | 11.34 | 11.34 | 11.34 | 11.34 | 11.34 | 11.34 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761446 | JOTMANS LANE | BENFLEET | ESSEX | Castle Point Borough Council | 510857652 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 22.94 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 22.95 | 22.95 | [22 empty] | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761446 | JOTMANS LANE | BENFLEET | ESSEX | Castle Point Borough Council | 510857653 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 326.59 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 326.6 | 326.6 | [22 empty] | 65.32 | 65.32 | 65.32 | 65.32 | 65.32 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761446 | JOTMANS LANE | BENFLEET | ESSEX | Castle Point Borough Council | 510857654 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 5.52 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 5.5 | 5.5 | [22 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761446 | JOTMANS LANE | BENFLEET | ESSEX | Castle Point Borough Council | 220000638001 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 2.93 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 2.95 | 2.95 | [22 empty] | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761446 | JOTMANS LANE | BENFLEET | ESSEX | Castle Point Borough Council | 220000664208 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 2.4 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 2.4 | 2.4 | [22 empty] | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761447 | WATLINGTON ROAD |  |  | Castle Point Borough Council | 220000620443 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 2.68 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 2.7 | 2.7 | [22 empty] | 0.54 | 0.54 | 0.54 | 0.54 | 0.54 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761447 | WATLINGTON ROAD |  |  | Castle Point Borough Council | 220000620446 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 4.02 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 4 | 4 | [22 empty] | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761448 | APPLETON ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 220000708694 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 2.89 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 2.9 | 2.9 | [22 empty] | 0.58 | 0.58 | 0.58 | 0.58 | 0.58 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761448 | APPLETON ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 220000708697 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 3.23 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 3.25 | 3.25 | [22 empty] | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Jamie Clarke | IMGA223046 | WO-0761449 | HIGH ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510849793 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 20.61 | MR1 | N | T1 SECONDARY |  | 44620 | 44652 | 0 | 20.6 | 20.6 | [22 empty] | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510970739 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 123.86 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 123.84 | 0 | 123.84 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | 10.32 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510970741 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1150.54 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 1150.56 | 0 | 1150.56 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | 95.88 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510970742 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 50.91 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 50.88 | 0 | 50.88 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | 4.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 606496190 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 143.94 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 143.88 | 0 | 143.88 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | 11.99 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 636005097 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 54.24 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 54.12 | 0 | 54.12 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 636005098 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 776.72 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | -261.36 | 0 | -261.36 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | -21.78 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761456 | BRAGG CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510970743 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 15.63 | MR1 | N | T1 SECONDARY |  | 44445 | 44547 | 15.6 | 0 | 15.6 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223178 | WO-0761455 | LODGE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 606662749 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 15 | 8.74 | MR1 | N | T1 CONNECTED |  | 44445 | 44547 | 8.76 | 0 | 8.76 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223144 | WO-0759697 | RENWICK ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510900314 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 242.4 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 242.4 | 242.4 | [14 empty] | 80.8 | 80.8 | 80.8 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Jamie Wilder | IMGA223144 | WO-0759697 | RENWICK ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510900310 | 200 |  | T1 | mm | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 1 | 7.04 | MR1 | N | T1 CONNECTED |  | 44565 | 44578 | 0 | 7.05 | 7.05 | [14 empty] | 2.35 | 2.35 | 2.35 | [10 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | LDP Blank | Jamie Wilder | IMGA223362 | WO-0759771 | SPRINGFIELD GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 220000562915 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 107.64 | MR1 | N | T1 SECONDARY |  | 44578 | 44610 | 0 | 53.8 | 53.8 | [16 empty] | 10.76 | 10.76 | 10.76 | 10.76 | 10.76 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | LDP Blank | Jamie Wilder | IMGA223362 | WO-0759771 | SPRINGFIELD GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 220000564394 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 675.69 | MR1 | N | T1 SECONDARY |  | 44578 | 44610 | 0 | 337.9 | 337.9 | [16 empty] | 67.58 | 67.58 | 67.58 | 67.58 | 67.58 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | LDP Blank | Jamie Wilder | IMGA223362 | WO-0759771 | SPRINGFIELD GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 220000562915 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 107.64 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 53.82 | 53.82 | [21 empty] | 8.97 | 8.97 | 8.97 | 8.97 | 8.97 | 8.97 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | LDP Blank | Jamie Wilder | IMGA223362 | WO-0759771 | SPRINGFIELD GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 220000564394 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 675.69 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 337.86 | 337.86 | [21 empty] | 56.31 | 56.31 | 56.31 | 56.31 | 56.31 | 56.31 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761758 | BEAUCHAMPS DRIVE | WICKFORD | ESSEX | Basildon Borough Council | 510788716 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 251.1 | MR1 | N | T1 SECONDARY |  | 44389 | 44547 | 251.16 | 0 | 251.16 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | 20.93 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761758 | BEAUCHAMPS DRIVE | WICKFORD | ESSEX | Basildon Borough Council | 510788726 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 715.28 | MR1 | N | T1 SECONDARY |  | 44389 | 44547 | 403.32 | 0 | 403.32 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | 33.61 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761758 | BEAUCHAMPS DRIVE | WICKFORD | ESSEX | Basildon Borough Council | 220001597240 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.21 | MR1 | N | T1 SECONDARY |  | 44389 | 44547 | 2.28 | 0 | 2.28 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761758 | BEAUCHAMPS DRIVE | WICKFORD | ESSEX | Basildon Borough Council | 220001198877 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 12 | 76.7 | MR1 | N | T1 CONNECTED |  | 44389 | 44547 | 76.56 | 0 | 76.56 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761759 | ST CLERES CRESCENT | WICKFORD | ESSEX | Basildon Borough Council | 510905834 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 94.14 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 94.16 | 94.16 | [14 empty] | 23.54 | 23.54 | 23.54 | 23.54 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761759 | ST CLERES CRESCENT | WICKFORD | ESSEX | Basildon Borough Council | 510905835 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 49.06 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 49.08 | 49.08 | [14 empty] | 12.27 | 12.27 | 12.27 | 12.27 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761759 | ST CLERES CRESCENT | WICKFORD | ESSEX | Basildon Borough Council | 510905836 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 131.58 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 131.6 | 131.6 | [14 empty] | 32.9 | 32.9 | 32.9 | 32.9 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Forefront | Jason Skinner | IMGA223084 | WO-0761759 | ST CLERES CRESCENT | WICKFORD | ESSEX | Basildon Borough Council | 606716012 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 1.86 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 1.88 | 1.88 | [14 empty] | 0.47 | 0.47 | 0.47 | 0.47 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223106 | WO-0761396 | HIGH ROAD | GRAYS | THURROCK | Thurrock Council | 510850090 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 613.79 | MR1 | N | T1 SECONDARY |  | 44494 | 44547 | 613.76 | 0 | 613.76 |  |  |  |  | 76.72 | 76.72 | 76.72 | 76.72 | 76.72 | 76.72 | 76.72 | 76.72 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223106 | WO-0761397 | SHERWOOD | GRAYS | THURROCK | Thurrock Council | 510911247 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 192.64 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 192.64 | 192.64 | [14 empty] | 96.32 | 96.32 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223122 | WO-0761502 | NORTH ROAD | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510884066 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 370.56 | MR1 | N | T1 SECONDARY |  | 44578 | 44652 | 0 | 370.59 | 370.59 | [16 empty] | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | 33.69 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223122 | WO-0761503 | SOUTHGATE | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510913900 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 140 | MR1 | N | T1 SECONDARY |  | 44578 | 44652 | 0 | 140.03 | 140.03 | [16 empty] | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | 12.73 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223122 | WO-0761504 | WATTS CRESCENT | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510933473 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 142.14 | MR1 | N | T1 SECONDARY |  | 44578 | 44652 | 0 | 142.12 | 142.12 | [16 empty] | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223122 | WO-0761505 | WOOD AVENUE | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510940323 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 227.42 | MR1 | N | T1 SECONDARY |  | 44578 | 44652 | 0 | 227.37 | 227.37 | [16 empty] | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | 20.67 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223122 | WO-0761506 | ARTERIAL ROAD | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510975329 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 52.13 | MR1 | N | T1 SECONDARY |  | 44578 | 44652 | 0 | 52.14 | 52.14 | [16 empty] | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | 4.74 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | JDT TBA 1 | IMGA223122 | WO-0761506 | ARTERIAL ROAD | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510975330 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 106.82 | MR1 | N | T1 SECONDARY |  | 44578 | 44652 | 0 | 106.81 | 106.81 | [16 empty] | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | 9.71 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | JDT TBA 2 | IMGA223363 | WO-0759791 | ST LAWRENCE ROAD | UPMINSTER | HAVERING | Havering London Borough Council | 220001242255 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 38.6 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 38.6 | 38.6 | [14 empty] | 19.3 | 19.3 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | JDT TBA 2 | IMGA223349 | WO-0759631 | MERCURY GARDENS | ROMFORD | HAVERING | Havering London Borough Council | 630616200 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 59.76 | MR1 | N | T1 SECONDARY |  | 44578 | 44582 | 0 | 59.76 | 59.76 | [16 empty] | 59.76 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | JDT TBA 2 | IMGA223404 | WO-0764665 | FAIRLAWNS CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 220001850827 | 4 |  | T1 | Inch | PE | Ducted | LP | Non-Policy | T1Non-Policy | 4"-5" | 1 | 3.87 | MR1 | N | PE |  | 44585 | 44589 | 0 | 3.87 | 3.87 | [17 empty] | 3.87 | [9 empty] | #N/A | 4"-5" | LP | Non-Policy | T1 | PE | #N/A
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | JDT TBA 2 | IMGA223092 | WO-0759852 | THORN LANE | RAINHAM | HAVERING | Havering London Borough Council | 510924738 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 177 | 49.51 | MR1 | N | T1 PAST |  | 44592 | 44596 | 0 | 49.51 | 49.51 | [18 empty] | 49.51 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | JDT TBA 2 | IMGA223371 | WO-0762150 | ARDLEIGH GREEN ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510782704 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 8.5 | MR1 | N | T1 CBA |  | 44599 | 44603 | 0 | 8.5 | 8.5 | [19 empty] | 8.5 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | John Redmond | IMGA223394 | WO-0762246 | CHELMSFORD ROAD | RAWRETH | ESSEX | Rochford District Council | 510806625 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 3167 | 624.87 | MR1 | N | T1 PAST |  | 44473 | 44645 | 299.88 | 299.88 | 599.76 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 |  |  | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 | 24.99 |  | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | John Redmond | IMGA223394 | WO-0762246 | CHELMSFORD ROAD | RAWRETH | ESSEX | Rochford District Council | 510806634 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 0 | 61.23 | MR1 | N | T1 CONNECTED |  | 44473 | 44645 | 29.4 | 29.4 | 58.8 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 |  |  | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 |  | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761708 | DEVON CLOSE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510821078 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 267.74 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 267.75 | 0 | 267.75 |  | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | 38.25 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761708 | DEVON CLOSE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510821079 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 7.43 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 7.42 | 0 | 7.42 |  | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761709 | STAG LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510915389 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 66.13 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 66.15 | 0 | 66.15 |  | 9.45 | 9.45 | 9.45 | 9.45 | 9.45 | 9.45 | 9.45 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761709 | STAG LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510915390 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 122.36 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 122.36 | 0 | 122.36 |  | 17.48 | 17.48 | 17.48 | 17.48 | 17.48 | 17.48 | 17.48 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761709 | STAG LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510915391 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 54.84 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 54.81 | 0 | 54.81 |  | 7.83 | 7.83 | 7.83 | 7.83 | 7.83 | 7.83 | 7.83 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761709 | STAG LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510915392 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 33.38 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 33.39 | 0 | 33.39 |  | 4.77 | 4.77 | 4.77 | 4.77 | 4.77 | 4.77 | 4.77 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223258 | WO-0761709 | STAG LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510915394 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 34.43 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 34.44 | 0 | 34.44 |  | 4.92 | 4.92 | 4.92 | 4.92 | 4.92 | 4.92 | 4.92 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223265 | WO-0760452 | BROOK ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510797842 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 88.44 | MR1 | N | T1 SECONDARY |  | 44522 | 44533 | 88.44 | 0 | 88.44 | [8 empty] | 44.22 | 44.22 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223265 | WO-0760452 | BROOK ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510797843 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 102.38 | MR1 | N | T1 SECONDARY |  | 44522 | 44533 | 102.38 | 0 | 102.38 | [8 empty] | 51.19 | 51.19 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223265 | WO-0760453 | BROOKLYN AVENUE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 220001858610 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.4 | MR1 | N | T1 SECONDARY |  | 44522 | 44533 | 1.4 | 0 | 1.4 | [8 empty] | 0.7 | 0.7 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223260 | WO-0761407 | THE DRUMMONDS | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510973316 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 84.42 | MR1 | N | T1 SECONDARY |  | 44565 | 44624 | 0 | 84.42 | 84.42 | [14 empty] | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 | 9.38 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223260 | WO-0761408 | KNIGHTON LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510861716 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 220.77 | MR1 | N | T1 SECONDARY |  | 44565 | 44624 | 0 | 220.77 | 220.77 | [14 empty] | 24.53 | 24.53 | 24.53 | 24.53 | 24.53 | 24.53 | 24.53 | 24.53 | 24.53 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223260 | WO-0761408 | KNIGHTON LANE | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510861717 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 24.42 | MR1 | N | T1 SECONDARY |  | 44565 | 44624 | 0 | 24.39 | 24.39 | [14 empty] | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223260 | WO-0761409 | QUEENS ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510896995 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 215.79 | MR1 | N | T1 SECONDARY |  | 44565 | 44624 | 0 | 215.82 | 215.82 | [14 empty] | 23.98 | 23.98 | 23.98 | 23.98 | 23.98 | 23.98 | 23.98 | 23.98 | 23.98 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223260 | WO-0761410 | PALMERSTON ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510889142 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 33 | 175.59 | MR1 | N | T1 SECONDARY |  | 44565 | 44624 | 0 | 175.59 | 175.59 | [14 empty] | 19.51 | 19.51 | 19.51 | 19.51 | 19.51 | 19.51 | 19.51 | 19.51 | 19.51 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223270 | WO-0761224 | DEBDEN LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510820117 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" | 3 | 7.09 | MR1 | N | T1 SECONDARY |  | 44627 | 44694 | 0 | 2.84 | 2.84 | [23 empty] | 0.71 | 0.71 | 0.71 | 0.71 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223270 | WO-0761224 | DEBDEN LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510820117 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 289.55 | MR1 | N | T1 SECONDARY |  | 44627 | 44694 | 0 | 115.84 | 115.84 | [23 empty] | 28.96 | 28.96 | 28.96 | 28.96 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223270 | WO-0761225 | ENGLANDS LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510828199 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" | 1 | 330.7 | MR1 | N | T1 SECONDARY |  | 44627 | 44694 | 0 | 132.28 | 132.28 | [23 empty] | 33.07 | 33.07 | 33.07 | 33.07 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223270 | WO-0761225 | ENGLANDS LANE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510828199 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 131.51 | MR1 | N | T1 SECONDARY |  | 44627 | 44694 | 0 | 52.6 | 52.6 | [23 empty] | 13.15 | 13.15 | 13.15 | 13.15 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | KLT TBA | IMGA223270 | WO-0761226 | RIPLEY VIEW | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510901205 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 104.69 | MR1 | N | T1 SECONDARY |  | 44627 | 44694 | 0 | 41.88 | 41.88 | [23 empty] | 10.47 | 10.47 | 10.47 | 10.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223153 | WO-0759899 | WESTROW DRIVE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510936144 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 159 | 549.59 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 144.62 | 0 | 144.62 | 20.66 | 20.66 | 20.66 | 20.66 | 20.66 | 20.66 | 20.66 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223153 | WO-0759899 | WESTROW DRIVE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510936149 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 589.26 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 589.26 | 0 | 589.26 | 84.18 | 84.18 | 84.18 | 84.18 | 84.18 | 84.18 | 84.18 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223153 | WO-0759899 | WESTROW DRIVE | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 630961044 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 15.74 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 15.75 | 0 | 15.75 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223172 | WO-0761488 | CHITTYS LANE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001631776 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 2.48 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 2.5 | 0 | 2.5 | [7 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223172 | WO-0761489 | MAYFIELD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510875433 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 584.43 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 398.85 | 0 | 398.85 | [7 empty] | 79.77 | 79.77 | 79.77 | 79.77 | 79.77 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223172 | WO-0761489 | MAYFIELD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510875434 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 202.82 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 138.4 | 0 | 138.4 | [7 empty] | 27.68 | 27.68 | 27.68 | 27.68 | 27.68 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223172 | WO-0761490 | BURNSIDE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001642602 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.8 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 1.8 | 0 | 1.8 | [7 empty] | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223172 | WO-0761489 | MAYFIELD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510875433 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 584.43 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 185.6 | 185.6 | [14 empty] | 92.8 | 92.8 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223172 | WO-0761489 | MAYFIELD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510875434 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 202.82 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 64.42 | 64.42 | [14 empty] | 32.21 | 32.21 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | LDP Blank | Lee Bulter | IMGA223423 | WO-0765360 | SHORTCROFTS ROAD |  |  |  | 220001599845 | 4 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 2.41 | MR1 | N | T1 SECONDARY |  | 44578 | 44603 | 0 | 2.4 | 2.4 | [16 empty] | 0.6 | 0.6 | 0.6 | 0.6 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | LDP Blank | Lee Bulter | IMGA223423 | WO-0765361 | IVYHOUSE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220002003692 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 3.3 | MR1 | N | T1 SECONDARY |  | 44578 | 44603 | 0 | 3.32 | 3.32 | [16 empty] | 0.83 | 0.83 | 0.83 | 0.83 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | LDP Blank | Lee Bulter | IMGA223423 | WO-0765361 | IVYHOUSE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220002003698 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 317.45 | MR1 | N | T1 SECONDARY |  | 44578 | 44603 | 0 | 317.44 | 317.44 | [16 empty] | 79.36 | 79.36 | 79.36 | 79.36 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | LDP Blank | Lee Bulter | IMGA223423 | WO-0765361 | IVYHOUSE ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220002003711 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 184.66 | MR1 | N | T1 SECONDARY |  | 44578 | 44603 | 0 | 184.68 | 184.68 | [16 empty] | 46.17 | 46.17 | 46.17 | 46.17 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Lee Bulter | IMGA223414 | WO-0764947 | KING EDWARDS ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510832489 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 6.18 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 6.18 | 6.18 | [20 empty] | 6.18 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Lee Maddocks | IMGA223361 | WO-0759682 | THE MEADS | UPMINSTER | HAVERING | Havering London Borough Council | 510923622 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 178.78 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 178.8 | 0 | 178.8 | 29.8 | 29.8 | 29.8 | 29.8 | 29.8 | 29.8 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Lee Maddocks | IMGA223361 | WO-0759682 | THE MEADS | UPMINSTER | HAVERING | Havering London Borough Council | 510923623 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 53.79 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 53.76 | 0 | 53.76 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | 8.96 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Lee Maddocks | IMGA223361 | WO-0759683 | RECTORY GARDENS | UPMINSTER | HAVERING | Havering London Borough Council | 510899340 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 213 | 300.97 | MR1 | N | T1 PAST |  | 44459 | 44505 | 301.02 | 0 | 301.02 | 50.17 | 50.17 | 50.17 | 50.17 | 50.17 | 50.17 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223358 | WO-0764639 | BROOKDALE AVENUE |  |  | Havering London Borough Council | 510797913 | 4 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 61.01 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 61.02 | 0 | 61.02 | [6 empty] | 10.17 | 10.17 | 10.17 | 10.17 | 10.17 | 10.17 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223358 | WO-0764639 | BROOKDALE AVENUE |  |  | Havering London Borough Council | 510797914 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 108.19 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 108.18 | 0 | 108.18 | [6 empty] | 18.03 | 18.03 | 18.03 | 18.03 | 18.03 | 18.03 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223358 | WO-0764639 | BROOKDALE AVENUE |  |  | Havering London Borough Council | 510797915 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 187.13 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 187.14 | 0 | 187.14 | [6 empty] | 31.19 | 31.19 | 31.19 | 31.19 | 31.19 | 31.19 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223358 | WO-0764639 | BROOKDALE AVENUE |  |  | Havering London Borough Council | 220001930663 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 1.6 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 1.62 | 0 | 1.62 | [6 empty] | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223358 | WO-0764640 | BROOKDALE CLOSE |  |  | Havering London Borough Council | 510797916 | 4 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 62.95 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 62.94 | 0 | 62.94 | [6 empty] | 10.49 | 10.49 | 10.49 | 10.49 | 10.49 | 10.49 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223091 | WO-0759866 | LAMBS LANE NORTH | RAINHAM | HAVERING | Havering London Borough Council | 510862635 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 267.46 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 267.48 | 267.48 | [14 empty] | 44.58 | 44.58 | 44.58 | 44.58 | 44.58 | 44.58 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223091 | WO-0759866 | LAMBS LANE NORTH | RAINHAM | HAVERING | Havering London Borough Council | 603601667 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 0.95 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 0.96 | 0.96 | [14 empty] | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223091 | WO-0759867 | WARWICK ROAD | RAINHAM | HAVERING | Havering London Borough Council | 220000441313 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 217.77 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 217.8 | 217.8 | [14 empty] | 36.3 | 36.3 | 36.3 | 36.3 | 36.3 | 36.3 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223091 | WO-0759867 | WARWICK ROAD | RAINHAM | HAVERING | Havering London Borough Council | 220000503330 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 57.08 | MR1 | N | T1 SECONDARY |  | 44565 | 44603 | 0 | 57.06 | 57.06 | [14 empty] | 9.51 | 9.51 | 9.51 | 9.51 | 9.51 | 9.51 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223351 | WO-0760119 | FARNHAM ROAD | ROMFORD | HAVERING | Havering London Borough Council | 220000121714 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 68 | 252.88 | MR1 | N | T1 SECONDARY |  | 44606 | 44631 | 0 | 252.88 | 252.88 | [20 empty] | 63.22 | 63.22 | 63.22 | 63.22 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223351 | WO-0760845 | HILLDENE AVENUE |  |  |  | 220000121836 | 8 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" | 183 | 44.58 | MR1 | N | T1 SECONDARY |  | 44606 | 44631 | 0 | 44.6 | 44.6 | [20 empty] | 11.15 | 11.15 | 11.15 | 11.15 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223403 | WO-0764434 | IVY LODGE LANE | ROMFORD | HAVERING | Havering London Borough Council | 510959158 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 104.19 | MR1 | N | T1 SECONDARY |  | 44634 | 44701 | 0 | 31.26 | 31.26 | [24 empty] | 10.42 | 10.42 | 10.42 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223403 | WO-0764435 | SHEPHERDS HILL | ROMFORD | HAVERING | Havering London Borough Council | 510910922 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 131 | 600.1 | MR1 | N | T1 SECONDARY |  | 44634 | 44701 | 0 | 180.03 | 180.03 | [24 empty] | 60.01 | 60.01 | 60.01 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223403 | WO-0764435 | SHEPHERDS HILL | ROMFORD | HAVERING | Havering London Borough Council | 612043585 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 1.52 | MR1 | N | T1 SECONDARY |  | 44634 | 44701 | 0 | 0.45 | 0.45 | [24 empty] | 0.15 | 0.15 | 0.15 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Lee Maddocks | IMGA223403 | WO-0764435 | SHEPHERDS HILL | ROMFORD | HAVERING | Havering London Borough Council | 510991618 | 4 |  | T1 | Inch | CI | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 0 | 119.26 | MR2 | Y | T1 SECONDARY |  | 44634 | 44701 | 0 | 35.79 | 35.79 | [24 empty] | 11.93 | 11.93 | 11.93 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223053 | WO-0760387 | PLUMBEROW AVENUE | HOCKLEY | ESSEX | Rochford District Council | 220000143392 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.32 | MR1 | N | T1 SECONDARY |  | 44424 | 44505 | 1.32 | 0 | 1.32 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223053 | WO-0760387 | PLUMBEROW AVENUE | HOCKLEY | ESSEX | Rochford District Council | 510893500 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 268 | 716.43 | MR1 | N | T1 PAST |  | 44424 | 44505 | 464.4 | 0 | 464.4 | 77.4 | 77.4 | 77.4 | 77.4 | 77.4 | 77.4 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223053 | WO-0760387 | PLUMBEROW AVENUE | HOCKLEY | ESSEX | Rochford District Council | 602858126 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 25 | 3.27 | MR1 | N | T1 CONNECTED |  | 44424 | 44505 | 3.24 | 0 | 3.24 | 0.54 | 0.54 | 0.54 | 0.54 | 0.54 | 0.54 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223053 | WO-0760387 | PLUMBEROW AVENUE | HOCKLEY | ESSEX | Rochford District Council | 220000812861 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 24 | 1.19 | MR1 | N | T1 CONNECTED |  | 44424 | 44505 | 1.2 | 0 | 1.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223056 | WO-0761328 | HAMBRO AVENUE | RAYLEIGH | ESSEX | Rochford District Council | 510844395 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 442 | 330.3 | MR1 | N | T1 PAST |  | 44508 | 44547 | 330.3 | 0 | 330.3 | [6 empty] | 55.05 | 55.05 | 55.05 | 55.05 | 55.05 | 55.05 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223056 | WO-0761329 | PRESTON GARDENS | RAYLEIGH | ESSEX | Rochford District Council | 635869182 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 62 | 82.35 | MR1 | N | T1 CONNECTED |  | 44508 | 44547 | 82.38 | 0 | 82.38 | [6 empty] | 13.73 | 13.73 | 13.73 | 13.73 | 13.73 | 13.73 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761737 | THE RIDGEWAY | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510924008 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 59.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 59.64 | 59.64 | [14 empty] | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 | 4.97 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761737 | THE RIDGEWAY | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 636225104 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 0.29 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 0.24 | 0.24 | [14 empty] | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761737 | THE RIDGEWAY | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220000011116 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 0.82 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 0.84 | 0.84 | [14 empty] | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761737 | THE RIDGEWAY | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220000313100 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 469.31 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 469.32 | 469.32 | [14 empty] | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 | 39.11 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761738 | THE CROSSWAYS | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 624703681 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 6.84 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 6.84 | 6.84 | [14 empty] | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 | 0.57 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761738 | THE CROSSWAYS | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220001189870 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 2.66 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 2.64 | 2.64 | [14 empty] | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 | 0.22 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761739 | RIDGEWAY GARDENS | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510901008 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 75.52 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 75.48 | 75.48 | [14 empty] | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Robert Ashdown | Terra Firma | Lee Miles | IMGA223074 | WO-0761740 | HILLWAY | WESTCLIFF-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220000967665 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 391.5 | MR1 | N | T1 SECONDARY |  | 44565 | 44645 | 0 | 391.56 | 391.56 | [14 empty] | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 | 32.63 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223070 | WO-0761563 | PEEL AVENUE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 606865091 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.63 | MR1 | N | T1 SECONDARY |  | 44403 | 44477 | 1.66 | 0 | 1.66 | 0.83 | 0.83 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223070 | WO-0761563 | PEEL AVENUE | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510792497 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 26.79 | MR1 | N | T1 SECONDARY |  | 44403 | 44477 | 26.84 | 0 | 26.84 | 13.42 | 13.42 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223070 | WO-0761563 | PEEL AVENUE | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510891111 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 372.45 | MR1 | N | T1 SECONDARY |  | 44403 | 44477 | -3.54 | 0 | -3.54 | -1.77 | -1.77 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223070 | WO-0761564 | CASTLE CLOSE | SHOEBURYNESS | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510803712 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 29 | 81.8 | MR1 | N | T1 SECONDARY |  | 44403 | 44477 | 1.84 | 0 | 1.84 | 0.92 | 0.92 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223070 | WO-0761565 | NEWELL AVENUE | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510882544 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 171.9 | MR1 | N | T1 SECONDARY |  | 44403 | 44477 | 16.94 | 0 | 16.94 | 8.47 | 8.47 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223070 | WO-0761566 | SERVICE ROAD FOR 9 TO 29 BLACKGATE ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510792493 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 207.03 | MR1 | N | T1 SECONDARY |  | 44403 | 44477 | 27.02 | 0 | 27.02 | 13.51 | 13.51 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223040 | WO-0760122 | FERNLEA ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510831572 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 383 | 102.71 | MR1 | N | T1 PAST |  | 44480 | 44491 | 102.72 | 0 | 102.72 |  |  | 51.36 | 51.36 | [23 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223141 | WO-0759850 | THOMPSON AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510924692 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 173.3 | MR1 | N | T1 SECONDARY |  | 44494 | 44505 | 173.3 | 0 | 173.3 |  |  |  |  | 86.65 | 86.65 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223143 | WO-0760462 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866907 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 251 | 247.06 | MR1 | N | T1 PAST |  | 44508 | 44533 | 247.08 | 0 | 247.08 | [6 empty] | 61.77 | 61.77 | 61.77 | 61.77 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761437 | THE LARCHES | BENFLEET | ESSEX | Castle Point Borough Council | 510957249 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 113.4 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 113.4 | 0 | 113.4 | [10 empty] | 56.7 | 56.7 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761437 | THE LARCHES | BENFLEET | ESSEX | Castle Point Borough Council | 510957248 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 10 | 11.32 | MR1 | N | T1 CONNECTED |  | 44536 | 44547 | 11.32 | 0 | 11.32 | [10 empty] | 5.66 | 5.66 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761436 | OAK WALK | BENFLEET | ESSEX | Castle Point Borough Council | 510885548 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 75.48 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 75.48 | 75.48 | [14 empty] | 18.87 | 18.87 | 18.87 | 18.87 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761436 | OAK WALK | BENFLEET | ESSEX | Castle Point Borough Council | 510885549 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 16.73 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 16.72 | 16.72 | [14 empty] | 4.18 | 4.18 | 4.18 | 4.18 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761438 | HORNBEAMS | BENFLEET | ESSEX | Castle Point Borough Council | 510957262 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 24.16 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 24.16 | 24.16 | [14 empty] | 6.04 | 6.04 | 6.04 | 6.04 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761438 | HORNBEAMS | BENFLEET | ESSEX | Castle Point Borough Council | 510957263 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 138.65 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 138.64 | 138.64 | [14 empty] | 34.66 | 34.66 | 34.66 | 34.66 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761438 | HORNBEAMS | BENFLEET | ESSEX | Castle Point Borough Council | 510957264 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 117.84 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 117.84 | 117.84 | [14 empty] | 29.46 | 29.46 | 29.46 | 29.46 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Lloyd Smith | IMGA223045 | WO-0761438 | HORNBEAMS | BENFLEET | ESSEX | Castle Point Borough Council | 510957265 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 65.83 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 65.84 | 65.84 | [14 empty] | 16.46 | 16.46 | 16.46 | 16.46 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761450 | KENSINGTON ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510858993 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 307.1 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 276.39 | 276.39 | [18 empty] | 30.71 | 30.71 | 30.71 | 30.71 | 30.71 | 30.71 | 30.71 | 30.71 | 30.71 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761450 | KENSINGTON ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510858994 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 66 | 304.43 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 273.96 | 273.96 | [18 empty] | 30.44 | 30.44 | 30.44 | 30.44 | 30.44 | 30.44 | 30.44 | 30.44 | 30.44 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761450 | KENSINGTON ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 510858995 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 178.12 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 160.29 | 160.29 | [18 empty] | 17.81 | 17.81 | 17.81 | 17.81 | 17.81 | 17.81 | 17.81 | 17.81 | 17.81 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761450 | KENSINGTON ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 602634653 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 6.46 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 5.85 | 5.85 | [18 empty] | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761450 | KENSINGTON ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 606869557 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 1.51 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 1.35 | 1.35 | [18 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761450 | KENSINGTON ROAD | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 606874853 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 1.4 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 1.26 | 1.26 | [18 empty] | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Lloyd Smith | IMGA223065 | WO-0761451 | WOODGRANGE DRIVE | SOUTHEND-ON-SEA | SOUTHEND-ON-SEA | Southend-on-Sea Borough Council | 220000968125 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 1.96 | MR1 | N | T1 SECONDARY |  | 44592 | 44659 | 0 | 1.8 | 1.8 | [18 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761936 | CANEWDON CLOSE | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 510802114 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 61.26 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 61.26 | 0 | 61.26 |  |  |  | 10.21 | 10.21 | 10.21 | 10.21 | 10.21 | 10.21 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761937 | CANEWDON GARDENS | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 510802118 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 18.53 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 18.54 | 0 | 18.54 |  |  |  | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761938 | REGENCY CLOSE | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 510900073 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 89.18 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 89.16 | 0 | 89.16 |  |  |  | 14.86 | 14.86 | 14.86 | 14.86 | 14.86 | 14.86 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761936 | CANEWDON CLOSE | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 510802115 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 7 | 4.48 | MR1 | N | T1 CONNECTED |  | 44487 | 44526 | 4.5 | 0 | 4.5 |  |  |  | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761936 | CANEWDON CLOSE | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 510802116 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 8 | 12.13 | MR1 | N | T1 CONNECTED |  | 44487 | 44526 | 12.12 | 0 | 12.12 |  |  |  | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | 2.02 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761936 | CANEWDON CLOSE | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 607101093 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 24 | 1.88 | MR1 | N | T1 CONNECTED |  | 44487 | 44526 | 1.86 | 0 | 1.86 |  |  |  | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Chris Southam | Terra Firma | Luke Daughters-Wright | IMGA223089 | WO-0761937 | CANEWDON GARDENS | WICKFORD | ESSEX | Chelmsford Borough Council (Lower) | 220000534644 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 331 | 199.63 | MR1 | N | T1 PAST |  | 44487 | 44526 | 199.62 | 0 | 199.62 |  |  |  | 33.27 | 33.27 | 33.27 | 33.27 | 33.27 | 33.27 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761875 | ARBOUR CLOSE | WARLEY | ESSEX | Brentwood Borough Council | 510782509 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 65.28 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 65.3 | 0 | 65.3 | 6.53 | 6.53 | 6.53 | 6.53 | 6.53 | 6.53 | 6.53 | 6.53 | 6.53 | 6.53 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761875 | ARBOUR CLOSE | WARLEY | ESSEX | Brentwood Borough Council | 510782510 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 31 | 74.83 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 74.8 | 0 | 74.8 | 7.48 | 7.48 | 7.48 | 7.48 | 7.48 | 7.48 | 7.48 | 7.48 | 7.48 | 7.48 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761876 | GUARDSMAN CLOSE | WARLEY | ESSEX | Brentwood Borough Council | 510843050 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 60.27 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 60.3 | 0 | 60.3 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | 6.03 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761876 | GUARDSMAN CLOSE | WARLEY | ESSEX | Brentwood Borough Council | 510843051 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 22.82 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 22.8 | 0 | 22.8 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD |  |  | Brentwood Borough Council | 631934591 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 60.21 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 60.2 | 0 | 60.2 | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD | WARLEY | ESSEX | Brentwood Borough Council | 510941458 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 202 | 518.53 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 518.5 | 0 | 518.5 | 51.85 | 51.85 | 51.85 | 51.85 | 51.85 | 51.85 | 51.85 | 51.85 | 51.85 | 51.85 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD | WARLEY | ESSEX | Brentwood Borough Council | 621583676 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 204 | 384.13 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 384.1 | 0 | 384.1 | 38.41 | 38.41 | 38.41 | 38.41 | 38.41 | 38.41 | 38.41 | 38.41 | 38.41 | 38.41 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD | WARLEY | ESSEX | Brentwood Borough Council | 220001577707 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.6 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 2.6 | 0 | 2.6 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761878 | NELSON CLOSE | WARLEY | ESSEX | Brentwood Borough Council | 510881222 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 31 | 56.75 | MR1 | N | T1 SECONDARY |  | 44466 | 44533 | 56.8 | 0 | 56.8 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | 5.68 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD |  |  | Brentwood Borough Council | 510963630 | 1 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 14.02 | MR1 | N | T1 CONNECTED |  | 44466 | 44533 | 14 | 0 | 14 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | [17 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD | WARLEY | ESSEX | Brentwood Borough Council | 510963629 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 23.38 | MR1 | N | T1 CONNECTED |  | 44466 | 44533 | 23.4 | 0 | 23.4 | 2.34 | 2.34 | 2.34 | 2.34 | 2.34 | 2.34 | 2.34 | 2.34 | 2.34 | 2.34 | [17 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD | WARLEY | ESSEX | Brentwood Borough Council | 607071477 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 8 | 4.42 | MR1 | N | T1 CONNECTED |  | 44466 | 44533 | 4.4 | 0 | 4.4 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | [17 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223025 | WO-0761877 | WOODMAN ROAD | WARLEY | ESSEX | Brentwood Borough Council | 607371124 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 3.95 | MR1 | N | T1 CONNECTED |  | 44466 | 44533 | 4 | 0 | 4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | [17 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760973 | THORNDALES | WARLEY | ESSEX | Brentwood Borough Council | 510963622 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 100.48 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 100.48 | 0 | 100.48 | [10 empty] | 50.24 | 50.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760973 | THORNDALES | WARLEY | ESSEX | Brentwood Borough Council | 510963623 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 72.83 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 72.84 | 0 | 72.84 | [10 empty] | 36.42 | 36.42 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760971 | HARTSWOOD ROAD | WARLEY | ESSEX | Brentwood Borough Council | 510846534 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 35 | 383.84 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 383.85 | 383.85 | [14 empty] | 76.77 | 76.77 | 76.77 | 76.77 | 76.77 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760971 | HARTSWOOD ROAD | WARLEY | ESSEX | Brentwood Borough Council | 220000656305 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 26.42 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 26.4 | 26.4 | [14 empty] | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760971 | HARTSWOOD ROAD | WARLEY | ESSEX | Brentwood Borough Council | 220001686162 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 13.5 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 13.5 | 13.5 | [14 empty] | 2.7 | 2.7 | 2.7 | 2.7 | 2.7 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760971 | HARTSWOOD ROAD | WARLEY | ESSEX | Brentwood Borough Council | 220001811277 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.04 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 1.05 | 1.05 | [14 empty] | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761774 | THE DELL | GREAT WARLEY | ESSEX | Brentwood Borough Council | 510945473 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 109.15 | MR1 | N | T1 SECONDARY |  | 44593 | 44613 | 0 | 109.16 | 109.16 | [18 empty] | 27.29 | 27.29 | 27.29 | 27.29 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761774 | THE DELL | GREAT WARLEY | ESSEX | Brentwood Borough Council | 510945474 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 155.85 | MR1 | N | T1 SECONDARY |  | 44593 | 44613 | 0 | 155.84 | 155.84 | [18 empty] | 38.96 | 38.96 | 38.96 | 38.96 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761775 | HAMMONDS LANE | GREAT WARLEY | ESSEX | Brentwood Borough Council | 510844741 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 218.46 | MR1 | N | T1 SECONDARY |  | 44593 | 44613 | 0 | 218.48 | 218.48 | [18 empty] | 54.62 | 54.62 | 54.62 | 54.62 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761775 | HAMMONDS LANE | GREAT WARLEY | ESSEX | Brentwood Borough Council | 510844742 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 88.52 | MR1 | N | T1 SECONDARY |  | 44593 | 44613 | 0 | 88.52 | 88.52 | [18 empty] | 22.13 | 22.13 | 22.13 | 22.13 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760972 | ST JOHNS AVENUE | WARLEY | ESSEX | Brentwood Borough Council | 510906419 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 451.16 | MR1 | N | T1 SECONDARY |  | 44614 | 44627 | 0 | 451.17 | 451.17 | [21 empty] | 150.39 | 150.39 | 150.39 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223026 | WO-0760974 | HARTSWOOD CLOSE | WARLEY | ESSEX | Brentwood Borough Council | 510846522 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 94.11 | MR1 | N | T1 SECONDARY |  | 44614 | 44627 | 0 | 94.11 | 94.11 | [21 empty] | 31.37 | 31.37 | 31.37 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761773 | WARLEY HILL | WARLEY | ESSEX | Brentwood Borough Council | 510974459 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 480.06 | MR1 | N | T1 SECONDARY |  | 44628 | 44652 | 0 | 480.08 | 480.08 | [23 empty] | 120.02 | 120.02 | 120.02 | 120.02 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761773 | WARLEY HILL | WARLEY | ESSEX | Brentwood Borough Council | 510974460 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 290.7 | MR1 | N | T1 SECONDARY |  | 44628 | 44652 | 0 | 290.72 | 290.72 | [23 empty] | 72.68 | 72.68 | 72.68 | 72.68 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761773 | WARLEY HILL | WARLEY | ESSEX | Brentwood Borough Council | 510974461 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 90.78 | MR1 | N | T1 SECONDARY |  | 44628 | 44652 | 0 | 90.8 | 90.8 | [23 empty] | 22.7 | 22.7 | 22.7 | 22.7 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761773 | WARLEY HILL | WARLEY | ESSEX | Brentwood Borough Council | 516186802 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 58.23 | MR1 | N | T1 CONNECTED |  | 44628 | 44652 | 0 | 58.24 | 58.24 | [23 empty] | 14.56 | 14.56 | 14.56 | 14.56 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Luke Kamenshut | IMGA223020 | WO-0761773 | WARLEY HILL | WARLEY | ESSEX | Brentwood Borough Council | 606622849 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 11.8 | MR1 | N | T1 CONNECTED |  | 44628 | 44652 | 0 | 11.8 | 11.8 | [23 empty] | 2.95 | 2.95 | 2.95 | 2.95 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762183 | ARUNDEL ROAD | ASHINGDON | ESSEX | Rochford District Council | 510783609 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 257.56 | MR1 | N | T1 CONNECTED |  | 44529 | 44718 | 36.8 | 119.6 | 156.4 | [8 empty] | 9.2 | 9.2 | 9.2 | 9.2 |  |  | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | 9.2 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762184 | RADNOR ROAD | ASHINGDON | ESSEX | Rochford District Council | 510897655 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 53.42 | MR1 | N | T1 CONNECTED |  | 44529 | 44718 | 7.64 | 24.83 | 32.47 | [8 empty] | 1.91 | 1.91 | 1.91 | 1.91 |  |  | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | 1.91 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762185 | ULVERSTON ROAD | ASHINGDON | ESSEX | Rochford District Council | 510928097 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 336.65 | MR1 | N | T1 CBA |  | 44529 | 44718 | 48.08 | 156.26 | 204.34 | [8 empty] | 12.02 | 12.02 | 12.02 | 12.02 |  |  | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | 12.02 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762186 | ETHELBERT ROAD | ASHINGDON | ESSEX | Rochford District Council | 510828903 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 224.72 | MR1 | N | T1 CONNECTED |  | 44529 | 44718 | 32.12 | 104.39 | 136.51 | [8 empty] | 8.03 | 8.03 | 8.03 | 8.03 |  |  | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762187 | ELLESMERE ROAD | ASHINGDON | ESSEX | Rochford District Council | 510826818 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 481.86 | MR1 | N | T1 CONNECTED |  | 44529 | 44718 | 68.84 | 223.73 | 292.57 | [8 empty] | 17.21 | 17.21 | 17.21 | 17.21 |  |  | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | 17.21 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762188 | CANEWDON ROAD | ASHINGDON | ESSEX | Rochford District Council | 510802120 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 147.71 | MR1 | N | T1 CONNECTED |  | 44529 | 44718 | 21.12 | 68.64 | 89.76 | [8 empty] | 5.28 | 5.28 | 5.28 | 5.28 |  |  | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | 5.28 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Mark Clee | IMGA223400 | WO-0762189 | LYNDHURST ROAD | ASHINGDON | ESSEX | Rochford District Council | 510870934 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 132.22 | MR1 | N | T1 CONNECTED |  | 44529 | 44718 | 18.88 | 61.36 | 80.24 | [8 empty] | 4.72 | 4.72 | 4.72 | 4.72 |  |  | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | 4.72 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223052 | WO-0759836 | THE WESTERINGS | HAWKWELL | ESSEX | Rochford District Council | 510923689 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 213 | 88.27 | MR1 | N | T1 PAST |  | 44459 | 44477 | 88.26 | 0 | 88.26 | 44.13 | 44.13 | [25 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760342 | CANVEY ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510802554 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 73.8 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 73.8 | 0 | 73.8 |  |  | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | 8.2 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760342 | CANVEY ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 606700704 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 2.06 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 2.07 | 0 | 2.07 |  |  | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760343 | HOLLAND AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510853284 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 29.95 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 29.97 | 0 | 29.97 |  |  | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760343 | HOLLAND AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510853286 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 33.35 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 33.39 | 0 | 33.39 |  |  | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | 3.71 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760344 | HAARLEM ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510843475 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 292.92 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 292.95 | 0 | 292.95 |  |  | 32.55 | 32.55 | 32.55 | 32.55 | 32.55 | 32.55 | 32.55 | 32.55 | 32.55 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760345 | BATAVIA ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510787812 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 57.44 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 57.42 | 0 | 57.42 |  |  | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | 6.38 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760346 | DYKE CRESCENT | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510823944 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 133.22 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 133.2 | 0 | 133.2 |  |  | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760346 | DYKE CRESCENT | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 220000836087 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.61 | MR1 | N | T1 SECONDARY |  | 44480 | 44540 | 2.61 | 0 | 2.61 |  |  | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | 0.29 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760343 | HOLLAND AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510853285 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 12 | 55.1 | MR1 | N | T1 CONNECTED |  | 44480 | 44540 | 55.08 | 0 | 55.08 |  |  | 6.12 | 6.12 | 6.12 | 6.12 | 6.12 | 6.12 | 6.12 | 6.12 | 6.12 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760343 | HOLLAND AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510853287 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 8 | 25.05 | MR1 | N | T1 CONNECTED |  | 44480 | 44540 | 25.02 | 0 | 25.02 |  |  | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | 2.78 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Bob Sawyer | Terra Firma | Martin Tonge | IMGA223132 | WO-0760346 | DYKE CRESCENT | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510823946 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 9 | 56.87 | MR1 | N | T1 CONNECTED |  | 44480 | 44540 | 56.88 | 0 | 56.88 |  |  | 6.32 | 6.32 | 6.32 | 6.32 | 6.32 | 6.32 | 6.32 | 6.32 | 6.32 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223054 | WO-0761221 | DOWN HALL ROAD | RAYLEIGH | ESSEX | Rochford District Council | 510822555 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 19.45 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 19.44 | 19.44 | [14 empty] | 4.86 | 4.86 | 4.86 | 4.86 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223054 | WO-0761221 | DOWN HALL ROAD | RAYLEIGH | ESSEX | Rochford District Council | 510822556 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 99.09 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 99.08 | 99.08 | [14 empty] | 24.77 | 24.77 | 24.77 | 24.77 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223054 | WO-0761222 | HARPER WAY | RAYLEIGH | ESSEX | Rochford District Council | 510846007 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 47.38 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 47.4 | 47.4 | [14 empty] | 11.85 | 11.85 | 11.85 | 11.85 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223054 | WO-0761223 | BIRCH CLOSE | RAYLEIGH | ESSEX | Rochford District Council | 510791824 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 40.18 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 40.2 | 40.2 | [14 empty] | 10.05 | 10.05 | 10.05 | 10.05 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223370 | WO-0762247 | PARK ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510889911 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 71.15 | MR1 | N | T1 CONNECTED |  | 44592 | 44596 | 0 | 71.15 | 71.15 | [18 empty] | 71.15 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223370 | WO-0762247 | PARK ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510889912 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 213 | 67.12 | MR1 | N | T1 CBA |  | 44592 | 44596 | 0 | 67.12 | 67.12 | [18 empty] | 67.12 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223047 | WO-0761863 | CHANDOS PARADE | BENFLEET | ESSEX | Castle Point Borough Council | 510805465 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 36 | 89.84 | MR1 | N | T1 CONNECTED |  | 44599 | 44617 | 0 | 89.85 | 89.85 | [19 empty] | 29.95 | 29.95 | 29.95 | [5 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223047 | WO-0761864 | WOODFIELD ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510940904 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 331 | 90.5 | MR1 | N | T1 PAST |  | 44599 | 44617 | 0 | 90.51 | 90.51 | [19 empty] | 30.17 | 30.17 | 30.17 | [5 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223041 | WO-0761798 | UNDERHILL ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510928138 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 250 | 253.25 | MR1 | N | T1 PAST |  | 44599 | 44624 | 0 | 253.24 | 253.24 | [19 empty] | 63.31 | 63.31 | 63.31 | 63.31 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223041 | WO-0761798 | UNDERHILL ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 607103719 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 24 | 1.51 | MR1 | N | T1 CONNECTED |  | 44599 | 44624 | 0 | 1.52 | 1.52 | [19 empty] | 0.38 | 0.38 | 0.38 | 0.38 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Martin Tonge | IMGA223041 | WO-0761799 | AVENUE ROAD | BENFLEET | ESSEX | Castle Point Borough Council | 510785239 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 15 | 54.95 | MR1 | N | T1 CONNECTED |  | 44599 | 44624 | 0 | 54.96 | 54.96 | [19 empty] | 13.74 | 13.74 | 13.74 | 13.74 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Nathan Forge | IMGA223257 | WO-0761231 | OSBORNE ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510887889 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 71.58 | MR1 | N | T1 SECONDARY |  | 44354 | 44484 | 7.62 | 0 | 7.62 | 2.54 | 2.54 | 2.54 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Nathan Forge | IMGA223257 | WO-0761232 | EPPING NEW ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 603360826 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 537.55 | MR1 | N | T1 SECONDARY |  | 44354 | 44484 | -4.05 | 0 | -4.05 | -1.35 | -1.35 | -1.35 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | TBA - Lon | Forefront | Nathan Forge | IMGA223257 | WO-0761230 | CHURCH ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510809327 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 96.83 | MR1 | N | T1 SECONDARY |  | 44354 | 44484 | -22.98 | 0 | -22.98 | -7.66 | -7.66 | -7.66 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | TBA - Lon | Forefront | Nathan Forge | IMGA223257 | WO-0761230 | CHURCH ROAD | BUCKHURST HILL | ESSEX | Epping Forest District Council (Lower) | 510809328 | 7 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 271.87 | MR1 | N | T1 SECONDARY |  | 44354 | 44484 | 22.89 | 0 | 22.89 | 7.63 | 7.63 | 7.63 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Nathan Forge | IMGA223097 | WO-0761469 | LYNDHURST ROAD | CORRINGHAM | THURROCK | Thurrock Council | 510870942 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 226.08 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 226.1 | 0 | 226.1 |  | 45.22 | 45.22 | 45.22 | 45.22 | 45.22 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Nathan Forge | IMGA223097 | WO-0761469 | LYNDHURST ROAD | CORRINGHAM | THURROCK | Thurrock Council | 510870943 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 149.51 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 149.5 | 0 | 149.5 |  | 29.9 | 29.9 | 29.9 | 29.9 | 29.9 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Nathan Forge | IMGA223097 | WO-0761470 | CROFTON AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 220001204749 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 36.82 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 36.8 | 0 | 36.8 |  | 7.36 | 7.36 | 7.36 | 7.36 | 7.36 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Nathan Forge | IMGA223097 | WO-0761471 | HAWTHORNE ROAD | CORRINGHAM | THURROCK | Thurrock Council | 220001205306 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 11.4 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 11.4 | 0 | 11.4 |  | 2.28 | 2.28 | 2.28 | 2.28 | 2.28 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Nathan Forge | IMGA223379 | WO-0762176 | LENTHALL AVENUE | GRAYS | THURROCK | Thurrock Council | 220000862955 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 196.83 | MR1 | N | T1 CBA |  | 44508 | 44547 | 196.86 | 0 | 196.86 | [6 empty] | 32.81 | 32.81 | 32.81 | 32.81 | 32.81 | 32.81 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Nathan Forge | IMGA223379 | WO-0762177 | DUKES AVENUE | GRAYS | THURROCK | Thurrock Council | 510823335 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 257.96 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 257.94 | 0 | 257.94 | [6 empty] | 42.99 | 42.99 | 42.99 | 42.99 | 42.99 | 42.99 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 510867929 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 321.33 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 321.36 | 321.36 | [14 empty] | 40.17 | 40.17 | 40.17 | 40.17 | 40.17 | 40.17 | 40.17 | 40.17 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 510867932 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 127.97 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 128 | 128 | [14 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 510897808 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 19.96 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 20 | 20 | [14 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 220001229718 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 193.93 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 193.92 | 193.92 | [14 empty] | 24.24 | 24.24 | 24.24 | 24.24 | 24.24 | 24.24 | 24.24 | 24.24 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 220001285522 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 22.45 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 22.48 | 22.48 | [14 empty] | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | 2.81 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 220001285524 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 17.53 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 17.52 | 17.52 | [14 empty] | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223102 | WO-0759584 | LODGE LANE | GRAYS | THURROCK | Thurrock Council | 220001285526 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 101.28 | MR1 | N | T1 SECONDARY |  | 44565 | 44617 | 0 | 101.28 | 101.28 | [14 empty] | 12.66 | 12.66 | 12.66 | 12.66 | 12.66 | 12.66 | 12.66 | 12.66 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223123 | WO-0761310 | FOYLE DRIVE | SOUTH OCKENDON | THURROCK | Thurrock Council | 220001212293 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 26.87 | MR1 | N | T1 SECONDARY |  | 44620 | 44624 | 0 | 26.87 | 26.87 | [22 empty] | 26.87 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Nathan Forge | IMGA223123 | WO-0761311 | GARRON LANE | SOUTH OCKENDON | THURROCK | Thurrock Council | 220000733185 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 0.58 | MR1 | N | T1 SECONDARY |  | 44620 | 44624 | 0 | 0.58 | 0.58 | [22 empty] | 0.58 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223158 | WO-0761431 | BECONTREE AVENUE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510789102 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 423.9 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 0.06 | 0 | 0.06 | 0.06 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223158 | WO-0761432 | HOMESTEAD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510854085 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 17.39 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 13.4 | 0 | 13.4 | 13.4 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223158 | WO-0761432 | HOMESTEAD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510854086 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 40.92 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 6.92 | 0 | 6.92 | 6.92 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223158 | WO-0761432 | HOMESTEAD ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001571826 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 349.38 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | 69.44 | 0 | 69.44 | 69.44 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223158 | WO-0761435 | ROWLANDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510903877 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 270.75 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | -1.28 | 0 | -1.28 | -1.28 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223158 | WO-0761435 | ROWLANDS ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001524411 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.2 | MR1 | N | T1 SECONDARY |  | 44389 | 44470 | -0.8 | 0 | -0.8 | -0.8 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761312 | CRANMER GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510816396 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 114.03 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 114 | 0 | 114 |  | 11.4 | 11.4 | 11.4 | 11.4 | 11.4 | 11.4 | 11.4 | 11.4 | 11.4 | 11.4 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761313 | GAY GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510836288 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 255.85 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 255.9 | 0 | 255.9 |  | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761313 | GAY GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510836289 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 57.54 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 57.5 | 0 | 57.5 |  | 5.75 | 5.75 | 5.75 | 5.75 | 5.75 | 5.75 | 5.75 | 5.75 | 5.75 | 5.75 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761313 | GAY GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510836290 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 39 | 107.12 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 107.1 | 0 | 107.1 |  | 10.71 | 10.71 | 10.71 | 10.71 | 10.71 | 10.71 | 10.71 | 10.71 | 10.71 | 10.71 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761314 | FOXLANDS CRESCENT | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510834278 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 222.85 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 222.9 | 0 | 222.9 |  | 22.29 | 22.29 | 22.29 | 22.29 | 22.29 | 22.29 | 22.29 | 22.29 | 22.29 | 22.29 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761314 | FOXLANDS CRESCENT | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510897923 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 2.74 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 2.7 | 0 | 2.7 |  | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761315 | WINSTEAD GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510939969 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 174.1 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 174.1 | 0 | 174.1 |  | 17.41 | 17.41 | 17.41 | 17.41 | 17.41 | 17.41 | 17.41 | 17.41 | 17.41 | 17.41 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761315 | WINSTEAD GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510939970 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 51.21 | MR1 | N | T1 SECONDARY |  | 44473 | 44540 | 51.2 | 0 | 51.2 |  | 5.12 | 5.12 | 5.12 | 5.12 | 5.12 | 5.12 | 5.12 | 5.12 | 5.12 | 5.12 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761313 | GAY GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510836291 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 48.17 | MR1 | N | T1 CONNECTED |  | 44473 | 44540 | 48.2 | 0 | 48.2 |  | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | 4.82 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223154 | WO-0761313 | GAY GARDENS | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510836292 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 8.02 | MR1 | N | T1 CONNECTED |  | 44473 | 44540 | 8 | 0 | 8 |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761632 | CHARLES ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220000782632 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 98.45 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 98.45 | 0 | 98.45 | [11 empty] | 98.45 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761629 | MANOR CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510872431 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 42.73 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 42.7 | 42.7 | [14 empty] | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761629 | MANOR CLOSE | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510872432 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 35.48 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 35.49 | 35.49 | [14 empty] | 5.07 | 5.07 | 5.07 | 5.07 | 5.07 | 5.07 | 5.07 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761630 | ROOSEVELT WAY | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510902895 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 294.14 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 294.14 | 294.14 | [14 empty] | 42.02 | 42.02 | 42.02 | 42.02 | 42.02 | 42.02 | 42.02 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761630 | ROOSEVELT WAY | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510902896 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 80.77 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 80.78 | 80.78 | [14 empty] | 11.54 | 11.54 | 11.54 | 11.54 | 11.54 | 11.54 | 11.54 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761630 | ROOSEVELT WAY | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510902898 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 138.35 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 138.32 | 138.32 | [14 empty] | 19.76 | 19.76 | 19.76 | 19.76 | 19.76 | 19.76 | 19.76 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761631 | NORTON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001253171 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 78.09 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 78.12 | 78.12 | [14 empty] | 11.16 | 11.16 | 11.16 | 11.16 | 11.16 | 11.16 | 11.16 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Jake Parry | JDT | Nicholas Pavitt | IMGA223163 | WO-0761633 | MANOR ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510872679 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 91.51 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 91.49 | 91.49 | [14 empty] | 13.07 | 13.07 | 13.07 | 13.07 | 13.07 | 13.07 | 13.07 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760323 | BRIDGE ROAD | GRAYS | THURROCK | Thurrock Council | 510796375 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 67.57 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 67.56 | 0 | 67.56 |  | 16.89 | 16.89 | 16.89 | 16.89 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760324 | NEW ROAD | GRAYS | THURROCK | Thurrock Council | 510882157 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 142.63 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 142.64 | 0 | 142.64 |  | 35.66 | 35.66 | 35.66 | 35.66 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760324 | NEW ROAD | GRAYS | THURROCK | Thurrock Council | 220001459073 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 4.76 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 4.76 | 0 | 4.76 |  | 1.19 | 1.19 | 1.19 | 1.19 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760325 | EXMOUTH ROAD | GRAYS | THURROCK | Thurrock Council | 510882156 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 23.26 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 23.28 | 0 | 23.28 |  | 5.82 | 5.82 | 5.82 | 5.82 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760325 | EXMOUTH ROAD | GRAYS | THURROCK | Thurrock Council | 510991660 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 24.88 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 24.88 | 0 | 24.88 |  | 6.22 | 6.22 | 6.22 | 6.22 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760325 | EXMOUTH ROAD | GRAYS | THURROCK | Thurrock Council | 510991661 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 19.36 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 19.36 | 0 | 19.36 |  | 4.84 | 4.84 | 4.84 | 4.84 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760325 | EXMOUTH ROAD | GRAYS | THURROCK | Thurrock Council | 510991662 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 35.97 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 35.96 | 0 | 35.96 |  | 8.99 | 8.99 | 8.99 | 8.99 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760325 | EXMOUTH ROAD | GRAYS | THURROCK | Thurrock Council | 510991663 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 19.01 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 19 | 0 | 19 |  | 4.75 | 4.75 | 4.75 | 4.75 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223113 | WO-0760325 | EXMOUTH ROAD | GRAYS | THURROCK | Thurrock Council | 510991664 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 85.59 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 85.6 | 0 | 85.6 |  | 21.4 | 21.4 | 21.4 | 21.4 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223130 | WO-0761198 | DOCK ROAD | TILBURY | THURROCK | Thurrock Council | 510821678 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 116.69 | MR1 | N | T1 SECONDARY |  | 44501 | 44512 | 116.7 | 0 | 116.7 | [5 empty] | 58.35 | 58.35 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223130 | WO-0761199 | MONTREAL ROAD | TILBURY | THURROCK | Thurrock Council | 220001794780 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 21.94 | MR1 | N | T1 SECONDARY |  | 44501 | 44512 | 21.94 | 0 | 21.94 | [5 empty] | 10.97 | 10.97 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223377 | WO-0762258 | SOUTH HILL | HORNDON ON THE HILL | THURROCK | Thurrock Council | 510905272 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 82.78 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 82.8 | 0 | 82.8 | [7 empty] | 16.56 | 16.56 | 16.56 | 16.56 | 16.56 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223377 | WO-0762259 | SOUTH HILL CRESCENT | HORNDON ON THE HILL | THURROCK | Thurrock Council | 510913048 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 79.46 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 79.45 | 0 | 79.45 | [7 empty] | 15.89 | 15.89 | 15.89 | 15.89 | 15.89 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223377 | WO-0762259 | SOUTH HILL CRESCENT | HORNDON ON THE HILL | THURROCK | Thurrock Council | 510913050 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 59.59 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 59.6 | 0 | 59.6 | [7 empty] | 11.92 | 11.92 | 11.92 | 11.92 | 11.92 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223377 | WO-0762258 | SOUTH HILL | HORNDON ON THE HILL | THURROCK | Thurrock Council | 510913040 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 27 | 271.2 | MR1 | N | T1 CBA |  | 44515 | 44547 | 271.2 | 0 | 271.2 | [7 empty] | 54.24 | 54.24 | 54.24 | 54.24 | 54.24 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223377 | WO-0762259 | SOUTH HILL CRESCENT | HORNDON ON THE HILL | THURROCK | Thurrock Council | 510913049 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 30.1 | MR1 | N | T1 CONNECTED |  | 44515 | 44547 | 30.1 | 0 | 30.1 | [7 empty] | 6.02 | 6.02 | 6.02 | 6.02 | 6.02 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223098 | WO-0761850 | WINDSOR AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 220001865701 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.96 | MR1 | N | T1 SECONDARY |  | 44565 | 44596 | 0 | 1.95 | 1.95 | [14 empty] | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223098 | WO-0761849 | YORK AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 510942841 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 213 | 97.46 | MR1 | N | T1 PAST |  | 44565 | 44596 | 0 | 97.45 | 97.45 | [14 empty] | 19.49 | 19.49 | 19.49 | 19.49 | 19.49 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223098 | WO-0761850 | WINDSOR AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 510939389 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 274 | 82.25 | MR1 | N | T1 PAST |  | 44565 | 44596 | 0 | 82.25 | 82.25 | [14 empty] | 16.45 | 16.45 | 16.45 | 16.45 | 16.45 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223098 | WO-0761850 | WINDSOR AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 510939390 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 213 | 94.87 | MR1 | N | T1 PAST |  | 44565 | 44596 | 0 | 94.85 | 94.85 | [14 empty] | 18.97 | 18.97 | 18.97 | 18.97 | 18.97 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223098 | WO-0761850 | WINDSOR AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 510939391 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 9 | 29.97 | MR1 | N | T1 CONNECTED |  | 44565 | 44596 | 0 | 29.95 | 29.95 | [14 empty] | 5.99 | 5.99 | 5.99 | 5.99 | 5.99 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Paul Pilkington | IMGA223378 | WO-0762220 | THE LIMES | PURFLEET-ON-THAMES | THURROCK | Thurrock Council | 510956751 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 97.33 | MR1 | N | T1 CBA |  | 44599 | 44610 | 0 | 97.34 | 97.34 | [19 empty] | 48.67 | 48.67 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Paul Pilkington | IMGA223105 | WO-0760459 | CONNAUGHT AVENUE | GRAYS | THURROCK | Thurrock Council | 220001733846 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.02 | MR1 | N | T1 SECONDARY |  | 44613 | 44638 | 0 | 2.04 | 2.04 | [21 empty] | 0.51 | 0.51 | 0.51 | 0.51 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Paul Pilkington | IMGA223105 | WO-0760460 | LONG LANE | GRAYS | THURROCK | Thurrock Council | 220001229292 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 72.13 | MR1 | N | T1 SECONDARY |  | 44613 | 44638 | 0 | 72.12 | 72.12 | [21 empty] | 18.03 | 18.03 | 18.03 | 18.03 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Paul Pilkington | IMGA223105 | WO-0760460 | LONG LANE | GRAYS | THURROCK | Thurrock Council | 220001312111 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 76.02 | MR1 | N | T1 SECONDARY |  | 44613 | 44638 | 0 | 76.04 | 76.04 | [21 empty] | 19.01 | 19.01 | 19.01 | 19.01 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Paul Pilkington | IMGA223105 | WO-0760461 | FAIRWAY | GRAYS | THURROCK | Thurrock Council | 220001494115 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 28.13 | MR1 | N | T1 SECONDARY |  | 44613 | 44638 | 0 | 28.12 | 28.12 | [21 empty] | 7.03 | 7.03 | 7.03 | 7.03 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | LDP Blank | Paul Pilkington | IMGA223105 | WO-0760459 | CONNAUGHT AVENUE | GRAYS | THURROCK | Thurrock Council | 220001733846 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.02 | MR1 | N | T1 SECONDARY |  | 44651 | 44651 | 0 | 2.02 | 2.02 | [26 empty] | 2.02 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Richard Clee | IMGA223401 | WO-0762228 | LONDON ROAD | RAWRETH | ESSEX | Rochford District Council | 606402519 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 115 | 101.51 | MR1 | N | T1 PAST |  | 44473 | 44491 | 101.52 | 0 | 101.52 |  | 33.84 | 33.84 | 33.84 | [23 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Richard Clee | IMGA223398 | WO-0762251 | PEVENSEY GARDENS | HULLBRIDGE | ESSEX | Rochford District Council | 510892522 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 4750 | 216.71 | MR1 | N | T1 PAST |  | 44494 | 44596 | 130.05 | 72.25 | 202.3 |  |  |  |  | 28.9 | 14.45 | 14.45 | 14.45 | 14.45 | 14.45 | 14.45 | 14.45 |  |  | 14.45 | 14.45 | 14.45 | 14.45 | 14.45 | [8 empty] | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Richard Clee | IMGA223396 | WO-0762219 | HULLBRIDGE ROAD | RAYLEIGH | ESSEX | Rochford District Council | 510855372 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 3080 | 357.68 | MR1 | N | T1 PAST |  | 44599 | 44666 | 0 | 286.16 | 286.16 | [19 empty] | 35.77 | 35.77 | 35.77 | 35.77 | 35.77 | 35.77 | 35.77 | 35.77 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Richard Clee | IMGA223396 | WO-0762219 | HULLBRIDGE ROAD | RAYLEIGH | ESSEX | Rochford District Council | 510855376 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 13.09 | MR1 | N | T1 CONNECTED |  | 44599 | 44666 | 0 | 10.48 | 10.48 | [19 empty] | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | LDP Blank | Richard Clee | IMGA223396 | WO-0762219 | HULLBRIDGE ROAD | RAYLEIGH | ESSEX | Rochford District Council | 622461887 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 347 | 0.52 | MR1 | N | T1 CONNECTED |  | 44599 | 44666 | 0 | 0.4 | 0.4 | [19 empty] | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Dave Bamber | Chris McVeigh | MURRAY | Sam Norris | IMGA223023 | WO-0761811 | MANOR WAY | BRENTWOOD | ESSEX | Brentwood Borough Council | 510872815 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 53.94 | MR1 | N | T1 SECONDARY |  | 44439 | 44470 | 0.01 | 0 | 0.01 | 0.01 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | MURRAY | Sam Norris | IMGA223023 | WO-0761812 | WEST PARK HILL | BRENTWOOD | ESSEX | Brentwood Borough Council | 220000871923 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 9.51 | MR1 | N | T1 SECONDARY |  | 44439 | 44470 | 9.5 | 0 | 9.5 | 9.5 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | MURRAY | Sam Norris | IMGA223023 | WO-0761813 | WEST WAY | BRENTWOOD | ESSEX | Brentwood Borough Council | 510961687 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 90.5 | MR1 | N | T1 SECONDARY |  | 44439 | 44470 | 90.5 | 0 | 90.5 | 90.5 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | MURRAY | Sam Norris | IMGA223023 | WO-0761813 | WEST WAY | BRENTWOOD | ESSEX | Brentwood Borough Council | 510961688 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 10.26 | MR1 | N | T1 SECONDARY |  | 44439 | 44470 | 10.25 | 0 | 10.25 | 10.25 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | MURRAY | Sam Norris | IMGA223023 | WO-0761814 | WESTWOOD AVENUE | BRENTWOOD | ESSEX | Brentwood Borough Council | 510936233 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 64.83 | MR1 | N | T1 SECONDARY |  | 44439 | 44470 | 4.85 | 0 | 4.85 | 4.85 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | MURRAY | Sam Norris | IMGA223023 | WO-0761814 | WESTWOOD AVENUE | BRENTWOOD | ESSEX | Brentwood Borough Council | 220000661505 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 281.7 | MR1 | N | T1 SECONDARY |  | 44439 | 44470 | 29.7 | 0 | 29.7 | 29.7 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761548 | ORCHARD LANE | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 631086806 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 2.11 | MR1 | N | T1 SECONDARY |  | 44473 | 44526 | 2.08 | 0 | 2.08 |  | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761548 | ORCHARD LANE | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 631111430 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 2.08 | MR1 | N | T1 SECONDARY |  | 44473 | 44526 | 2.08 | 0 | 2.08 |  | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761549 | ONGAR ROAD | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 510961739 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 144.11 | MR1 | N | T1 SECONDARY |  | 44473 | 44526 | 144.08 | 0 | 144.08 |  | 18.01 | 18.01 | 18.01 | 18.01 | 18.01 | 18.01 | 18.01 | 18.01 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761549 | ONGAR ROAD | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 626275841 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 276.55 | MR1 | N | T1 SECONDARY |  | 44473 | 44526 | 276.56 | 0 | 276.56 |  | 34.57 | 34.57 | 34.57 | 34.57 | 34.57 | 34.57 | 34.57 | 34.57 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761549 | ONGAR ROAD | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 220001328171 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 3.83 | MR1 | N | T1 SECONDARY |  | 44473 | 44526 | 3.84 | 0 | 3.84 |  | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | 0.48 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761549 | ONGAR ROAD | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 220001332192 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.64 | MR1 | N | T1 SECONDARY |  | 44473 | 44526 | 1.68 | 0 | 1.68 |  | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761548 | ORCHARD LANE | PILGRIMS HATCH | ESSEX | Brentwood Borough Council | 510887433 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 405 | 316.36 | MR1 | N | T1 PAST |  | 44473 | 44526 | 316.4 | 0 | 316.4 |  | 39.55 | 39.55 | 39.55 | 39.55 | 39.55 | 39.55 | 39.55 | 39.55 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Sam Norris | IMGA223032 | WO-0761549 | ONGAR ROAD | SOUTH WEALD | ESSEX | Brentwood Borough Council | 510816009 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 15 | 19.66 | MR1 | N | T1 CONNECTED |  | 44473 | 44526 | 19.68 | 0 | 19.68 |  | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | 2.46 | [18 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223024 | WO-0761546 | ONGAR ROAD | BRENTWOOD | ESSEX | Brentwood Borough Council | 510887127 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 70 | 452.4 | MR1 | N | T1 SECONDARY |  | 44571 | 44610 | 0 | 452.4 | 452.4 | [15 empty] | 75.4 | 75.4 | 75.4 | 75.4 | 75.4 | 75.4 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223024 | WO-0761546 | ONGAR ROAD | BRENTWOOD | ESSEX | Brentwood Borough Council | 510887128 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 69.34 | MR1 | N | T1 SECONDARY |  | 44571 | 44610 | 0 | 69.36 | 69.36 | [15 empty] | 11.56 | 11.56 | 11.56 | 11.56 | 11.56 | 11.56 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223024 | WO-0761546 | ONGAR ROAD | BRENTWOOD | ESSEX | Brentwood Borough Council | 510887143 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 26.29 | MR1 | N | T1 SECONDARY |  | 44571 | 44610 | 0 | 26.28 | 26.28 | [15 empty] | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | 4.38 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223024 | WO-0761547 | WINGWAY | BRENTWOOD | ESSEX | Brentwood Borough Council | 510961729 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 77.27 | MR1 | N | T1 SECONDARY |  | 44571 | 44610 | 0 | 77.28 | 77.28 | [15 empty] | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223024 | WO-0761547 | WINGWAY | BRENTWOOD | ESSEX | Brentwood Borough Council | 510961730 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 23.96 | MR1 | N | T1 SECONDARY |  | 44571 | 44610 | 0 | 23.94 | 23.94 | [15 empty] | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | 3.99 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223022 | WO-0761873 | BRENTWOOD ROAD | INGRAVE | ESSEX | Brentwood Borough Council | 510997034 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 88.72 | MR1 | N | T1 SECONDARY |  | 44613 | 44624 | 0 | 88.72 | 88.72 | [21 empty] | 44.36 | 44.36 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223022 | WO-0761874 | PEARTREES | INGRAVE | ESSEX | Brentwood Borough Council | 220000780187 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 39.14 | MR1 | N | T1 SECONDARY |  | 44613 | 44624 | 0 | 39.14 | 39.14 | [21 empty] | 19.57 | 19.57 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | LDP Blank | Sam Norris | IMGA223022 | WO-0761874 | PEARTREES | INGRAVE | ESSEX | Brentwood Borough Council | 220000780198 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 11.06 | MR1 | N | T1 SECONDARY |  | 44613 | 44624 | 0 | 11.06 | 11.06 | [21 empty] | 5.53 | 5.53 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223181 | WO-0761344 | GRAFTON ROAD |  |  |  | side street | 4 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 3.7 | MR1 | N | T1 SECONDARY |  | 44431 | 44505 | 0.06 | 0 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223181 | WO-0761344 | GRAFTON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001521686 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 631.78 | MR1 | N | T1 SECONDARY |  | 44431 | 44505 | 390.72 | 0 | 390.72 | 65.12 | 65.12 | 65.12 | 65.12 | 65.12 | 65.12 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223181 | WO-0761345 | BRITTAIN ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001601155 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.5 | MR1 | N | T1 SECONDARY |  | 44431 | 44505 | 1.56 | 0 | 1.56 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223181 | WO-0761346 | BOULTON ROAD | DAGENHAM | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001591071 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1 | MR1 | N | T1 SECONDARY |  | 44431 | 44505 | 1.02 | 0 | 1.02 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223152 | WO-0759701 | RIPPLE ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901244 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 15.81 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 15.84 | 0 | 15.84 | [6 empty] | 2.64 | 2.64 | 2.64 | 2.64 | 2.64 | 2.64 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223152 | WO-0759701 | RIPPLE ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901245 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 26.74 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 26.76 | 0 | 26.76 | [6 empty] | 4.46 | 4.46 | 4.46 | 4.46 | 4.46 | 4.46 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223152 | WO-0759701 | RIPPLE ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 510901249 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 491.32 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 491.34 | 0 | 491.34 | [6 empty] | 81.89 | 81.89 | 81.89 | 81.89 | 81.89 | 81.89 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223152 | WO-0759701 | RIPPLE ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 517062155 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 0.91 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 0.9 | 0 | 0.9 | [6 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223152 | WO-0759701 | RIPPLE ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001616234 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.94 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 1.92 | 0 | 1.92 | [6 empty] | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | JDT | Sam Webb | IMGA223152 | WO-0759701 | RIPPLE ROAD | BARKING | BARKING AND DAGENHAM | Barking and Dagenham London Borough Council | 220001616324 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.53 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 1.56 | 0 | 1.56 | [6 empty] | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | LDP Blank | Sam Webb | IMGA223341 | WO-0760191 | GRASSMERE ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510840257 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 103.88 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 103.88 | 103.88 | [14 empty] | 51.94 | 51.94 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | Andy Bond | LDP Blank | Sam Webb | IMGA223341 | WO-0760191 | GRASSMERE ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510840258 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 203 | 68.95 | MR1 | N | T1 SECONDARY |  | 44565 | 44575 | 0 | 68.96 | 68.96 | [14 empty] | 34.48 | 34.48 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | JDT | Shaun Hughes | IMGA223352 | WO-0759640 | NORWOOD AVENUE | ROMFORD | HAVERING | Havering London Borough Council | 220001456792 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 424.16 | MR1 | N | T1 SECONDARY |  | 44445 | 44470 | 82.16 | 0 | 82.16 | 82.16 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223343 | WO-0761896 | WYCH ELM ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 220000241232 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 309.83 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 309.84 | 0 | 309.84 |  | 77.46 | 77.46 | 77.46 | 77.46 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223343 | WO-0761897 | WYCH ELM CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510942379 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 94.19 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 94.2 | 0 | 94.2 |  | 23.55 | 23.55 | 23.55 | 23.55 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223343 | WO-0761897 | WYCH ELM CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510942380 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 45.88 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 45.88 | 0 | 45.88 |  | 11.47 | 11.47 | 11.47 | 11.47 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223343 | WO-0761897 | WYCH ELM CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510942382 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 41 | 87.57 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 87.56 | 0 | 87.56 |  | 21.89 | 21.89 | 21.89 | 21.89 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223343 | WO-0761897 | WYCH ELM CLOSE | HORNCHURCH | HAVERING | Havering London Borough Council | 510942383 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 9.55 | MR1 | N | T1 CONNECTED |  | 44473 | 44498 | 9.56 | 0 | 9.56 |  | 2.39 | 2.39 | 2.39 | 2.39 | [22 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223090 | WO-0761209 | VENETTE CLOSE | RAINHAM | HAVERING | Havering London Borough Council | 510929817 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 19.75 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 19.74 | 0 | 19.74 | [5 empty] | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | 3.29 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223090 | WO-0761209 | VENETTE CLOSE | RAINHAM | HAVERING | Havering London Borough Council | 510929818 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 37.76 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 37.74 | 0 | 37.74 | [5 empty] | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | 6.29 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223090 | WO-0761209 | VENETTE CLOSE | RAINHAM | HAVERING | Havering London Borough Council | 220001624007 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 91.53 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 91.56 | 0 | 91.56 | [5 empty] | 15.26 | 15.26 | 15.26 | 15.26 | 15.26 | 15.26 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223090 | WO-0761210 | FINDON GARDENS | RAINHAM | HAVERING | Havering London Borough Council | 510832182 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 29 | 140.13 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 140.16 | 0 | 140.16 | [5 empty] | 23.36 | 23.36 | 23.36 | 23.36 | 23.36 | 23.36 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223090 | WO-0761211 | WILFRED AVENUE | RAINHAM | HAVERING | Havering London Borough Council | 510938206 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 112.7 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 112.68 | 0 | 112.68 | [5 empty] | 18.78 | 18.78 | 18.78 | 18.78 | 18.78 | 18.78 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223090 | WO-0761212 | ELLIS AVENUE | RAINHAM | HAVERING | Havering London Borough Council | 220001624030 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 205.48 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 205.5 | 0 | 205.5 | [5 empty] | 34.25 | 34.25 | 34.25 | 34.25 | 34.25 | 34.25 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223342 | WO-0759617 | MAYBUSH ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510875309 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 33.24 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 33.24 | 0 | 33.24 | [11 empty] | 33.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223342 | WO-0759617 | MAYBUSH ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510875310 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 36.03 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 36.03 | 0 | 36.03 | [11 empty] | 36.03 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223342 | WO-0759617 | MAYBUSH ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 220001761921 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 86.25 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 86.25 | 0 | 86.25 | [11 empty] | 86.25 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223336 | WO-0761248 | DYMOKE ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510823959 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 199.13 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 199.12 | 199.12 | [14 empty] | 49.78 | 49.78 | 49.78 | 49.78 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223336 | WO-0761249 | KYME ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 510861910 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 127.9 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 127.92 | 127.92 | [14 empty] | 31.98 | 31.98 | 31.98 | 31.98 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223336 | WO-0761250 | BRENTWOOD ROAD | ROMFORD | HAVERING | Havering London Borough Council | 510795921 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 46 | 173.39 | MR1 | N | T1 SECONDARY |  | 44565 | 44589 | 0 | 173.4 | 173.4 | [14 empty] | 43.35 | 43.35 | 43.35 | 43.35 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223336 | WO-0761248 | DYMOKE ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 606511206 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 2 | 6.55 | MR1 | N | T1 CONNECTED |  | 44565 | 44589 | 0 | 6.56 | 6.56 | [14 empty] | 1.64 | 1.64 | 1.64 | 1.64 | [9 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223336 | WO-0761249 | KYME ROAD | HORNCHURCH | HAVERING | Havering London Borough Council | 606520926 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 10.74 | MR1 | N | T1 CONNECTED |  | 44565 | 44589 | 0 | 10.76 | 10.76 | [14 empty] | 2.69 | 2.69 | 2.69 | 2.69 | [9 empty] | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223348 | WO-0761653 | JUNCTION ROAD | ROMFORD | HAVERING | Havering London Borough Council | 510857838 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 328 | 191.04 | MR1 | N | T1 PAST |  | 44592 | 44624 | 0 | 191.05 | 191.05 | [18 empty] | 38.21 | 38.21 | 38.21 | 38.21 | 38.21 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223348 | WO-0761654 | MAIN ROAD | ROMFORD | HAVERING | Havering London Borough Council | 510871729 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 66.94 | MR1 | N | T1 SECONDARY |  | 44592 | 44624 | 0 | 66.95 | 66.95 | [18 empty] | 13.39 | 13.39 | 13.39 | 13.39 | 13.39 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223348 | WO-0761655 | SIMS CLOSE | ROMFORD | HAVERING | Havering London Borough Council | 510912021 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 55 | 113.63 | MR1 | N | T1 SECONDARY |  | 44592 | 44624 | 0 | 113.65 | 113.65 | [18 empty] | 22.73 | 22.73 | 22.73 | 22.73 | 22.73 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223348 | WO-0761655 | SIMS CLOSE | ROMFORD | HAVERING | Havering London Borough Council | 510912022 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 95.63 | MR1 | N | T1 SECONDARY |  | 44592 | 44624 | 0 | 95.65 | 95.65 | [18 empty] | 19.13 | 19.13 | 19.13 | 19.13 | 19.13 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223348 | WO-0761655 | SIMS CLOSE | ROMFORD | HAVERING | Havering London Borough Council | 510912024 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 56.06 | MR1 | N | T1 SECONDARY |  | 44592 | 44624 | 0 | 56.05 | 56.05 | [18 empty] | 11.21 | 11.21 | 11.21 | 11.21 | 11.21 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223348 | WO-0761655 | SIMS CLOSE | ROMFORD | HAVERING | Havering London Borough Council | 510912026 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 17.72 | MR1 | N | T1 SECONDARY |  | 44592 | 44624 | 0 | 17.7 | 17.7 | [18 empty] | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223337 | WO-0760078 | ELMHURST DRIVE | HORNCHURCH | HAVERING | Havering London Borough Council | 510827437 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 49.78 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 49.78 | 49.78 | [23 empty] | 24.89 | 24.89 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223337 | WO-0760078 | ELMHURST DRIVE | HORNCHURCH | HAVERING | Havering London Borough Council | 510827438 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 63.27 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 63.28 | 63.28 | [23 empty] | 31.64 | 31.64 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223337 | WO-0760078 | ELMHURST DRIVE | HORNCHURCH | HAVERING | Havering London Borough Council | 510827440 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 54.4 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 54.4 | 54.4 | [23 empty] | 27.2 | 27.2 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223337 | WO-0760078 | ELMHURST DRIVE | HORNCHURCH | HAVERING | Havering London Borough Council | 510827441 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 43.03 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 43.04 | 43.04 | [23 empty] | 21.52 | 21.52 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223338 | WO-0759868 | TRUSTONS GARDENS | HORNCHURCH | HAVERING | Havering London Borough Council | 510927182 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 137.16 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 137.16 | 137.16 | [25 empty] | 68.58 | 68.58 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Alex Wright | TBA - Lon | LDP Blank | Shaun Hughes | IMGA223338 | WO-0759868 | TRUSTONS GARDENS | HORNCHURCH | HAVERING | Havering London Borough Council | 510927183 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 44.04 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 44.04 | 44.04 | [25 empty] | 22.02 | 22.02 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760370 | MEADOW VIEW WALK | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510875815 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 52.66 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | 2.65 | 0 | 2.65 | 0.53 | 0.53 | 0.53 | 0.53 | 0.53 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD |  |  |  | 510873167 | 8 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 150.25 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | 149.95 | 0 | 149.95 | 29.99 | 29.99 | 29.99 | 29.99 | 29.99 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD |  |  |  | 220001973017 | 6 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 4 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | 0.05 | 0 | 0.05 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD |  |  |  | 220001973018 | 4 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 3 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | -0.05 | 0 | -0.05 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866898 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 10.27 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | 10.2 | 0 | 10.2 | 2.04 | 2.04 | 2.04 | 2.04 | 2.04 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866899 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 93.06 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | 55.8 | 0 | 55.8 | 11.16 | 11.16 | 11.16 | 11.16 | 11.16 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866900 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 60.51 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | -5.65 | 0 | -5.65 | -1.13 | -1.13 | -1.13 | -1.13 | -1.13 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866901 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 161.53 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | -0.85 | 0 | -0.85 | -0.17 | -0.17 | -0.17 | -0.17 | -0.17 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866904 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 94.78 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | -0.35 | 0 | -0.35 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866905 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 92.26 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | -9.9 | 0 | -9.9 | -1.98 | -1.98 | -1.98 | -1.98 | -1.98 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866906 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 110.82 | MR1 | N | T1 SECONDARY |  | 44403 | 44498 | 106.6 | 0 | 106.6 | 21.32 | 21.32 | 21.32 | 21.32 | 21.32 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Stuart Griffiths | Paul Illingworth | Terra Firma | Stephen Fellows | IMGA223142 | WO-0760371 | LINK ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866907 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 251 | 110.53 | MR1 | N | T1 PAST |  | 44403 | 44498 | -1.7 | 0 | -1.7 | -0.34 | -0.34 | -0.34 | -0.34 | -0.34 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765101 | LIMETREE ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510866489 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 151.47 | MR1 | N | T1 CONNECTED |  | 44508 | 44750 | 30.31 | 56.29 | 86.6 | [5 empty] | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 |  |  | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | 4.33 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765102 | GEYLEN ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510836688 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 142.84 | MR1 | N | T1 CONNECTED |  | 44508 | 44750 | 28.56 | 53.04 | 81.6 | [5 empty] | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 |  |  | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765103 | GIFHORN ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510836828 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 6711 | 255.89 | MR1 | N | T1 CONNECTED |  | 44508 | 44750 | 51.17 | 95.03 | 146.2 | [5 empty] | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 |  |  | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | 7.31 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765104 | TEMPTIN AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510921393 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 4795 | 264.44 | MR1 | N | T1 CONNECTED |  | 44508 | 44750 | 52.92 | 98.28 | 151.2 | [5 empty] | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 |  |  | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765105 | NORTON AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510884983 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 290.84 | MR2 | Y | T1 CONNECTED |  | 44508 | 44750 | 58.17 | 108.03 | 166.2 | [5 empty] | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 |  |  | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | 8.31 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765106 | HALLET ROAD | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510844274 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 304.8 | MR2 | Y | T1 CONNECTED |  | 44508 | 44750 | 60.97 | 113.23 | 174.2 | [5 empty] | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 |  |  | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765107 | SMALLGAINS AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510912426 | 4 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | 1122 | 100.9 | MR1 | N | T1 PAST |  | 44508 | 44750 | 20.16 | 37.44 | 57.6 | [5 empty] | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 |  |  | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Bernie Parrott | TBA - Lon | Terra Firma | Stephen Fellows | IMGA223412 | WO-0765107 | SMALLGAINS AVENUE | CANVEY ISLAND | ESSEX | Castle Point Borough Council | 510912427 | 2 |  | T1 | Inch | ST | Open Cut | MP | Non-Policy | T1Non-Policy | 4"-5" | -1 | 118.48 | MR1 | N | T1 CONNECTED |  | 44508 | 44750 | 23.73 | 44.07 | 67.8 | [5 empty] | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 |  |  | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | 3.39 | LMPS | 4"-5" | MP | Non-Policy | T1 | ST | LMPS
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Stuart Clark | IMGA223099 | WO-0760984 | THAMES HAVEN ROAD | CORRINGHAM | THURROCK | Thurrock Council | 220000658323 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 90.95 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 90.96 | 0 | 90.96 | 15.16 | 15.16 | 15.16 | 15.16 | 15.16 | 15.16 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Stuart Clark | IMGA223099 | WO-0760985 | GIFFORDS CROSS ROAD | CORRINGHAM | THURROCK | Thurrock Council | 220000650961 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 144.26 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 144.3 | 0 | 144.3 | 24.05 | 24.05 | 24.05 | 24.05 | 24.05 | 24.05 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Stuart Clark | IMGA223099 | WO-0760986 | SPRINGHOUSE ROAD | CORRINGHAM | THURROCK | Thurrock Council | 220000639614 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 135.37 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 135.36 | 0 | 135.36 | 22.56 | 22.56 | 22.56 | 22.56 | 22.56 | 22.56 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Stuart Clark | IMGA223099 | WO-0760987 | GOLDSMITHS AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 220000621316 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 15.65 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 15.66 | 0 | 15.66 | 2.61 | 2.61 | 2.61 | 2.61 | 2.61 | 2.61 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Darren Francis | Forefront | Stuart Clark | IMGA223099 | WO-0760988 | PRINCES AVENUE | CORRINGHAM | THURROCK | Thurrock Council | 220000620144 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.19 | MR1 | N | T1 SECONDARY |  | 44459 | 44505 | 1.2 | 0 | 1.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Stuart Clark | IMGA223021 | WO-0760085 | ESSEX WAY | GREAT WARLEY | ESSEX | Brentwood Borough Council | 220000663595 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 164.86 | MR1 | N | T1 PAST |  | 44508 | 44526 | 164.85 | 0 | 164.85 | [6 empty] | 54.95 | 54.95 | 54.95 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Stuart Clark | IMGA223029 | WO-0760005 | CHELMSFORD ROAD - B1002 |  |  | Brentwood Borough Council | 510963714 | 8 |  | T1 | Inch | ST |  | LP | Non-Policy | T1Non-Policy | 4"-5" | 138 | 2.86 | MR1 | N | T1 PAST |  | 44627 | 44673 | 0 | 1.64 | 1.64 | [23 empty] | 0.41 | 0.41 | 0.41 | 0.41 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Stuart Clark | IMGA223029 | WO-0760005 | CHELMSFORD ROAD - B1002 |  |  | Brentwood Borough Council | 510963714 | 8 |  | T1 | Inch | ST |  | LP | Non-Policy | T1Non-Policy | 4"-5" | 138 | 4.25 | MR1 | N | T1 PAST |  | 44627 | 44673 | 0 | 2.44 | 2.44 | [23 empty] | 0.61 | 0.61 | 0.61 | 0.61 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Stuart Clark | IMGA223029 | WO-0760005 | CHELMSFORD ROAD - B1002 |  |  | Brentwood Borough Council | 510963714 | 8 |  | T1 | Inch | ST | Insertion | LP | Non-Policy | T1Non-Policy | 4"-5" | 138 | 86.15 | MR1 | N | T1 PAST |  | 44627 | 44673 | 0 | 49.24 | 49.24 | [23 empty] | 12.31 | 12.31 | 12.31 | 12.31 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Chris McVeigh | Forefront | Stuart Clark | IMGA223029 | WO-0760005 | CHELMSFORD ROAD - B1002 |  |  | Brentwood Borough Council | 510963715 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non-Policy | T1Non-Policy | 4"-5" | 3 | 63.03 | MR1 | N | T1 CONNECTED |  | 44627 | 44673 | 0 | 36 | 36 | [23 empty] | 9 | 9 | 9 | 9 | ST LP 4"-5" | 4"-5" | LP | Non-Policy | T1 | ST | ST LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760910 | NURSERY ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510885226 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 120.4 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | -0.06 | 0 | -0.06 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760910 | NURSERY ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510885227 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 254.16 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | 104.16 | 0 | 104.16 | 17.36 | 17.36 | 17.36 | 17.36 | 17.36 | 17.36 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760910 | NURSERY ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510885234 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 77.32 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | 77.34 | 0 | 77.34 | 12.89 | 12.89 | 12.89 | 12.89 | 12.89 | 12.89 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760910 | NURSERY ROAD | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 220000797193 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 1.18 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | 1.2 | 0 | 1.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760911 | HIGHVIEW CLOSE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510851740 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 122.56 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | 122.58 | 0 | 122.58 | 20.43 | 20.43 | 20.43 | 20.43 | 20.43 | 20.43 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760912 | ALBION HILL | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510780058 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 248 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | -0.66 | 0 | -0.66 | -0.11 | -0.11 | -0.11 | -0.11 | -0.11 | -0.11 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760912 | ALBION HILL | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510780060 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 150 | 220.83 | MR1 | N | T1 PAST |  | 44389 | 44505 | 0.66 | 0 | 0.66 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO East 2 | Dave Bamber | Mick Linwood | Forefront | Warren Brackett | IMGA223273 | WO-0760913 | POLLARDS CLOSE | LOUGHTON | ESSEX | Epping Forest District Council (Lower) | 510965630 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 74.25 | MR1 | N | T1 SECONDARY |  | 44389 | 44505 | -1.74 | 0 | -1.74 | -0.29 | -0.29 | -0.29 | -0.29 | -0.29 | -0.29 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760433 | GORDON AVENUE |  |  | Harrow Council | 510838948 | 10 |  | T2 | Inch | DI |  | LP | Policy | T2Policy | 10"-12" |  | 1005.27 | MR2 | N | T2 PAST |  | 2021-06-21 | 2021-12-17 | 566.64 | 0 | 566.64 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | 47.22 | [15 empty] | T2A | 10"-12" | LP | Policy | T2 | DI | T2A
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760433 | GORDON AVENUE | STANMORE | HARROW | Harrow Council | 510838949 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 42.2 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | -0.84 | 0 | -0.84 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760433 | GORDON AVENUE | STANMORE | HARROW | Harrow Council | 510954500 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 38.12 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 0.24 | 0 | 0.24 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760433 | GORDON AVENUE | STANMORE | HARROW | Harrow Council | 621147465 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 4.03 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | -2.88 | 0 | -2.88 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | -0.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760434 | ASH CLOSE | STANMORE | HARROW | Harrow Council | 220000444596 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.98 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 2.04 | 0 | 2.04 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760435 | GREENACRES DRIVE | STANMORE | HARROW | Harrow Council | 510841447 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 266.35 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 6.24 | 0 | 6.24 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760436 | LEAVESDEN ROAD | STANMORE | HARROW | Harrow Council | 510946562 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 29 | 62.01 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 0.12 | 0 | 0.12 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760436 | LEAVESDEN ROAD | STANMORE | HARROW | Harrow Council | 510946563 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 115 | 172.25 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 0.36 | 0 | 0.36 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760437 | MAYTREE LANE | STANMORE | HARROW | Harrow Council | 220000196435 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 0.61 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 0.48 | 0 | 0.48 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760438 | SUNNINGDALE CLOSE | STANMORE | HARROW | Harrow Council | 510954497 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 155.6 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | -0.48 | 0 | -0.48 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760438 | SUNNINGDALE CLOSE | STANMORE | HARROW | Harrow Council | 510954498 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 15.33 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 0.36 | 0 | 0.36 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760438 | SUNNINGDALE CLOSE | STANMORE | HARROW | Harrow Council | 510954499 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 63.63 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 0.72 | 0 | 0.72 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760439 | THE CHASE | STANMORE | HARROW | Harrow Council | 220000454373 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 2.4 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 2.4 | 0 | 2.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | AARON BLAKE | IMGA222179 | WO-0760440 | WOODLANDS DRIVE | STANMORE | HARROW | Harrow Council | 602558308 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 9.99 | MR1 | N | T1 SECONDARY |  | 2021-06-21 | 2021-12-17 | 9.84 | 0 | 9.84 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | 0.82 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | HARROW | HARROW | Harrow Council | 510938625 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 97.48 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 60.32 | 60.32 | [14 empty] | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | 4.64 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | HARROW | HARROW | Harrow Council | 510938626 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 1292.21 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 799.89 | 799.89 | [14 empty] | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | 61.53 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | HARROW | HARROW | Harrow Council | 510938627 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 1450.23 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 897.78 | 897.78 | [14 empty] | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | 69.06 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | HARROW | HARROW | Harrow Council | 510938637 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 9.9 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 6.11 | 6.11 | [14 empty] | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | HARROW | HARROW | Harrow Council | 620611699 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 50.65 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 31.33 | 31.33 | [14 empty] | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | 2.41 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | HARROW | HARROW | Harrow Council | 220000305490 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 3.8 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 2.34 | 2.34 | [14 empty] | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | AARON BLAKE | IMGA222165 | WO-0761370 | HEADSTONE LANE | NORTH HARROW | HARROW | Harrow Council | 220001856950 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.18 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-05-23 | 0 | 0.78 | 0.78 | [14 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA222149 | WO-0760184 | HARBORD STREET |  |  | Hammersmith and Fulham London Borough Council | 510845486 | 4 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 31 | MR1 | N | T1 SECONDARY |  | 2021-08-16 | 2021-11-05 | 30.96 | 0 | 30.96 |  | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA222149 | WO-0760184 | HARBORD STREET |  |  | Hammersmith and Fulham London Borough Council | 510845494 | 4 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 90 | MR1 | N | T1 SECONDARY |  | 2021-08-16 | 2021-11-05 | 90 | 0 | 90 |  | 15 | 15 | 15 | 15 | 15 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA222149 | WO-0760184 | HARBORD STREET |  |  | Hammersmith and Fulham London Borough Council | 510845495 | 4 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 38 | MR1 | N | T1 SECONDARY |  | 2021-08-16 | 2021-11-05 | 38.04 | 0 | 38.04 |  | 6.34 | 6.34 | 6.34 | 6.34 | 6.34 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA222149 | WO-0760184 | HARBORD STREET | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510845488 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 201.06 | MR1 | N | T1 SECONDARY |  | 2021-08-16 | 2021-11-05 | 145.98 | 0 | 145.98 |  | 24.33 | 24.33 | 24.33 | 24.33 | 24.33 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | ALEC MASON | IMGA222157 | WO-0760171 | GOLDHAWK ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510838451 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 236 | 36.66 | MR1 | N | T1 PAST |  | 2021-11-08 | 2021-11-12 | 36.66 | 0 | 36.66 | [6 empty] | 36.66 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA221051 | WO-0759970 | BRUNEL ESTATE | LONDON | CITY OF WESTMINSTER | Westminster City Council | 510993829 | 200 |  | T1 | mm | ST | Insertion Dead | LP | Non policy | T1Non policy | 4"-5" | 331 | 265.33 | MR1 | N | T1 PAST |  | 2021-11-15 | 2021-12-24 | 265.32 | 0 | 265.32 | [7 empty] | 44.22 | 44.22 | 58.96 | 58.96 | 58.96 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA221051 | WO-0759970 | BRUNEL ESTATE | LONDON | CITY OF WESTMINSTER | Westminster City Council | 220000365822 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 3.91 | MR1 | N | T1 CONNECTED |  | 2021-11-15 | 2021-12-24 | 3.25 | 0 | 3.25 | [7 empty] | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA221051 | WO-0759970 | BRUNEL ESTATE | LONDON | CITY OF WESTMINSTER | Westminster City Council | 510993828 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 60.52 | MR1 | N | T1 SECONDARY |  | 2021-11-15 | 2021-12-24 | 60.54 | 0 | 60.54 | [7 empty] | 10.09 | 10.09 | 13.4533 | 13.4533 | 13.4533 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA221051 | WO-0759970 | BRUNEL ESTATE | LONDON | CITY OF WESTMINSTER | Westminster City Council | 605923911 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 1.53 | MR1 | N | T1 SECONDARY |  | 2021-11-15 | 2021-12-24 | 1.3 | 0 | 1.3 | [7 empty] | 0.26 | 0.26 | 0.26 | 0.26 | 0.26 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | ALEC MASON | IMGA222154 | WO-0759656 | MORE CLOSE | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510975593 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 234 | 112.1 | MR1 | N | T1 PAST |  | 2022-01-04 | 2022-02-14 | 0 | 112.07 | 112.07 | [14 empty] | 16.01 | 16.01 | 16.01 | 16.01 | 16.01 | 16.01 | 16.01 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | ALEC MASON | IMGA222413 | WO-0762196 | PARSONS GREEN LANE | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510890644 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 35 | 48.48 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-28 | 0 | 48.48 | 48.48 | [20 empty] | 16.16 | 16.16 | 16.16 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | ALEC MASON | IMGA222413 | WO-0762196 | PARSONS GREEN LANE | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510890647 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 43.74 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-28 | 0 | 43.74 | 43.74 | [20 empty] | 14.58 | 14.58 | 14.58 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | ALEC MASON | IMGA222413 | WO-0762196 | PARSONS GREEN LANE | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 220001421362 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 1.06 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-28 | 0 | 1.05 | 1.05 | [20 empty] | 0.35 | 0.35 | 0.35 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | ALEC MASON | IMGA222413 | WO-0762195 | FULHAM ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510835269 | 12 |  | T2 | Inch | CI | Open Cut | LP | Non policy | T2Non policy | 10"-12" | 26 | 871.65 | MR2 | Y | T2 CBA |  | 2022-02-15 | 2022-04-11 | 0 | 677.95 | 677.95 | [20 empty] | 96.85 | 96.85 | 96.85 | 96.85 | 96.85 | 96.85 | 96.85 | T2B | 10"-12" | LP | Non policy | T2 | CI | T2B
CMO West 1 | TBA - Lon | Marc Alexander | DIRECT MOLE | ALEX MCKENDRICK | IMGA222028 | WO-0761237 | BROUGHTON STREET | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510798460 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 288.26 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 288.36 | 0 | 288.36 |  | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | 24.03 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | TBA - Lon | Marc Alexander | DIRECT MOLE | ALEX MCKENDRICK | IMGA222028 | WO-0761237 | BROUGHTON STREET | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510798461 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 338.24 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 97.2 | 0 | 97.2 |  | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | 8.1 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | TBA - Lon | Marc Alexander | DIRECT MOLE | ALEX MCKENDRICK | IMGA222028 | WO-0761238 | CAROLINE PLACE | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510788829 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 62.09 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 61.92 | 0 | 61.92 |  | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | KLT | ALFIE CLAIRE | IMGA222398 | WO-0760088 | DRAYTON GREEN |  |  | Ealing Council | 510822775 | 100 |  | T1 | mm | DI |  | LP | Policy | T1Policy | 4"-5" |  | 17 | MR1 | N | T1 SECONDARY |  | 2021-07-26 | 2021-11-12 | -0.84 | 0 | -0.84 |  | -0.12 | -0.12 | -0.12 | -0.12 | -0.12 | -0.12 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | KLT | ALFIE CLAIRE | IMGA222398 | WO-0760088 | DRAYTON GREEN | WEST EALING | EALING | Ealing Council | 510822776 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 56 | 189.64 | MR1 | N | T1 SECONDARY |  | 2021-07-26 | 2021-11-12 | -9.03 | 0 | -9.03 |  | -1.29 | -1.29 | -1.29 | -1.29 | -1.29 | -1.29 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | KLT | ALFIE CLAIRE | IMGA222398 | WO-0760088 | DRAYTON GREEN | WEST EALING | EALING | Ealing Council | 510822777 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 162.32 | MR1 | N | T1 SECONDARY |  | 2021-07-26 | 2021-11-12 | 116.9 | 0 | 116.9 |  | 16.7 | 16.7 | 16.7 | 16.7 | 16.7 | 16.7 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | KLT | ALFIE CLAIRE | IMGA222398 | WO-0760088 | DRAYTON GREEN | WEST EALING | EALING | Ealing Council | 620654351 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 5.13 | MR1 | N | T1 SECONDARY |  | 2021-07-26 | 2021-11-12 | -0.07 | 0 | -0.07 |  | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | KLT | ALFIE CLAIRE | IMGA222398 | WO-0760089 | SUTHERLAND ROAD | WEST EALING | EALING | Ealing Council | 633235248 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 169 | 251.06 | MR1 | N | T1 SECONDARY |  | 2021-07-26 | 2021-11-12 | 251.02 | 0 | 251.02 |  | 35.86 | 35.86 | 35.86 | 35.86 | 35.86 | 35.86 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222071 | WO-0761425 | LANGTRY ROAD | NORTHOLT | EALING | Ealing Council | 510863518 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 71.7 | MR1 | N | T1 SECONDARY |  | 2021-11-15 | 2021-12-10 | 71.72 | 0 | 71.72 | [7 empty] | 17.93 | 17.93 | 17.93 | 17.93 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222071 | WO-0761425 | LANGTRY ROAD | NORTHOLT | EALING | Ealing Council | 510863519 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 72.54 | MR1 | N | T1 SECONDARY |  | 2021-11-15 | 2021-12-10 | 72.56 | 0 | 72.56 | [7 empty] | 18.14 | 18.14 | 18.14 | 18.14 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222071 | WO-0761425 | LANGTRY ROAD | NORTHOLT | EALING | Ealing Council | 510863520 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 10.98 | MR1 | N | T1 SECONDARY |  | 2021-11-15 | 2021-12-10 | 11 | 0 | 11 | [7 empty] | 2.75 | 2.75 | 2.75 | 2.75 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222071 | WO-0761424 | HAWTREY AVENUE | NORTHOLT | EALING | Ealing Council | 220001480644 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 7.48 | MR1 | N | T1 SECONDARY |  | 2021-12-13 | 2021-12-15 | 7.48 | 0 | 7.48 | [11 empty] | 7.48 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222071 | WO-0761426 | LAUGHTON ROAD | NORTHOLT | EALING | Ealing Council | 220001698952 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 5.92 | MR1 | N | T1 SECONDARY |  | 2021-12-16 | 2021-12-17 | 5.92 | 0 | 5.92 | [11 empty] | 5.92 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222401 | WO-0759897 | WESTFIELD ROAD | WEST EALING | EALING | Ealing Council | 510935825 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 260.82 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-31 | 0 | 260.8 | 260.8 | [14 empty] | 52.16 | 52.16 | 52.16 | 52.16 | 52.16 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222401 | WO-0759897 | WESTFIELD ROAD | WEST EALING | EALING | Ealing Council | 510935826 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 60.15 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-31 | 0 | 60.15 | 60.15 | [14 empty] | 12.03 | 12.03 | 12.03 | 12.03 | 12.03 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222401 | WO-0759897 | WESTFIELD ROAD | WEST EALING | EALING | Ealing Council | 510935827 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 118.49 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-31 | 0 | 118.5 | 118.5 | [14 empty] | 23.7 | 23.7 | 23.7 | 23.7 | 23.7 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222434 | WO-0765140 | MAPLE GROVE | SOUTHALL | EALING | Ealing Council | 510873136 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 77.98 | MR1 | N | T1 SECONDARY |  | 2022-02-01 | 2022-02-14 | 0 | 77.97 | 77.97 | [18 empty] | 25.99 | 25.99 | 25.99 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222058 | WO-0761939 | UXBRIDGE ROAD | EALING | EALING | Ealing Council | 510929169 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 34 | 608.45 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-03-28 | 0 | 608.44 | 608.44 | [20 empty] | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | 86.92 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222058 | WO-0761939 | UXBRIDGE ROAD | EALING | EALING | Ealing Council | 633986238 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 3.67 | MR1 | N | T1 SEED |  | 2022-02-15 | 2022-03-28 | 0 | 3.64 | 3.64 | [20 empty] | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222058 | WO-0761939 | UXBRIDGE ROAD | WEST EALING | EALING | Ealing Council | 510929170 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 2.34 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-03-28 | 0 | 2.31 | 2.31 | [20 empty] | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | LDP Blank | ALFIE CLAIRE | IMGA222058 | WO-0761939 | UXBRIDGE ROAD | WEST EALING | EALING | Ealing Council | 611262069 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 3.28 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-03-28 | 0 | 3.29 | 3.29 | [20 empty] | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222068 | WO-0761807 | BENGARTH ROAD | NORTHOLT | EALING | Ealing Council | 510790472 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 209.99 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-11 | 0 | 17.48 | 17.48 | [26 empty] | 17.48 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222068 | WO-0761807 | BENGARTH ROAD | NORTHOLT | EALING | Ealing Council | 510790473 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 221.27 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-11 | 0 | 18.41 | 18.41 | [26 empty] | 18.41 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222068 | WO-0761807 | BENGARTH ROAD | NORTHOLT | EALING | Ealing Council | 220000010575 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 246.57 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-11 | 0 | 20.52 | 20.52 | [26 empty] | 20.52 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | ALFIE CLAIRE | IMGA222068 | WO-0761807 | BENGARTH ROAD | NORTHOLT | EALING | Ealing Council | 220001617746 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 263.44 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-11 | 0 | 21.92 | 21.92 | [26 empty] | 21.92 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | BRADLEY SMITH | IMGA222167 | WO-0759891 | UXBRIDGE ROAD | HATCH END | HARROW | Harrow Council | 510922217 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 0 | 24.05 | MR1 | N | T1 CONNECTED |  | 2021-07-19 | 2021-10-01 | 0.09 | 0 | 0.09 | 0.09 | [26 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | BRADLEY SMITH | IMGA222167 | WO-0759890 | ROWLANDS AVENUE | HATCH END | HARROW | Harrow Council | 510903873 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 30.59 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-10-01 | 5.58 | 0 | 5.58 | [27 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | BRADLEY SMITH | IMGA222167 | WO-0759890 | ROWLANDS AVENUE | HATCH END | HARROW | Harrow Council | 220000058625 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 10.13 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-10-01 | 10.12 | 0 | 10.12 | [27 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | BRADLEY SMITH | IMGA222167 | WO-0759891 | UXBRIDGE ROAD | HATCH END | HARROW | Harrow Council | 510922213 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 50.69 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-10-01 | -0.29 | 0 | -0.29 | [27 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | BRADLEY SMITH | IMGA222167 | WO-0759891 | UXBRIDGE ROAD | HATCH END | HARROW | Harrow Council | 510922214 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 0 | 82.8 | MR2 | Y | T1 ENM CANDIDATE |  | 2021-07-19 | 2021-10-01 | -0.17 | 0 | -0.17 | [27 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | BRADLEY SMITH | IMGA222167 | WO-0759891 | UXBRIDGE ROAD | HATCH END | HARROW | Harrow Council | 510922218 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 98.67 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-10-01 | -0.33 | 0 | -0.33 | [27 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | BRADLEY SMITH | IMGA222072 | WO-0760037 | HORSENDEN LANE SOUTH | PERIVALE | EALING | Ealing Council | 510854766 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 292.54 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 2021-10-04 | 2021-10-29 | 292.56 | 0 | 292.56 |  | 73.14 | 73.14 | 73.14 | 73.14 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | BRADLEY SMITH | IMGA222072 | WO-0760037 | HORSENDEN LANE SOUTH | PERIVALE | EALING | Ealing Council | 606700702 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 2.06 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-10-29 | 2.08 | 0 | 2.08 |  | 0.52 | 0.52 | 0.52 | 0.52 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | BRADLEY SMITH | IMGA222072 | WO-0760038 | DAWLISH AVENUE | PERIVALE | EALING | Ealing Council | 510854764 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 21.28 | MR1 | N | T1 SECONDARY |  | 2021-11-01 | 2021-11-05 | 21.28 | 0 | 21.28 | [5 empty] | 21.28 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | BRADLEY SMITH | IMGA222072 | WO-0760038 | DAWLISH AVENUE | PERIVALE | EALING | Ealing Council | 220000415054 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 3.97 | MR1 | N | T1 SECONDARY |  | 2021-11-01 | 2021-11-05 | 3.97 | 0 | 3.97 | [5 empty] | 3.97 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222409 | WO-0762235 | VICTORIA ROAD | LONDON | BRENT | Brent Council | 510930526 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 327.04 | MR1 | N | T1 CBA |  | 2021-09-06 | 2021-11-19 | 327.04 | 0 | 327.04 |  | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | 40.88 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761697 | STONEBRIDGE PARK | LONDON | BRENT | Brent Council | 510917856 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 86 | 39.31 | MR1 | N | T1 PAST |  | 2021-11-22 | 2022-01-14 | 24.55 | 9.82 | 34.37 | [8 empty] | 4.91 | 6.5467 | 6.5467 | 6.5467 |  |  | 4.91 | 4.91 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761697 | STONEBRIDGE PARK | LONDON | BRENT | Brent Council | 510955809 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 107 | 43.86 | MR1 | N | T1 PAST |  | 2021-11-22 | 2022-01-14 | 25.69 | 10.96 | 36.65 | [8 empty] | 5.48 | 6.7367 | 6.7367 | 6.7367 |  |  | 5.48 | 5.48 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761697 | STONEBRIDGE PARK | LONDON | BRENT | Brent Council | 510955812 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 26.15 | MR1 | N | T1 SECONDARY |  | 2021-11-22 | 2022-01-14 | 24.54 | 6.54 | 31.08 | [8 empty] | 3.27 | 7.09 | 7.09 | 7.09 |  |  | 3.27 | 3.27 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761697 | STONEBRIDGE PARK | LONDON | BRENT | Brent Council | 510955813 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 180 | 135.45 | MR1 | N | T1 PAST |  | 2021-11-22 | 2022-01-14 | 65.52 | 33.86 | 99.38 | [8 empty] | 16.93 | 16.1967 | 16.1967 | 16.1967 |  |  | 16.93 | 16.93 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761697 | STONEBRIDGE PARK | LONDON | BRENT | Brent Council | 510955818 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 45 | 125.9 | MR1 | N | T1 SECONDARY |  | 2021-11-22 | 2022-01-14 | 61.95 | 31.48 | 93.43 | [8 empty] | 15.74 | 15.4033 | 15.4033 | 15.4033 |  |  | 15.74 | 15.74 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761697 | STONEBRIDGE PARK | LONDON | BRENT | Brent Council | 220001454286 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 1.8 | MR1 | N | T1 SECONDARY |  | 2021-11-22 | 2022-01-14 | 0.92 | 0.46 | 1.38 | [8 empty] | 0.23 | 0.23 | 0.23 | 0.23 |  |  | 0.23 | 0.23 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761696 | MELVILLE ROAD | LONDON | BRENT | Brent Council | 510876327 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 267 | 179.96 | MR1 | N | T1 PAST |  | 2022-01-17 | 2022-03-11 | 0 | 180 | 180 | [16 empty] | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 | 22.5 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761696 | MELVILLE ROAD | LONDON | BRENT | Brent Council | 510876328 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 50.5 | MR1 | N | T1 SECONDARY |  | 2022-01-17 | 2022-03-11 | 0 | 50.48 | 50.48 | [16 empty] | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761696 | MELVILLE ROAD | LONDON | BRENT | Brent Council | 510956073 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 114 | 46.19 | MR1 | N | T1 PAST |  | 2022-01-17 | 2022-03-11 | 0 | 46.16 | 46.16 | [16 empty] | 5.77 | 5.77 | 5.77 | 5.77 | 5.77 | 5.77 | 5.77 | 5.77 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761696 | MELVILLE ROAD | LONDON | BRENT | Brent Council | 510956074 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 55.2 | MR1 | N | T1 SECONDARY |  | 2022-01-17 | 2022-03-11 | 0 | 55.2 | 55.2 | [16 empty] | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | DARREN BORE | IMGA222041 | WO-0761696 | MELVILLE ROAD | LONDON | BRENT | Brent Council | 637997844 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 4.73 | MR1 | N | T1 SECONDARY |  | 2022-01-17 | 2022-03-11 | 0 | 4.72 | 4.72 | [16 empty] | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | LDP Blank | DARREN BORE | IMGA222410 | WO-0762245 | WINCHESTER AVENUE | LONDON | BRENT | Brent Council | 510936076 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 101 | 54.28 | MR1 | N | T1 CBA |  | 2022-03-14 | 2022-03-18 | 0 | 54.28 | 54.28 | [24 empty] | 54.28 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222173 | WO-0761903 | DURLEY AVENUE | RAYNERS LANE | HARROW | Harrow Council | 220001726161 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.39 | MR1 | N | T1 CONNECTED |  | 2021-09-13 | 2021-12-17 | 2.4 | 0 | 2.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222173 | WO-0761902 | CANNON LANE |  |  | Harrow Council | 510802280 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 104 | MR1 | N | T1 CBA |  | 2021-09-13 | 2021-12-17 | 103.92 | 0 | 103.92 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | 8.66 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222173 | WO-0761902 | CANNON LANE | PINNER | HARROW | Harrow Council | 510802305 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 599.95 | MR1 | N | T1 SECONDARY |  | 2021-09-13 | 2021-12-17 | 599.16 | 0 | 599.16 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | 49.93 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222173 | WO-0761903 | DURLEY AVENUE | RAYNERS LANE | HARROW | Harrow Council | 630751070 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 63 | 3.28 | MR2 | N | T1 ENM CANDIDATE |  | 2021-09-13 | 2021-12-17 | 3.24 | 0 | 3.24 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222173 | WO-0761904 | TEWKESBURY AVENUE | RAYNERS LANE | HARROW | Harrow Council | 510921653 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 237.87 | MR1 | N | T1 SECONDARY |  | 2021-09-13 | 2021-12-17 | 237.84 | 0 | 237.84 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | 19.82 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222173 | WO-0761904 | TEWKESBURY AVENUE | RAYNERS LANE | HARROW | Harrow Council | 510921654 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 199.72 | MR1 | N | T1 SECONDARY |  | 2021-09-13 | 2021-12-17 | 199.8 | 0 | 199.8 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | 16.65 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222164 | WO-0761609 | PINNER PARK AVENUE | HARROW | HARROW | Harrow Council | 510893091 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 480.96 | MR1 | N | T1 SECONDARY |  | 2021-11-08 | 2021-12-03 | 480.96 | 0 | 480.96 | [6 empty] | 120.24 | 120.24 | 120.24 | 120.24 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222164 | WO-0761608 | HOLMWOOD CLOSE | HARROW | HARROW | Harrow Council | 510853809 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 146.18 | MR1 | N | T1 SECONDARY |  | 2021-12-06 | 2021-12-10 | 146.18 | 0 | 146.18 | [10 empty] | 146.18 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222175 | WO-0761007 | CANNON LANE | PINNER | HARROW | Harrow Council | 510802287 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 236.87 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 2022-01-04 | 2022-01-24 | 0 | 236.88 | 236.88 | [14 empty] | 59.22 | 59.22 | 59.22 | 59.22 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | GAVIN CARTY | IMGA222175 | WO-0761008 | VALE CROFT | PINNER | HARROW | Harrow Council | 510929333 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 71.76 | MR1 | N | T1 SECONDARY |  | 2022-01-25 | 2022-01-31 | 0 | 71.76 | 71.76 | [17 empty] | 35.88 | 35.88 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761570 | RAVENSBOURNE GARDENS | WEST EALING | EALING | Ealing Council | 510898561 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 8.02 | MR1 | N | T1 SECONDARY |  | 2022-02-01 | 2022-02-07 | 0 | 8.02 | 8.02 | [18 empty] | 4.01 | 4.01 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761568 | HOLLINGBOURNE GARDENS | WEST EALING | EALING | Ealing Council | 220000798418 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 4.1 | MR1 | N | T1 SECONDARY |  | 2022-02-08 | 2022-02-14 | 0 | 4.1 | 4.1 | [19 empty] | 2.05 | 2.05 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761569 | NORTH AVENUE | WEST EALING | EALING | Ealing Council | 510883570 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 154.67 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-21 | 0 | 154.68 | 154.68 | [20 empty] | 77.34 | 77.34 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761569 | NORTH AVENUE | WEST EALING | EALING | Ealing Council | 510883571 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 7.32 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-21 | 0 | 7.32 | 7.32 | [20 empty] | 3.66 | 3.66 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761571 | SHERBORNE GARDENS | WEST EALING | EALING | Ealing Council | 510910994 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 201.63 | MR1 | N | T1 SECONDARY |  | 2022-02-22 | 2022-03-07 | 0 | 201.63 | 201.63 | [21 empty] | 67.21 | 67.21 | 67.21 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761571 | SHERBORNE GARDENS | WEST EALING | EALING | Ealing Council | 510910995 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 5.57 | MR1 | N | T1 SECONDARY |  | 2022-02-22 | 2022-03-07 | 0 | 5.58 | 5.58 | [21 empty] | 1.86 | 1.86 | 1.86 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761572 | ST STEPHENS AVENUE | WEST EALING | EALING | Ealing Council | 510907632 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 52.67 | MR1 | N | T1 SECONDARY |  | 2022-03-08 | 2022-03-14 | 0 | 52.68 | 52.68 | [23 empty] | 26.34 | 26.34 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761573 | ST STEPHENS ROAD | WEST EALING | EALING | Ealing Council | 510907637 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 151.65 | MR1 | N | T1 SECONDARY |  | 2022-03-15 | 2022-03-21 | 0 | 151.66 | 151.66 | [24 empty] | 75.83 | 75.83 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761574 | WIMBORNE GARDENS | WEST EALING | EALING | Ealing Council | 510938974 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 136.34 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-04-04 | 0 | 90.9 | 90.9 | [25 empty] | 45.45 | 45.45 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761574 | WIMBORNE GARDENS | WEST EALING | EALING | Ealing Council | 510938975 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 246.12 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-04-04 | 0 | 164.08 | 164.08 | [25 empty] | 82.04 | 82.04 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | GAVIN CARTY | IMGA222399 | WO-0761574 | WIMBORNE GARDENS | WEST EALING | EALING | Ealing Council | 620666780 | 3 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 1.01 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-04-04 | 0 | 0.68 | 0.68 | [25 empty] | 0.34 | 0.34 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761610 | PINNER VIEW | NORTH HARROW | HARROW | Harrow Council | 510893127 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 92.05 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 11.16 | 0.93 | 12.09 |  | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 |  |  | 0.93 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761610 | PINNER VIEW | NORTH HARROW | HARROW | Harrow Council | 510893128 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 185.47 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 160.68 | 12.36 | 173.04 |  | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 16.48 | 16.48 | 16.48 |  |  | 12.36 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761610 | PINNER VIEW | NORTH HARROW | HARROW | Harrow Council | 510893130 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 1041.73 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 794.56 | 61.12 | 855.68 |  | 61.12 | 61.12 | 61.12 | 61.12 | 61.12 | 61.12 | 61.12 | 61.12 | 81.4933 | 81.4933 | 81.4933 |  |  | 61.12 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761610 | PINNER VIEW | NORTH HARROW | HARROW | Harrow Council | 510893133 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 9.89 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 7.8 | 0.65 | 8.45 |  | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 | 0.65 |  |  | 0.65 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761610 | PINNER VIEW | NORTH HARROW | HARROW | Harrow Council | 637532019 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 6.67 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 5.28 | 0.44 | 5.72 |  | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 |  |  | 0.44 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761611 | BOLTON ROAD | HARROW | HARROW | Harrow Council | 220001365784 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.78 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 2.28 | 0.19 | 2.47 |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 |  |  | 0.19 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761612 | CHANDOS ROAD | HARROW | HARROW | Harrow Council | 602558644 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 7.06 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 5.64 | 0.47 | 6.11 |  | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 | 0.47 |  |  | 0.47 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761613 | LONGLEY ROAD | HARROW | HARROW | Harrow Council | 220001425378 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 1 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 0.84 | 0.07 | 0.91 |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  |  | 0.07 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761614 | HIDE ROAD | HARROW | HARROW | Harrow Council | 220001311194 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 2.35 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 1.92 | 0.16 | 2.08 |  | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 |  |  | 0.16 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761615 | CANTERBURY ROAD | NORTH HARROW | HARROW | Harrow Council | 220001583510 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.64 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 2.04 | 0.17 | 2.21 |  | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 |  |  | 0.17 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761616 | MOAT DRIVE | HARROW | HARROW | Harrow Council | 220001436458 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1.9 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 1.56 | 0.13 | 1.69 |  | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  |  | 0.13 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Darren Smith | KLT | JAMIE TAYLOR | IMGA222162 | WO-0761617 | SUSSEX ROAD | NORTH HARROW | HARROW | Harrow Council | 220001599060 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1.31 | MR1 | N | T1 SECONDARY |  | 2021-08-23 | 2022-01-07 | 1.08 | 0.09 | 1.17 |  | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 |  |  | 0.09 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761889 | WORTON WAY | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510942103 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 334.24 | MR1 | N | T1 SECONDARY |  | 2022-01-10 | 2022-02-18 | 0 | 334.26 | 334.26 | [15 empty] | 55.71 | 55.71 | 55.71 | 55.71 | 55.71 | 55.71 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761889 | WORTON WAY | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510942104 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 315.51 | MR1 | N | T1 SECONDARY |  | 2022-01-10 | 2022-02-18 | 0 | 315.54 | 315.54 | [15 empty] | 52.59 | 52.59 | 52.59 | 52.59 | 52.59 | 52.59 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761889 | WORTON WAY | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510969099 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 113.92 | MR1 | N | T1 SECONDARY |  | 2022-01-10 | 2022-02-18 | 0 | 113.94 | 113.94 | [15 empty] | 18.99 | 18.99 | 18.99 | 18.99 | 18.99 | 18.99 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761889 | WORTON WAY | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510969100 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 183.94 | MR1 | N | T1 SECONDARY |  | 2022-01-10 | 2022-02-18 | 0 | 183.96 | 183.96 | [15 empty] | 30.66 | 30.66 | 30.66 | 30.66 | 30.66 | 30.66 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761888 | THE DRIVE | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510922785 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 33.79 | MR1 | N | T1 SECONDARY |  | 2022-02-21 | 2022-03-25 | 0 | 33.8 | 33.8 | [21 empty] | 6.76 | 6.76 | 6.76 | 6.76 | 6.76 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761888 | THE DRIVE | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510922786 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 356.12 | MR1 | N | T1 SECONDARY |  | 2022-02-21 | 2022-03-25 | 0 | 356.1 | 356.1 | [21 empty] | 71.22 | 71.22 | 71.22 | 71.22 | 71.22 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761888 | THE DRIVE | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510976055 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 201.83 | MR1 | N | T1 SECONDARY |  | 2022-02-21 | 2022-03-25 | 0 | 201.85 | 201.85 | [21 empty] | 40.37 | 40.37 | 40.37 | 40.37 | 40.37 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | JAMIE TAYLOR | IMGA222193 | WO-0761888 | THE DRIVE | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510976056 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 179.5 | MR1 | N | T1 SECONDARY |  | 2022-02-21 | 2022-03-25 | 0 | 179.5 | 179.5 | [21 empty] | 35.9 | 35.9 | 35.9 | 35.9 | 35.9 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 1 | IMGA222399 | WO-0761567 | CLEVELAND ROAD | WEST EALING | EALING | Ealing Council | 510811206 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 411.5 | MR1 | N | T1 SECONDARY |  | 2022-02-01 | 2022-03-14 | 0 | 411.53 | 411.53 | [18 empty] | 58.79 | 58.79 | 58.79 | 58.79 | 58.79 | 58.79 | 58.79 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 1 | IMGA222399 | WO-0761567 | CLEVELAND ROAD | WEST EALING | EALING | Ealing Council | 510938979 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 5.25 | MR1 | N | T1 SECONDARY |  | 2022-02-01 | 2022-03-14 | 0 | 5.25 | 5.25 | [18 empty] | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 1 | IMGA222399 | WO-0761567 | CLEVELAND ROAD | WEST EALING | EALING | Ealing Council | 633162799 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 14.38 | MR1 | N | T1 SEED |  | 2022-02-01 | 2022-03-14 | 0 | 14.35 | 14.35 | [18 empty] | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | KLT TBA 2 | IMGA222193 | WO-0761890 | NORTH DRIVE | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510883832 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 348.32 | MR1 | N | T1 SECONDARY |  | 2022-02-07 | 2022-03-25 | 0 | 348.32 | 348.32 | [19 empty] | 49.76 | 49.76 | 49.76 | 49.76 | 49.76 | 49.76 | 49.76 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | KLT TBA 2 | IMGA222193 | WO-0761890 | NORTH DRIVE | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510883834 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 351.35 | MR1 | N | T1 SECONDARY |  | 2022-02-07 | 2022-03-25 | 0 | 351.33 | 351.33 | [19 empty] | 50.19 | 50.19 | 50.19 | 50.19 | 50.19 | 50.19 | 50.19 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | KLT TBA 2 | IMGA222193 | WO-0761891 | SPRING GROVE ROAD | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510914657 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 137.14 | MR1 | N | T1 SECONDARY |  | 2022-03-28 | 2022-04-01 | 0 | 137.14 | 137.14 | [26 empty] | 137.14 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | LDP Blank | KLT TBA 3 | IMGA222435 | WO-0765143 | MONTGOMERY ROAD | EDGWARE | HARROW | Harrow Council | 510878656 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 188.8 | MR1 | N | T1 SECONDARY |  | 2022-01-10 | 2022-01-21 | 0 | 188.8 | 188.8 | [15 empty] | 94.4 | 94.4 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 3 | IMGA222070 | WO-0760166 | GODFREY AVENUE | NORTHOLT | EALING | Ealing Council | 510838211 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 282.58 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-11 | 0 | 282.6 | 282.6 | [20 empty] | 70.65 | 70.65 | 70.65 | 70.65 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 3 | IMGA222070 | WO-0760166 | GODFREY AVENUE | NORTHOLT | EALING | Ealing Council | 510838213 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 90.16 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-11 | 0 | 90.16 | 90.16 | [20 empty] | 22.54 | 22.54 | 22.54 | 22.54 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 3 | IMGA222070 | WO-0760166 | GODFREY AVENUE | NORTHOLT | EALING | Ealing Council | 510838214 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 85.81 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-11 | 0 | 85.8 | 85.8 | [20 empty] | 21.45 | 21.45 | 21.45 | 21.45 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 3 | IMGA222070 | WO-0760166 | GODFREY AVENUE | NORTHOLT | EALING | Ealing Council | 510838216 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 16.46 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-11 | 0 | 16.48 | 16.48 | [20 empty] | 4.12 | 4.12 | 4.12 | 4.12 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | KLT TBA 3 | IMGA222070 | WO-0760166 | GODFREY AVENUE | NORTHOLT | EALING | Ealing Council | 630910135 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 10.81 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-11 | 0 | 10.8 | 10.8 | [20 empty] | 2.7 | 2.7 | 2.7 | 2.7 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | KLT TBA 4 | IMGA222189 | WO-0759591 | ARMADALE ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510783077 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 97.3 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-14 | 0 | 97.3 | 97.3 | [14 empty] | 13.9 | 13.9 | 13.9 | 13.9 | 13.9 | 13.9 | 13.9 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | KLT TBA 4 | IMGA222189 | WO-0759591 | ARMADALE ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510783078 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 132.51 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-14 | 0 | 132.51 | 132.51 | [14 empty] | 18.93 | 18.93 | 18.93 | 18.93 | 18.93 | 18.93 | 18.93 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Simon White | KLT | KLT TBA 4 | IMGA222163 | WO-0759853 | WALTON ROAD | HARROW | HARROW | Harrow Council | 220001236126 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 30.76 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-28 | 0 | 30.75 | 30.75 | [20 empty] | 10.25 | 10.25 | 10.25 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Simon White | KLT | KLT TBA 4 | IMGA222163 | WO-0759853 | WALTON ROAD | HARROW | HARROW | Harrow Council | 220001236129 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 31.73 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-28 | 0 | 31.74 | 31.74 | [20 empty] | 10.58 | 10.58 | 10.58 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | KLT TBA 4 | IMGA222181 | WO-0761044 | BETHANY WAYE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510791225 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 119.2 | MR1 | N | T1 SECONDARY |  | 2022-03-30 | 2022-04-26 | 0 | 16.47 | 16.47 | [26 empty] | 16.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | KLT TBA 4 | IMGA222181 | WO-0761044 | BETHANY WAYE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510791226 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 138.01 | MR1 | N | T1 SECONDARY |  | 2022-03-30 | 2022-04-26 | 0 | 19.06 | 19.06 | [26 empty] | 19.06 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | KLT TBA 4 | IMGA222181 | WO-0761044 | BETHANY WAYE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510791227 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 36.47 | MR1 | N | T1 SECONDARY |  | 2022-03-30 | 2022-04-26 | 0 | 5.04 | 5.04 | [26 empty] | 5.04 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | KLT TBA 4 | IMGA222181 | WO-0761044 | BETHANY WAYE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510791228 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 108.83 | MR1 | N | T1 SECONDARY |  | 2022-03-30 | 2022-04-26 | 0 | 15.03 | 15.03 | [26 empty] | 15.03 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761256 | EAST SHEEN AVENUE |  |  | Richmond upon Thames London Borough Council | 510824655 | 4 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 527.1 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 125.8 | 0 | 125.8 | 25.16 | 25.16 | 25.16 | 25.16 | 25.16 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761256 | EAST SHEEN AVENUE |  |  | Richmond upon Thames London Borough Council | 220001860379 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 300.27 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 47.2 | 0 | 47.2 | 9.44 | 9.44 | 9.44 | 9.44 | 9.44 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761256 | EAST SHEEN AVENUE | EAST SHEEN | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 220001860376 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 215.97 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | -0.2 | 0 | -0.2 | -0.04 | -0.04 | -0.04 | -0.04 | -0.04 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761256 | EAST SHEEN AVENUE | EAST SHEEN | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 220001860380 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.23 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 0.2 | 0 | 0.2 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761257 | VICARAGE DRIVE | EAST SHEEN | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510930040 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 98.43 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 0.4 | 0 | 0.4 | 0.08 | 0.08 | 0.08 | 0.08 | 0.08 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761257 | VICARAGE DRIVE | EAST SHEEN | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510930041 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 28 | 45.42 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 16.4 | 0 | 16.4 | 3.28 | 3.28 | 3.28 | 3.28 | 3.28 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761258 | VICARAGE ROAD | EAST SHEEN | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510930161 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 362.65 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 361.8 | 0 | 361.8 | 72.36 | 72.36 | 72.36 | 72.36 | 72.36 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | MICHAEL COX | IMGA222210 | WO-0761258 | VICARAGE ROAD | EAST SHEEN | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 220001854694 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.24 | MR1 | N | T1 SECONDARY |  | 2021-06-14 | 2021-10-29 | 2.2 | 0 | 2.2 | 0.44 | 0.44 | 0.44 | 0.44 | 0.44 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | MICHAEL COX | IMGA222027 | WO-0760041 | CULVERT ROAD | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510818273 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.52 | MR1 | N | T1 CONNECTED |  | 2021-11-01 | 2021-12-10 | 2.52 | 0 | 2.52 | [5 empty] | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | MICHAEL COX | IMGA222027 | WO-0760041 | CULVERT ROAD | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510818267 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 277.82 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 2021-11-01 | 2021-12-10 | 277.8 | 0 | 277.8 | [5 empty] | 46.3 | 46.3 | 46.3 | 46.3 | 46.3 | 46.3 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | MICHAEL COX | IMGA222027 | WO-0760041 | CULVERT ROAD | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510818271 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 36 | 210.75 | MR1 | N | T1 SECONDARY |  | 2021-11-01 | 2021-12-10 | 210.78 | 0 | 210.78 | [5 empty] | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | MICHAEL COX | IMGA222027 | WO-0760042 | DAGNALL STREET | LONDON | WANDSWORTH | Wandsworth London Borough Council | 607067944 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 16.81 | MR1 | N | T1 CONNECTED |  | 2021-12-13 | 2021-12-17 | 16.81 | 0 | 16.81 | [11 empty] | 16.81 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | MICHAEL COX | IMGA222027 | WO-0760042 | DAGNALL STREET | LONDON | WANDSWORTH | Wandsworth London Borough Council | 510971967 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 22.74 | MR1 | N | T1 SEED |  | 2021-12-13 | 2021-12-17 | 22.74 | 0 | 22.74 | [11 empty] | 22.74 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | PAUL GREEN | IMGA222432 | WO-0764421 | ONSLOW ROAD | RICHMOND | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510887209 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 79.43 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-10-01 | 79.44 | 0 | 79.44 | 79.44 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761284 | FORTESCUE AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510833798 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 26.15 | MR2 | Y | T1 ENM CANDIDATE |  | 2021-09-20 | 2022-03-04 | 13.68 | 10.26 | 23.94 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 |  |  | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761284 | FORTESCUE AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510833796 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 308.32 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 174.33 | 120.69 | 295.02 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 17.88 | 17.88 | 17.88 |  |  | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761284 | FORTESCUE AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510833797 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 9.92 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 5.16 | 3.87 | 9.03 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 |  |  | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761285 | FIELDING AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510831876 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 267.45 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 151.06 | 104.58 | 255.64 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 15.4933 | 15.4933 | 15.4933 |  |  | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 | 11.62 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761285 | FIELDING AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510831877 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 261.56 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 147.81 | 102.33 | 250.14 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 15.16 | 15.16 | 15.16 |  |  | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 | 11.37 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761285 | FIELDING AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510831878 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 152.02 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 85.93 | 59.49 | 145.42 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 8.8133 | 8.8133 | 8.8133 |  |  | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 | 6.61 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761285 | FIELDING AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 220001514382 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 197.78 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 111.8 | 77.4 | 189.2 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 11.4667 | 11.4667 | 11.4667 |  |  | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222221 | WO-0761286 | TURNER AVENUE | TWICKENHAM | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510954546 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 176.14 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2022-03-04 | 99.58 | 68.94 | 168.52 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 10.2133 | 10.2133 | 10.2133 |  |  | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222418 | WO-0762218 | THE HERMITAGE | RICHMOND | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510792088 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 42.25 | MR1 | N | T1 CONNECTED |  | 2022-03-08 | 2022-04-04 | 0 | 33.8 | 33.8 | [23 empty] | 8.45 | 8.45 | 8.45 | 8.45 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Peter Giannini | Marc Alexander | LDP Blank | PAUL GREEN | IMGA222418 | WO-0762218 | THE HERMITAGE | RICHMOND | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510923360 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 380 | 161.35 | MR1 | N | T1 PAST |  | 2022-03-08 | 2022-04-04 | 0 | 129.08 | 129.08 | [23 empty] | 32.27 | 32.27 | 32.27 | 32.27 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RICKY LEFLEUR | IMGA222084 | WO-0760282 | ARDEN ROAD | WEST EALING | EALING | Ealing Council | 515466045 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 14.1 | MR1 | N | T1 CONNECTED |  | 2021-09-13 | 2021-11-05 | 14.1 | 0 | 14.1 | 2.35 | 2.35 | 2.35 | 2.35 | 2.35 | 2.35 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RICKY LEFLEUR | IMGA222084 | WO-0760282 | ARDEN ROAD | WEST EALING | EALING | Ealing Council | 510968698 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 301 | 94.73 | MR1 | N | T1 PAST |  | 2021-09-13 | 2021-11-05 | 55.74 | 0 | 55.74 | 9.29 | 9.29 | 9.29 | 9.29 | 9.29 | 9.29 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RICKY LEFLEUR | IMGA222397 | WO-0761840 | OVERDALE ROAD | EALING | EALING | Ealing Council | 510888270 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 196.15 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2022-01-07 | 168.12 | 14.01 | 182.13 |  | 14.01 | 14.01 | 14.01 | 14.01 | 14.01 | 14.01 | 14.01 | 14.01 | 18.68 | 18.68 | 18.68 |  |  | 14.01 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RICKY LEFLEUR | IMGA222397 | WO-0761841 | WINDERMERE ROAD | EALING | EALING | Ealing Council | 510939228 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 219.78 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2022-01-07 | 188.4 | 15.7 | 204.1 |  | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 15.7 | 20.9333 | 20.9333 | 20.9333 |  |  | 15.7 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | LDP Blank | RICKY LEFLEUR | IMGA222435 | WO-0765141 | GRESHAM ROAD | EDGWARE | HARROW | Harrow Council | 510842001 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 130 | 94.28 | MR1 | N | T1 SECONDARY |  | 2022-01-24 | 2022-01-28 | 0 | 94.28 | 94.28 | [17 empty] | 94.28 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | LDP Blank | RICKY LEFLEUR | IMGA222435 | WO-0765142 | CHURCHILL ROAD | EDGWARE | HARROW | Harrow Council | 510809819 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 46 | 159.81 | MR1 | N | T1 SECONDARY |  | 2022-01-31 | 2022-02-11 | 0 | 159.82 | 159.82 | [18 empty] | 79.91 | 79.91 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | RICKY LEFLEUR | IMGA222070 | WO-0760167 | HINDHEAD GARDENS | NORTHOLT | EALING | Ealing Council | 510852733 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 115.47 | MR1 | N | T1 SECONDARY |  | 2022-03-14 | 2022-04-01 | 0 | 115.47 | 115.47 | [24 empty] | 38.49 | 38.49 | 38.49 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | RICKY LEFLEUR | IMGA222070 | WO-0760167 | HINDHEAD GARDENS | NORTHOLT | EALING | Ealing Council | 510852739 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 54.27 | MR1 | N | T1 SECONDARY |  | 2022-03-14 | 2022-04-01 | 0 | 54.27 | 54.27 | [24 empty] | 18.09 | 18.09 | 18.09 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | RICKY LEFLEUR | IMGA222070 | WO-0760167 | HINDHEAD GARDENS | NORTHOLT | EALING | Ealing Council | 606703052 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 5.08 | MR1 | N | T1 SECONDARY |  | 2022-03-14 | 2022-04-01 | 0 | 5.07 | 5.07 | [24 empty] | 1.69 | 1.69 | 1.69 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Darren Smith | LDP Blank | RICKY LEFLEUR | IMGA222070 | WO-0760167 | HINDHEAD GARDENS | NORTHOLT | EALING | Ealing Council | 220000034159 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 82.15 | MR1 | N | T1 SECONDARY |  | 2022-03-14 | 2022-04-01 | 0 | 82.14 | 82.14 | [24 empty] | 27.38 | 27.38 | 27.38 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761038 | MARLBOROUGH ROAD |  |  | Hounslow London Borough Council |  | 2 |  | T1 | Inch | ST |  | LP | Non policy | T1Non policy | 4"-5" |  | 30 | MR1 | N | T1 CONNECTED |  | 2021-07-19 | 2021-12-17 | 29.88 | 0 | 29.88 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0760206 | AMESBURY ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510781827 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 216.75 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 2021-07-19 | 2021-12-17 | 135.72 | 0 | 135.72 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | 11.31 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0760206 | AMESBURY ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510781828 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 219 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | 218.88 | 0 | 218.88 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | 18.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0760207 | WESTBURY ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 220001560072 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 142.5 | MR1 | N | T1 SEED |  | 2021-07-19 | 2021-12-17 | 142.56 | 0 | 142.56 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761038 | MARLBOROUGH ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510873964 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 147.4 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | -0.6 | 0 | -0.6 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | -0.05 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761038 | MARLBOROUGH ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510873965 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 97.82 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | -0.12 | 0 | -0.12 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761038 | MARLBOROUGH ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510873966 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 39.06 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | -0.84 | 0 | -0.84 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | -0.07 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761038 | MARLBOROUGH ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510873967 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 69.17 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | -0.96 | 0 | -0.96 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | -0.08 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761039 | EASTBOURNE ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510824803 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 73.48 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | 10.44 | 0 | 10.44 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761039 | EASTBOURNE ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510824805 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 24.83 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | 24.84 | 0 | 24.84 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | 2.07 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761039 | EASTBOURNE ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510824806 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 96.36 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | 96.36 | 0 | 96.36 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | 8.03 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222184 | WO-0761039 | EASTBOURNE ROAD | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 220001560809 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 2.38 | MR1 | N | T1 SECONDARY |  | 2021-07-19 | 2021-12-17 | 2.4 | 0 | 2.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | ROB MEARE | IMGA222195 | WO-0761712 | STAINES ROAD | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 606662404 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 45.09 | MR1 | N | T1 CONNECTED |  | 2022-01-04 | 2022-02-28 | 0 | 45.09 | 45.09 | [14 empty] | 5.01 | 5.01 | 5.01 | 5.01 | 5.01 | 5.01 | 5.01 | 5.01 | 5.01 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | ROB MEARE | IMGA222195 | WO-0761712 | STAINES ROAD | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 625423501 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 31 | 464.3 | MR2 | N | T1 ENM SPECIFIED |  | 2022-01-04 | 2022-02-28 | 0 | 464.31 | 464.31 | [14 empty] | 51.59 | 51.59 | 51.59 | 51.59 | 51.59 | 51.59 | 51.59 | 51.59 | 51.59 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | LDP Blank | ROB MEARE | IMGA222195 | WO-0761713 | WIVENHOE COURT | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510969535 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 58.61 | MR1 | N | T1 SECONDARY |  | 2022-03-01 | 2022-03-07 | 0 | 58.62 | 58.62 | [22 empty] | 29.31 | 29.31 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222192 | WO-0761650 | SHAKESPEARE AVENUE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510910219 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 354.35 | MR1 | N | T1 SECONDARY |  | 2022-03-08 | 2022-03-21 | 0 | 53.16 | 53.16 | [23 empty] | 17.72 | 17.72 | 17.72 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222192 | WO-0761650 | SHAKESPEARE AVENUE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510910220 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 200.64 | MR1 | N | T1 SECONDARY |  | 2022-03-08 | 2022-03-21 | 0 | 30.09 | 30.09 | [23 empty] | 10.03 | 10.03 | 10.03 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222192 | WO-0761650 | SHAKESPEARE AVENUE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 634962957 | 2 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 24.92 | MR1 | N | T1 SECONDARY |  | 2022-03-08 | 2022-03-21 | 0 | 3.75 | 3.75 | [23 empty] | 1.25 | 1.25 | 1.25 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | ROB MEARE | IMGA222192 | WO-0761652 | TENNYSON CLOSE | FELTHAM | HOUNSLOW | Hounslow London Borough Council | 510921449 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 74.96 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-04-04 | 0 | 49.98 | 49.98 | [25 empty] | 24.99 | 24.99 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761808 | WEST WAY | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510969074 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 431.48 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 421.56 | 0 | 421.56 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | 35.13 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761808 | WEST WAY | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510969075 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 452.11 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 9.12 | 0 | 9.12 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761809 | SUTTON SQUARE | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510919686 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 237.98 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 238.08 | 0 | 238.08 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | 19.84 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761809 | SUTTON SQUARE | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510919687 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 111.61 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 111.6 | 0 | 111.6 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761810 | SUTTON WAY | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510919732 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 176.51 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 176.52 | 0 | 176.52 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | 14.71 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761810 | SUTTON WAY | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510919733 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 223.38 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 223.32 | 0 | 223.32 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | 18.61 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Lee Blackmore | KLT | RUSSELL ANTHONY JNR | IMGA222203 | WO-0761810 | SUTTON WAY | HOUNSLOW | HOUNSLOW | Hounslow London Borough Council | 510919734 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 18.02 | MR1 | N | T1 SECONDARY |  | 2021-09-06 | 2021-12-17 | 18 | 0 | 18 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001740655 | 1 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.9 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 2.88 | 0 | 2.88 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001740656 | 1 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.82 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 2.88 | 0 | 2.88 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001740717 | 2 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 3.21 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 3.24 | 0 | 3.24 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001741015 | 1 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.48 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 2.52 | 0 | 2.52 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | 0.21 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001741020 | 1 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.94 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 3 | 0 | 3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001741027 | 2 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 1.73 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 1.68 | 0 | 1.68 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | 0.14 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 220001748054 | 2 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.78 | MR1 | N | T1 CONNECTED |  | 2021-09-20 | 2021-12-17 | 2.76 | 0 | 2.76 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 510813649 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 346.58 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-12-17 | 171.6 | 0 | 171.6 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | 14.3 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761150 | COMPTON CRESCENT | NORTHOLT | EALING | Ealing Council | 510813650 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 73.67 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-12-17 | 73.68 | 0 | 73.68 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | 6.14 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761151 | FOOTPATH LINKING VANBROUGH CRESCENT AND IRVING AVENUE | NORTHOLT | EALING | Ealing Council | 510856686 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 42.46 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-12-17 | 42.48 | 0 | 42.48 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | 3.54 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761152 | HEARN RISE | NORTHOLT | EALING | Ealing Council | 510847889 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 62.69 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-12-17 | 62.64 | 0 | 62.64 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | 5.22 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761152 | HEARN RISE | NORTHOLT | EALING | Ealing Council | 510847890 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 61.25 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-12-17 | 61.2 | 0 | 61.2 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | 5.1 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222069 | WO-0761153 | IRVING AVENUE | NORTHOLT | EALING | Ealing Council | 220001617737 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 287.45 | MR1 | N | T1 SECONDARY |  | 2021-09-20 | 2021-12-17 | 287.4 | 0 | 287.4 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | 23.95 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760914 | DELAMERE ROAD | EALING | EALING | Ealing Council | 510820333 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 206.51 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-28 | 0 | 206.55 | 206.55 | [14 empty] | 22.95 | 22.95 | 22.95 | 22.95 | 22.95 | 22.95 | 22.95 | 22.95 | 22.95 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760914 | DELAMERE ROAD | EALING | EALING | Ealing Council | 510820334 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 446.19 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-28 | 0 | 446.22 | 446.22 | [14 empty] | 49.58 | 49.58 | 49.58 | 49.58 | 49.58 | 49.58 | 49.58 | 49.58 | 49.58 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760914 | DELAMERE ROAD | EALING | EALING | Ealing Council | 510820335 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 30.45 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-28 | 0 | 30.42 | 30.42 | [14 empty] | 3.38 | 3.38 | 3.38 | 3.38 | 3.38 | 3.38 | 3.38 | 3.38 | 3.38 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760914 | DELAMERE ROAD | EALING | EALING | Ealing Council | 510820336 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 82.86 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-28 | 0 | 82.89 | 82.89 | [14 empty] | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760914 | DELAMERE ROAD | EALING | EALING | Ealing Council | 510826420 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 128.76 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-28 | 0 | 128.79 | 128.79 | [14 empty] | 14.31 | 14.31 | 14.31 | 14.31 | 14.31 | 14.31 | 14.31 | 14.31 | 14.31 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760915 | ELM AVENUE | EALING | EALING | Ealing Council | 606146835 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 6 | 14.74 | MR1 | N | T1 CONNECTED |  | 2022-03-01 | 2022-03-14 | 0 | 14.73 | 14.73 | [22 empty] | 4.91 | 4.91 | 4.91 |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760915 | ELM AVENUE | EALING | EALING | Ealing Council | 510826936 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 233.07 | MR1 | N | T1 SECONDARY |  | 2022-03-01 | 2022-03-14 | 0 | 233.07 | 233.07 | [22 empty] | 77.69 | 77.69 | 77.69 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760915 | ELM AVENUE | EALING | EALING | Ealing Council | 510843343 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 19.15 | MR1 | N | T1 SECONDARY |  | 2022-03-01 | 2022-03-14 | 0 | 19.14 | 19.14 | [22 empty] | 6.38 | 6.38 | 6.38 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760915 | ELM AVENUE | EALING | EALING | Ealing Council | 220000839834 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1.36 | MR1 | N | T1 SECONDARY |  | 2022-03-01 | 2022-03-14 | 0 | 1.35 | 1.35 | [22 empty] | 0.45 | 0.45 | 0.45 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760916 | ELM CRESCENT | EALING | EALING | Ealing Council | 220000839839 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 127 | MR1 | N | T1 SECONDARY |  | 2022-03-15 | 2022-03-21 | 0 | 127 | 127 | [24 empty] | 63.5 | 63.5 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760917 | ST PAULS CLOSE | EALING | EALING | Ealing Council | 510968767 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 26.15 | MR1 | N | T1 CONNECTED |  | 2022-03-22 | 2022-03-28 | 0 | 26.16 | 26.16 | [25 empty] | 13.08 | 13.08 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760917 | ST PAULS CLOSE | EALING | EALING | Ealing Council | 510968769 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 28.42 | MR1 | N | T1 CONNECTED |  | 2022-03-22 | 2022-03-28 | 0 | 28.42 | 28.42 | [25 empty] | 14.21 | 14.21 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | LDP Blank | RUSSELL ANTONY SNR | IMGA222395 | WO-0760917 | ST PAULS CLOSE | EALING | EALING | Ealing Council | 510968772 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 90.4 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-03-28 | 0 | 90.4 | 90.4 | [25 empty] | 45.2 | 45.2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Paul Burke | KLT | RUSSELL ANTONY SNR | IMGA222208 | WO-0759796 | SUMMERWOOD ROAD | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510973247 | 12 |  | T2 | Inch | DI | Open Cut | LP | Policy | T2Policy | 10"-12" | 201 | 119.3 | MR2 | N | T2 PAST |  | 2022-03-29 | 2022-04-11 | 0 | 39.5 | 39.5 | [26 empty] | 39.5 | T2A | 10"-12" | LP | Policy | T2 | DI | T2A
CMO West 1 | Roger Fearn | Paul Burke | KLT | RUSSELL ANTONY SNR | IMGA222208 | WO-0759796 | SUMMERWOOD ROAD | ISLEWORTH | HOUNSLOW | Hounslow London Borough Council | 510973246 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 5.55 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-11 | 0 | 1.84 | 1.84 | [26 empty] | 1.84 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RUSSELL SMITH | IMGA222067 | WO-0760203 | GREENFORD AVENUE |  |  | Ealing Council | 220001237423 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 8.54 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-10-08 | 0.52 | 0 | 0.52 |  | 0.52 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RUSSELL SMITH | IMGA222067 | WO-0760203 | GREENFORD AVENUE | HANWELL | EALING | Ealing Council | 510841565 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 130 | 36.59 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-10-08 | 2.22 | 0 | 2.22 |  | 2.22 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RUSSELL SMITH | IMGA222067 | WO-0760203 | GREENFORD AVENUE | HANWELL | EALING | Ealing Council | 627496739 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 15.03 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-10-08 | 0.91 | 0 | 0.91 |  | 0.91 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RUSSELL SMITH | IMGA222067 | WO-0760203 | GREENFORD AVENUE | HANWELL | EALING | Ealing Council | 627496740 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 88.06 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-10-08 | 5.35 | 0 | 5.35 |  | 5.35 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Paul Burke | KLT | RUSSELL SMITH | IMGA222067 | WO-0761123 | KENNEDY ROAD | HANWELL | EALING | Ealing Council | 220000519934 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 5.29 | MR1 | N | T1 SECONDARY |  | 2021-10-11 | 2021-10-15 | 5 | 0 | 5 |  |  | 5 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | LDP Blank | RUSSELL SMITH | IMGA222166 | WO-0760192 | HARROW VIEW | HARROW | HARROW | Harrow Council | 220000162070 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 154.33 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-17 | 0 | 154.32 | 154.32 | [14 empty] | 51.44 | 51.44 | 51.44 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | KLT | RUSSELL SMITH | IMGA222158 | WO-0759637 | METHUEN ROAD | EDGWARE | HARROW | Harrow Council | 510876722 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 5 | 17.5 | MR1 | N | T1 CONNECTED |  | 2022-01-18 | 2022-03-28 | 0 | 15.07 | 15.07 | [16 empty] | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | KLT | RUSSELL SMITH | IMGA222158 | WO-0759637 | METHUEN ROAD | EDGWARE | HARROW | Harrow Council | 627555103 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 283.82 | MR1 | N | T1 SECONDARY |  | 2022-01-18 | 2022-03-28 | 0 | 244.42 | 244.42 | [16 empty] | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | 22.22 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | KLT | RUSSELL SMITH | IMGA222158 | WO-0759637 | METHUEN ROAD | EDGWARE | HARROW | Harrow Council | 629790742 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 290.81 | MR1 | N | T1 SECONDARY |  | 2022-01-18 | 2022-03-28 | 0 | 250.47 | 250.47 | [16 empty] | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | KLT | RUSSELL SMITH | IMGA222158 | WO-0759637 | METHUEN ROAD | EDGWARE | HARROW | Harrow Council | 629790745 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 25.54 | MR1 | N | T1 SECONDARY |  | 2022-01-18 | 2022-03-28 | 0 | 22 | 22 | [16 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Paul Burke | KLT | RUSSELL SMITH | IMGA222158 | WO-0761943 | MILFORD GARDENS | EDGWARE | HARROW | Harrow Council | 606673950 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 2.81 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-04 | 0 | 1.41 | 1.41 | [26 empty] | 1.41 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | RYAN SEAMAN | IMGA222214 | WO-0759737 | FIRST AVENUE | LONDON | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510832393 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 272.05 | MR1 | N | T1 SECONDARY |  | 2021-06-07 | 2021-11-26 | 5.04 | 0 | 5.04 | 0.56 | 0.56 | 0.56 | 0.56 | 0.56 | 0.56 | 0.56 | 0.56 | 0.56 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | RYAN SEAMAN | IMGA222214 | WO-0759737 | FIRST AVENUE | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510832392 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 252.5 | MR1 | N | T1 SECONDARY |  | 2021-06-07 | 2021-11-26 | 21.51 | 0 | 21.51 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | 2.39 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | RYAN SEAMAN | IMGA222214 | WO-0761036 | SECOND AVENUE | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510909236 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 237.84 | MR1 | N | T1 SECONDARY |  | 2021-06-07 | 2021-11-26 | 105.75 | 0 | 105.75 | 11.75 | 11.75 | 11.75 | 11.75 | 11.75 | 11.75 | 11.75 | 11.75 | 11.75 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | DIRECT MOLE | RYAN SEAMAN | IMGA222214 | WO-0761036 | SECOND AVENUE | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510909237 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 267.7 | MR1 | N | T1 SECONDARY |  | 2021-06-07 | 2021-11-26 | 267.75 | 0 | 267.75 | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | 29.75 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | KLT | RYAN SEAMAN | IMGA222216 | WO-0760889 | ASHLEIGH ROAD | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510972948 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 239.72 | MR1 | N | T1 SECONDARY |  | 2021-11-29 | 2022-01-21 | 119.88 | 89.91 | 209.79 | [9 empty] | 39.96 | 39.96 | 39.96 |  |  | 29.97 | 29.97 | 29.97 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | KLT | RYAN SEAMAN | IMGA222216 | WO-0760889 | ASHLEIGH ROAD | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510972949 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 91 | 186.66 | MR1 | N | T1 SECONDARY |  | 2021-11-29 | 2022-01-21 | 93.32 | 69.99 | 163.31 | [9 empty] | 31.1067 | 31.1067 | 31.1067 |  |  | 23.33 | 23.33 | 23.33 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | KLT | RYAN SEAMAN | IMGA222216 | WO-0759625 | COWLEY ROAD | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510815892 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 255.55 | MR1 | N | T1 SECONDARY |  | 2022-01-24 | 2022-02-04 | 0 | 255.56 | 255.56 | [17 empty] | 127.78 | 127.78 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | KLT | RYAN SEAMAN | IMGA222216 | WO-0760890 | MORTLAKE HIGH STREET | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510815895 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 7.95 | MR1 | N | T1 SECONDARY |  | 2022-02-07 | 2022-02-11 | 0 | 7.95 | 7.95 | [19 empty] | 7.95 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761398 | KINGSWAY | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510861326 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 290.64 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-04 | 0 | 290.64 | 290.64 | [20 empty] | 96.88 | 96.88 | 96.88 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761398 | KINGSWAY | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510861328 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 94.57 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-04 | 0 | 94.56 | 94.56 | [20 empty] | 31.52 | 31.52 | 31.52 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761398 | KINGSWAY | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510861334 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 7.43 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-04 | 0 | 7.44 | 7.44 | [20 empty] | 2.48 | 2.48 | 2.48 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761398 | KINGSWAY | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 634376654 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 8.65 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-04 | 0 | 8.64 | 8.64 | [20 empty] | 2.88 | 2.88 | 2.88 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761398 | KINGSWAY | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 220000188635 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 10.41 | MR1 | N | T1 SECONDARY |  | 2022-02-14 | 2022-03-04 | 0 | 10.41 | 10.41 | [20 empty] | 3.47 | 3.47 | 3.47 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761399 | LOWER RICHMOND ROAD | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510870232 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 289.2 | MR1 | N | T1 SECONDARY |  | 2022-03-07 | 2022-03-18 | 0 | 289.2 | 289.2 | [23 empty] | 144.6 | 144.6 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761400 | RUTLAND CLOSE | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510904950 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 24.75 | MR1 | N | T1 CONNECTED |  | 2022-03-21 | 2022-03-25 | 0 | 24.75 | 24.75 | [25 empty] | 24.75 |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761400 | RUTLAND CLOSE | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510904951 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 40.4 | MR1 | N | T1 CONNECTED |  | 2022-03-21 | 2022-03-25 | 0 | 40.4 | 40.4 | [25 empty] | 40.4 |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761400 | RUTLAND CLOSE | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510904949 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 44.8 | MR1 | N | T1 SECONDARY |  | 2022-03-21 | 2022-03-25 | 0 | 44.8 | 44.8 | [25 empty] | 44.8 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Peter Giannini | Mick Bradley | LDP Blank | RYAN SEAMAN | IMGA222215 | WO-0761401 | SHALSTONE ROAD | MORTLAKE | RICHMOND UPON THAMES | Richmond upon Thames London Borough Council | 510910336 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 45 | 219.9 | MR1 | N | T1 SECONDARY |  | 2022-03-28 | 2022-04-01 | 0 | 219.9 | 219.9 | [26 empty] | 219.9 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222151 | WO-0761481 | ARMINGER ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510783095 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 0 | 164.35 | MR1 | N | T1 SECONDARY |  | 2021-08-09 | 2021-12-17 | 23.4 | 0 | 23.4 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | 1.95 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222151 | WO-0761481 | ARMINGER ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 611306104 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 2.3 | MR1 | N | T1 SECONDARY |  | 2021-08-09 | 2021-12-17 | 2.28 | 0 | 2.28 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222151 | WO-0761482 | ETHELDEN ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510828909 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 59 | 95.53 | MR1 | N | T1 SECONDARY |  | 2021-08-09 | 2021-12-17 | 95.52 | 0 | 95.52 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222151 | WO-0761482 | ETHELDEN ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 220001187038 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 86 | 51.57 | MR1 | N | T1 SECONDARY |  | 2021-08-09 | 2021-12-17 | 0.48 | 0 | 0.48 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222151 | WO-0761483 | INGERSOLL ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 220001187020 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 1.6 | MR1 | N | T1 SECONDARY |  | 2021-08-09 | 2021-12-17 | 1.56 | 0 | 1.56 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222152 | WO-0759906 | WHITE CITY CLOSE | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510968537 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 77.68 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-17 | 0 | 77.67 | 77.67 | [14 empty] | 25.89 | 25.89 | 25.89 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | DPF | SAM HOXHAJ | IMGA222152 | WO-0759905 | EXHIBITION CLOSE | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510968539 | 2 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 37.54 | MR2 | N | T1 ENM SPECIFIED |  | 2022-01-18 | 2022-01-24 | 0 | 37.54 | 37.54 | [16 empty] | 18.77 | 18.77 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA222144 | WO-0759855 | WANDSWORTH BRIDGE ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 637330494 | 2 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 0.85 | MR1 | N | T1 CONNECTED |  | 2022-01-25 | 2022-05-02 | 0 | 0.6 | 0.6 | [17 empty] | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | 0.06 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA222144 | WO-0759855 | WANDSWORTH BRIDGE ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510787614 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 2.36 | MR1 | N | T1 SECONDARY |  | 2022-01-25 | 2022-05-02 | 0 | 1.6 | 1.6 | [17 empty] | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA222144 | WO-0759855 | WANDSWORTH BRIDGE ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 510932203 | 6 |  | T1 | Inch | CI | Unknown | LP | Policy | T1Policy | 4"-5" | 8 | 945.36 | MR1 | N | T1 SECONDARY |  | 2022-01-25 | 2022-05-02 | 0 | 630.2 | 630.2 | [17 empty] | 63.02 | 63.02 | 63.02 | 63.02 | 63.02 | 63.02 | 63.02 | 63.02 | 63.02 | 63.02 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA222144 | WO-0759855 | WANDSWORTH BRIDGE ROAD | LONDON | HAMMERSMITH AND FULHAM | Hammersmith and Fulham London Borough Council | 606467489 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 8.88 | MR1 | N | T1 SECONDARY |  | 2022-01-25 | 2022-05-02 | 0 | 5.9 | 5.9 | [17 empty] | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | 0.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA221062 | WO-0765416 | ALBA PLACE | LONDON | KENSINGTON AND CHELSEA | Kensington and Chelsea Royal Borough Council | 220000159297 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 5.6 | MR1 | N | T1 SECONDARY |  | 2022-03-31 | 2022-04-06 | 0 | 2.8 | 2.8 | [26 empty] | 2.8 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA221062 | WO-0765415 | PORTOBELLO ROAD | LONDON | KENSINGTON AND CHELSEA | Kensington and Chelsea Royal Borough Council | 510847545 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 41.43 | MR1 | N | T1 CONNECTED |  | 2022-03-31 | 2022-06-08 | 0 | 3.77 | 3.77 | [26 empty] | 3.77 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA221062 | WO-0765415 | PORTOBELLO ROAD | LONDON | KENSINGTON AND CHELSEA | Kensington and Chelsea Royal Borough Council | 510894344 | 18 |  | T3 | Inch | CI | Open Cut | LP | Non policy | T3Non policy | 18"-24" | 40 | 733.94 | MR2 | Y | T3 CBA SPECIFIED |  | 2022-03-31 | 2022-06-08 | 0 | 66.72 | 66.72 | [26 empty] | 66.72 | T3 | 18"-24" | LP | Non policy | T3 | CI | T3
CMO West 1 | Roger Fearn | Ben Noble | LDP Blank | SAM HOXHAJ | IMGA221062 | WO-0765415 | PORTOBELLO ROAD | LONDON | KENSINGTON AND CHELSEA | Kensington and Chelsea Royal Borough Council | 220000530032 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 2.6 | MR1 | N | T1 ALARP |  | 2022-03-31 | 2022-06-08 | 0 | 0.24 | 0.24 | [26 empty] | 0.24 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222061 | WO-0760205 | GREENFORD ROAD SERVICE ROAD TO NUMBERS 355-413 | GREENFORD | EALING | Ealing Council | 510843808 | 8 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 342 | 496.66 | MR1 | N | T1 PAST |  | 2021-09-27 | 2021-12-17 | 496.68 | 0 | 496.68 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | 41.39 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222080 | WO-0759989 | CAVENDISH AVENUE | WEST EALING | EALING | Ealing Council | 510804116 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 178.16 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-24 | 0 | 178.16 | 178.16 | [14 empty] | 44.54 | 44.54 | 44.54 | 44.54 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222080 | WO-0759989 | CAVENDISH AVENUE | WEST EALING | EALING | Ealing Council | 510804122 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 118.81 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-24 | 0 | 118.8 | 118.8 | [14 empty] | 29.7 | 29.7 | 29.7 | 29.7 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222080 | WO-0759989 | CAVENDISH AVENUE | WEST EALING | EALING | Ealing Council | 510804124 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 101.5 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-01-24 | 0 | 101.52 | 101.52 | [14 empty] | 25.38 | 25.38 | 25.38 | 25.38 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Simon White | LDP Blank | TERRY LEGGATT | IMGA222168 | WO-0760450 | WOODHALL GATE | PINNER | HARROW | Harrow Council | 510941025 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 190.12 | MR1 | N | T1 SECONDARY |  | 2022-01-25 | 2022-02-07 | 0 | 190.11 | 190.11 | [17 empty] | 63.37 | 63.37 | 63.37 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Simon White | LDP Blank | TERRY LEGGATT | IMGA222168 | WO-0760450 | WOODHALL GATE | PINNER | HARROW | Harrow Council | 220001423181 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 7.48 | MR1 | N | T1 SECONDARY |  | 2022-01-25 | 2022-02-07 | 0 | 7.47 | 7.47 | [17 empty] | 2.49 | 2.49 | 2.49 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Simon White | LDP Blank | TERRY LEGGATT | IMGA222168 | WO-0760449 | LIMEDENE CLOSE | HATCH END | HARROW | Harrow Council | 510866364 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 76.13 | MR1 | N | T1 SECONDARY |  | 2022-02-08 | 2022-02-14 | 0 | 76.14 | 76.14 | [19 empty] | 38.07 | 38.07 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Trevor Trent | Simon White | LDP Blank | TERRY LEGGATT | IMGA222168 | WO-0760451 | UXBRIDGE ROAD | PINNER | HARROW | Harrow Council | 220001437815 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 95 | 148.73 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-21 | 0 | 148.74 | 148.74 | [20 empty] | 74.37 | 74.37 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760347 | GORDON ROAD | EALING | EALING | Ealing Council | 510839136 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 36 | 664.11 | MR1 | N | T1 SECONDARY |  | 2022-02-22 | 2022-03-14 | 0 | 227.16 | 227.16 | [21 empty] | 56.79 | 56.79 | 56.79 | 56.79 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760347 | GORDON ROAD | EALING | EALING | Ealing Council | 510839137 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 417 | 619.26 | MR1 | N | T1 PAST |  | 2022-02-22 | 2022-03-14 | 0 | 211.84 | 211.84 | [21 empty] | 52.96 | 52.96 | 52.96 | 52.96 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760348 | ST LEONARDS ROAD | WEST EALING | EALING | Ealing Council | 510906641 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 68.76 | MR1 | N | T1 SECONDARY |  | 2022-03-15 | 2022-03-21 | 0 | 68.76 | 68.76 | [24 empty] | 34.38 | 34.38 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760349 | LONGFIELD WALK | EALING | EALING | Ealing Council | 510778600 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 58.03 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-03-28 | 0 | 58.04 | 58.04 | [25 empty] | 29.02 | 29.02 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760349 | LONGFIELD WALK | EALING | EALING | Ealing Council | 612850079 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 5.03 | MR1 | N | T1 SECONDARY |  | 2022-03-22 | 2022-03-28 | 0 | 5.04 | 5.04 | [25 empty] | 2.52 | 2.52 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760350 | LONGFIELD ROAD | EALING | EALING | Ealing Council | 510869366 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 156.32 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-04 | 0 | 4.42 | 4.42 | [26 empty] | 4.42 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Simon White | KLT | TERRY LEGGATT | IMGA222054 | WO-0760350 | LONGFIELD ROAD | EALING | EALING | Ealing Council | 510869367 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 3 | MR1 | N | T1 SECONDARY |  | 2022-03-29 | 2022-04-04 | 0 | 0.09 | 0.09 | [26 empty] | 0.09 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TERRY PARKER | IMGA222394 | WO-0761675 | SOUTHVIEW AVENUE | LONDON | BRENT | Brent Council | 510913291 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 150.27 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-12-17 | 150.26 | 0 | 150.26 |  | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | 13.66 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TERRY PARKER | IMGA222394 | WO-0761675 | SOUTHVIEW AVENUE | LONDON | BRENT | Brent Council | 510913292 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 394.84 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-12-17 | 394.79 | 0 | 394.79 |  | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | 35.89 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TERRY PARKER | IMGA222394 | WO-0761675 | SOUTHVIEW AVENUE | LONDON | BRENT | Brent Council | 606702496 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 2.13 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-12-17 | 2.09 | 0 | 2.09 |  | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TERRY PARKER | IMGA222394 | WO-0761676 | NORTHVIEW CRESCENT | LONDON | BRENT | Brent Council | 510884878 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 184.25 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-12-17 | 184.25 | 0 | 184.25 |  | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | 16.75 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TERRY PARKER | IMGA222394 | WO-0761677 | WESTVIEW CLOSE | LONDON | BRENT | Brent Council | 510935150 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 135.94 | MR1 | N | T1 SECONDARY |  | 2021-10-04 | 2021-12-17 | 135.96 | 0 | 135.96 |  | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | 12.36 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | LDP Blank | TERRY PARKER | IMGA222036 | WO-0759872 | TUBBS ROAD | LONDON | BRENT | Brent Council | 633051857 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 117 | 264.69 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-14 | 0 | 264.67 | 264.67 | [14 empty] | 37.81 | 37.81 | 37.81 | 37.81 | 37.81 | 37.81 | 37.81 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | LDP Blank | TERRY PARKER | IMGA222036 | WO-0759872 | TUBBS ROAD | LONDON | BRENT | Brent Council | 633051858 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 47 | 340.37 | MR1 | N | T1 SECONDARY |  | 2022-01-04 | 2022-02-14 | 0 | 340.34 | 340.34 | [14 empty] | 48.62 | 48.62 | 48.62 | 48.62 | 48.62 | 48.62 | 48.62 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | LDP Blank | TERRY PARKER | IMGA222036 | WO-0760869 | CLIFTON ROAD |  |  |  | 510811561 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" | 26 | 91.79 | MR1 | N | T1 SECONDARY |  | 2022-02-15 | 2022-02-21 | 0 | 91.8 | 91.8 | [20 empty] | 45.9 | 45.9 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760066 | DOLLIS HILL LANE | LONDON | BRENT | Brent Council | 510864790 | 2 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 12.32 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 6.24 | 0 | 6.24 |  | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | 0.52 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760066 | DOLLIS HILL LANE | LONDON | BRENT | Brent Council | 220000478706 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 38 | 351.75 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 351.84 | 0 | 351.84 |  | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760066 | DOLLIS HILL LANE | LONDON | BRENT | Brent Council | 220000478707 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 128.81 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 128.88 | 0 | 128.88 |  | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | 10.74 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760066 | DOLLIS HILL LANE | LONDON | BRENT | Brent Council | 220000478712 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 50 | 344.61 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 244.68 | 0 | 244.68 |  | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | 20.39 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760066 | DOLLIS HILL LANE | LONDON | BRENT | Brent Council | 220000478713 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 408.42 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 94.44 | 0 | 94.44 |  | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | 7.87 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760066 | DOLLIS HILL LANE | LONDON | BRENT | Brent Council | 220000804319 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 13.66 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 13.68 | 0 | 13.68 |  | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | 1.14 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 1 | Gary Conway | Dominic St. John | SQS | TREVOR DAWSON | IMGA222393 | WO-0760067 | HOMESTEAD PARK | LONDON | BRENT | Brent Council | 510854077 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 93.86 | MR1 | N | T1 SECONDARY |  | 2021-07-05 | 2021-12-17 | 93.84 | 0 | 93.84 |  | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | 7.82 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0759824 | THE DRIVE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510922772 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 259.27 | MR1 | N | T1 SECONDARY |  | 44466 | 44491 | 259.28 | 0 | 259.28 |  | 64.82 | 64.82 | 64.82 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0759824 | THE DRIVE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510971267 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 15.45 | MR1 | N | T1 SECONDARY |  | 44466 | 44491 | 15.44 | 0 | 15.44 |  | 3.86 | 3.86 | 3.86 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0759824 | THE DRIVE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220001634376 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 22.02 | MR1 | N | T1 SECONDARY |  | 44466 | 44491 | 22.04 | 0 | 22.04 |  | 5.51 | 5.51 | 5.51 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0759824 | THE DRIVE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220001634382 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 184.11 | MR1 | N | T1 SECONDARY |  | 44466 | 44491 | 184.12 | 0 | 184.12 |  | 46.03 | 46.03 | 46.03 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0761094 | SAILING CLUB ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510778243 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 173.35 | MR1 | N | T1 SECONDARY |  | 44494 | 44505 | 173.36 | 0 | 173.36 |  |  |  |  | 86.68 | 86.68 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0761094 | SAILING CLUB ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510778244 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 22.9 | MR1 | N | T1 SECONDARY |  | 44494 | 44505 | 22.9 | 0 | 22.9 |  |  |  |  | 11.45 | 11.45 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0761095 | THE AVENUE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510971264 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 56.19 | MR1 | N | T1 SECONDARY |  | 44508 | 44526 | 56.19 | 0 | 56.19 | [6 empty] | 18.73 | 18.73 | 18.73 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0761095 | THE AVENUE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510971265 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 62.98 | MR1 | N | T1 SECONDARY |  | 44508 | 44526 | 62.97 | 0 | 62.97 | [6 empty] | 20.99 | 20.99 | 20.99 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0761095 | THE AVENUE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510971266 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 167.99 | MR1 | N | T1 SECONDARY |  | 44508 | 44526 | 168 | 0 | 168 | [6 empty] | 56 | 56 | 56 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222354 | WO-0761095 | THE AVENUE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510971268 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 97.84 | MR1 | N | T1 SECONDARY |  | 44508 | 44526 | 97.83 | 0 | 97.83 | [6 empty] | 32.61 | 32.61 | 32.61 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222372 | WO-0761178 | COATES LANE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 624995393 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 203 | 45.27 | MR1 | N | T1 PAST |  | 44529 | 44540 | 45.28 | 0 | 45.28 | [9 empty] | 22.64 | 22.64 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222372 | WO-0761178 | COATES LANE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 220000633131 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 101.61 | MR1 | N | T1 SECONDARY |  | 44529 | 44540 | 101.62 | 0 | 101.62 | [9 empty] | 50.81 | 50.81 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222372 | WO-0761178 | COATES LANE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 220000634090 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 20 | MR1 | N | T1 SECONDARY |  | 44529 | 44540 | 20 | 0 | 20 | [9 empty] | 10 | 10 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222372 | WO-0761179 | MANOR GARDENS | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510872510 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 38 | 158.76 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 158.76 | 0 | 158.76 | [11 empty] | 158.76 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | LDP Blank | AARON VALE | IMGA222379 | WO-0760239 | HILLSIDE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510852408 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 236 | 172.88 | MR1 | N | T1 PAST |  | 44565 | 44578 | 0 | 172.89 | 172.89 | [14 empty] | 57.63 | 57.63 | 57.63 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222356 | WO-0759753 | SOUTHBOURNE DRIVE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510954429 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 344.86 | MR1 | N | T1 SECONDARY |  | 44579 | 44624 | 0 | 343.98 | 343.98 | [16 empty] | 49.14 | 49.14 | 49.14 | 49.14 | 49.14 | 49.14 | 49.14 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222356 | WO-0761091 | DONKEY LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510936520 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 96.91 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 96.58 | 96.58 | [23 empty] | 48.29 | 48.29 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222356 | WO-0761091 | DONKEY LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510936521 | 4 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 8.46 | MR1 | N | T1 CONNECTED |  | 44627 | 44638 | 0 | 8.44 | 8.44 | [23 empty] | 4.22 | 4.22 |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222356 | WO-0761092 | THE ROSERY | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510971279 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 51.12 | MR1 | N | T1 SECONDARY |  | 44641 | 44645 | 0 | 51 | 51 | [25 empty] | 51 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | AARON VALE | IMGA222356 | WO-0761093 | WALDENS CLOSE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510931692 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 111.19 | MR1 | N | T1 SECONDARY |  | 44648 | 44652 | 0 | 111 | 111 | [26 empty] | 111 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765589 | WALLINGFORD CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510931821 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 46.79 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 33 | 13.75 | 46.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 |  |  | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765589 | WALLINGFORD CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510931822 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 28.24 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 19.92 | 8.3 | 28.22 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 |  |  | 1.66 | 1.66 | 1.66 | 1.66 | 1.66 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765591 | SEGSBURY GROVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510909386 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 65.73 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 46.44 | 19.35 | 65.79 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 |  |  | 3.87 | 3.87 | 3.87 | 3.87 | 3.87 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765591 | SEGSBURY GROVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510909387 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 145.12 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 102.48 | 42.7 | 145.18 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 |  |  | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765591 | SEGSBURY GROVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510909388 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 218.99 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 154.56 | 64.4 | 218.96 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 |  |  | 12.88 | 12.88 | 12.88 | 12.88 | 12.88 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765591 | SEGSBURY GROVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510909389 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 231.84 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 163.68 | 68.2 | 231.88 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 |  |  | 13.64 | 13.64 | 13.64 | 13.64 | 13.64 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765591 | SEGSBURY GROVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510909390 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 46.61 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 32.88 | 13.7 | 46.58 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 |  |  | 2.74 | 2.74 | 2.74 | 2.74 | 2.74 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765591 | SEGSBURY GROVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510909391 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 40.5 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 28.56 | 11.9 | 40.46 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 |  |  | 2.38 | 2.38 | 2.38 | 2.38 | 2.38 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765594 | MEMBURY WALK | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510876344 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 110.5 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 78 | 32.5 | 110.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  |  | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | ALLUN JANES | IMGA222440 | WO-0765596 | LITTLE RINGDALE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510867496 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 88.9 | MR1 | N | T1 SECONDARY |  | 44473 | 44589 | 62.76 | 26.15 | 88.91 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 |  |  | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | ASHTON JONES | IMGA222427 | WO-0762171 | KNIGHTON WAY LANE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510969834 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 149.56 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 149.58 | 0 | 149.58 |  |  |  | 24.93 | 24.93 | 24.93 | 24.93 | 24.93 | 24.93 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | ASHTON JONES | IMGA222427 | WO-0762172 | DENHAM FOOTPATH 24 | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510969835 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 391.26 | MR1 | N | T1 CBA |  | 44487 | 44526 | 391.26 | 0 | 391.26 |  |  |  | 65.21 | 65.21 | 65.21 | 65.21 | 65.21 | 65.21 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | ASHTON JONES | IMGA222427 | WO-0762172 | DENHAM FOOTPATH 24 | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510969837 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 27.47 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 27.48 | 0 | 27.48 |  |  |  | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 | 4.58 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | ASHTON JONES | IMGA222427 | WO-0762173 | NINE STILES CLOSE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510883124 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 29 | 105.14 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 105.12 | 0 | 105.12 |  |  |  | 17.52 | 17.52 | 17.52 | 17.52 | 17.52 | 17.52 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | ASHTON JONES | IMGA222427 | WO-0762174 | OXFORD ROAD | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510969836 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 13.93 | MR1 | N | T1 SECONDARY |  | 44487 | 44526 | 13.92 | 0 | 13.92 |  |  |  | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | 2.32 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | ASHTON JONES | IMGA222279 | WO-0761661 | SOUTH PARK CRESCENT | GERRARDS CROSS | BUCKINGHAMSHIRE | South Bucks District Council | 510913112 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 438.69 | MR1 | N | T1 SECONDARY |  | 44529 | 44554 | 338 | 0 | 338 | [8 empty] | 84.5 | 84.5 | 84.5 | 84.5 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | ASHTON JONES | IMGA222279 | WO-0761663 | SOUTH PARK VIEW | GERRARDS CROSS | BUCKINGHAMSHIRE | South Bucks District Council | 510913125 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 104.88 | MR1 | N | T1 SECONDARY |  | 44557 | 44582 | 0 | 104.88 | 104.88 | [14 empty] | 26.22 | 26.22 | 26.22 | 26.22 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | ASHTON JONES | IMGA222279 | WO-0761663 | SOUTH PARK VIEW | GERRARDS CROSS | BUCKINGHAMSHIRE | South Bucks District Council | 510913126 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 63.53 | MR1 | N | T1 SECONDARY |  | 44557 | 44582 | 0 | 63.52 | 63.52 | [14 empty] | 15.88 | 15.88 | 15.88 | 15.88 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | ASHTON JONES | IMGA222279 | WO-0761663 | SOUTH PARK VIEW | GERRARDS CROSS | BUCKINGHAMSHIRE | South Bucks District Council | 510913127 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 252.73 | MR1 | N | T1 SECONDARY |  | 44557 | 44582 | 0 | 252.72 | 252.72 | [14 empty] | 63.18 | 63.18 | 63.18 | 63.18 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0761347 | ADAM CLOSE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510778940 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 123 | 232.61 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | 92.64 | 0 | 92.64 | 15.44 | 15.44 | 15.44 | 15.44 | 15.44 | 15.44 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0761347 | ADAM CLOSE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510778942 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 130.33 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | 130.38 | 0 | 130.38 | 21.73 | 21.73 | 21.73 | 21.73 | 21.73 | 21.73 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0761348 | AMERSHAM HILL DRIVE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510781691 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 397.95 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | -0.06 | 0 | -0.06 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0761348 | AMERSHAM HILL DRIVE | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510781694 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 26.4 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | -0.6 | 0 | -0.6 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0761349 | MAYHEW CRESCENT | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 220001382256 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 235.87 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | 235.86 | 0 | 235.86 | 39.31 | 39.31 | 39.31 | 39.31 | 39.31 | 39.31 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0761349 | MAYHEW CRESCENT | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 220001786991 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 49.46 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | 49.44 | 0 | 49.44 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | 8.24 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0765495 | TUCKER CLOSE | HIGH WYCOMBE | WYCOMBE | Wycombe District Council | 510781692 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 70 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | 0.06 | 0 | 0.06 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222373 | WO-0765616 | AMERSHAM ROAD |  |  | Buckinghamshire County Council | 510781778 | 8 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 125 | MR1 | N | T1 SECONDARY |  | 44396 | 44505 | -0.06 | 0 | -0.06 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765668 | WELDERS LANE | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510933992 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 1061.12 | MR1 | N | T1 SECONDARY |  | 44508 | 44547 | 1061.1 | 0 | 1061.1 | [6 empty] | 176.85 | 176.85 | 176.85 | 176.85 | 176.85 | 176.85 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765669 | ELEANOR ROAD | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220000270736 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 201.8 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 201.81 | 201.81 | [14 empty] | 28.83 | 28.83 | 28.83 | 28.83 | 28.83 | 28.83 | 28.83 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765670 | NICOL ROAD | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510882966 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 95.72 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 95.69 | 95.69 | [14 empty] | 13.67 | 13.67 | 13.67 | 13.67 | 13.67 | 13.67 | 13.67 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765670 | NICOL ROAD | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510882967 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 48.63 | MR1 | N | T1 SEED |  | 44565 | 44610 | 0 | 48.65 | 48.65 | [14 empty] | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | 6.95 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765670 | NICOL ROAD | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220000857098 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 2.38 | MR1 | N | T1 ALARP |  | 44565 | 44610 | 0 | 2.38 | 2.38 | [14 empty] | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765671 | GLEBE ROAD | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220000270738 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 324.49 | MR1 | N | T1 SECONDARY |  | 44565 | 44610 | 0 | 324.52 | 324.52 | [14 empty] | 46.36 | 46.36 | 46.36 | 46.36 | 46.36 | 46.36 | 46.36 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | BARRY GARDENER | IMGA222443 | WO-0765672 | CHALFONT ST PETER FOOTPATH 22 | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 607003469 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 81.96 | MR1 | N | T1 CONNECTED |  | 44565 | 44610 | 0 | 81.97 | 81.97 | [14 empty] | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | 11.71 | [6 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | BARRY GARDENER | IMGA222355 | WO-0761374 | HEDSOR ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510848283 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 161 | 148.1 | MR1 | N | T1 PAST |  | 44613 | 44617 | 0 | 148.1 | 148.1 | [21 empty] | 148.1 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | BARRY GARDENER | IMGA222355 | WO-0761373 | ANDREWS REACH | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 605069363 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 49.04 | MR1 | N | T1 SECONDARY |  | 44620 | 44624 | 0 | 49.04 | 49.04 | [22 empty] | 49.04 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | BARRY GARDENER | IMGA222370 | WO-0760028 | CRESSEX ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510816915 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 32.83 | MR1 | N | T1 CONNECTED |  | 44627 | 44645 | 0 | 32.82 | 32.82 | [23 empty] | 10.94 | 10.94 | 10.94 |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | BARRY GARDENER | IMGA222370 | WO-0760028 | CRESSEX ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510816927 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 10.63 | MR1 | N | T1 CONNECTED |  | 44627 | 44645 | 0 | 10.62 | 10.62 | [23 empty] | 3.54 | 3.54 | 3.54 |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | BARRY GARDENER | IMGA222370 | WO-0760028 | CRESSEX ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510816913 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 279.8 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44627 | 44645 | 0 | 279.81 | 279.81 | [23 empty] | 93.27 | 93.27 | 93.27 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | BARRY MCQUADE | IMGA222301 | WO-0760251 | LALEHAM ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510944404 | 15 |  | T2 | Inch | DI | Open Cut | LP | Policy | T2Policy | >12"-15" | 508 | 722.36 | MR2 | N | T2 PAST |  | 44361 | 44491 | 564.4 | 0 | 564.4 | 141.1 | 141.1 | 141.1 | 141.1 | [23 empty] | T2A | >12"-15" | LP | Policy | T2 | DI | T2A
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | BARRY MCQUADE | IMGA222301 | WO-0760251 | LALEHAM ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510944409 | 12 |  | T2 | Inch | DI | Open Cut | LP | Policy | T2Policy | 10"-12" | 234 | 645.73 | MR2 | N | T2 PAST |  | 44361 | 44491 | 4.64 | 0 | 4.64 | 1.16 | 1.16 | 1.16 | 1.16 | [23 empty] | T2A | 10"-12" | LP | Policy | T2 | DI | T2A
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | BARRY MCQUADE | IMGA222301 | WO-0760251 | LALEHAM ROAD |  |  | Surrey County Council | Side Street | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 6 | MR1 | N | T1 SECONDARY |  | 44361 | 44491 | 0.08 | 0 | 0.08 | 0.02 | 0.02 | 0.02 | 0.02 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222231 | WO-0759839 | VICARAGE ROAD | EGHAM | SURREY | Runnymede Borough Council | 510930175 | 12 |  | T2 | Inch | DI | Open Cut | LP | Policy | T2Policy | 10"-12" | 202 | 185.65 | MR2 | N | T2 PAST |  | 44494 | 44512 | 185.64 | 0 | 185.64 |  |  |  |  | 61.88 | 61.88 | 61.88 | [20 empty] | T2A | 10"-12" | LP | Policy | T2 | DI | T2A
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222294 | WO-0760409 | STAINES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944497 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 235.06 | MR1 | N | T1 SECONDARY |  | 44515 | 44533 | 235.05 | 0 | 235.05 | [7 empty] | 78.35 | 78.35 | 78.35 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222294 | WO-0760409 | STAINES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944499 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 137 | 16.56 | MR1 | N | T1 PAST |  | 44515 | 44533 | 16.56 | 0 | 16.56 | [7 empty] | 5.52 | 5.52 | 5.52 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222294 | WO-0760409 | STAINES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944500 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 256 | 366.44 | MR1 | N | T1 PAST |  | 44515 | 44533 | 366.45 | 0 | 366.45 | [7 empty] | 122.15 | 122.15 | 122.15 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222294 | WO-0760409 | STAINES ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 220001723580 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 13.25 | MR1 | N | T1 SECONDARY |  | 44515 | 44533 | 13.26 | 0 | 13.26 | [7 empty] | 4.42 | 4.42 | 4.42 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222294 | WO-0760410 | HEREFORD CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510944012 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 182.35 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 182.36 | 0 | 182.36 | [10 empty] | 91.18 | 91.18 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222294 | WO-0760411 | WORPLE ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510943166 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 197 | 126.81 | MR1 | N | T1 PAST |  | 44565 | 44585 | 0 | 126.8 | 126.8 | [14 empty] | 31.7 | 31.7 | 31.7 | 31.7 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 514927405 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 6.21 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 6.2 | 6.2 | [17 empty] | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | 0.62 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 516243614 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 9.19 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 9.2 | 9.2 | [17 empty] | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 606075708 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 10.68 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 10.7 | 10.7 | [17 empty] | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | 1.07 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 606419715 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 7.39 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 7.4 | 7.4 | [17 empty] | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 606429267 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 7.28 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 7.3 | 7.3 | [17 empty] | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | 0.73 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 606432496 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 7.07 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 7.1 | 7.1 | [17 empty] | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 606661953 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 12.26 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 12.3 | 12.3 | [17 empty] | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | 1.23 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607033857 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 6.44 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 6.4 | 6.4 | [17 empty] | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607037705 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 7.67 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 7.7 | 7.7 | [17 empty] | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607046647 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 9.45 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 9.5 | 9.5 | [17 empty] | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607047542 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 9.34 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 9.3 | 9.3 | [17 empty] | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | 0.93 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607165384 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 8.34 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 8.3 | 8.3 | [17 empty] | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | 0.83 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607369785 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 7.6 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 7.6 | 7.6 | [17 empty] | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 607389591 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 16.01 | MR1 | N | T1 CONNECTED |  | 44586 | 44652 | 0 | 16 | 16 | [17 empty] | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510823516 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 6.58 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 6.6 | 6.6 | [17 empty] | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | 0.66 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510888386 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 95.93 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 95.9 | 95.9 | [17 empty] | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510966184 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 271.53 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 271.5 | 271.5 | [17 empty] | 27.15 | 27.15 | 27.15 | 27.15 | 27.15 | 27.15 | 27.15 | 27.15 | 27.15 | 27.15 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510966185 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 74 | 320.49 | MR1 | N | T1 CBA |  | 44586 | 44652 | 0 | 320.5 | 320.5 | [17 empty] | 32.05 | 32.05 | 32.05 | 32.05 | 32.05 | 32.05 | 32.05 | 32.05 | 32.05 | 32.05 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510966187 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 10.96 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 11 | 11 | [17 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 612916172 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 12.93 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 12.9 | 12.9 | [17 empty] | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 612916174 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 7.2 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 7.2 | 7.2 | [17 empty] | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | 0.72 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | BARRY MCQUADE | IMGA222423 | WO-0762151 | BANBURY AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 220001195265 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 7.59 | MR1 | N | T1 SECONDARY |  | 44586 | 44652 | 0 | 7.6 | 7.6 | [17 empty] | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | 0.76 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0761870 | BRADENHAM ROAD |  |  | Hillingdon London Borough Council | 510947979 | 6 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 233.84 | MR1 | N | T1 SECONDARY |  | 44445 | 44477 | -0.26 | 0 | -0.26 |  | -0.13 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0761870 | BRADENHAM ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510947978 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 62 | 231.92 | MR1 | N | T1 SECONDARY |  | 44445 | 44477 | 231.8 | 0 | 231.8 |  | 115.9 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0761870 | BRADENHAM ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510995038 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 71.51 | MR1 | N | T1 SECONDARY |  | 44445 | 44477 | 16.5 | 0 | 16.5 |  | 8.25 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0761869 | LYNTON WALK | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950986 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 108.81 | MR1 | N | T1 SECONDARY |  | 44480 | 44484 | 108.81 | 0 | 108.81 |  |  | 108.81 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0761871 | PORTLAND ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510951972 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 47 | 245.12 | MR1 | N | T1 SECONDARY |  | 44487 | 44498 | 245.12 | 0 | 245.12 |  |  |  | 122.56 | 122.56 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0761872 | KINGSBRIDGE WAY | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950984 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 33.22 | MR1 | N | T1 SECONDARY |  | 44501 | 44505 | 33.22 | 0 | 33.22 | [5 empty] | 33.22 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222104 | WO-0765683 | PERCY GARDENS |  |  | Hillingdon London Borough Council | 510951846 | 4 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 78 | MR1 | N | T1 SECONDARY |  | 44508 | 44512 | 78 | 0 | 78 | [6 empty] | 78 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | billy jackman | IMGA222118 | WO-0760204 | HEATH ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 510950046 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 119 | 275.26 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 275.25 | 0 | 275.25 | [7 empty] | 55.05 | 55.05 | 55.05 | 55.05 | 55.05 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | billy jackman | IMGA222118 | WO-0760204 | HEATH ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 510950047 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 234.19 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 234.2 | 0 | 234.2 | [7 empty] | 46.84 | 46.84 | 46.84 | 46.84 | 46.84 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222088 | WO-0761119 | SYCAMORE AVENUE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510952953 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 146.45 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 74.44 | 74.44 | [14 empty] | 37.22 | 37.22 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | billy jackman | IMGA222088 | WO-0761119 | SYCAMORE AVENUE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510952954 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 140.82 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 71.58 | 71.58 | [14 empty] | 35.79 | 35.79 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | billy jackman | IMGA222416 | WO-0762192 | FIELD END ROAD | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510949455 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 152.01 | MR1 | N | T1 CBA |  | 44572 | 44585 | 0 | 152.01 | 152.01 | [15 empty] | 50.67 | 50.67 | 50.67 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761542 | BACONSMEAD | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510785735 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 95.49 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 95.52 | 0 | 95.52 |  | 23.88 | 23.88 | 23.88 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761543 | DENHAM WAY | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510820593 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 96.75 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 13.72 | 0 | 13.72 |  | 3.43 | 3.43 | 3.43 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761543 | DENHAM WAY | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510820594 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 185.74 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 65.76 | 0 | 65.76 |  | 16.44 | 16.44 | 16.44 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761544 | OLD MILL ROAD | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510886631 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 266.66 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 66.64 | 0 | 66.64 |  | 16.66 | 16.66 | 16.66 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761544 | OLD MILL ROAD | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510886632 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 197.26 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 7.28 | 0 | 7.28 |  | 1.82 | 1.82 | 1.82 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761545 | PRIORY CLOSE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 220001555193 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 2.34 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 2.32 | 0 | 2.32 |  | 0.58 | 0.58 | 0.58 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DAVE SCOTT | IMGA222275 | WO-0761545 | PRIORY CLOSE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 220001555194 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 3.53 | MR1 | N | T1 SECONDARY |  | 44438 | 44491 | 3.52 | 0 | 3.52 |  | 0.88 | 0.88 | 0.88 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222274 | WO-0761926 | CHEAPSIDE LANE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510806485 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 558.28 | MR1 | N | T1 SECONDARY |  | 44509 | 44547 | 558.3 | 0 | 558.3 | [6 empty] | 93.05 | 93.05 | 93.05 | 93.05 | 93.05 | 93.05 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222274 | WO-0761924 | ASHMEAD LANE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510784320 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 189.57 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 189.58 | 189.58 | [14 empty] | 94.79 | 94.79 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222274 | WO-0761925 | MEAD CLOSE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510875649 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 144.58 | MR1 | N | T1 SECONDARY |  | 44572 | 44578 | 0 | 144.58 | 144.58 | [15 empty] | 72.29 | 72.29 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222274 | WO-0761927 | BRONSDON WAY | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510994563 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 161.45 | MR1 | N | T1 SECONDARY |  | 44579 | 44585 | 0 | 161.46 | 161.46 | [16 empty] | 80.73 | 80.73 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222274 | WO-0761928 | RONAN WAY | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510994564 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 5.2 | MR1 | N | T1 SECONDARY |  | 44586 | 44592 | 0 | 5.2 | 5.2 | [17 empty] | 2.6 | 2.6 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222273 | WO-0761557 | OXFORD ROAD | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 611306978 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 3.28 | MR1 | N | T1 SECONDARY |  | 44593 | 44599 | 0 | 3.28 | 3.28 | [18 empty] | 1.64 | 1.64 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222273 | WO-0761555 | COURTFIELD GARDENS | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510815656 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 73.48 | MR1 | N | T1 SECONDARY |  | 44600 | 44606 | 0 | 73.48 | 73.48 | [19 empty] | 36.74 | 36.74 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222273 | WO-0761555 | COURTFIELD GARDENS | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510815657 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 74.52 | MR1 | N | T1 SECONDARY |  | 44600 | 44606 | 0 | 74.52 | 74.52 | [19 empty] | 37.26 | 37.26 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222273 | WO-0761556 | DENHAM CLOSE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510820549 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 96.3 | MR1 | N | T1 SECONDARY |  | 44607 | 44613 | 0 | 96.3 | 96.3 | [20 empty] | 48.15 | 48.15 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222273 | WO-0761556 | DENHAM CLOSE | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510820550 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 92.66 | MR1 | N | T1 SECONDARY |  | 44607 | 44613 | 0 | 92.66 | 92.66 | [20 empty] | 46.33 | 46.33 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DAVE SCOTT | IMGA222273 | WO-0761558 | OXFORD GARDENS | DENHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510888411 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 459.53 | MR1 | N | T1 SECONDARY |  | 44614 | 44620 | 0 | 459.54 | 459.54 | [21 empty] | 229.77 | 229.77 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760961 | STEVENSON ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510917402 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 253.76 | MR1 | N | T1 SECONDARY |  | 44452 | 44547 | 253.8 | 0 | 253.8 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | 21.15 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760961 | STEVENSON ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510917403 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 164.29 | MR1 | N | T1 SECONDARY |  | 44452 | 44547 | 164.4 | 0 | 164.4 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760961 | STEVENSON ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510917404 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 73.49 | MR1 | N | T1 SECONDARY |  | 44452 | 44547 | 73.56 | 0 | 73.56 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | 6.13 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760962 | ROBERT ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510901678 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 94.94 | MR1 | N | T1 SECONDARY |  | 44452 | 44547 | 94.92 | 0 | 94.92 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | 7.91 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760963 | COTTAGE PARK ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510815403 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 112.45 | MR1 | N | T1 SECONDARY |  | 44452 | 44547 | 112.44 | 0 | 112.44 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | 9.37 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760963 | COTTAGE PARK ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510815404 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 172.32 | MR1 | N | T1 SECONDARY |  | 44452 | 44547 | 172.32 | 0 | 172.32 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | 14.36 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760964 | ELKINS ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510826680 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 135.97 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 135.96 | 135.96 | [14 empty] | 45.32 | 45.32 | 45.32 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760965 | JONES WAY | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510857602 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 214.47 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 214.48 | 214.48 | [16 empty] | 53.62 | 53.62 | 53.62 | 53.62 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760965 | JONES WAY | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510857603 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 141.87 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 141.88 | 141.88 | [16 empty] | 35.47 | 35.47 | 35.47 | 35.47 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | SQS | DEAN TUNRBULL | IMGA222280 | WO-0760966 | GREGORY ROAD | HEDGERLEY | BUCKINGHAMSHIRE | South Bucks District Council | 510841912 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 181.76 | MR1 | N | T1 SECONDARY |  | 44600 | 44606 | 0 | 181.76 | 181.76 | [19 empty] | 90.88 | 90.88 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DEAN TUNRBULL | IMGA222282 | WO-0761241 | DUFFIELD LANE | STOKE POGES | BUCKINGHAMSHIRE | South Bucks District Council | 510966205 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 273.64 | MR1 | N | T1 SECONDARY |  | 44607 | 44627 | 0 | 273.64 | 273.64 | [20 empty] | 68.41 | 68.41 | 68.41 | 68.41 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DEAN TUNRBULL | IMGA222282 | WO-0761241 | DUFFIELD LANE | STOKE POGES | BUCKINGHAMSHIRE | South Bucks District Council | 625624497 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 59.13 | MR1 | N | T1 SECONDARY |  | 44607 | 44627 | 0 | 59.12 | 59.12 | [20 empty] | 14.78 | 14.78 | 14.78 | 14.78 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | DEAN TUNRBULL | IMGA222282 | WO-0761242 | NEVILLE CLOSE | STOKE POGES | BUCKINGHAMSHIRE | South Bucks District Council | 510966243 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 114 | 183.01 | MR1 | N | T1 SECONDARY |  | 44628 | 44648 | 0 | 183 | 183 | [23 empty] | 45.75 | 45.75 | 45.75 | 45.75 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | OMJ | JAMES CLARKE | IMGA222278 | WO-0761561 | PACKHORSE ROAD | GERRARDS CROSS | BUCKINGHAMSHIRE | South Bucks District Council | 510888691 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 621.24 | MR1 | N | T1 SECONDARY |  | 44417 | 44470 | 71.28 | 0 | 71.28 | 71.28 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | OMJ | JAMES CLARKE | IMGA222278 | WO-0761562 | ORCHEHILL AVENUE | GERRARDS CROSS | BUCKINGHAMSHIRE | South Bucks District Council | 220001421380 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 2.67 | MR1 | N | T1 SECONDARY |  | 44417 | 44470 | 2.64 | 0 | 2.64 | 2.64 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765593 | PRIORY WALK | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510895889 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 42.77 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 42.77 | 0 | 42.77 |  | 6.11 | 6.11 | 6.11 | 6.11 | 6.11 | 6.11 | 6.11 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765597 | LETCOMBE SQUARE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510865587 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 98.37 | MR1 | N | T1 SECONDARY |  | 44473 | 44519 | 98.35 | 0 | 98.35 |  | 14.05 | 14.05 | 14.05 | 14.05 | 14.05 | 14.05 | 14.05 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933674 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 72.34 | MR1 | N | T1 CONNECTED |  | 44522 | 44547 | 38.8 | 0 | 38.8 | [8 empty] | 9.7 | 9.7 | 9.7 | 9.7 | [15 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510797702 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 215.03 | MR1 | N | T1 SECONDARY |  | 44522 | 44547 | 115.36 | 0 | 115.36 | [8 empty] | 28.84 | 28.84 | 28.84 | 28.84 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933673 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 130.09 | MR1 | N | T1 SECONDARY |  | 44522 | 44547 | 69.8 | 0 | 69.8 | [8 empty] | 17.45 | 17.45 | 17.45 | 17.45 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933675 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 26.78 | MR1 | N | T1 SECONDARY |  | 44522 | 44547 | 14.36 | 0 | 14.36 | [8 empty] | 3.59 | 3.59 | 3.59 | 3.59 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933677 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 165.79 | MR1 | N | T1 SECONDARY |  | 44522 | 44547 | 88.96 | 0 | 88.96 | [8 empty] | 22.24 | 22.24 | 22.24 | 22.24 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 621183546 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 21.17 | MR1 | N | T1 SECONDARY |  | 44522 | 44547 | 11.36 | 0 | 11.36 | [8 empty] | 2.84 | 2.84 | 2.84 | 2.84 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 621183556 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 16.07 | MR1 | N | T1 SECONDARY |  | 44522 | 44547 | 8.64 | 0 | 8.64 | [8 empty] | 2.16 | 2.16 | 2.16 | 2.16 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933674 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 72.34 | MR1 | N | T1 CONNECTED |  | 44565 | 44582 | 0 | 33.54 | 33.54 | [14 empty] | 11.18 | 11.18 | 11.18 | [10 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510797702 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 215.03 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 99.66 | 99.66 | [14 empty] | 33.22 | 33.22 | 33.22 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933673 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 130.09 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 60.3 | 60.3 | [14 empty] | 20.1 | 20.1 | 20.1 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933675 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 26.78 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 12.42 | 12.42 | [14 empty] | 4.14 | 4.14 | 4.14 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510933677 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 165.79 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 76.83 | 76.83 | [14 empty] | 25.61 | 25.61 | 25.61 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 621183546 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 21.17 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 9.81 | 9.81 | [14 empty] | 3.27 | 3.27 | 3.27 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | JAMES CLARKE | IMGA222440 | WO-0765588 | WAYLAND CLOSE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 621183556 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 27 | 16.07 | MR1 | N | T1 SECONDARY |  | 44565 | 44582 | 0 | 7.44 | 7.44 | [14 empty] | 2.48 | 2.48 | 2.48 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | OMJ | JAMES CLARKE | IMGA222268 | WO-0760366 | HOLTSPUR WAY | BEACONSFIELD | BUCKINGHAMSHIRE | South Bucks District Council | 510853903 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 25 | 351.05 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 242.16 | 242.16 | [17 empty] | 60.54 | 60.54 | 60.54 | 60.54 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | OMJ | JAMES CLARKE | IMGA222268 | WO-0760366 | HOLTSPUR WAY | BEACONSFIELD | BUCKINGHAMSHIRE | South Bucks District Council | 510853905 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 42.44 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 29.28 | 29.28 | [17 empty] | 7.32 | 7.32 | 7.32 | 7.32 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | OMJ | JAMES CLARKE | IMGA222268 | WO-0760366 | HOLTSPUR WAY | BEACONSFIELD | BUCKINGHAMSHIRE | South Bucks District Council | 510853906 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 3.75 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 2.6 | 2.6 | [17 empty] | 0.65 | 0.65 | 0.65 | 0.65 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | OMJ | JAMES CLARKE | IMGA222268 | WO-0760366 | HOLTSPUR WAY | BEACONSFIELD | BUCKINGHAMSHIRE | South Bucks District Council | 510853907 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 5.78 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 4 | 4 | [17 empty] | 1 | 1 | 1 | 1 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765506 | BARKER ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 220001624303 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 397.61 | MR1 | N | T1 SECONDARY |  | 44473 | 44498 | 397.6 | 0 | 397.6 |  | 99.4 | 99.4 | 99.4 | 99.4 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765507 | LASSWADE ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510863911 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 182.47 | MR1 | N | T1 SECONDARY |  | 44501 | 44512 | 182.48 | 0 | 182.48 | [5 empty] | 91.24 | 91.24 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815875 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 288.96 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 216.72 | 72.24 | 288.96 | [6 empty] | 36.12 | 36.12 | 36.12 | 36.12 | 36.12 | 36.12 |  |  | 36.12 | 36.12 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815876 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 51.38 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 38.52 | 12.84 | 51.36 | [6 empty] | 6.42 | 6.42 | 6.42 | 6.42 | 6.42 | 6.42 |  |  | 6.42 | 6.42 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815877 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 32.6 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 24.48 | 8.16 | 32.64 | [6 empty] | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 | 4.08 |  |  | 4.08 | 4.08 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815878 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 35.6 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 26.7 | 8.9 | 35.6 | [6 empty] | 4.45 | 4.45 | 4.45 | 4.45 | 4.45 | 4.45 |  |  | 4.45 | 4.45 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815879 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 107.48 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 80.64 | 26.88 | 107.52 | [6 empty] | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 | 13.44 |  |  | 13.44 | 13.44 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815880 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 80.54 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 60.42 | 20.14 | 80.56 | [6 empty] | 10.07 | 10.07 | 10.07 | 10.07 | 10.07 | 10.07 |  |  | 10.07 | 10.07 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815881 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 96.57 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 72.42 | 24.14 | 96.56 | [6 empty] | 12.07 | 12.07 | 12.07 | 12.07 | 12.07 | 12.07 |  |  | 12.07 | 12.07 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510815882 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 80.43 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 60.3 | 20.1 | 80.4 | [6 empty] | 10.05 | 10.05 | 10.05 | 10.05 | 10.05 | 10.05 |  |  | 10.05 | 10.05 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765504 | COWLEY AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 634330994 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1 | MR1 | N | T1 SECONDARY |  | 44515 | 44568 | 0.78 | 0.26 | 1.04 | [6 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 |  |  | 0.13 | 0.13 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765505 | PYRCROFT ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510896300 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 244.11 | MR1 | N | T1 SECONDARY |  | 44571 | 44589 | 0 | 244.11 | 244.11 | [15 empty] | 81.37 | 81.37 | 81.37 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765505 | PYRCROFT ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 604834958 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 13.1 | MR1 | N | T1 SECONDARY |  | 44571 | 44589 | 0 | 13.11 | 13.11 | [15 empty] | 4.37 | 4.37 | 4.37 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765508 | FRITHWALD ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510834874 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 78.59 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 78.6 | 78.6 | [18 empty] | 39.3 | 39.3 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765508 | FRITHWALD ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510834875 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 65.53 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 65.54 | 65.54 | [18 empty] | 32.77 | 32.77 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765509 | ST ANNS ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510905570 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 0 | 39.03 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 39.03 | 39.03 | [20 empty] | 39.03 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765509 | ST ANNS ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510905582 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 10 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 10 | 10 | [20 empty] | 10 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765509 | ST ANNS ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 611292464 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1.79 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 1.79 | 1.79 | [20 empty] | 1.79 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765510 | STAINES ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510994521 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 173.99 | MR1 | N | T1 SECONDARY |  | 44613 | 44631 | 0 | 174 | 174 | [21 empty] | 58 | 58 | 58 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765510 | STAINES ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 611292120 | 2 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 29.62 | MR1 | N | T1 SECONDARY |  | 44613 | 44631 | 0 | 29.61 | 29.61 | [21 empty] | 9.87 | 9.87 | 9.87 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765510 | STAINES ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 611292462 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 1.88 | MR1 | N | T1 SECONDARY |  | 44613 | 44631 | 0 | 1.89 | 1.89 | [21 empty] | 0.63 | 0.63 | 0.63 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765511 | CHILSEY GREEN ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510808053 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 150.64 | MR1 | N | T1 SECONDARY |  | 44634 | 44687 | 0 | 56.49 | 56.49 | [24 empty] | 18.83 | 18.83 | 18.83 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765511 | CHILSEY GREEN ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510808054 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 41 | 316.68 | MR1 | N | T1 SECONDARY |  | 44634 | 44687 | 0 | 118.77 | 118.77 | [24 empty] | 39.59 | 39.59 | 39.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765511 | CHILSEY GREEN ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510808055 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 53.97 | MR1 | N | T1 SECONDARY |  | 44634 | 44687 | 0 | 20.25 | 20.25 | [24 empty] | 6.75 | 6.75 | 6.75 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765511 | CHILSEY GREEN ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510808056 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 78.55 | MR1 | N | T1 SECONDARY |  | 44634 | 44687 | 0 | 29.46 | 29.46 | [24 empty] | 9.82 | 9.82 | 9.82 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765511 | CHILSEY GREEN ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510828466 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 65.62 | MR1 | N | T1 SECONDARY |  | 44634 | 44687 | 0 | 24.6 | 24.6 | [24 empty] | 8.2 | 8.2 | 8.2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | JOHNATHAN HALL | IMGA222439 | WO-0765511 | CHILSEY GREEN ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510828469 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 52.36 | MR1 | N | T1 SECONDARY |  | 44634 | 44687 | 0 | 19.65 | 19.65 | [24 empty] | 6.55 | 6.55 | 6.55 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 608065028 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 42.44 | MR1 | N | T1 CONNECTED |  | 44466 | 44505 | 42.42 | 0 | 42.42 | 7.07 | 7.07 | 7.07 | 7.07 | 7.07 | 7.07 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852064 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 69.25 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 69.24 | 0 | 69.24 | 11.54 | 11.54 | 11.54 | 11.54 | 11.54 | 11.54 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852065 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 153.56 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 153.54 | 0 | 153.54 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | 25.59 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852066 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 153.5 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 153.48 | 0 | 153.48 | 25.58 | 25.58 | 25.58 | 25.58 | 25.58 | 25.58 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852067 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 29.98 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 30 | 0 | 30 | 5 | 5 | 5 | 5 | 5 | 5 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852068 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 30.56 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 30.54 | 0 | 30.54 | 5.09 | 5.09 | 5.09 | 5.09 | 5.09 | 5.09 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852069 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 20.86 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 20.88 | 0 | 20.88 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | 3.48 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852070 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 9.13 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 9.12 | 0 | 9.12 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | 1.52 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510852071 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 52.24 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 52.26 | 0 | 52.26 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | 8.71 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765532 | HILLTOP CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 621164711 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 4.85 | MR1 | N | T1 SECONDARY |  | 44466 | 44505 | 4.86 | 0 | 4.86 | 0.81 | 0.81 | 0.81 | 0.81 | 0.81 | 0.81 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765533 | WATERSPLASH LANE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510933311 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 396.22 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 396.2 | 0 | 396.2 | [6 empty] | 79.24 | 79.24 | 79.24 | 79.24 | 79.24 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765533 | WATERSPLASH LANE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510933312 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 48.17 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 48.15 | 0 | 48.15 | [6 empty] | 9.63 | 9.63 | 9.63 | 9.63 | 9.63 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765533 | WATERSPLASH LANE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510933313 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 120.54 | MR1 | N | T1 SECONDARY |  | 44508 | 44540 | 120.55 | 0 | 120.55 | [6 empty] | 24.11 | 24.11 | 24.11 | 24.11 | 24.11 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222438 | WO-0765534 | DORIAN DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510933314 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 16.75 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 16.75 | 0 | 16.75 | [11 empty] | 16.75 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765522 | BEECHWOOD CLOSE | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510789470 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 135.57 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 135.57 | 135.57 | [14 empty] | 45.19 | 45.19 | 45.19 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765522 | BEECHWOOD CLOSE | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510789471 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 207.29 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 207.3 | 207.3 | [14 empty] | 69.1 | 69.1 | 69.1 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765529 | NEW ROAD | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510882088 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 322.13 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 322.12 | 322.12 | [16 empty] | 80.53 | 80.53 | 80.53 | 80.53 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765529 | NEW ROAD | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510882089 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 188.04 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 188.04 | 188.04 | [16 empty] | 47.01 | 47.01 | 47.01 | 47.01 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765529 | NEW ROAD | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510882096 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 7.3 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 7.32 | 7.32 | [16 empty] | 1.83 | 1.83 | 1.83 | 1.83 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765529 | NEW ROAD | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510882097 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 8.07 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 8.08 | 8.08 | [16 empty] | 2.02 | 2.02 | 2.02 | 2.02 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765529 | NEW ROAD | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 220001938555 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.81 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 1.8 | 1.8 | [16 empty] | 0.45 | 0.45 | 0.45 | 0.45 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765524 | FERNBANK ROAD |  |  | Surrey County Council | 612883550 | 3 |  | T1 | Inch | ST |  | LP | Non policy | T1Non policy | 4"-5" |  | 19.93 | MR1 | N | T1 CONNECTED |  | 44600 | 44620 | 0 | 19.92 | 19.92 | [19 empty] | 4.98 | 4.98 | 4.98 | 4.98 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765524 | FERNBANK ROAD |  |  | Surrey County Council | 510831438 | 4 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 188.36 | MR1 | N | T1 SECONDARY |  | 44600 | 44620 | 0 | 188.36 | 188.36 | [19 empty] | 47.09 | 47.09 | 47.09 | 47.09 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765524 | FERNBANK ROAD | ASCOT | BRACKNELL FOREST | Bracknell Forest Borough Council | 510831437 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 604.34 | MR1 | N | T1 SECONDARY |  | 44600 | 44620 | 0 | 604.36 | 604.36 | [19 empty] | 151.09 | 151.09 | 151.09 | 151.09 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765525 | KENNEL AVENUE | ASCOT | WINDSOR AND MAIDENHEAD | Bracknell Forest Borough Council | 510858494 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 20.16 | MR1 | N | T1 SECONDARY |  | 44621 | 44621 | 0 | 20.16 | 20.16 | [22 empty] | 20.16 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765526 | KENNEL RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Bracknell Forest Borough Council | 612894589 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 11.57 | MR1 | N | T1 CONNECTED |  | 44622 | 44656 | 0 | 9.65 | 9.65 | [22 empty] | 1.93 | 1.93 | 1.93 | 1.93 | 1.93 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | KIRT BARRACLOUGH | IMGA222437 | WO-0765526 | KENNEL RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Bracknell Forest Borough Council | 510858537 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 501.74 | MR1 | N | T1 SECONDARY |  | 44622 | 44656 | 0 | 418.1 | 418.1 | [22 empty] | 83.62 | 83.62 | 83.62 | 83.62 | 83.62 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761523 | MIDDLE WALK | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967126 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 74.42 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 74.4 | 0 | 74.4 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761523 | MIDDLE WALK | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967127 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 30.9 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 30.88 | 0 | 30.88 | 3.86 | 3.86 | 3.86 | 3.86 | 3.86 | 3.86 | 3.86 | 3.86 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761524 | SUMMERS ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967403 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 133.03 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 133.04 | 0 | 133.04 | 16.63 | 16.63 | 16.63 | 16.63 | 16.63 | 16.63 | 16.63 | 16.63 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761524 | SUMMERS ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967404 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 54.18 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 54.16 | 0 | 54.16 | 6.77 | 6.77 | 6.77 | 6.77 | 6.77 | 6.77 | 6.77 | 6.77 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761525 | WILMOT ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967543 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 69.84 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 69.84 | 0 | 69.84 | 8.73 | 8.73 | 8.73 | 8.73 | 8.73 | 8.73 | 8.73 | 8.73 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761525 | WILMOT ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967544 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 60.51 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 60.48 | 0 | 60.48 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | 7.56 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761525 | WILMOT ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967545 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 71.94 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 71.92 | 0 | 71.92 | 8.99 | 8.99 | 8.99 | 8.99 | 8.99 | 8.99 | 8.99 | 8.99 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761526 | MINNIECROFT ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967130 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 66.03 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 66 | 0 | 66 | 8.25 | 8.25 | 8.25 | 8.25 | 8.25 | 8.25 | 8.25 | 8.25 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761526 | MINNIECROFT ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967131 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 50.39 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 50.4 | 0 | 50.4 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761526 | MINNIECROFT ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510967132 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 163.61 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 163.6 | 0 | 163.6 | 20.45 | 20.45 | 20.45 | 20.45 | 20.45 | 20.45 | 20.45 | 20.45 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222270 | WO-0761527 | BURN WALK | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510966691 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 9.61 | MR1 | N | T1 SECONDARY |  | 44466 | 44519 | 9.6 | 0 | 9.6 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761172 | CRISPIN WAY | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510817143 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 113.94 | MR1 | N | T1 SECONDARY |  | 44522 | 44533 | 113.94 | 0 | 113.94 | [8 empty] | 56.97 | 56.97 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761172 | CRISPIN WAY | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510817144 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 382.04 | MR1 | N | T1 SECONDARY |  | 44522 | 44533 | 382.04 | 0 | 382.04 | [8 empty] | 191.02 | 191.02 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761170 | ASHENDEN WALK | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510784091 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 156.13 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 156.14 | 0 | 156.14 | [10 empty] | 78.07 | 78.07 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761170 | ASHENDEN WALK | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510784092 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 12.67 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 12.68 | 0 | 12.68 | [10 empty] | 6.34 | 6.34 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761170 | ASHENDEN WALK | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510784093 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 8.51 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 8.52 | 0 | 8.52 | [10 empty] | 4.26 | 4.26 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761171 | SHERBOURNE WALK | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510911030 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 289.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 289.68 | 289.68 | [14 empty] | 96.56 | 96.56 | 96.56 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761171 | SHERBOURNE WALK | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510911031 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 7.55 | MR1 | N | T1 SECONDARY |  | 44565 | 44578 | 0 | 7.56 | 7.56 | [14 empty] | 2.52 | 2.52 | 2.52 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761173 | MAYFLOWER WAY | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510875466 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 41.9 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 41.92 | 41.92 | [16 empty] | 10.48 | 10.48 | 10.48 | 10.48 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222276 | WO-0761173 | MAYFLOWER WAY | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510875467 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 294.44 | MR1 | N | T1 SECONDARY |  | 44579 | 44599 | 0 | 294.44 | 294.44 | [16 empty] | 73.61 | 73.61 | 73.61 | 73.61 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0760999 | WYNDHAM CRESCENT | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510883614 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 69.93 | MR1 | N | T1 SECONDARY |  | 44600 | 44631 | 0 | 69.95 | 69.95 | [19 empty] | 13.99 | 13.99 | 13.99 | 13.99 | 13.99 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0760999 | WYNDHAM CRESCENT | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510954809 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 258.37 | MR1 | N | T1 SECONDARY |  | 44600 | 44631 | 0 | 258.35 | 258.35 | [19 empty] | 51.67 | 51.67 | 51.67 | 51.67 | 51.67 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0760999 | WYNDHAM CRESCENT | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510954810 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 91.07 | MR1 | N | T1 SECONDARY |  | 44600 | 44631 | 0 | 91.05 | 91.05 | [19 empty] | 18.21 | 18.21 | 18.21 | 18.21 | 18.21 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0760999 | WYNDHAM CRESCENT | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510954811 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 156.5 | MR1 | N | T1 SECONDARY |  | 44600 | 44631 | 0 | 156.5 | 156.5 | [19 empty] | 31.3 | 31.3 | 31.3 | 31.3 | 31.3 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0760999 | WYNDHAM CRESCENT | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510954812 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 51.48 | MR1 | N | T1 SECONDARY |  | 44600 | 44631 | 0 | 51.5 | 51.5 | [19 empty] | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0760999 | WYNDHAM CRESCENT | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510954814 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 80.31 | MR1 | N | T1 SECONDARY |  | 44600 | 44631 | 0 | 80.3 | 80.3 | [19 empty] | 16.06 | 16.06 | 16.06 | 16.06 | 16.06 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0761000 | GREEN WAY | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 510954813 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 20.57 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 20.57 | 20.57 | [24 empty] | 20.57 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222272 | WO-0761001 | ALMOND ROAD | BURNHAM | BUCKINGHAMSHIRE | South Bucks District Council | 220001545221 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 39.25 | MR1 | N | T1 SECONDARY |  | 44641 | 44645 | 0 | 39.25 | 39.25 | [25 empty] | 39.25 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | LDP Blank | LIAM ARNOLD | IMGA222425 | WO-0762152 | BEACONSFIELD ROAD | FARNHAM COMMON | BUCKINGHAMSHIRE | South Bucks District Council | 510788523 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 159 | 72.83 | MR1 | N | T1 CBA |  | 44648 | 44652 | 0 | 72.83 | 72.83 | [26 empty] | 72.83 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222420 | WO-0762240 | WEIR ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510933927 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 109.69 | MR1 | N | T1 CBA |  | 44466 | 44477 | 109.7 | 0 | 109.7 | 54.85 | 54.85 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | MATTHEW CLIFFORD | IMGA222019 | WO-0759933 | WINDSOR ROAD | WOKING | SURREY | Surrey Heath Borough Council | 510939531 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 224 | 274.02 | MR1 | N | T1 PAST |  | 44480 | 44498 | 274.02 | 0 | 274.02 |  |  | 91.34 | 91.34 | 91.34 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | MATTHEW CLIFFORD | IMGA222308 | WO-0760007 | CHERTSEY ROAD | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510807159 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 59 | 110.48 | MR1 | N | T1 PAST |  | 44501 | 44512 | 110.48 | 0 | 110.48 | [5 empty] | 55.24 | 55.24 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222341 | WO-0760254 | HOLMANLEAZE | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 612031686 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 44 | 11.05 | MR1 | N | T1 GD1 ALARP |  | 44515 | 44519 | 11.05 | 0 | 11.05 | [7 empty] | 11.05 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | MATTHEW CLIFFORD | IMGA222295 | WO-0761729 | VICARAGE LANE | LALEHAM | SURREY | Spelthorne Borough Council | 510943293 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 180.09 | MR1 | N | T1 SECONDARY |  | 44522 | 44526 | 6 | 0 | 6 | [8 empty] | 6 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222243 | WO-0760975 | SUMMERLEA | SLOUGH | SLOUGH | Slough Borough Council | 510918825 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 114.88 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 114.88 | 0 | 114.88 | [9 empty] | 114.88 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222243 | WO-0760976 | STONEY MEADE | SLOUGH | SLOUGH | Slough Borough Council | 510974921 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 63.54 | MR1 | N | T1 SECONDARY |  | 44536 | 44540 | 63.54 | 0 | 63.54 | [10 empty] | 63.54 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222243 | WO-0760977 | WEEKES DRIVE | SLOUGH | SLOUGH | Slough Borough Council | 510967506 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 70 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 70 | 0 | 70 | [11 empty] | 70 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222243 | WO-0760977 | WEEKES DRIVE | SLOUGH | SLOUGH | Slough Borough Council | 626534212 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 5.5 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 5.5 | 0 | 5.5 | [11 empty] | 5.5 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222243 | WO-0760978 | VANTAGE ROAD | SLOUGH | SLOUGH | Slough Borough Council | 220000532629 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 7.08 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 7.08 | 7.08 | [14 empty] | 3.54 | 3.54 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222243 | WO-0760979 | COURT FARM CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 606474023 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 6.8 | MR1 | N | T1 CONNECTED |  | 44572 | 44578 | 0 | 6.8 | 6.8 | [15 empty] | 3.4 | 3.4 | [10 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761366 | GREENFIELDS | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510841528 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 195.34 | MR1 | N | T1 SECONDARY |  | 44579 | 44620 | 0 | 195.3 | 195.3 | [16 empty] | 27.9 | 27.9 | 27.9 | 27.9 | 27.9 | 27.9 | 27.9 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761366 | GREENFIELDS | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510841530 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 45.58 | MR1 | N | T1 SECONDARY |  | 44579 | 44620 | 0 | 45.57 | 45.57 | [16 empty] | 6.51 | 6.51 | 6.51 | 6.51 | 6.51 | 6.51 | 6.51 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761366 | GREENFIELDS | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510841531 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 46.43 | MR1 | N | T1 SECONDARY |  | 44579 | 44620 | 0 | 46.41 | 46.41 | [16 empty] | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 | 6.63 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761366 | GREENFIELDS | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510841533 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 308.86 | MR1 | N | T1 SECONDARY |  | 44579 | 44620 | 0 | 308.77 | 308.77 | [16 empty] | 44.11 | 44.11 | 44.11 | 44.11 | 44.11 | 44.11 | 44.11 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761368 | STAFFERTON WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966032 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 80.37 | MR1 | N | T1 SECONDARY |  | 44621 | 44648 | 0 | 80.35 | 80.35 | [22 empty] | 16.07 | 16.07 | 16.07 | 16.07 | 16.07 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761368 | STAFFERTON WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966039 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 35.03 | MR1 | N | T1 SECONDARY |  | 44621 | 44648 | 0 | 35.05 | 35.05 | [22 empty] | 7.01 | 7.01 | 7.01 | 7.01 | 7.01 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761368 | STAFFERTON WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 634342519 | 3 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 2.47 | MR1 | N | T1 ALARP |  | 44621 | 44648 | 0 | 2.45 | 2.45 | [22 empty] | 0.49 | 0.49 | 0.49 | 0.49 | 0.49 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | MATTHEW CLIFFORD | IMGA222310 | WO-0761367 | VICUS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966033 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 43.16 | MR1 | N | T1 SECONDARY |  | 44649 | 44652 | 0 | 43.16 | 43.16 | [26 empty] | 43.16 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222101 | WO-0761781 | JONSON CLOSE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950579 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 151.43 | MR1 | N | T1 SECONDARY |  | 44445 | 44466 | -0.56 | 0 | -0.56 | -0.56 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222101 | WO-0761782 | WYATT CLOSE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510953995 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 149.21 | MR1 | N | T1 SECONDARY |  | 44445 | 44466 | -2.8 | 0 | -2.8 | -2.8 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222101 | WO-0761783 | BALMORAL DRIVE |  |  | Hillingdon London Borough Council | 220001337503 | 6 |  | T1 | Inch | CI |  | LP | Policy | T1Policy | 4"-5" |  | 264 | MR1 | N | T1 SECONDARY |  | 44445 | 44466 | -4 | 0 | -4 | -4 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222101 | WO-0761783 | BALMORAL DRIVE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001337503 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 10.43 | MR1 | N | T1 SECONDARY |  | 44445 | 44466 | 10.44 | 0 | 10.44 | 10.44 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761822 | SELAN GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001651124 | 10 |  | T2 | Inch | SI | Open Cut | LP | Non policy | T2Non policy | 10"-12" | 2 | 2.36 | MR2 | N | T2 CBA |  | 44467 | 44487 | 2.36 | 0 | 2.36 |  | 0.59 | 0.59 | 0.59 | [23 empty] | T2B | 10"-12" | LP | Non policy | T2 | SI | T2B
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761821 | YEADING GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 510954009 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 92.8 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 92.8 | 0 | 92.8 | 23.2 | 23.2 | 23.2 | 23.2 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761821 | YEADING GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 510954011 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 180.56 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 180.56 | 0 | 180.56 | 45.14 | 45.14 | 45.14 | 45.14 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761821 | YEADING GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001551099 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 286.64 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 286.64 | 0 | 286.64 | 71.66 | 71.66 | 71.66 | 71.66 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761822 | SELAN GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001633547 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 6.09 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 6.08 | 0 | 6.08 | 1.52 | 1.52 | 1.52 | 1.52 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761822 | SELAN GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001633548 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 2.02 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 2.04 | 0 | 2.04 | 0.51 | 0.51 | 0.51 | 0.51 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761822 | SELAN GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001634610 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 0.8 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 0.8 | 0 | 0.8 | 0.2 | 0.2 | 0.2 | 0.2 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761823 | HOLLYWOOD GARDENS | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001633753 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 1.6 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 1.6 | 0 | 1.6 | 0.4 | 0.4 | 0.4 | 0.4 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222102 | WO-0761824 | BEDFORD AVENUE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001648089 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 12.24 | MR1 | N | T1 SECONDARY |  | 44467 | 44487 | 12.24 | 0 | 12.24 | 3.06 | 3.06 | 3.06 | 3.06 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222101 | WO-0761780 | KEATS CLOSE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950586 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 76.72 | MR1 | N | T1 SECONDARY |  | 44503 | 44509 | 76.72 | 0 | 76.72 | [5 empty] | 38.36 | 38.36 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222091 | WO-0761319 | HALSWAY | HAYES | HILLINGDON | Hillingdon London Borough Council | 510949850 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 234.46 | MR1 | N | T1 SECONDARY |  | 44510 | 44516 | 12.94 | 0 | 12.94 | [6 empty] | 6.47 | 6.47 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MEL STEPHENSON | IMGA222091 | WO-0761319 | HALSWAY | HAYES | HILLINGDON | Hillingdon London Borough Council | 510949852 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 218.68 | MR1 | N | T1 SECONDARY |  | 44510 | 44516 | 12.06 | 0 | 12.06 | [6 empty] | 6.03 | 6.03 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222107 | WO-0761710 | BARNHILL ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510947600 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 166.36 | MR1 | N | T1 SECONDARY |  | 44517 | 44547 | 166.35 | 0 | 166.35 | [7 empty] | 33.27 | 33.27 | 33.27 | 33.27 | 33.27 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222107 | WO-0761710 | BARNHILL ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510947601 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 265.68 | MR1 | N | T1 SECONDARY |  | 44517 | 44547 | 265.7 | 0 | 265.7 | [7 empty] | 53.14 | 53.14 | 53.14 | 53.14 | 53.14 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222107 | WO-0761710 | BARNHILL ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510947602 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 33.32 | MR1 | N | T1 SECONDARY |  | 44517 | 44547 | 33.3 | 0 | 33.3 | [7 empty] | 6.66 | 6.66 | 6.66 | 6.66 | 6.66 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222107 | WO-0761711 | CHATSWORTH ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510948314 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 13.56 | MR1 | N | T1 SECONDARY |  | 44517 | 44547 | 13.55 | 0 | 13.55 | [7 empty] | 2.71 | 2.71 | 2.71 | 2.71 | 2.71 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222107 | WO-0761711 | CHATSWORTH ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 610440769 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 26.17 | MR1 | N | T1 SECONDARY |  | 44517 | 44547 | 26.15 | 0 | 26.15 | [7 empty] | 5.23 | 5.23 | 5.23 | 5.23 | 5.23 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761415 | KNOLL CRESCENT | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510950692 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 76.17 | MR1 | N | T1 SECONDARY |  | 44565 | 44585 | 0 | 76.16 | 76.16 | [14 empty] | 19.04 | 19.04 | 19.04 | 19.04 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761415 | KNOLL CRESCENT | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510950693 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 30.34 | MR1 | N | T1 SECONDARY |  | 44565 | 44585 | 0 | 30.36 | 30.36 | [14 empty] | 7.59 | 7.59 | 7.59 | 7.59 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761415 | KNOLL CRESCENT | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510950694 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 111.72 | MR1 | N | T1 SECONDARY |  | 44565 | 44585 | 0 | 111.72 | 111.72 | [14 empty] | 27.93 | 27.93 | 27.93 | 27.93 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761415 | KNOLL CRESCENT | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510950695 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 239.92 | MR1 | N | T1 SECONDARY |  | 44565 | 44585 | 0 | 239.92 | 239.92 | [14 empty] | 59.98 | 59.98 | 59.98 | 59.98 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761414 | LYNWOOD DRIVE | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510871126 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 85.47 | MR1 | N | T1 SECONDARY |  | 44586 | 44592 | 0 | 85.48 | 85.48 | [17 empty] | 42.74 | 42.74 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761416 | MANOR COTTAGES | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510951016 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 12.37 | MR1 | N | T1 SECONDARY |  | 44593 | 44599 | 0 | 12.38 | 12.38 | [18 empty] | 6.19 | 6.19 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761416 | MANOR COTTAGES | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510951017 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 111.15 | MR1 | N | T1 SECONDARY |  | 44593 | 44599 | 0 | 111.16 | 111.16 | [18 empty] | 55.58 | 55.58 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | MEL STEPHENSON | IMGA222110 | WO-0761417 | LEES AVENUE | NORTHWOOD | HILLINGDON | Hillingdon London Borough Council | 510950822 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 172.27 | MR1 | N | T1 SECONDARY |  | 44600 | 44610 | 0 | 172.28 | 172.28 | [19 empty] | 86.14 | 86.14 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761817 | ST NICHOLAS CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510907233 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 27.52 | MR1 | N | T1 CONNECTED |  | 44494 | 44561 | 19.52 | 4.88 | 24.4 |  |  |  |  | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 | 2.44 |  |  | 2.44 | 2.44 | [11 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761817 | ST NICHOLAS CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510907238 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 4.11 | MR1 | N | T1 CONNECTED |  | 44494 | 44561 | 2.88 | 0.72 | 3.6 |  |  |  |  | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 |  |  | 0.36 | 0.36 | [11 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761817 | ST NICHOLAS CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510907234 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 242.38 | MR1 | N | T1 SECONDARY |  | 44494 | 44561 | 171.52 | 42.88 | 214.4 |  |  |  |  | 21.44 | 21.44 | 21.44 | 21.44 | 21.44 | 21.44 | 21.44 | 21.44 |  |  | 21.44 | 21.44 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761817 | ST NICHOLAS CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510907235 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 55.23 | MR1 | N | T1 SECONDARY |  | 44494 | 44561 | 39.12 | 9.78 | 48.9 |  |  |  |  | 4.89 | 4.89 | 4.89 | 4.89 | 4.89 | 4.89 | 4.89 | 4.89 |  |  | 4.89 | 4.89 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761817 | ST NICHOLAS CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510907236 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 73.69 | MR1 | N | T1 SECONDARY |  | 44494 | 44561 | 52.16 | 13.04 | 65.2 |  |  |  |  | 6.52 | 6.52 | 6.52 | 6.52 | 6.52 | 6.52 | 6.52 | 6.52 |  |  | 6.52 | 6.52 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761817 | ST NICHOLAS CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510907237 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 75.19 | MR1 | N | T1 SECONDARY |  | 44494 | 44561 | 53.2 | 13.3 | 66.5 |  |  |  |  | 6.65 | 6.65 | 6.65 | 6.65 | 6.65 | 6.65 | 6.65 | 6.65 |  |  | 6.65 | 6.65 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | MICHAEL GOODMAN | IMGA222356 | WO-0761116 | WHARF LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510885691 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 78.45 | MR1 | N | T1 SECONDARY |  | 44522 | 44526 | 78 | 0 | 78 | [8 empty] | 78 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761816 | CUMBERLAND CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510818324 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 65.68 | MR1 | N | T1 SECONDARY |  | 44564 | 44596 | 0 | 65.7 | 65.7 | [14 empty] | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761816 | CUMBERLAND CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510818325 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 54 | 213.4 | MR1 | N | T1 SECONDARY |  | 44564 | 44596 | 0 | 213.4 | 213.4 | [14 empty] | 42.68 | 42.68 | 42.68 | 42.68 | 42.68 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761816 | CUMBERLAND CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510818326 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 8.98 | MR1 | N | T1 SECONDARY |  | 44564 | 44596 | 0 | 9 | 9 | [14 empty] | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Kerry Dolan | KLT | MICHAEL GOODMAN | IMGA222140 | WO-0761818 | BEEL CLOSE | LITTLE CHALFONT | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510789678 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 115.97 | MR1 | N | T1 SECONDARY |  | 44599 | 44610 | 0 | 115.98 | 115.98 | [19 empty] | 57.99 | 57.99 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222411 | WO-0762260 | SOUTH SIDE | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510913238 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 219.62 | MR1 | N | T1 SECONDARY |  | 44613 | 44631 | 0 | 219.63 | 219.63 | [21 empty] | 73.21 | 73.21 | 73.21 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222411 | WO-0762260 | SOUTH SIDE | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220001389995 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 8.69 | MR1 | N | T1 SECONDARY |  | 44613 | 44631 | 0 | 8.7 | 8.7 | [21 empty] | 2.9 | 2.9 | 2.9 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222411 | WO-0762260 | SOUTH SIDE | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220001430733 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 0.2 | MR1 | N | T1 SECONDARY |  | 44613 | 44631 | 0 | 0.21 | 0.21 | [21 empty] | 0.07 | 0.07 | 0.07 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222411 | WO-0762260 | SOUTH SIDE | CHALFONT ST PETER | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220001442826 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 113.64 | MR1 | N | T1 CBA |  | 44613 | 44631 | 0 | 113.64 | 113.64 | [21 empty] | 37.88 | 37.88 | 37.88 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222388 | WO-0759869 | WATERSIDE | WOOBURN GREEN | BUCKINGHAMSHIRE | Wycombe District Council | 510933300 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 115.58 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 115.58 | 115.58 | [24 empty] | 115.58 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222431 | WO-0762253 | PLOMER HILL | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510893463 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 126.48 | MR1 | N | T1 CBA |  | 44641 | 44645 | 0 | 126.48 | 126.48 | [25 empty] | 126.48 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222431 | WO-0762253 | PLOMER HILL | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 612062214 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 4.28 | MR1 | N | T1 SECONDARY |  | 44641 | 44645 | 0 | 4.28 | 4.28 | [25 empty] | 4.28 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | LDP Blank | MICHAEL GOODMAN | IMGA222431 | WO-0762252 | SOUTHFIELD ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 633164212 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 177 | 26.64 | MR1 | N | T1 SECONDARY |  | 44648 | 44652 | 0 | 26.64 | 26.64 | [26 empty] | 26.64 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760354 | HAMILTON ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510949855 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 234.65 | MR1 | N | T1 SECONDARY |  | 44466 | 44491 | 234.64 | 0 | 234.64 | 58.66 | 58.66 | 58.66 | 58.66 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760354 | HAMILTON ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510949856 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 239.58 | MR1 | N | T1 SECONDARY |  | 44466 | 44491 | 239.6 | 0 | 239.6 | 59.9 | 59.9 | 59.9 | 59.9 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760358 | HITHERBROOM ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950357 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 270.46 | MR1 | N | T1 SECONDARY |  | 44494 | 44519 | 270.48 | 0 | 270.48 |  |  |  |  | 67.62 | 67.62 | 67.62 | 67.62 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760358 | HITHERBROOM ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950359 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 223.38 | MR1 | N | T1 SECONDARY |  | 44494 | 44519 | 223.4 | 0 | 223.4 |  |  |  |  | 55.85 | 55.85 | 55.85 | 55.85 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760355 | HUGHES ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950501 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 297.53 | MR1 | N | T1 SECONDARY |  | 44522 | 44533 | 297.54 | 0 | 297.54 | [8 empty] | 148.77 | 148.77 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760356 | NEWMAN ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510951429 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 82.78 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 82.78 | 0 | 82.78 | [10 empty] | 41.39 | 41.39 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760356 | NEWMAN ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510951430 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 110.63 | MR1 | N | T1 SECONDARY |  | 44536 | 44547 | 110.64 | 0 | 110.64 | [10 empty] | 55.32 | 55.32 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760357 | STIRLING ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510952853 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 225.16 | MR1 | N | T1 SECONDARY |  | 44550 | 44568 | 75.05 | 150.1 | 225.15 | [10 empty] | 75.05 |  |  |  | 75.05 | 75.05 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222092 | WO-0760357 | STIRLING ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510952854 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 91 | 47.27 | MR1 | N | T1 SECONDARY |  | 44550 | 44568 | 15.76 | 31.52 | 47.28 | [10 empty] | 15.76 |  |  |  | 15.76 | 15.76 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761174 | CROWLAND AVENUE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220000784340 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 244.59 | MR1 | N | T1 SECONDARY |  | 44571 | 44603 | 0 | 244.6 | 244.6 | [15 empty] | 48.92 | 48.92 | 48.92 | 48.92 | 48.92 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761174 | CROWLAND AVENUE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220000784348 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.53 | MR1 | N | T1 SECONDARY |  | 44571 | 44603 | 0 | 1.55 | 1.55 | [15 empty] | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761174 | CROWLAND AVENUE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220000784359 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 389.88 | MR1 | N | T1 SECONDARY |  | 44571 | 44603 | 0 | 389.9 | 389.9 | [15 empty] | 77.98 | 77.98 | 77.98 | 77.98 | 77.98 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761175 | CRANFORD DRIVE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510948824 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 184.03 | MR1 | N | T1 SECONDARY |  | 44606 | 44638 | 0 | 184.05 | 184.05 | [20 empty] | 36.81 | 36.81 | 36.81 | 36.81 | 36.81 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761175 | CRANFORD DRIVE | HAYES | HILLINGDON | Hillingdon London Borough Council | 510948825 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 330.05 | MR1 | N | T1 SECONDARY |  | 44606 | 44638 | 0 | 330.05 | 330.05 | [20 empty] | 66.01 | 66.01 | 66.01 | 66.01 | 66.01 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761175 | CRANFORD DRIVE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220000776511 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 2.11 | MR1 | N | T1 SECONDARY |  | 44606 | 44638 | 0 | 2.1 | 2.1 | [20 empty] | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222093 | WO-0761175 | CRANFORD DRIVE | HAYES | HILLINGDON | Hillingdon London Borough Council | 220000776563 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 1.89 | MR1 | N | T1 SECONDARY |  | 44606 | 44638 | 0 | 1.9 | 1.9 | [20 empty] | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222126 | WO-0760996 | WORCESTER ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 510953987 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 311.17 | MR1 | N | T1 SECONDARY |  | 44641 | 44701 | 0 | 2.9 | 2.9 | [25 empty] | 1.45 | 1.45 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222126 | WO-0760996 | WORCESTER ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 510953988 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 231.49 | MR1 | N | T1 SECONDARY |  | 44641 | 44701 | 0 | 2.16 | 2.16 | [25 empty] | 1.08 | 1.08 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222126 | WO-0760996 | WORCESTER ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 510953989 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 67.05 | MR1 | N | T1 SECONDARY |  | 44641 | 44701 | 0 | 0.62 | 0.62 | [25 empty] | 0.31 | 0.31 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222126 | WO-0760996 | WORCESTER ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 606497147 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 7.65 | MR1 | N | T1 SECONDARY |  | 44641 | 44701 | 0 | 0.08 | 0.08 | [25 empty] | 0.04 | 0.04 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | MICHAEL NELMES | IMGA222126 | WO-0760996 | WORCESTER ROAD | UXBRIDGE | HILLINGDON | Hillingdon London Borough Council | 220001422661 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 120.92 | MR1 | N | T1 SECONDARY |  | 44641 | 44701 | 0 | 1.12 | 1.12 | [25 empty] | 0.56 | 0.56 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0759785 | WHITEPIT LANE | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 510937064 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 375.66 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 89.7 | 0 | 89.7 | 22.425 | 22.425 | 22.425 | 22.425 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0759785 | WHITEPIT LANE | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 510937065 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 39.57 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | -0.48 | 0 | -0.48 | -0.12 | -0.12 | -0.12 | -0.12 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0759785 | WHITEPIT LANE | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 621163913 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 3.45 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 3.38 | 0 | 3.38 | 0.845 | 0.845 | 0.845 | 0.845 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0759786 | STRAIGHT BIT | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 220001244906 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 521.24 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 301.3 | 0 | 301.3 | 75.325 | 75.325 | 75.325 | 75.325 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0761088 | STRATHCONA WAY | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 510969469 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 78 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | -4 | 0 | -4 | -1 | -1 | -1 | -1 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0761089 | STRATHCONA CLOSE | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 510918216 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 205.69 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | -3.34 | 0 | -3.34 | -0.835 | -0.835 | -0.835 | -0.835 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0761090 | PHILIP DRIVE | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 220000611522 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 4 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 3.9 | 0 | 3.9 | 0.975 | 0.975 | 0.975 | 0.975 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0761944 | NORLAND DRIVE | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 220000648637 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 3.81 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 3.9 | 0 | 3.9 | 0.975 | 0.975 | 0.975 | 0.975 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0761945 | THE FAIRWAY | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 510922874 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 34.31 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 34.32 | 0 | 34.32 | 8.58 | 8.58 | 8.58 | 8.58 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222360 | WO-0761945 | THE FAIRWAY | FLACKWELL HEATH | BUCKINGHAMSHIRE | Wycombe District Council | 510922875 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 29.29 | MR1 | N | T1 SECONDARY |  | 44291 | 44470 | 29.38 | 0 | 29.38 | 7.345 | 7.345 | 7.345 | 7.345 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222367 | WO-0759895 | WEST WYCOMBE ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510935158 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 188 | 593.81 | MR1 | N | T1 PAST |  | 44494 | 44547 | 279.36 | 0 | 279.36 |  |  |  |  | 34.92 | 34.92 | 34.92 | 34.92 | 34.92 | 34.92 | 34.92 | 34.92 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222367 | WO-0759895 | WEST WYCOMBE ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510935163 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 256 | 1079.8 | MR1 | N | T1 PAST |  | 44494 | 44547 | 508 | 0 | 508 |  |  |  |  | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222367 | WO-0759895 | WEST WYCOMBE ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 220000479703 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 730.35 | MR1 | N | T1 SECONDARY |  | 44494 | 44547 | 343.6 | 0 | 343.6 |  |  |  |  | 42.95 | 42.95 | 42.95 | 42.95 | 42.95 | 42.95 | 42.95 | 42.95 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222367 | WO-0759895 | WEST WYCOMBE ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510935158 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 188 | 593.81 | MR1 | N | T1 PAST |  | 44565 | 44680 | 0 | 240.5 | 240.5 | [14 empty] | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222367 | WO-0759895 | WEST WYCOMBE ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510935163 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 256 | 1079.8 | MR1 | N | T1 PAST |  | 44565 | 44680 | 0 | 437.19 | 437.19 | [14 empty] | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | 33.63 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | MICK MCPADDEN | IMGA222367 | WO-0759895 | WEST WYCOMBE ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 220000479703 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 730.35 | MR1 | N | T1 SECONDARY |  | 44565 | 44680 | 0 | 295.75 | 295.75 | [14 empty] | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765513 | GAINSBOROUGH DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963898 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 144.34 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 144.27 | 0 | 144.27 | 20.61 | 20.61 | 20.61 | 20.61 | 20.61 | 20.61 | 20.61 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765513 | GAINSBOROUGH DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963899 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 61.41 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 0.35 | 0 | 0.35 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765513 | GAINSBOROUGH DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963901 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 72.48 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 14.56 | 0 | 14.56 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | 2.08 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765513 | GAINSBOROUGH DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963902 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 57.01 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 7.07 | 0 | 7.07 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | 1.01 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765513 | GAINSBOROUGH DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510972936 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 68.35 | MR1 | N | T1 SECONDARY |  | 44424 | 44512 | 68.39 | 0 | 68.39 | 9.77 | 9.77 | 9.77 | 9.77 | 9.77 | 9.77 | 9.77 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765515 | SUTHERLAND CHASE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510964099 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 138.36 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 138.35 | 0 | 138.35 | [7 empty] | 27.67 | 27.67 | 27.67 | 27.67 | 27.67 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765515 | SUTHERLAND CHASE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510964106 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 52.78 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 52.8 | 0 | 52.8 | [7 empty] | 10.56 | 10.56 | 10.56 | 10.56 | 10.56 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765515 | SUTHERLAND CHASE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220001610925 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 174.55 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 174.55 | 0 | 174.55 | [7 empty] | 34.91 | 34.91 | 34.91 | 34.91 | 34.91 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765514 | BLACKMOOR WOOD | ASCOT | BRACKNELL FOREST | Windsor & Maidenhead Royal Borough | 510792405 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 24.37 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 24.35 | 24.35 | [14 empty] | 4.87 | 4.87 | 4.87 | 4.87 | 4.87 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765514 | BLACKMOOR WOOD | ASCOT | BRACKNELL FOREST | Windsor & Maidenhead Royal Borough | 510792406 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 152.78 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 152.8 | 152.8 | [14 empty] | 30.56 | 30.56 | 30.56 | 30.56 | 30.56 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765514 | BLACKMOOR WOOD | ASCOT | BRACKNELL FOREST | Windsor & Maidenhead Royal Borough | 510792408 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 66.68 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 66.7 | 66.7 | [14 empty] | 13.34 | 13.34 | 13.34 | 13.34 | 13.34 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765516 | RUSTON WAY | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510964042 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 104.6 | MR1 | N | T1 SECONDARY |  | 44593 | 44599 | 0 | 104.6 | 104.6 | [18 empty] | 52.3 | 52.3 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765517 | NASH GARDENS | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963998 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 98.62 | MR1 | N | T1 SECONDARY |  | 44600 | 44610 | 0 | 98.62 | 98.62 | [19 empty] | 49.31 | 49.31 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765517 | NASH GARDENS | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963999 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 86.99 | MR1 | N | T1 SECONDARY |  | 44600 | 44610 | 0 | 87 | 87 | [19 empty] | 43.5 | 43.5 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765518 | BLACKMOOR CLOSE | ASCOT | BRACKNELL FOREST | Windsor & Maidenhead Royal Borough | 510792552 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 177.17 | MR1 | N | T1 SECONDARY |  | 44613 | 44624 | 0 | 177.18 | 177.18 | [21 empty] | 88.59 | 88.59 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765519 | HALLEY DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510972937 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 49.7 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 49.7 | 49.7 | [23 empty] | 49.7 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765520 | LANGDALE DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963966 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 118.27 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 118.27 | 118.27 | [24 empty] | 118.27 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | PAT COLLINS | IMGA222436 | WO-0765521 | LOCKTON CHASE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963976 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 65.93 | MR1 | N | T1 SECONDARY |  | 44641 | 44645 | 0 | 65.93 | 65.93 | [25 empty] | 65.93 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222020 | WO-0761452 | LLANVAIR DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963972 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 833.62 | MR1 | N | T1 SECONDARY |  | 44375 | 44526 | 283.59 | 0 | 283.59 | 31.51 | 31.51 | 31.51 | 31.51 | 31.51 | 31.51 | 31.51 | 31.51 | 31.51 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222020 | WO-0761452 | LLANVAIR DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963973 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 502.88 | MR1 | N | T1 SECONDARY |  | 44375 | 44526 | -0.09 | 0 | -0.09 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | -0.01 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222020 | WO-0761452 | LLANVAIR DRIVE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510963974 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 9.36 | MR1 | N | T1 SECONDARY |  | 44375 | 44526 | 9.45 | 0 | 9.45 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222020 | WO-0761454 | WOODLANDS CLOSE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941285 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 165.07 | MR1 | N | T1 SECONDARY |  | 44431 | 44498 | 105.1 | 0 | 105.1 | 21.02 | 21.02 | 21.02 | 21.02 | 21.02 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222021 | WO-0759952 | WOODLANDS RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941330 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 50.62 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 11.19 | 0 | 11.19 | [9 empty] | 11.19 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222021 | WO-0759952 | WOODLANDS RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941331 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 315.09 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 69.67 | 0 | 69.67 | [9 empty] | 69.67 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222021 | WO-0759952 | WOODLANDS RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941332 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 93.74 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 20.73 | 0 | 20.73 | [9 empty] | 20.73 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222021 | WO-0759952 | WOODLANDS RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941334 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 298.23 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 65.94 | 0 | 65.94 | [9 empty] | 65.94 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222021 | WO-0759952 | WOODLANDS RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941336 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 47.85 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 10.58 | 0 | 10.58 | [9 empty] | 10.58 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222021 | WO-0759952 | WOODLANDS RIDE | ASCOT | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510941337 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 8.58 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 1.9 | 0 | 1.9 | [9 empty] | 1.9 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222424 | WO-0762211 | STOKE POGES LANE |  |  | Slough Borough Council | 510917785 | 6 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 99.07 | MR1 | N | T1 CBA |  | 44536 | 44547 | 98.76 | 0 | 98.76 | [10 empty] | 49.38 | 49.38 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222424 | WO-0762211 | STOKE POGES LANE | SLOUGH | SLOUGH | Slough Borough Council | 510917770 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 293 | 133.69 | MR1 | N | T1 PAST |  | 44536 | 44547 | 133.26 | 0 | 133.26 | [10 empty] | 66.63 | 66.63 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760388 | BARCHESTER ROAD | SLOUGH | SLOUGH | Slough Borough Council |  | 4 |  | T1 | Inch | SI | Insertion Dead | LP | Non policy | T1Non policy | 4"-5" |  | 8.49 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 8.5 | 8.5 | [14 empty] | 4.25 | 4.25 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Non policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760388 | BARCHESTER ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510786612 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 159.24 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 159.24 | 159.24 | [14 empty] | 79.62 | 79.62 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760388 | BARCHESTER ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510786613 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 36.27 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 36.28 | 36.28 | [14 empty] | 18.14 | 18.14 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760388 | BARCHESTER ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510786614 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 70.81 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 70.82 | 70.82 | [14 empty] | 35.41 | 35.41 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760388 | BARCHESTER ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510786615 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 37.16 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 37.16 | 37.16 | [14 empty] | 18.58 | 18.58 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760389 | MINSTER WAY |  |  | Slough Borough Council | 220000755927 | 32 |  | T1 | mm | PE | Insertion Live | LP | Non policy | T1Non policy | 4"-5" | -1 | 1.82 | MR1 | N | PE |  | 44572 | 44578 | 0 | 1.82 | 1.82 | [15 empty] | 0.91 | 0.91 | [10 empty] | #N/A | 4"-5" | LP | Non policy | T1 | PE | #N/A
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760389 | MINSTER WAY |  |  | Slough Borough Council | 220000755944 | 32 |  | T1 | mm | PE | Insertion Live | LP | Non policy | T1Non policy | 4"-5" | -1 | 2.18 | MR1 | N | PE |  | 44572 | 44578 | 0 | 2.18 | 2.18 | [15 empty] | 1.09 | 1.09 | [10 empty] | #N/A | 4"-5" | LP | Non policy | T1 | PE | #N/A
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760389 | MINSTER WAY |  |  | Slough Borough Council | 220000755945 | 32 |  | T1 | mm | PE | Insertion Live | LP | Non policy | T1Non policy | 4"-5" | -1 | 1.24 | MR1 | N | PE |  | 44572 | 44578 | 0 | 1.24 | 1.24 | [15 empty] | 0.62 | 0.62 | [10 empty] | #N/A | 4"-5" | LP | Non policy | T1 | PE | #N/A
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760389 | MINSTER WAY |  |  | Slough Borough Council | 220000755946 | 32 |  | T1 | mm | PE | Insertion Live | LP | Non policy | T1Non policy | 4"-5" | -1 | 1.31 | MR1 | N | PE |  | 44572 | 44578 | 0 | 1.32 | 1.32 | [15 empty] | 0.66 | 0.66 | [10 empty] | #N/A | 4"-5" | LP | Non policy | T1 | PE | #N/A
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760389 | MINSTER WAY | SLOUGH | SLOUGH | Slough Borough Council | 510877998 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 74.45 | MR1 | N | T1 SECONDARY |  | 44572 | 44578 | 0 | 74.46 | 74.46 | [15 empty] | 37.23 | 37.23 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760389 | MINSTER WAY | SLOUGH | SLOUGH | Slough Borough Council | 510878000 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 72.07 | MR1 | N | T1 SECONDARY |  | 44572 | 44578 | 0 | 72.08 | 72.08 | [15 empty] | 36.04 | 36.04 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222267 | WO-0760390 | PUBLIC RIGHT OF WAY SLOUGH FOOTPATH NUMBER 72B | SLOUGH | SLOUGH | Slough Borough Council | 510877999 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 246.54 | MR1 | N | T1 SECONDARY |  | 44579 | 44585 | 0 | 246.54 | 246.54 | [16 empty] | 123.27 | 123.27 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761581 | PENTON ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510972557 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 82.76 | MR1 | N | T1 SECONDARY |  | 44586 | 44599 | 0 | 82.77 | 82.77 | [17 empty] | 27.59 | 27.59 | 27.59 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761581 | PENTON ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510972742 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 539.39 | MR1 | N | T1 SECONDARY |  | 44586 | 44599 | 0 | 539.4 | 539.4 | [17 empty] | 179.8 | 179.8 | 179.8 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761584 | ST OLAVES CLOSE | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510944049 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 89.46 | MR1 | N | T1 SECONDARY |  | 44600 | 44606 | 0 | 89.46 | 89.46 | [19 empty] | 44.73 | 44.73 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761584 | ST OLAVES CLOSE | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510944050 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 17 | 53.91 | MR1 | N | T1 SECONDARY |  | 44600 | 44606 | 0 | 53.92 | 53.92 | [19 empty] | 26.96 | 26.96 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761584 | ST OLAVES CLOSE | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510944051 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 85.54 | MR1 | N | T1 SECONDARY |  | 44600 | 44606 | 0 | 85.54 | 85.54 | [19 empty] | 42.77 | 42.77 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761582 | ARGOSY GARDENS | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510972740 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 478.06 | MR1 | N | T1 SECONDARY |  | 44607 | 44620 | 0 | 478.05 | 478.05 | [20 empty] | 159.35 | 159.35 | 159.35 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761583 | ALLYN CLOSE | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510943481 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 54.71 | MR1 | N | T1 SECONDARY |  | 44621 | 44627 | 0 | 54.72 | 54.72 | [22 empty] | 27.36 | 27.36 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | PHIL MADLEY | IMGA222300 | WO-0761585 | RIVERSIDE ROAD | STAINES-UPON-THAMES | SURREY | Spelthorne Borough Council | 510944663 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 216 | 37.7 | MR1 | N | T1 PAST |  | 44628 | 44634 | 0 | 37.7 | 37.7 | [23 empty] | 18.85 | 18.85 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222306 | WO-0761842 | WINDMILL ROAD | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510939341 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 255 | 172.74 | MR1 | N | T1 PAST |  | 44635 | 44641 | 0 | 172.74 | 172.74 | [24 empty] | 86.37 | 86.37 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | PHIL MADLEY | IMGA222306 | WO-0761843 | BROOKLANDS CLOSE | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510798066 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 177 | 84.66 | MR1 | N | T1 PAST |  | 44642 | 44648 | 0 | 84.66 | 84.66 | [25 empty] | 42.33 | 42.33 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | RAURI FYFFE | IMGA222322 | WO-0761599 | PINKNEYS ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220001315404 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 651.49 | MR1 | N | T1 SECONDARY |  | 44424 | 44470 | 9.49 | 0 | 9.49 | 9.49 | [26 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | RAURI FYFFE | IMGA222419 | WO-0762157 | BROX ROAD | OTTERSHAW | SURREY | Runnymede Borough Council | 510798623 | 5 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 572.64 | MR1 | N | T1 CBA |  | 44459 | 44477 | 377.64 | 0 | 377.64 | 188.82 | 188.82 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | RAURI FYFFE | IMGA222419 | WO-0762158 | TIMBER HILL CLOSE |  |  | Runnymede Borough Council | 510798622 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 74.28 | MR1 | N | T1 SECONDARY |  | 44459 | 44477 | 0.28 | 0 | 0.28 | 0.14 | 0.14 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761002 | CADBURY ROAD | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 606576451 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 61.14 | MR1 | N | T1 CONNECTED |  | 44480 | 44505 | 61.16 | 0 | 61.16 |  |  | 15.29 | 15.29 | 15.29 | 15.29 | [21 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761002 | CADBURY ROAD | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510800870 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 506.7 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44480 | 44505 | 506.72 | 0 | 506.72 |  |  | 126.68 | 126.68 | 126.68 | 126.68 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761002 | CADBURY ROAD | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510800871 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 290.74 | MR1 | N | T1 SECONDARY |  | 44480 | 44505 | 290.76 | 0 | 290.76 |  |  | 72.69 | 72.69 | 72.69 | 72.69 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761003 | BURGOYNE ROAD | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 220000800622 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 3.83 | MR1 | N | T1 SECONDARY |  | 44508 | 44508 | 3.83 | 0 | 3.83 | [6 empty] | 3.83 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761004 | CARDINALS WALK | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510802718 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 69.12 | MR1 | N | T1 SECONDARY |  | 44508 | 44508 | 69.12 | 0 | 69.12 | [6 empty] | 69.12 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761005 | HELGIFORD GARDENS | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510848356 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 133.48 | MR1 | N | T1 SECONDARY |  | 44509 | 44512 | 133.48 | 0 | 133.48 | [6 empty] | 133.48 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222307 | WO-0761006 | SEYMOUR WAY | SUNBURY ON THAMES | SURREY | Spelthorne Borough Council | 510909917 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 314.27 | MR1 | N | T1 SECONDARY |  | 44515 | 44519 | 314.27 | 0 | 314.27 | [7 empty] | 314.27 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910144 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 113.75 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 113.76 | 0 | 113.76 | [8 empty] | 37.92 | 37.92 | 37.92 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910145 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 63.47 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 63.48 | 0 | 63.48 | [8 empty] | 21.16 | 21.16 | 21.16 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910146 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 118.34 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 118.35 | 0 | 118.35 | [8 empty] | 39.45 | 39.45 | 39.45 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910148 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 46.17 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 46.17 | 0 | 46.17 | [8 empty] | 15.39 | 15.39 | 15.39 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910149 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 71.15 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 71.16 | 0 | 71.16 | [8 empty] | 23.72 | 23.72 | 23.72 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910150 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 159.85 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 159.84 | 0 | 159.84 | [8 empty] | 53.28 | 53.28 | 53.28 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910151 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 100.63 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 100.62 | 0 | 100.62 | [8 empty] | 33.54 | 33.54 | 33.54 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910152 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 49.75 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 49.74 | 0 | 49.74 | [8 empty] | 16.58 | 16.58 | 16.58 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761647 | SHAFTESBURY CRESCENT | LALEHAM | SURREY | Spelthorne Borough Council | 510910153 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 38.61 | MR1 | N | T1 SECONDARY |  | 44522 | 44540 | 38.61 | 0 | 38.61 | [8 empty] | 12.87 | 12.87 | 12.87 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761649 | SHAFTESBURY CRESCENT FOOTPATH | LALEHAM | SURREY | Spelthorne Borough Council | 510910147 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 139.6 | MR1 | N | T1 SECONDARY |  | 44543 | 44547 | 139.6 | 0 | 139.6 | [11 empty] | 139.6 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222293 | WO-0761648 | TAVISTOCK CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510972262 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 59.61 | MR1 | N | T1 SECONDARY |  | 44565 | 44568 | 0 | 59.61 | 59.61 | [14 empty] | 59.61 | [12 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761916 | CHARLES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944106 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 19.03 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44571 | 44575 | 0 | 19.03 | 19.03 | [15 empty] | 19.03 | [11 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761916 | CHARLES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944107 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 26.93 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44571 | 44575 | 0 | 26.93 | 26.93 | [15 empty] | 26.93 | [11 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761916 | CHARLES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944108 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 23.15 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44571 | 44575 | 0 | 23.15 | 23.15 | [15 empty] | 23.15 | [11 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761916 | CHARLES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944109 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 14.8 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44571 | 44575 | 0 | 14.8 | 14.8 | [15 empty] | 14.8 | [11 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761916 | CHARLES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944110 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 347.24 | MR1 | N | T1 SECONDARY |  | 44571 | 44575 | 0 | 347.24 | 347.24 | [15 empty] | 347.24 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761916 | CHARLES ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944111 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 78.28 | MR1 | N | T1 SECONDARY |  | 44571 | 44575 | 0 | 78.28 | 78.28 | [15 empty] | 78.28 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761915 | PHILIP ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944260 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 63.97 | MR1 | N | T1 SECONDARY |  | 44578 | 44582 | 0 | 63.97 | 63.97 | [16 empty] | 63.97 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761915 | PHILIP ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510944261 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 80.1 | MR1 | N | T1 SECONDARY |  | 44578 | 44582 | 0 | 80.1 | 80.1 | [16 empty] | 80.1 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761915 | PHILIP ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 220001644618 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 298.47 | MR1 | N | T1 SECONDARY |  | 44578 | 44582 | 0 | 298.47 | 298.47 | [16 empty] | 298.47 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761917 | MARGARET CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510873399 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 76.45 | MR1 | N | T1 SECONDARY |  | 44585 | 44589 | 0 | 76.45 | 76.45 | [17 empty] | 76.45 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761917 | MARGARET CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510873400 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 76.02 | MR1 | N | T1 SECONDARY |  | 44585 | 44589 | 0 | 76.02 | 76.02 | [17 empty] | 76.02 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761918 | KINGS CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510943765 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 21.35 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44592 | 44596 | 0 | 21.35 | 21.35 | [18 empty] | 21.35 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761918 | KINGS CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510943766 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 15.68 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44592 | 44596 | 0 | 15.68 | 15.68 | [18 empty] | 15.68 | [8 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761918 | KINGS CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510943764 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 76.18 | MR1 | N | T1 SECONDARY |  | 44592 | 44596 | 0 | 76.18 | 76.18 | [18 empty] | 76.18 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761919 | BOOTH DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510945220 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 84.93 | MR1 | N | T1 SECONDARY |  | 44599 | 44603 | 0 | 84.93 | 84.93 | [19 empty] | 84.93 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761919 | BOOTH DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510945221 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 58.77 | MR1 | N | T1 SECONDARY |  | 44599 | 44603 | 0 | 58.77 | 58.77 | [19 empty] | 58.77 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222292 | WO-0761919 | BOOTH DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 220001644617 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 168.91 | MR1 | N | T1 SECONDARY |  | 44599 | 44603 | 0 | 168.91 | 168.91 | [19 empty] | 168.91 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791767 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 138.38 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 138.38 | 138.38 | [20 empty] | 138.38 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791768 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 70.85 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 70.85 | 70.85 | [20 empty] | 70.85 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791769 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 171.38 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 171.38 | 171.38 | [20 empty] | 171.38 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791770 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 90.26 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 90.26 | 90.26 | [20 empty] | 90.26 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791771 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 19.29 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 19.29 | 19.29 | [20 empty] | 19.29 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791772 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 63.49 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 63.49 | 63.49 | [20 empty] | 63.49 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761834 | BINGHAM DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510791773 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 84.83 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 84.83 | 84.83 | [20 empty] | 84.83 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761833 | GREENE FIELDE END | LALEHAM | SURREY | Spelthorne Borough Council | 510943324 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 95.72 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 95.72 | 95.72 | [21 empty] | 95.72 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761833 | GREENE FIELDE END | LALEHAM | SURREY | Spelthorne Borough Council | 510943325 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 49.31 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 49.31 | 49.31 | [21 empty] | 49.31 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761833 | GREENE FIELDE END | LALEHAM | SURREY | Spelthorne Borough Council | 510943326 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 89.31 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 89.31 | 89.31 | [21 empty] | 89.31 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761833 | GREENE FIELDE END | LALEHAM | SURREY | Spelthorne Borough Council | 510943327 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 77.2 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 77.2 | 77.2 | [21 empty] | 77.2 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761835 | MONKS WAY | LALEHAM | SURREY | Spelthorne Borough Council | 510973570 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 146.44 | MR1 | N | T1 SECONDARY |  | 44620 | 44624 | 0 | 146.44 | 146.44 | [22 empty] | 146.44 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761836 | LUCAN DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510897662 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 98.92 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 98.92 | 98.92 | [23 empty] | 98.92 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761836 | LUCAN DRIVE | LALEHAM | SURREY | Spelthorne Borough Council | 510897663 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 57 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 57 | 57 | [23 empty] | 57 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761837 | HONNOR ROAD | LALEHAM | SURREY | Spelthorne Borough Council | 510854236 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 110.85 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 110.85 | 110.85 | [24 empty] | 110.85 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761838 | BUCKLAND ESTATE WALKWAYS | LALEHAM | SURREY | Spelthorne Borough Council | 510954345 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 128.55 | MR1 | N | T1 SECONDARY |  | 44641 | 44645 | 0 | 128.55 | 128.55 | [25 empty] | 128.55 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | LDP Blank | RAURI FYFFE | IMGA222291 | WO-0761839 | ABBOT CLOSE | LALEHAM | SURREY | Spelthorne Borough Council | 510778336 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 104.95 | MR1 | N | T1 SECONDARY |  | 44648 | 44652 | 0 | 104.95 | 104.95 | [26 empty] | 104.95 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222234 | WO-0761749 | VEGAL CRESCENT | ENGLEFIELD GREEN | SURREY | Runnymede Borough Council | 510929800 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 40.01 | MR1 | N | T1 SECONDARY |  | 44417 | 44491 | 10.68 | 0 | 10.68 | 2.67 | 2.67 | 2.67 | 2.67 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222234 | WO-0761749 | VEGAL CRESCENT | ENGLEFIELD GREEN | SURREY | Runnymede Borough Council | 510929801 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 511.76 | MR1 | N | T1 SECONDARY |  | 44417 | 44491 | 121.4 | 0 | 121.4 | 30.35 | 30.35 | 30.35 | 30.35 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222234 | WO-0761750 | LAUREL AVENUE | ENGLEFIELD GREEN | SURREY | Runnymede Borough Council | 510864087 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 234.47 | MR1 | N | T1 SECONDARY |  | 44417 | 44491 | -0.48 | 0 | -0.48 | -0.12 | -0.12 | -0.12 | -0.12 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222234 | WO-0761751 | WILLSON ROAD | ENGLEFIELD GREEN | SURREY | Runnymede Borough Council | 510938789 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 255.34 | MR1 | N | T1 SECONDARY |  | 44417 | 44491 | 255.32 | 0 | 255.32 | 63.83 | 63.83 | 63.83 | 63.83 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761069 | BIRCH LANE | WOKING | SURREY | Surrey Heath Borough Council | 510791865 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 322.97 | MR1 | N | T1 SECONDARY |  | 44494 | 44498 | 8.16 | 0 | 8.16 |  |  |  |  | 8.16 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761069 | BIRCH LANE | WOKING | SURREY | Surrey Heath Borough Council | 510791866 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 151.71 | MR1 | N | T1 SECONDARY |  | 44494 | 44498 | 3.84 | 0 | 3.84 |  |  |  |  | 3.84 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761065 | ASHLEY WAY | WOKING | SURREY | Surrey Heath Borough Council | 510784307 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 112.68 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 112.68 | 0 | 112.68 | [5 empty] | 18.78 | 18.78 | 18.78 | 18.78 | 18.78 | 18.78 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761065 | ASHLEY WAY | WOKING | SURREY | Surrey Heath Borough Council | 510784308 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 108.72 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 108.72 | 0 | 108.72 | [5 empty] | 18.12 | 18.12 | 18.12 | 18.12 | 18.12 | 18.12 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761065 | ASHLEY WAY | WOKING | SURREY | Surrey Heath Borough Council | 510784309 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 80.45 | MR1 | N | T1 SECONDARY |  | 44501 | 44540 | 80.46 | 0 | 80.46 | [5 empty] | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | 13.41 | [16 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761066 | CUCKOO LANE | WOKING | SURREY | Surrey Heath Borough Council | 510818166 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 26 | 56.31 | MR1 | N | T1 SECONDARY |  | 44543 | 44568 | 28.16 | 42 | 70.16 | [10 empty] | 14.08 | 14.08 |  |  | 21 | 21 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761066 | CUCKOO LANE | WOKING | SURREY | Surrey Heath Borough Council | 510818167 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 175.6 | MR1 | N | T1 SECONDARY |  | 44543 | 44568 | 87.8 | 87.8 | 175.6 | [10 empty] | 43.9 | 43.9 |  |  | 43.9 | 43.9 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761067 | BROAD STREET | WOKING | SURREY | Surrey Heath Borough Council | 510797006 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 77.06 | MR1 | N | T1 SECONDARY |  | 44571 | 44596 | 0 | 43.56 | 43.56 | [15 empty] | 10.89 | 10.89 | 10.89 | 10.89 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761067 | BROAD STREET | WOKING | SURREY | Surrey Heath Borough Council | 510797007 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 260.73 | MR1 | N | T1 SECONDARY |  | 44571 | 44596 | 0 | 147.44 | 147.44 | [15 empty] | 36.86 | 36.86 | 36.86 | 36.86 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761068 | ORCHARD CLOSE | WOKING | SURREY | Surrey Heath Borough Council | 510965876 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 23.85 | MR1 | N | T1 SECONDARY |  | 44599 | 44624 | 0 | 23.88 | 23.88 | [19 empty] | 5.97 | 5.97 | 5.97 | 5.97 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761068 | ORCHARD CLOSE | WOKING | SURREY | Surrey Heath Borough Council | 510965877 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 187.76 | MR1 | N | T1 SECONDARY |  | 44599 | 44624 | 0 | 188.12 | 188.12 | [19 empty] | 47.03 | 47.03 | 47.03 | 47.03 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761070 | REVESBY CLOSE | WOKING | SURREY | Surrey Heath Borough Council | 510965888 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 46.82 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 46.82 | 46.82 | [23 empty] | 46.82 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222025 | WO-0761070 | REVESBY CLOSE | WOKING | SURREY | Surrey Heath Borough Council | 606521536 | 2 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 40 | 6.3 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 6.3 | 6.3 | [23 empty] | 6.3 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222237 | WO-0760447 | BOWES ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 635651224 | 2 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 1.43 | MR1 | N | T1 CONNECTED |  | 44634 | 44638 | 0 | 0.16 | 0.16 | [24 empty] | 0.16 |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222237 | WO-0760447 | BOWES ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 635651225 | 2 |  | T1 | Inch | ST | Unknown | LP | Non policy | T1Non policy | 4"-5" | -1 | 1.42 | MR1 | N | T1 CONNECTED |  | 44634 | 44638 | 0 | 0.16 | 0.16 | [24 empty] | 0.16 |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222237 | WO-0760447 | BOWES ROAD |  |  | Surrey County Council |  | 4 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 15 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 1.67 | 1.67 | [24 empty] | 1.67 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222237 | WO-0760447 | BOWES ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510943503 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 135.5 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 15.11 | 15.11 | [24 empty] | 15.11 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222237 | WO-0760447 | BOWES ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510943504 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 239.26 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 26.68 | 26.68 | [24 empty] | 26.68 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | ROB HARRIS | IMGA222237 | WO-0760447 | BOWES ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 220000868368 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.96 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 0.22 | 0.22 | [24 empty] | 0.22 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | ROB HARRIS | IMGA222303 | WO-0761463 | LONGFORD AVENUE | STANWELL | SURREY | Spelthorne Borough Council | 510869380 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 119.81 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 119.82 | 119.82 | [25 empty] | 59.91 | 59.91 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | ROB HARRIS | IMGA222303 | WO-0761463 | LONGFORD AVENUE | STANWELL | SURREY | Spelthorne Borough Council | 510869381 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 104.58 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 104.58 | 104.58 | [25 empty] | 52.29 | 52.29 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | ROB HARRIS | IMGA222303 | WO-0761463 | LONGFORD AVENUE | STANWELL | SURREY | Spelthorne Borough Council | 510869382 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 62.67 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 62.68 | 62.68 | [25 empty] | 31.34 | 31.34 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | ROB HARRIS | IMGA222303 | WO-0761463 | LONGFORD AVENUE | STANWELL | SURREY | Spelthorne Borough Council | 220000641764 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 33.43 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 33.44 | 33.44 | [25 empty] | 16.72 | 16.72 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | ROB HARRIS | IMGA222303 | WO-0761463 | LONGFORD AVENUE | STANWELL | SURREY | Spelthorne Borough Council | 220000641765 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 24.53 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 24.54 | 24.54 | [25 empty] | 12.27 | 12.27 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | ROB HARRIS | IMGA222303 | WO-0761463 | LONGFORD AVENUE | STANWELL | SURREY | Spelthorne Borough Council | 220000641766 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 10.93 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 10.94 | 10.94 | [25 empty] | 5.47 | 5.47 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222429 | WO-0762248 | PENYSTON ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510891870 | 7 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 485.37 | MR1 | N | T1 CBA |  | 44459 | 44484 | 385.35 | 0 | 385.35 | 128.45 | 128.45 | 128.45 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222429 | WO-0762249 | COURTFIELD DRIVE | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510815622 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 141.93 | MR1 | N | T1 SECONDARY |  | 44487 | 44491 | 141.93 | 0 | 141.93 |  |  |  | 141.93 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222429 | WO-0762250 | PORTLOCK ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220000663342 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 23 | 1.02 | MR1 | N | T1 SECONDARY |  | 44494 | 44498 | 1.02 | 0 | 1.02 |  |  |  |  | 1.02 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222239 | WO-0759881 | WENDOVER ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510972864 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 593.3 | MR1 | N | T1 SECONDARY |  | 44501 | 44568 | 474.64 | 118.66 | 593.3 | [5 empty] | 67.8057 | 67.8057 | 67.8057 | 67.8057 | 67.8057 | 67.8057 | 67.8057 |  |  | 59.33 | 59.33 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222239 | WO-0759881 | WENDOVER ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510972865 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 113 | 633.41 | MR1 | N | T1 SECONDARY |  | 44501 | 44568 | 506.72 | 126.68 | 633.4 | [5 empty] | 72.3886 | 72.3886 | 72.3886 | 72.3886 | 72.3886 | 72.3886 | 72.3886 |  |  | 63.34 | 63.34 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222239 | WO-0759881 | WENDOVER ROAD | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 606739973 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 2.89 | MR1 | N | T1 SECONDARY |  | 44501 | 44568 | 2.32 | 0.58 | 2.9 | [5 empty] | 0.33143 | 0.33143 | 0.33143 | 0.33143 | 0.33143 | 0.33143 | 0.33143 |  |  | 0.29 | 0.29 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222239 | WO-0759882 | WENDOVER PLACE | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510972863 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 75.78 | MR1 | N | T1 SECONDARY |  | 44571 | 44575 | 0 | 75.78 | 75.78 | [15 empty] | 75.78 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222239 | WO-0759883 | NEW ROAD (SOUTH OF RAILWAY) | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510972866 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 25.58 | MR1 | N | T1 SECONDARY |  | 44578 | 44582 | 0 | 25.58 | 25.58 | [16 empty] | 25.58 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222239 | WO-0759883 | NEW ROAD (SOUTH OF RAILWAY) | STAINES-UPON-THAMES | SURREY | Runnymede Borough Council | 510972870 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 4.39 | MR1 | N | T1 SECONDARY |  | 44578 | 44582 | 0 | 4.39 | 4.39 | [16 empty] | 4.39 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | ROB LAMOR | IMGA222255 | WO-0760137 | FRANKLIN AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510834460 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 35.78 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 35.8 | 35.8 | [17 empty] | 8.95 | 8.95 | 8.95 | 8.95 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | ROB LAMOR | IMGA222255 | WO-0760137 | FRANKLIN AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510834461 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 43.48 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 43.48 | 43.48 | [17 empty] | 10.87 | 10.87 | 10.87 | 10.87 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | ROB LAMOR | IMGA222255 | WO-0760137 | FRANKLIN AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510834462 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 231.93 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 231.92 | 231.92 | [17 empty] | 57.98 | 57.98 | 57.98 | 57.98 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | ROB LAMOR | IMGA222255 | WO-0760137 | FRANKLIN AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510834464 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 67.06 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 67.08 | 67.08 | [17 empty] | 16.77 | 16.77 | 16.77 | 16.77 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | ROB LAMOR | IMGA222255 | WO-0760137 | FRANKLIN AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510834465 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 43.9 | MR1 | N | T1 SEED |  | 44585 | 44610 | 0 | 43.92 | 43.92 | [17 empty] | 10.98 | 10.98 | 10.98 | 10.98 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | LDP Blank | ROB LAMOR | IMGA222255 | WO-0760137 | FRANKLIN AVENUE | SLOUGH | SLOUGH | Slough Borough Council | 510834466 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 26.29 | MR1 | N | T1 SECONDARY |  | 44585 | 44610 | 0 | 26.28 | 26.28 | [17 empty] | 6.57 | 6.57 | 6.57 | 6.57 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 636601133 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 1 | 12.3 | MR1 | N | T1 CONNECTED |  | 44613 | 44652 | 0 | 12.3 | 12.3 | [21 empty] | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510814716 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 26.19 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 26.22 | 26.22 | [21 empty] | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | 4.37 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510830673 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 125.39 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 125.4 | 125.4 | [21 empty] | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | 20.9 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510830674 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 173.26 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 173.28 | 173.28 | [21 empty] | 28.88 | 28.88 | 28.88 | 28.88 | 28.88 | 28.88 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510830677 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 78.45 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 78.48 | 78.48 | [21 empty] | 13.08 | 13.08 | 13.08 | 13.08 | 13.08 | 13.08 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510830679 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 166.45 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 166.44 | 166.44 | [21 empty] | 27.74 | 27.74 | 27.74 | 27.74 | 27.74 | 27.74 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966048 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 11.98 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 12 | 12 | [21 empty] | 2 | 2 | 2 | 2 | 2 | 2 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Leigh Osaer | DHB Utilities | ROB LAMOR | IMGA222314 | WO-0760334 | FARMERS WAY | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220001306742 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 31.01 | MR1 | N | T1 SECONDARY |  | 44613 | 44652 | 0 | 31.02 | 31.02 | [21 empty] | 5.17 | 5.17 | 5.17 | 5.17 | 5.17 | 5.17 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761911 | CHAPMAN LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510805733 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 142.29 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 142.29 | 0 | 142.29 | 15.81 | 15.81 | 15.81 | 15.81 | 15.81 | 15.81 | 15.81 | 15.81 | 15.81 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761911 | CHAPMAN LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220000621734 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 21.89 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 21.87 | 0 | 21.87 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | 2.43 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761912 | ABBEY ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220000565430 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 7.76 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 7.83 | 0 | 7.83 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | 0.87 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761912 | ABBEY ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220000621735 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 4.37 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 4.41 | 0 | 4.41 | 0.49 | 0.49 | 0.49 | 0.49 | 0.49 | 0.49 | 0.49 | 0.49 | 0.49 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761912 | ABBEY ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220001234728 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 32.24 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 32.22 | 0 | 32.22 | 3.58 | 3.58 | 3.58 | 3.58 | 3.58 | 3.58 | 3.58 | 3.58 | 3.58 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761913 | VINEYARD DRIVE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510931167 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 143.7 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 143.73 | 0 | 143.73 | 15.97 | 15.97 | 15.97 | 15.97 | 15.97 | 15.97 | 15.97 | 15.97 | 15.97 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761914 | ELM LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510827031 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 194.53 | MR1 | N | T1 SECONDARY |  | 44459 | 44526 | 194.49 | 0 | 194.49 | 21.61 | 21.61 | 21.61 | 21.61 | 21.61 | 21.61 | 21.61 | 21.61 | 21.61 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222358 | WO-0761914 | ELM LANE | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 510827032 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 40.56 | MR1 | N | T1 SEED |  | 44459 | 44526 | 40.59 | 0 | 40.59 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | 4.51 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | ROSS WALKER | IMGA222357 | WO-0760426 | FARM ROAD | BOURNE END | BUCKINGHAMSHIRE | Wycombe District Council | 220000687264 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 12.73 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 12.73 | 0 | 12.73 | [9 empty] | 12.73 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761442 | ARLINGTON DRIVE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510947422 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 287.2 | MR1 | N | T1 SECONDARY |  | 44466 | 44498 | 287.2 | 0 | 287.2 |  | 57.44 | 57.44 | 57.44 | 57.44 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761442 | ARLINGTON DRIVE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510947423 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 146.21 | MR1 | N | T1 SECONDARY |  | 44466 | 44498 | 146.2 | 0 | 146.2 |  | 29.24 | 29.24 | 29.24 | 29.24 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761443 | BURY AVENUE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510948129 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 185.14 | MR1 | N | T1 SECONDARY |  | 44501 | 44512 | 185.14 | 0 | 185.14 | [5 empty] | 92.57 | 92.57 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761444 | BOSTON GROVE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 220000797287 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 3.57 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44515 | 44519 | 3.57 | 0 | 3.57 | [7 empty] | 3.57 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761445 | ST CATHERINES ROAD | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510946748 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 104.01 | MR1 | N | T1 SECONDARY |  | 44522 | 44554 | 104 | 0 | 104 | [7 empty] | 20.8 | 20.8 | 20.8 | 20.8 | 20.8 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761445 | ST CATHERINES ROAD | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510952389 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 190.39 | MR1 | N | T1 SECONDARY |  | 44522 | 44554 | 190.4 | 0 | 190.4 | [7 empty] | 38.08 | 38.08 | 38.08 | 38.08 | 38.08 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761445 | ST CATHERINES ROAD | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510952390 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 155.18 | MR1 | N | T1 SECONDARY |  | 44522 | 44554 | 155.2 | 0 | 155.2 | [7 empty] | 31.04 | 31.04 | 31.04 | 31.04 | 31.04 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222114 | WO-0761445 | ST CATHERINES ROAD | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510952391 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 9.46 | MR1 | N | T1 SECONDARY |  | 44522 | 44554 | 9.45 | 0 | 9.45 | [7 empty] | 1.89 | 1.89 | 1.89 | 1.89 | 1.89 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761831 | WILLOW GARDENS | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510953803 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 210.58 | MR1 | N | T1 SECONDARY |  | 44557 | 44575 | 0 | 210.57 | 210.57 | [14 empty] | 70.19 | 70.19 | 70.19 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761831 | WILLOW GARDENS | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510953804 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 249.83 | MR1 | N | T1 SECONDARY |  | 44557 | 44575 | 0 | 249.84 | 249.84 | [14 empty] | 83.28 | 83.28 | 83.28 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761829 | NORTHDOWN CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510951523 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 231.08 | MR1 | N | T1 SECONDARY |  | 44578 | 44589 | 0 | 231.08 | 231.08 | [16 empty] | 115.54 | 115.54 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761830 | RALEIGH CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510952326 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 47.54 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 47.54 | 47.54 | [18 empty] | 23.77 | 23.77 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761830 | RALEIGH CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510952327 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 56.23 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 56.24 | 56.24 | [18 empty] | 28.12 | 28.12 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761830 | RALEIGH CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510953805 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 37.51 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 37.52 | 37.52 | [18 empty] | 18.76 | 18.76 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761830 | RALEIGH CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510994756 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 91.79 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 91.8 | 91.8 | [18 empty] | 45.9 | 45.9 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761830 | RALEIGH CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510994757 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 54.23 | MR1 | N | T1 SECONDARY |  | 44592 | 44603 | 0 | 54.24 | 54.24 | [18 empty] | 27.12 | 27.12 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | LDP Blank | SCOTT BARNES | IMGA222113 | WO-0761832 | DENBIGH CLOSE | RUISLIP | HILLINGDON | Hillingdon London Borough Council | 510949031 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 107.39 | MR1 | N | T1 SECONDARY |  | 44606 | 44617 | 0 | 107.4 | 107.4 | [20 empty] | 53.7 | 53.7 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222098 | WO-0760454 | BROOKSIDE ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510948085 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 138 | 424.37 | MR1 | N | T1 SECONDARY |  | 44620 | 44659 | 0 | 353.65 | 353.65 | [22 empty] | 70.73 | 70.73 | 70.73 | 70.73 | 70.73 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222098 | WO-0760454 | BROOKSIDE ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510948088 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 16.6 | MR1 | N | T1 SECONDARY |  | 44620 | 44659 | 0 | 13.85 | 13.85 | [22 empty] | 2.77 | 2.77 | 2.77 | 2.77 | 2.77 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222098 | WO-0760454 | BROOKSIDE ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001574854 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 1.7 | MR1 | N | T1 SECONDARY |  | 44620 | 44659 | 0 | 1.4 | 1.4 | [22 empty] | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | SCOTT BARNES | IMGA222098 | WO-0760454 | BROOKSIDE ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 220001575346 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 1.4 | MR1 | N | T1 SECONDARY |  | 44620 | 44659 | 0 | 1.15 | 1.15 | [22 empty] | 0.23 | 0.23 | 0.23 | 0.23 | 0.23 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN |  |  | Bracknell Forest Borough Council | 510926848 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 175 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 1.53 | 0 | 1.53 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN |  |  | Bracknell Forest Borough Council | 510926849 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 125 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 126 | 0 | 126 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN |  |  | Bracknell Forest Borough Council | 510926850 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 30 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 30.24 | 0 | 30.24 | 3.36 | 3.36 | 3.36 | 3.36 | 3.36 | 3.36 | 3.36 | 3.36 | 3.36 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN |  |  | Bracknell Forest Borough Council | 510926851 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 106 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 106.92 | 0 | 106.92 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | 11.88 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN |  |  | Bracknell Forest Borough Council | 510926853 | 6 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 168 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 169.38 | 0 | 169.38 | 18.82 | 18.82 | 18.82 | 18.82 | 18.82 | 18.82 | 18.82 | 18.82 | 18.82 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN |  |  | Bracknell Forest Borough Council | 510926854 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 124 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 0.99 | 0 | 0.99 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222011 | WO-0761714 | TREVELYAN | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510926852 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 307.19 | MR1 | N | T1 SECONDARY |  | 44431 | 44526 | 2.79 | 0 | 2.79 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | 0.31 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510928045 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | 2 | 47.23 | MR1 | N | T1 CONNECTED |  | 44529 | 44652 | 13.1 | 34.06 | 47.16 | [7 empty] | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 |  |  | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | 2.62 | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510867497 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 172.03 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 47.8 | 124.28 | 172.08 | [7 empty] | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 |  |  | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | 9.56 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510898054 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 10.84 | MR1 | N | T1 SEED |  | 44529 | 44652 | 3 | 7.8 | 10.8 | [7 empty] | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 |  |  | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510928046 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 33.52 | MR1 | N | T1 SEED |  | 44529 | 44652 | 9.3 | 24.18 | 33.48 | [7 empty] | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 |  |  | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | 1.86 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510928050 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 76.88 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 21.35 | 55.51 | 76.86 | [7 empty] | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 |  |  | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | 4.27 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510928052 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 266.51 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 74.05 | 192.53 | 266.58 | [7 empty] | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 |  |  | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | 14.81 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510928053 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 7.09 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 1.95 | 5.07 | 7.02 | [7 empty] | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 |  |  | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | 0.39 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 510928054 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 44.86 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 12.45 | 32.37 | 44.82 | [7 empty] | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 |  |  | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | 2.49 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 220001725571 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 1.97 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 0.55 | 1.43 | 1.98 | [7 empty] | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 220001725580 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 1.28 | MR1 | N | T1 SEED |  | 44529 | 44652 | 0.35 | 0.91 | 1.26 | [7 empty] | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 |  |  | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | 0.07 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 220002010233 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 7.77 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 2.15 | 5.59 | 7.74 | [7 empty] | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 |  |  | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | 0.43 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | William Sadler | OMJ | SCOTT DOMINY | IMGA222440 | WO-0765590 | UFFINGTON DRIVE | BRACKNELL | BRACKNELL FOREST | Bracknell Forest Borough Council | 220002010237 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 467.73 | MR1 | N | T1 SECONDARY |  | 44529 | 44652 | 129.95 | 337.87 | 467.82 | [7 empty] | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 |  |  | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | 25.99 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761768 | GREENSIDE | SLOUGH | SLOUGH | Slough Borough Council | 510966867 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 64.49 | MR1 | N | T1 ENM CONDITION CANDIDATE |  | 44445 | 44512 | 64.47 | 0 | 64.47 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | 9.21 | [20 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761767 | BELMONT | SLOUGH | SLOUGH | Slough Borough Council | 510790116 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 241.94 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 241.92 | 0 | 241.92 | 34.56 | 34.56 | 34.56 | 34.56 | 34.56 | 34.56 | 34.56 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761767 | BELMONT | SLOUGH | SLOUGH | Slough Borough Council | 510790117 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 252.83 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 17.78 | 0 | 17.78 | 2.54 | 2.54 | 2.54 | 2.54 | 2.54 | 2.54 | 2.54 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761767 | BELMONT | SLOUGH | SLOUGH | Slough Borough Council | 638667060 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 18.76 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 12.81 | 0 | 12.81 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | 1.83 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761768 | GREENSIDE | SLOUGH | SLOUGH | Slough Borough Council | 510966868 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 36.05 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 36.12 | 0 | 36.12 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | 5.16 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761768 | GREENSIDE | SLOUGH | SLOUGH | Slough Borough Council | 510966869 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 288.73 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | -3.29 | 0 | -3.29 | -0.47 | -0.47 | -0.47 | -0.47 | -0.47 | -0.47 | -0.47 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761769 | THORNDIKE | SLOUGH | SLOUGH | Slough Borough Council | 510924813 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 362.63 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 199.57 | 0 | 199.57 | 28.51 | 28.51 | 28.51 | 28.51 | 28.51 | 28.51 | 28.51 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761769 | THORNDIKE | SLOUGH | SLOUGH | Slough Borough Council | 510924814 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 316.68 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 316.68 | 0 | 316.68 | 45.24 | 45.24 | 45.24 | 45.24 | 45.24 | 45.24 | 45.24 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761770 | WILLONERS | SLOUGH | SLOUGH | Slough Borough Council | 510938444 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 59.79 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 59.78 | 0 | 59.78 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | 8.54 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761770 | WILLONERS | SLOUGH | SLOUGH | Slough Borough Council | 510938445 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 59.02 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 59.01 | 0 | 59.01 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 | 8.43 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222254 | WO-0761770 | WILLONERS | SLOUGH | SLOUGH | Slough Borough Council | 510938446 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 58.85 | MR1 | N | T1 SECONDARY |  | 44445 | 44512 | 58.87 | 0 | 58.87 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | 8.41 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | STUART PORTER | IMGA222245 | WO-0760956 | BELGRAVE ROAD |  |  | Slough Borough Council |  | 6 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 250 | MR1 | N | T1 SECONDARY |  | 44466 | 44477 | 31.24 | 0 | 31.24 | 15.62 | 15.62 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | STUART PORTER | IMGA222245 | WO-0760956 | BELGRAVE ROAD |  |  | Slough Borough Council | 220000796792 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" |  | 63 | MR1 | N | T1 SECONDARY |  | 44466 | 44477 | 7.88 | 0 | 7.88 | 3.94 | 3.94 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Chris Douglas | DHB Utilities | STUART PORTER | IMGA222245 | WO-0760956 | BELGRAVE ROAD | SLOUGH | SLOUGH | Slough Borough Council | 220000796795 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 191.13 | MR1 | N | T1 SECONDARY |  | 44466 | 44477 | 23.9 | 0 | 23.9 | 11.95 | 11.95 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761339 | GOODWIN ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510838859 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 30 | 314.83 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 314.85 | 0 | 314.85 | [7 empty] | 62.97 | 62.97 | 62.97 | 62.97 | 62.97 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761339 | GOODWIN ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510838860 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 283.3 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 283.3 | 0 | 283.3 | [7 empty] | 56.66 | 56.66 | 56.66 | 56.66 | 56.66 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761338 | CHILWICK ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510808172 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 193.51 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 193.52 | 193.52 | [14 empty] | 96.76 | 96.76 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761338 | CHILWICK ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510808173 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 69.25 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 69.26 | 69.26 | [14 empty] | 34.63 | 34.63 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761340 | MARUNDEN GREEN | SLOUGH | SLOUGH | Slough Borough Council | 220000680890 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 25.62 | MR1 | N | T1 SECONDARY |  | 44572 | 44578 | 0 | 25.62 | 25.62 | [15 empty] | 12.81 | 12.81 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761340 | MARUNDEN GREEN | SLOUGH | SLOUGH | Slough Borough Council | 220000680893 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 26.68 | MR1 | N | T1 SECONDARY |  | 44572 | 44578 | 0 | 26.68 | 26.68 | [15 empty] | 13.34 | 13.34 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761341 | UMBERVILLE WAY | SLOUGH | SLOUGH | Slough Borough Council | 510928108 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 72.4 | MR1 | N | T1 SECONDARY |  | 44579 | 44592 | 0 | 72.39 | 72.39 | [16 empty] | 24.13 | 24.13 | 24.13 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761341 | UMBERVILLE WAY | SLOUGH | SLOUGH | Slough Borough Council | 510928109 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 44.2 | MR1 | N | T1 SECONDARY |  | 44579 | 44592 | 0 | 44.19 | 44.19 | [16 empty] | 14.73 | 14.73 | 14.73 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761341 | UMBERVILLE WAY | SLOUGH | SLOUGH | Slough Borough Council | 510928110 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 110.73 | MR1 | N | T1 SECONDARY |  | 44579 | 44592 | 0 | 110.73 | 110.73 | [16 empty] | 36.91 | 36.91 | 36.91 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222260 | WO-0761341 | UMBERVILLE WAY | SLOUGH | SLOUGH | Slough Borough Council | 510928111 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 167.61 | MR1 | N | T1 SECONDARY |  | 44579 | 44592 | 0 | 167.61 | 167.61 | [16 empty] | 55.87 | 55.87 | 55.87 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510801092 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 57.8 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 57.81 | 57.81 | [18 empty] | 19.27 | 19.27 | 19.27 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510849305 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 156.54 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 156.54 | 156.54 | [18 empty] | 52.18 | 52.18 | 52.18 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510849306 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 179.74 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 179.73 | 179.73 | [18 empty] | 59.91 | 59.91 | 59.91 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510849307 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 62 | 104.32 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 104.31 | 104.31 | [18 empty] | 34.77 | 34.77 | 34.77 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510849308 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 170.86 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 170.85 | 170.85 | [18 empty] | 56.95 | 56.95 | 56.95 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 606522075 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 6.77 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 6.78 | 6.78 | [18 empty] | 2.26 | 2.26 | 2.26 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761393 | HETHERINGTON CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 621164638 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 8.14 | MR1 | N | T1 SECONDARY |  | 44593 | 44606 | 0 | 8.13 | 8.13 | [18 empty] | 2.71 | 2.71 | 2.71 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761392 | GAVESTON ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510966227 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 237.76 | MR1 | N | T1 SECONDARY |  | 44607 | 44620 | 0 | 237.75 | 237.75 | [20 empty] | 79.25 | 79.25 | 79.25 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761392 | GAVESTON ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510966228 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 234.56 | MR1 | N | T1 SECONDARY |  | 44607 | 44620 | 0 | 234.57 | 234.57 | [20 empty] | 78.19 | 78.19 | 78.19 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761392 | GAVESTON ROAD | SLOUGH | SLOUGH | Slough Borough Council | 606306668 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 81.16 | MR1 | N | T1 SECONDARY |  | 44607 | 44620 | 0 | 81.15 | 81.15 | [20 empty] | 27.05 | 27.05 | 27.05 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761394 | LYNCH HILL LANE | SLOUGH | SLOUGH | Slough Borough Council | 510966226 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 36 | 121.94 | MR1 | N | T1 SECONDARY |  | 44621 | 44623 | 0 | 121.94 | 121.94 | [22 empty] | 121.94 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | STUART PORTER | IMGA222259 | WO-0761395 | MASCALL PATH | SLOUGH | SLOUGH | Slough Borough Council | 510874879 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 57.06 | MR1 | N | T1 SECONDARY |  | 44624 | 44624 | 0 | 57.06 | 57.06 | [22 empty] | 57.06 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761255 | EYRE GREEN | SLOUGH | SLOUGH | Slough Borough Council | 510829649 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 59.65 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 59.65 | 59.65 | [23 empty] | 59.65 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761255 | EYRE GREEN | SLOUGH | SLOUGH | Slough Borough Council | 510829650 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 56.39 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 56.39 | 56.39 | [23 empty] | 56.39 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761255 | EYRE GREEN | SLOUGH | SLOUGH | Slough Borough Council | 510829651 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 9.76 | MR1 | N | T1 SECONDARY |  | 44627 | 44631 | 0 | 9.76 | 9.76 | [23 empty] | 9.76 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761251 | MANFIELD CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510872900 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 35.38 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 35.38 | 35.38 | [24 empty] | 35.38 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761251 | MANFIELD CLOSE | SLOUGH | SLOUGH | Slough Borough Council | 510872901 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 155.19 | MR1 | N | T1 SECONDARY |  | 44634 | 44638 | 0 | 155.19 | 155.19 | [24 empty] | 155.19 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761252 | ODENCROFT ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510886193 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 21 | 301.86 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 301.86 | 301.86 | [25 empty] | 150.93 | 150.93 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | STUART PORTER | IMGA222256 | WO-0761252 | ODENCROFT ROAD | SLOUGH | SLOUGH | Slough Borough Council | 510886194 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 276.75 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 276.76 | 276.76 | [25 empty] | 138.38 | 138.38 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761776 | LONGSIDE CLOSE | EGHAM | SURREY | Runnymede Borough Council | 510869480 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 73.28 | MR1 | N | T1 SECONDARY |  | 44396 | 44512 | -0.7 | 0 | -0.7 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761777 | THORPE LEA ROAD | EGHAM | SURREY | Runnymede Borough Council | 510925044 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 561.62 | MR1 | N | T1 ENM CONDITION SPECIFIED |  | 44396 | 44512 | 561.68 | 0 | 561.68 | 80.24 | 80.24 | 80.24 | 80.24 | 80.24 | 80.24 | 80.24 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761777 | THORPE LEA ROAD | EGHAM | SURREY | Runnymede Borough Council | 510972463 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 25.41 | MR1 | N | T1 SECONDARY |  | 44396 | 44512 | 25.34 | 0 | 25.34 | 3.62 | 3.62 | 3.62 | 3.62 | 3.62 | 3.62 | 3.62 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761777 | THORPE LEA ROAD | EGHAM | SURREY | Runnymede Borough Council | 220001479828 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 2.63 | MR1 | N | T1 SECONDARY |  | 44396 | 44512 | 2.52 | 0 | 2.52 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761778 | CLOCKHOUSE LANE EAST | EGHAM | SURREY | Runnymede Borough Council | 510811826 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 273.3 | MR1 | N | T1 SECONDARY |  | 44396 | 44512 | 12.39 | 0 | 12.39 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 | 1.77 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761779 | TEN ACRE LANE | EGHAM | SURREY | Runnymede Borough Council | 510921398 | 8 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 90.41 | MR1 | N | T1 SECONDARY |  | 44396 | 44512 | 90.44 | 0 | 90.44 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | 12.92 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761779 | TEN ACRE LANE | EGHAM | SURREY | Runnymede Borough Council | 220001292175 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 0.97 | MR1 | N | T1 SECONDARY |  | 44396 | 44512 | 1.05 | 0 | 1.05 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | [20 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761382 | HEMWOOD ROAD | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510848431 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 182.97 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 182.95 | 0 | 182.95 | [7 empty] | 36.59 | 36.59 | 36.59 | 36.59 | 36.59 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761382 | HEMWOOD ROAD | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510848434 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 15 | 99.97 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 99.95 | 0 | 99.95 | [7 empty] | 19.99 | 19.99 | 19.99 | 19.99 | 19.99 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761382 | HEMWOOD ROAD | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220001431402 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 126.96 | MR1 | N | T1 SECONDARY |  | 44515 | 44547 | 126.95 | 0 | 126.95 | [7 empty] | 25.39 | 25.39 | 25.39 | 25.39 | 25.39 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761375 | DUNCANNON CRESCENT | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966795 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 98.74 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 98.74 | 98.74 | [14 empty] | 49.37 | 49.37 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761375 | DUNCANNON CRESCENT | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966796 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 104.75 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 104.76 | 104.76 | [14 empty] | 52.38 | 52.38 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761375 | DUNCANNON CRESCENT | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966797 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 11.13 | MR1 | N | T1 SECONDARY |  | 44565 | 44571 | 0 | 11.14 | 11.14 | [14 empty] | 5.57 | 5.57 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761376 | STROUD CLOSE | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510967402 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 18 | 109.84 | MR1 | N | T1 SECONDARY |  | 44572 | 44578 | 0 | 109.84 | 109.84 | [15 empty] | 54.92 | 54.92 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761377 | FRANKLYN CRESCENT | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220001424689 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 67.54 | MR1 | N | T1 SECONDARY |  | 44579 | 44580 | 0 | 67.54 | 67.54 | [16 empty] | 67.54 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761378 | BENNING CLOSE | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966635 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 67.52 | MR1 | N | T1 SECONDARY |  | 44581 | 44582 | 0 | 67.52 | 67.52 | [16 empty] | 67.52 | [10 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761379 | ROWLAND CLOSE | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510903865 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 110.09 | MR1 | N | T1 SECONDARY |  | 44585 | 44589 | 0 | 110.09 | 110.09 | [17 empty] | 110.09 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761380 | GILMAN CRESCENT | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510836986 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 81.46 | MR1 | N | T1 SECONDARY |  | 44592 | 44594 | 0 | 81.46 | 81.46 | [18 empty] | 81.46 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761381 | BRYER PLACE | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510966682 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 65.58 | MR1 | N | T1 SECONDARY |  | 44595 | 44596 | 0 | 65.58 | 65.58 | [18 empty] | 65.58 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222349 | WO-0761383 | FOOTPATH FROM TINKERS LANE TO HEMWOOD ROAD | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510848429 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 124.54 | MR1 | N | T1 SECONDARY |  | 44599 | 44603 | 0 | 124.54 | 124.54 | [19 empty] | 124.54 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222350 | WO-0761384 | HEMWOOD ROAD | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510848428 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 279 | 266.41 | MR1 | N | T1 PAST |  | 44606 | 44610 | 0 | 266.41 | 266.41 | [20 empty] | 266.41 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222350 | WO-0761384 | HEMWOOD ROAD | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 220001433827 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 88.07 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 88.07 | 88.07 | [20 empty] | 88.07 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222350 | WO-0761386 | ST LEONARDS HILL | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510915223 | 200 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 111.95 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 111.95 | 111.95 | [21 empty] | 111.95 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222350 | WO-0761385 | WILTON CRESCENT | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510954691 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 142 | 94.61 | MR1 | N | T1 PAST |  | 44620 | 44622 | 0 | 94.61 | 94.61 | [22 empty] | 94.61 |  |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222350 | WO-0761387 | FOOTPATH FROM HEMWOOD ROAD TOWARDS BENNING CLOSE | WINDSOR | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510848430 | 2 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 40.59 | MR2 | Y | T1 ENM CANDIDATE |  | 44623 | 44624 | 0 | 40.59 | 40.59 | [22 empty] | 40.59 |  |  |  |  | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761848 | BLENHEIM ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792945 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 66.97 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 66.98 | 66.98 | [23 empty] | 33.49 | 33.49 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761848 | BLENHEIM ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792946 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 95 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 95 | 95 | [23 empty] | 47.5 | 47.5 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761848 | BLENHEIM ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792950 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 130.42 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 130.42 | 130.42 | [23 empty] | 65.21 | 65.21 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761848 | BLENHEIM ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792951 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 155.42 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 155.42 | 155.42 | [23 empty] | 77.71 | 77.71 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761848 | BLENHEIM ROAD | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792954 | 8 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 7.16 | MR1 | N | T1 SECONDARY |  | 44627 | 44638 | 0 | 7.16 | 7.16 | [23 empty] | 3.58 | 3.58 |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761844 | FOOTPATH FROM BLENHEIM ROAD TO NUMBER 114 | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792942 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 16 | 74.81 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 74.82 | 74.82 | [25 empty] | 37.41 | 37.41 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | LDP Blank | TBA - Lon | IMGA222321 | WO-0761844 | FOOTPATH FROM BLENHEIM ROAD TO NUMBER 114 | MAIDENHEAD | WINDSOR AND MAIDENHEAD | Windsor & Maidenhead Royal Borough | 510792943 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 20 | 37.85 | MR1 | N | T1 SECONDARY |  | 44641 | 44652 | 0 | 37.86 | 37.86 | [25 empty] | 18.93 | 18.93 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | TBA - Lon | Natasha Barrett | SQS | TBA - Lon | IMGA222092 | WO-0760355 | HUGHES ROAD | HAYES | HILLINGDON | Hillingdon London Borough Council | 510950501 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 297.53 | MR1 | N | T1 SECONDARY |  | 44651 | 44651 | 0 | 297.53 | 297.53 | [26 empty] | 297.53 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Mario Gesner | Phil Walden | DHB Utilities | TBA - Lon | IMGA222228 | WO-0761778 | CLOCKHOUSE LANE EAST | EGHAM | SURREY | Runnymede Borough Council | 510811826 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 273.3 | MR1 | N | T1 SECONDARY |  | 44651 | 44651 | 0 | 273.3 | 273.3 | [26 empty] | 273.3 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765573 | TRINGHAM CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 510926970 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 19 | 120.26 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 120.25 | 0 | 120.25 |  | 24.05 | 24.05 | 24.05 | 24.05 | 24.05 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765573 | TRINGHAM CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 510926971 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 84.85 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 84.85 | 0 | 84.85 |  | 16.97 | 16.97 | 16.97 | 16.97 | 16.97 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765573 | TRINGHAM CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 510926972 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 209 | 180.4 | MR1 | N | T1 PAST |  | 44473 | 44505 | 180.4 | 0 | 180.4 |  | 36.08 | 36.08 | 36.08 | 36.08 | 36.08 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765573 | TRINGHAM CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 510926973 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 30.22 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 30.2 | 0 | 30.2 |  | 6.04 | 6.04 | 6.04 | 6.04 | 6.04 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765573 | TRINGHAM CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 606705540 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 3.19 | MR1 | N | T1 SECONDARY |  | 44473 | 44505 | 3.2 | 0 | 3.2 |  | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | [21 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765583 | FLOWER CRESCENT | OTTERSHAW | SURREY | Runnymede Borough Council | 510833028 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 179.51 | MR1 | N | T1 SECONDARY |  | 44508 | 44519 | 179.52 | 0 | 179.52 | [6 empty] | 89.76 | 89.76 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765585 | THE MAPLES FOOTPATH | OTTERSHAW | SURREY | Runnymede Borough Council | 510923601 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 16.45 | MR1 | N | T1 SECONDARY |  | 44522 | 44526 | 16.45 | 0 | 16.45 | [8 empty] | 16.45 | [18 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765584 | OTTER CLOSE | CHERTSEY | SURREY | Runnymede Borough Council | 510888084 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 53.88 | MR1 | N | T1 SECONDARY |  | 44529 | 44533 | 53.88 | 0 | 53.88 | [9 empty] | 53.88 | [17 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765574 | GUILDFORD ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 220001848633 | 6 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | 4"-5" | -1 | 7.73 | MR1 | N | T1 CONNECTED |  | 44536 | 44540 | 7.73 | 0 | 7.73 | [10 empty] | 7.73 | [16 empty] | ST LP 4"-5" | 4"-5" | LP | Non policy | T1 | ST | ST LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765575 | FOXHILLS ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510834268 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 99.08 | MR1 | N | T1 SECONDARY |  | 44543 | 44568 | 49.54 | 49.54 | 99.08 | [10 empty] | 24.77 | 24.77 |  |  | 24.77 | 24.77 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765575 | FOXHILLS ROAD | CHERTSEY | SURREY | Runnymede Borough Council | 510834269 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 163.12 | MR1 | N | T1 SECONDARY |  | 44543 | 44568 | 81.56 | 81.56 | 163.12 | [10 empty] | 40.78 | 40.78 |  |  | 40.78 | 40.78 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765576 | FOXHILLS CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 510834267 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 11 | 96.03 | MR1 | N | T1 SECONDARY |  | 44571 | 44575 | 0 | 96.03 | 96.03 | [15 empty] | 96.03 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765577 | CHAWORTH ROAD | OTTERSHAW | SURREY | Runnymede Borough Council | 510806464 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 134.56 | MR1 | N | T1 SECONDARY |  | 44578 | 44603 | 0 | 134.56 | 134.56 | [16 empty] | 33.64 | 33.64 | 33.64 | 33.64 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765577 | CHAWORTH ROAD | OTTERSHAW | SURREY | Runnymede Borough Council | 220001848630 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | -1 | 150.7 | MR1 | N | T1 SECONDARY |  | 44578 | 44603 | 0 | 150.72 | 150.72 | [16 empty] | 37.68 | 37.68 | 37.68 | 37.68 | [7 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765578 | CHERTSEY FOOTPATH 32/20 | OTTERSHAW | SURREY | Runnymede Borough Council | 510974999 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 84.93 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 84.93 | 84.93 | [20 empty] | 84.93 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765578 | CHERTSEY FOOTPATH 32/20 | OTTERSHAW | SURREY | Runnymede Borough Council | 606701864 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 0 | 8.64 | MR1 | N | T1 SECONDARY |  | 44606 | 44610 | 0 | 8.64 | 8.64 | [20 empty] | 8.64 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765579 | CHOBHAM CLOSE | OTTERSHAW | SURREY | Runnymede Borough Council | 510808558 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 40.87 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 40.87 | 40.87 | [21 empty] | 40.87 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765580 | CHOBHAM ROAD | OTTERSHAW | SURREY | Runnymede Borough Council | 510808593 | 5 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 2 | 195.39 | MR1 | N | T1 SECONDARY |  | 44620 | 44631 | 0 | 195.4 | 195.4 | [22 empty] | 97.7 | 97.7 |  |  |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765581 | THE MAPLES | OTTERSHAW | SURREY | Runnymede Borough Council | 510923600 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 54 | 143.41 | MR1 | N | T1 SECONDARY |  | 44634 | 44652 | 0 | 143.4 | 143.4 | [24 empty] | 47.8 | 47.8 | 47.8 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | LDP Blank | TERYY NORRIS | IMGA222441 | WO-0765581 | THE MAPLES | OTTERSHAW | SURREY | Runnymede Borough Council | 510923602 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 89.84 | MR1 | N | T1 SECONDARY |  | 44634 | 44652 | 0 | 89.85 | 89.85 | [24 empty] | 29.95 | 29.95 | 29.95 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765572 | WAVERLEY DRIVE | CHERTSEY | SURREY | Runnymede Borough Council | 510954635 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 122.05 | MR1 | N | T1 SECONDARY |  | 44459 | 44498 | 122.05 | 0 | 122.05 |  | 24.41 | 24.41 | 24.41 | 24.41 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765572 | WAVERLEY DRIVE | CHERTSEY | SURREY | Runnymede Borough Council | 510954636 | 8 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 212.63 | MR1 | N | T1 SECONDARY |  | 44459 | 44498 | 212.65 | 0 | 212.65 |  | 42.53 | 42.53 | 42.53 | 42.53 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765572 | WAVERLEY DRIVE | CHERTSEY | SURREY | Runnymede Borough Council | 510954637 | 6 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 348.45 | MR1 | N | T1 SECONDARY |  | 44459 | 44498 | 348.5 | 0 | 348.5 |  | 69.7 | 69.7 | 69.7 | 69.7 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765566 | BITTAMS LANE | CHERTSEY | SURREY | Runnymede Borough Council | 510792373 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 283.84 | MR1 | N | T1 SECONDARY |  | 44501 | 44554 | 283.84 | 0 | 283.84 | [5 empty] | 40.5486 | 40.5486 | 40.5486 | 40.5486 | 40.5486 | 40.5486 | 40.5486 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765566 | BITTAMS LANE | CHERTSEY | SURREY | Runnymede Borough Council | 510792374 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 391.52 | MR1 | N | T1 SECONDARY |  | 44501 | 44554 | 391.52 | 0 | 391.52 | [5 empty] | 55.9314 | 55.9314 | 55.9314 | 55.9314 | 55.9314 | 55.9314 | 55.9314 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765566 | BITTAMS LANE | CHERTSEY | SURREY | Runnymede Borough Council | 510792376 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 90.36 | MR1 | N | T1 SECONDARY |  | 44501 | 44554 | 90.4 | 0 | 90.4 | [5 empty] | 12.9143 | 12.9143 | 12.9143 | 12.9143 | 12.9143 | 12.9143 | 12.9143 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765566 | BITTAMS LANE | CHERTSEY | SURREY | Runnymede Borough Council | 606672594 | 6 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 3.27 | MR1 | N | T1 SECONDARY |  | 44501 | 44554 | 3.28 | 0 | 3.28 | [5 empty] | 0.46857 | 0.46857 | 0.46857 | 0.46857 | 0.46857 | 0.46857 | 0.46857 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765566 | BITTAMS LANE | CHERTSEY | SURREY | Runnymede Borough Council | 220001301934 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 55.76 | MR1 | N | T1 SECONDARY |  | 44501 | 44554 | 55.76 | 0 | 55.76 | [5 empty] | 7.9657 | 7.9657 | 7.9657 | 7.9657 | 7.9657 | 7.9657 | 7.9657 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765567 | CROSSLANDS | CHERTSEY | SURREY | Runnymede Borough Council | 220001266820 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 1.21 | MR1 | N | T1 SECONDARY |  | 44557 | 44561 | 0 | 1.21 | 1.21 | [15 empty] | 1.21 | [11 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765568 | FERNDALE AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510831462 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 261.68 | MR1 | N | T1 SECONDARY |  | 44564 | 44589 | 0 | 261.68 | 261.68 | [14 empty] | 65.42 | 65.42 | 65.42 | 65.42 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765568 | FERNDALE AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510831463 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 231.35 | MR1 | N | T1 SECONDARY |  | 44564 | 44589 | 0 | 231.36 | 231.36 | [14 empty] | 57.84 | 57.84 | 57.84 | 57.84 | [9 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765569 | HILLCREST AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510852121 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 246.54 | MR1 | N | T1 SECONDARY |  | 44592 | 44610 | 0 | 246.54 | 246.54 | [18 empty] | 82.18 | 82.18 | 82.18 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765569 | HILLCREST AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510852122 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 93.38 | MR1 | N | T1 SECONDARY |  | 44592 | 44610 | 0 | 93.39 | 93.39 | [18 empty] | 31.13 | 31.13 | 31.13 | [6 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765570 | LITTLE GREEN LANE | CHERTSEY | SURREY | Runnymede Borough Council | 510867398 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 42.29 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 42.29 | 42.29 | [21 empty] | 42.29 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765570 | LITTLE GREEN LANE | CHERTSEY | SURREY | Runnymede Borough Council | 510867399 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 111.16 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 111.16 | 111.16 | [21 empty] | 111.16 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765570 | LITTLE GREEN LANE | CHERTSEY | SURREY | Runnymede Borough Council | 606703950 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 5.66 | MR1 | N | T1 SECONDARY |  | 44613 | 44617 | 0 | 5.66 | 5.66 | [21 empty] | 5.66 | [5 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765571 | SANDALWOOD AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510908147 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 306.78 | MR1 | N | T1 SECONDARY |  | 44620 | 44645 | 0 | 306.8 | 306.8 | [22 empty] | 76.7 | 76.7 | 76.7 | 76.7 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Shane Compton | Ryan Smeaton | OMJ | THOMAS HARRISON | IMGA222442 | WO-0765571 | SANDALWOOD AVENUE | CHERTSEY | SURREY | Runnymede Borough Council | 510908148 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 230.23 | MR1 | N | T1 SECONDARY |  | 44620 | 44645 | 0 | 230.24 | 230.24 | [22 empty] | 57.56 | 57.56 | 57.56 | 57.56 |  | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222375 | WO-0759940 | BOWERDEAN ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510794351 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 29 | 569.4 | MR1 | N | T1 SECONDARY |  | 44452 | 44477 | 450.4 | 0 | 450.4 | 225.2 | 225.2 | [25 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765654 | CHALFONT ST GILES FOOTPATH 41 | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510784469 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 14 | 116.49 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 55.92 | 60.58 | 116.5 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 |  |  | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | 4.66 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765655 | CHERRY RISE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510806982 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 169.57 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 81.36 | 88.14 | 169.5 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 |  |  | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | 6.78 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765656 | CROMWELL CLOSE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510969599 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 78 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 37.44 | 40.56 | 78 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 |  |  | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | 3.12 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765657 | ELLWOOD RISE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510969612 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 152.6 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 73.2 | 79.3 | 152.5 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 |  |  | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | 6.1 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765657 | ELLWOOD RISE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510969613 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 68.89 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 33.12 | 35.88 | 69 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 |  |  | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | 2.76 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765658 | GORELANDS LANE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510839209 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 66 | 114.94 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 55.2 | 59.8 | 115 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 |  |  | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | 4.6 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765658 | GORELANDS LANE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510839211 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 92.54 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 44.4 | 48.1 | 92.5 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 |  |  | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | 3.7 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765659 | KINGS ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510860713 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 86.45 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 41.52 | 44.98 | 86.5 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 |  |  | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | 3.46 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765659 | KINGS ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510860714 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 7 | 732.95 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 351.84 | 381.16 | 733 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 |  |  | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | 29.32 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765660 | LONDON ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510868324 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 8 | 580.74 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 278.76 | 301.99 | 580.75 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 |  |  | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | 23.23 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765660 | LONDON ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510868325 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 61.98 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 29.76 | 32.24 | 62 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 |  |  | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | 2.48 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765660 | LONDON ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220000659923 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 64.63 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 31.08 | 33.67 | 64.75 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 |  |  | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | 2.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765661 | VACHE LANE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510883057 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 1 | 317.52 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 152.4 | 165.1 | 317.5 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 |  |  | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | 12.7 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765661 | VACHE LANE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510883060 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 85.53 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 41.04 | 44.46 | 85.5 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 |  |  | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | 3.42 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765661 | VACHE LANE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510929315 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 10 | 613.06 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 294.24 | 318.76 | 613 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 |  |  | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | 24.52 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765661 | VACHE LANE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 220000505642 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 22 | 2.78 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 1.32 | 1.43 | 2.75 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765662 | ORCHARD ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510887456 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 173.15 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 83.16 | 90.09 | 173.25 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 |  |  | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | 6.93 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765663 | OUTLOOK DRIVE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510911868 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 102.92 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 49.44 | 53.56 | 103 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 |  |  | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765664 | SILSDEN CRESCENT | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510911867 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 51.16 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 24.6 | 26.65 | 51.25 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 |  |  | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | 2.05 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765664 | SILSDEN CRESCENT | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 611252534 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 9 | 2.7 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 1.32 | 1.43 | 2.75 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 |  |  | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765665 | STYLECROFT ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510918577 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 366.72 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 176.04 | 190.71 | 366.75 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 |  |  | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | 14.67 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765665 | STYLECROFT ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510918578 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 548.49 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 263.28 | 285.22 | 548.5 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 |  |  | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | 21.94 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765665 | STYLECROFT ROAD | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510995643 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 139.83 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 67.08 | 72.67 | 139.75 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 |  |  | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | 5.59 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765666 | TURNERS WOOD DRIVE | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510927543 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 156.49 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 75.12 | 81.38 | 156.5 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 |  |  | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | 6.26 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765667 | VALENTINE WAY | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510969669 | 2 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 26.58 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 12.72 | 13.78 | 26.5 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 |  |  | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765667 | VALENTINE WAY | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510969670 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 180.86 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 86.76 | 93.99 | 180.75 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 |  |  | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | 7.23 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222444 | WO-0765667 | VALENTINE WAY | CHALFONT ST GILES | BUCKINGHAMSHIRE | Chiltern District Council (Lower) | 510969671 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 82.42 | MR1 | N | T1 SECONDARY |  | 44480 | 44652 | 39.6 | 42.9 | 82.5 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 |  |  | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222380 | WO-0761900 | REDSHOTS CLOSE | MARLOW | BUCKINGHAMSHIRE | Wycombe District Council | 510946729 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 100.49 | MR1 | N | T1 SECONDARY |  | 44494 | 44498 | 100.49 | 0 | 100.49 |  |  |  |  | 100.49 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Adam Madge | KLT | TOM ASHDOWN | IMGA222380 | WO-0761901 | BOBMORE LANE | MARLOW | BUCKINGHAMSHIRE | Wycombe District Council | 510793291 | 4 |  | T1 | Inch | CI | Open Cut | LP | Policy | T1Policy | 4"-5" | 43 | 107.6 | MR1 | N | T1 SECONDARY |  | 44494 | 44498 | 107.6 | 0 | 107.6 |  |  |  |  | 107.6 | [22 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | CI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760980 | GAYHURST ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510836320 | 6 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 77.77 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 68.8 | 0 | 68.8 |  | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | 8.6 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760980 | GAYHURST ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510836321 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 13 | 106.48 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 106.48 | 0 | 106.48 |  | 13.31 | 13.31 | 13.31 | 13.31 | 13.31 | 13.31 | 13.31 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760980 | GAYHURST ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510968824 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 4 | 73.96 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 74 | 0 | 74 |  | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | 9.25 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760980 | GAYHURST ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510968840 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 6 | 49.44 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 49.44 | 0 | 49.44 |  | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | 6.18 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760980 | GAYHURST ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 606430639 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 27.98 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 28 | 0 | 28 |  | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760981 | BARING ROAD |  |  | Buckinghamshire County Council | 510786741 | 6 |  | T1 | Inch | SI |  | LP | Policy | T1Policy | 4"-5" |  | 97 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | -154.08 | 0 | -154.08 |  | -19.26 | -19.26 | -19.26 | -19.26 | -19.26 | -19.26 | -19.26 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760981 | BARING ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510786740 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 120.64 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 120.48 | 0 | 120.48 |  | 15.06 | 15.06 | 15.06 | 15.06 | 15.06 | 15.06 | 15.06 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760981 | BARING ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510786741 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 3 | 154.8 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 154.64 | 0 | 154.64 |  | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222377 | WO-0760982 | CROFTWOOD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510968960 | 4 |  | T1 | Inch | SI | Open Cut | LP | Policy | T1Policy | 4"-5" | 5 | 93.03 | MR1 | N | T1 SECONDARY |  | 44452 | 44519 | 93.04 | 0 | 93.04 |  | 11.63 | 11.63 | 11.63 | 11.63 | 11.63 | 11.63 | 11.63 | [19 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | SI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222381 | WO-0760035 | CROMWELL GARDENS | MARLOW | BUCKINGHAMSHIRE | Wycombe District Council | 510817347 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 179 | 161.88 | MR1 | N | T1 PAST |  | 44473 | 44484 | 161.88 | 0 | 161.88 |  | 80.94 | 80.94 | [24 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222381 | WO-0764283 | CROMWELL ROAD | MARLOW | WYCOMBE | Wycombe District Council | 627086536 | 4 |  | T1 | Inch | DI |  | LP | Policy | T1Policy | 4"-5" | 38 | 82.87 | MR1 | N | T1 SECONDARY |  | 44487 | 44491 | 82.87 | 0 | 82.87 |  |  |  | 82.87 | [23 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | William Madge | LDP Blank | WARREN BROWN | IMGA222387 | WO-0760079 | DOWNLEY ROAD | NAPHILL | BUCKINGHAMSHIRE | Wycombe District Council | 510822587 | 4 |  | T1 | Inch | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 213 | 275.27 | MR1 | N | T1 PAST |  | 44522 | 44547 | 275 | 0 | 275 | [8 empty] | 68.75 | 68.75 | 68.75 | 68.75 | [15 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | WARREN BROWN | IMGA222369 | WO-0759772 | STIRLING ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 609692095 | 3 |  | T1 | Inch | ST | Open Cut | LP | Non policy | T1Non policy | <=3" | 5 | 26.97 | MR1 | N | T1 CONNECTED |  | 44565 | 44592 | 0 | 26.95 | 26.95 | [14 empty] | 5.39 | 5.39 | 5.39 | 5.39 | 5.39 | [8 empty] | ST LP <=3" | <=3" | LP | Non policy | T1 | ST | ST LP <=3"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | WARREN BROWN | IMGA222369 | WO-0759772 | STIRLING ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510844047 | 100 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 4"-5" | 12 | 56.73 | MR1 | N | T1 SECONDARY |  | 44565 | 44592 | 0 | 56.75 | 56.75 | [14 empty] | 11.35 | 11.35 | 11.35 | 11.35 | 11.35 | [8 empty] | CI/SI/DI LP 4"-5" | 4"-5" | LP | Policy | T1 | DI | CI/SI/DI LP 4"-5"
CMO West 2 | Tony Ingram 2 | Kerry Dolan | KLT | WARREN BROWN | IMGA222369 | WO-0759772 | STIRLING ROAD | HIGH WYCOMBE | BUCKINGHAMSHIRE | Wycombe District Council | 510844048 | 150 |  | T1 | mm | DI | Open Cut | LP | Policy | T1Policy | 6"-7" | 52 | 173.07 | MR1 | N | T1 PAST |  | 44565 | 44592 | 0 | 173.05 | 173.05 | [14 empty] | 34.61 | 34.61 | 34.61 | 34.61 | 34.61 | [8 empty] | CI/SIDI LP 6"-7" | 6"-7" | LP | Policy | T1 | DI | CI/SIDI LP 6"-7"
CMO West 2 | Tony Ingram 2 | William Madge | KLT | WARREN BROWN | IMGA222384 | WO-0760057 | DEDMERE ROAD | MARLOW | BUCKINGHAMSHIRE | Wycombe District Council | 510916922 | 12 |  | T2 | Inch | DI | Open Cut | LP | Policy | T2Policy | 10"-12" | 252 | 159.41 | MR2 | N | T2 PAST |  | 44593 | 44634 | 0 | 159.39 | 159.39 | [18 empty] | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 | 22.77 |  |  | T2A | 10"-12" | LP | Policy | T2 | DI | T2A
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Forecast Lookup
Material | Diameter | Pressure | Code1 | Tier | Policy /Non Policy | Category
CI | <=3" | LP | CI<=3" | T1 |  | CI/SI/DI LP <=3"
CI | 4"-5" | LP | CI4"-5" | T1 |  | CI/SI/DI LP 4"-5"
CI | 6"-7" | LP | CI6"-7" | T1 |  | CI/SI/DI LP 6"-7"
CI | 8" | LP | CI8" | T1 |  | CI/SI/DI LP 8"
CI | 8" | LP | CI8" | T1 |  | CI/SI/DI MP 8"
CI | <=3" | MP | CI<=3" | T1 |  | LMPS
CI | 4"-5" | MP | CI4"-5" | T1 |  | LMPS
CI | 6"-7" | MP | CI6"-7" | T1 |  | LMPS
CI | 8" | MP | CI8" | T1 |  | LMPS
CI | 8" | MP | CI8" | T1 |  | LMPS
SI | <=3" | LP | SI<=3" | T1 |  | CI/SI/DI LP <=3"
SI | 4"-5" | LP | SI4"-5" | T1 |  | CI/SI/DI LP 4"-5"
SI | 6"-7" | LP | SI6"-7" | T1 |  | CI/SI/DI LP 6"-7"
SI | 8" | LP | SI8" | T1 |  | CI/SI/DI LP 8"
SI | 8" | LP | SI8" | T1 |  | CI/SI/DI MP 8"
SI | <=3" | MP | SI<=3" | T1 |  | LMPS
SI | 4"-5" | MP | SI4"-5" | T1 |  | LMPS
SI | 6"-7" | MP | SI6"-7" | T1 |  | LMPS
SI | 8" | MP | SI8" | T1 |  | LMPS
SI | 8" | MP | SI8" | T1 |  | LMPS
ST | 2" | LP | ST2" | T1 |  | 2" ST
ST | <=3" | LP | ST<=3" | T1 |  | ST LP <=3"
ST | 4"-5" | LP | ST4"-5" | T1 |  | ST LP 4"-5"
ST | 6"-7" | LP | ST6"-7" | T1 |  | ST LP 6"-7"
ST | 8" | LP | ST8" | T1 |  | ST LP 8"
ST | 8" | MP | ST8" | T1 |  | LMPS
ST | 2" | MP | ST2" | T1 |  | LMPS
ST | <=3" | MP | ST<=3" | T1 |  | LMPS
ST | 4"-5" | MP | ST4"-5" | T1 |  | LMPS
ST | 6"-7" | MP | ST6"-7" | T1 |  | LMPS
ST | 8" | LP | ST8" | T1 |  | ST LP 8"
ST | 8" | MP | ST8" | T1 |  | LMPS
DI | <=3" | LP | DI<=3" | T1 |  | CI/SI/DI LP <=3"
DI | 4"-5" | LP | DI4"-5" | T1 |  | CI/SI/DI LP 4"-5"
DI | 6"-7" | LP | DI6"-7" | T1 |  | CI/SIDI LP 6"-7"
DI | 8" | LP | DI8" | T1 |  | CI/SI/DI LP 8"
DI | <=3" | MP | DI<=3" | T1 |  | LMPS
DI | 4-5" | MP | DI4-5" | T1 |  | LMPS
DI | 6-7" | MP | DI6-7" | T1 |  | LMPS
DI | 8" | MP | DI8" | T1 |  | LMPS
|  |  |  | T2 | Policy | T2A
|  |  |  | T2 | Non Policy | T2B
|  |  |  | T3 |  | T3

## Sheet1
W/C | Week | Month | Area | LDP | Banding | LDP Meterage | Banding Meterage | LDP Forecast | LDP Banding
2021-03-29 | 1 | Mar-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-04-05 | 2 | Apr-21 | West 1 | Terra Firma | CI/SI LP <=3" | 146 | 0
2021-04-12 | 3 | Apr-21 | West 1 | Terra Firma | CI/SI LP <=3" | 714.7 | 0
2021-04-19 | 4 | Apr-21 | West 1 | Terra Firma | CI/SI LP <=3" | 465 | 0
2021-04-26 | 5 | Apr-21 | West 1 | Terra Firma | CI/SI LP <=3" | 432 | 0
2021-05-03 | 6 | May-21 | West 1 | Terra Firma | CI/SI LP <=3" | 532 | 0
2021-05-10 | 7 | May-21 | West 1 | Terra Firma | CI/SI LP <=3" | 569 | 0
2021-05-17 | 8 | May-21 | West 1 | Terra Firma | CI/SI LP <=3" | 561 | 0
2021-05-24 | 9 | May-21 | West 1 | Terra Firma | CI/SI LP <=3" | 957 | 0
2021-05-31 | 10 | May-21 | West 1 | Terra Firma | CI/SI LP <=3" | 675 | 0
2021-06-07 | 11 | Jun-21 | West 1 | Terra Firma | CI/SI LP <=3" | 275.9 | 0
2021-06-14 | 12 | Jun-21 | West 1 | Terra Firma | CI/SI LP <=3" | 924.6 | 0
2021-06-21 | 13 | Jun-21 | West 1 | Terra Firma | CI/SI LP <=3" | 686.9 | 0
2021-06-28 | 14 | Jun-21 | West 1 | Terra Firma | CI/SI LP <=3" | 323.8 | 0
2021-07-05 | 15 | Jul-21 | West 1 | Terra Firma | CI/SI LP <=3" | 640 | 0
2021-07-12 | 16 | Jul-21 | West 1 | Terra Firma | CI/SI LP <=3" | 573 | 0
2021-07-19 | 17 | Jul-21 | West 1 | Terra Firma | CI/SI LP <=3" | 1454 | 0
2021-07-26 | 18 | Jul-21 | West 1 | Terra Firma | CI/SI LP <=3" | 667 | 0
2021-08-02 | 19 | Aug-21 | West 1 | Terra Firma | CI/SI LP <=3" | 364 | 0
2021-08-09 | 20 | Aug-21 | West 1 | Terra Firma | CI/SI LP <=3" | 414.3 | 0
2021-08-16 | 21 | Aug-21 | West 1 | Terra Firma | CI/SI LP <=3" | 802.5 | 0
2021-08-23 | 22 | Aug-21 | West 1 | Terra Firma | CI/SI LP <=3" | 543 | 0
2021-08-30 | 23 | Aug-21 | West 1 | Terra Firma | CI/SI LP <=3" | 339 | 0
2021-09-06 | 24 | Sep-21 | West 1 | Terra Firma | CI/SI LP <=3" | 964.6 | 0
2021-09-13 | 25 | Sep-21 | West 1 | Terra Firma | CI/SI LP <=3" | 573.8 | 0
2021-09-20 | 26 | Sep-21 | West 1 | Terra Firma | CI/SI LP <=3" | 1043.5 | 0
2021-09-27 | 27 | Sep-21 | West 1 | Terra Firma | CI/SI LP <=3" | 374 | 0
2021-10-04 | 28 | Oct-21 | West 1 | Terra Firma | CI/SI LP <=3" | 749.9 | 0
2021-10-11 | 29 | Oct-21 | West 1 | Terra Firma | CI/SI LP <=3" | 561.8 | 0
2021-10-18 | 30 | Oct-21 | West 1 | Terra Firma | CI/SI LP <=3" | 552.6 | 0
2021-10-25 | 31 | Oct-21 | West 1 | Terra Firma | CI/SI LP <=3" | 688.9 | 0
2021-11-01 | 32 | Nov-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-11-08 | 33 | Nov-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-11-15 | 34 | Nov-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-11-22 | 35 | Nov-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-11-29 | 36 | Nov-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-12-06 | 37 | Dec-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-12-13 | 38 | Dec-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-12-20 | 39 | Dec-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-12-27 | 40 | Dec-21 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-01-03 | 41 | Jan-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-01-10 | 42 | Jan-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-01-17 | 43 | Jan-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-01-24 | 44 | Jan-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-01-31 | 45 | Jan-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-02-07 | 46 | Feb-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-02-14 | 47 | Feb-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-02-21 | 48 | Feb-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-02-28 | 49 | Feb-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-03-07 | 50 | Mar-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-03-14 | 51 | Mar-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-03-21 | 52 | Mar-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2022-03-28 | 53 | Mar-22 | West 1 | Terra Firma | CI/SI LP <=3" | 0 | 0
2021-03-29 | 1 | Mar-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-04-05 | 2 | Apr-21 | West 2 | KLT | CI/SI LP 4"-5" | 480 | 0
2021-04-12 | 3 | Apr-21 | West 2 | KLT | CI/SI LP 4"-5" | 1013 | 0
2021-04-19 | 4 | Apr-21 | West 2 | KLT | CI/SI LP 4"-5" | 2578 | 0
2021-04-26 | 5 | Apr-21 | West 2 | KLT | CI/SI LP 4"-5" | 1428 | 0
2021-05-03 | 6 | May-21 | West 2 | KLT | CI/SI LP 4"-5" | 992 | 0
2021-05-10 | 7 | May-21 | West 2 | KLT | CI/SI LP 4"-5" | 1355 | 0
2021-05-17 | 8 | May-21 | West 2 | KLT | CI/SI LP 4"-5" | 1708 | 0
2021-05-24 | 9 | May-21 | West 2 | KLT | CI/SI LP 4"-5" | 2149 | 0
2021-05-31 | 10 | May-21 | West 2 | KLT | CI/SI LP 4"-5" | 1497 | 0
2021-06-07 | 11 | Jun-21 | West 2 | KLT | CI/SI LP 4"-5" | 1506 | 0
2021-06-14 | 12 | Jun-21 | West 2 | KLT | CI/SI LP 4"-5" | 780 | 0
2021-06-21 | 13 | Jun-21 | West 2 | KLT | CI/SI LP 4"-5" | 1199 | 0
2021-06-28 | 14 | Jun-21 | West 2 | KLT | CI/SI LP 4"-5" | 1270 | 0
2021-07-05 | 15 | Jul-21 | West 2 | KLT | CI/SI LP 4"-5" | 1640 | 0
2021-07-12 | 16 | Jul-21 | West 2 | KLT | CI/SI LP 4"-5" | 1323 | 0
2021-07-19 | 17 | Jul-21 | West 2 | KLT | CI/SI LP 4"-5" | 1488 | 0
2021-07-26 | 18 | Jul-21 | West 2 | KLT | CI/SI LP 4"-5" | 1285 | 0
2021-08-02 | 19 | Aug-21 | West 2 | KLT | CI/SI LP 4"-5" | 1470 | 0
2021-08-09 | 20 | Aug-21 | West 2 | KLT | CI/SI LP 4"-5" | 1356 | 0
2021-08-16 | 21 | Aug-21 | West 2 | KLT | CI/SI LP 4"-5" | 1316 | 0
2021-08-23 | 22 | Aug-21 | West 2 | KLT | CI/SI LP 4"-5" | 1250 | 0
2021-08-30 | 23 | Aug-21 | West 2 | KLT | CI/SI LP 4"-5" | 1188 | 0
2021-09-06 | 24 | Sep-21 | West 2 | KLT | CI/SI LP 4"-5" | 1301.8 | 0
2021-09-13 | 25 | Sep-21 | West 2 | KLT | CI/SI LP 4"-5" | 893 | 0
2021-09-20 | 26 | Sep-21 | West 2 | KLT | CI/SI LP 4"-5" | 2305.4 | 0
2021-09-27 | 27 | Sep-21 | West 2 | KLT | CI/SI LP 4"-5" | 1408.1 | 0
2021-10-04 | 28 | Oct-21 | West 2 | KLT | CI/SI LP 4"-5" | 1167.5 | 0
2021-10-11 | 29 | Oct-21 | West 2 | KLT | CI/SI LP 4"-5" | 1808 | 0
2021-10-18 | 30 | Oct-21 | West 2 | KLT | CI/SI LP 4"-5" | 855 | 0
2021-10-25 | 31 | Oct-21 | West 2 | KLT | CI/SI LP 4"-5" | 1388.1 | 0
2021-11-01 | 32 | Nov-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-11-08 | 33 | Nov-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-11-15 | 34 | Nov-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-11-22 | 35 | Nov-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-11-29 | 36 | Nov-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-12-06 | 37 | Dec-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-12-13 | 38 | Dec-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-12-20 | 39 | Dec-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-12-27 | 40 | Dec-21 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-01-03 | 41 | Jan-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-01-10 | 42 | Jan-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-01-17 | 43 | Jan-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-01-24 | 44 | Jan-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-01-31 | 45 | Jan-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-02-07 | 46 | Feb-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-02-14 | 47 | Feb-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-02-21 | 48 | Feb-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-02-28 | 49 | Feb-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-03-07 | 50 | Mar-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-03-14 | 51 | Mar-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-03-21 | 52 | Mar-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2022-03-28 | 53 | Mar-22 | West 2 | KLT | CI/SI LP 4"-5" | 0 | 0
2021-03-29 | 1 | Mar-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-04-05 | 2 | Apr-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-04-12 | 3 | Apr-21 | East 1 | Forefront | CI/SI LP 6"-7" | 554 | 0
2021-04-19 | 4 | Apr-21 | East 1 | Forefront | CI/SI LP 6"-7" | 1232.1 | 0
2021-04-26 | 5 | Apr-21 | East 1 | Forefront | CI/SI LP 6"-7" | 859.5 | 0
2021-05-03 | 6 | May-21 | East 1 | Forefront | CI/SI LP 6"-7" | 422.2 | 0
2021-05-10 | 7 | May-21 | East 1 | Forefront | CI/SI LP 6"-7" | 581.5 | 0
2021-05-17 | 8 | May-21 | East 1 | Forefront | CI/SI LP 6"-7" | 356 | 0
2021-05-24 | 9 | May-21 | East 1 | Forefront | CI/SI LP 6"-7" | 1074.8 | 0
2021-05-31 | 10 | May-21 | East 1 | Forefront | CI/SI LP 6"-7" | 144.9 | 0
2021-06-07 | 11 | Jun-21 | East 1 | Forefront | CI/SI LP 6"-7" | 744.3 | 0
2021-06-14 | 12 | Jun-21 | East 1 | Forefront | CI/SI LP 6"-7" | 619 | 0
2021-06-21 | 13 | Jun-21 | East 1 | Forefront | CI/SI LP 6"-7" | 412 | 0
2021-06-28 | 14 | Jun-21 | East 1 | Forefront | CI/SI LP 6"-7" | 535 | 0
2021-07-05 | 15 | Jul-21 | East 1 | Forefront | CI/SI LP 6"-7" | 678.8 | 0
2021-07-12 | 16 | Jul-21 | East 1 | Forefront | CI/SI LP 6"-7" | 472.8 | 0
2021-07-19 | 17 | Jul-21 | East 1 | Forefront | CI/SI LP 6"-7" | 551 | 0
2021-07-26 | 18 | Jul-21 | East 1 | Forefront | CI/SI LP 6"-7" | 860 | 0
2021-08-02 | 19 | Aug-21 | East 1 | Forefront | CI/SI LP 6"-7" | 354 | 0
2021-08-09 | 20 | Aug-21 | East 1 | Forefront | CI/SI LP 6"-7" | 236 | 0
2021-08-16 | 21 | Aug-21 | East 1 | Forefront | CI/SI LP 6"-7" | 194 | 0
2021-08-23 | 22 | Aug-21 | East 1 | Forefront | CI/SI LP 6"-7" | 539 | 0
2021-08-30 | 23 | Aug-21 | East 1 | Forefront | CI/SI LP 6"-7" | 857.9 | 0
2021-09-06 | 24 | Sep-21 | East 1 | Forefront | CI/SI LP 6"-7" | 524.5 | 0
2021-09-13 | 25 | Sep-21 | East 1 | Forefront | CI/SI LP 6"-7" | 425.4 | 0
2021-09-20 | 26 | Sep-21 | East 1 | Forefront | CI/SI LP 6"-7" | 447 | 0
2021-09-27 | 27 | Sep-21 | East 1 | Forefront | CI/SI LP 6"-7" | 180.2 | 0
2021-10-04 | 28 | Oct-21 | East 1 | Forefront | CI/SI LP 6"-7" | 162.6 | 0
2021-10-11 | 29 | Oct-21 | East 1 | Forefront | CI/SI LP 6"-7" | 253 | 0
2021-10-18 | 30 | Oct-21 | East 1 | Forefront | CI/SI LP 6"-7" | 163 | 0
2021-10-25 | 31 | Oct-21 | East 1 | Forefront | CI/SI LP 6"-7" | 144.5 | 0
2021-11-01 | 32 | Nov-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-11-08 | 33 | Nov-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-11-15 | 34 | Nov-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-11-22 | 35 | Nov-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-11-29 | 36 | Nov-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-12-06 | 37 | Dec-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-12-13 | 38 | Dec-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-12-20 | 39 | Dec-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-12-27 | 40 | Dec-21 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-01-03 | 41 | Jan-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-01-10 | 42 | Jan-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-01-17 | 43 | Jan-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-01-24 | 44 | Jan-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-01-31 | 45 | Jan-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-02-07 | 46 | Feb-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-02-14 | 47 | Feb-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-02-21 | 48 | Feb-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-02-28 | 49 | Feb-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-03-07 | 50 | Mar-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-03-14 | 51 | Mar-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-03-21 | 52 | Mar-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2022-03-28 | 53 | Mar-22 | East 1 | Forefront | CI/SI LP 6"-7" | 0 | 0
2021-03-29 | 1 | Mar-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-04-05 | 2 | Apr-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-04-12 | 3 | Apr-21 | East 2 | DPF | CI/SI LP 8" | 325 | 0
2021-04-19 | 4 | Apr-21 | East 2 | DPF | CI/SI LP 8" | 338 | 0
2021-04-26 | 5 | Apr-21 | East 2 | DPF | CI/SI LP 8" | 522.5 | 0
2021-05-03 | 6 | May-21 | East 2 | DPF | CI/SI LP 8" | 194 | 0
2021-05-10 | 7 | May-21 | East 2 | DPF | CI/SI LP 8" | 534.8 | 0
2021-05-17 | 8 | May-21 | East 2 | DPF | CI/SI LP 8" | 268 | 0
2021-05-24 | 9 | May-21 | East 2 | DPF | CI/SI LP 8" | 170 | 0
2021-05-31 | 10 | May-21 | East 2 | DPF | CI/SI LP 8" | 150 | 0
2021-06-07 | 11 | Jun-21 | East 2 | DPF | CI/SI LP 8" | 370 | 0
2021-06-14 | 12 | Jun-21 | East 2 | DPF | CI/SI LP 8" | 620.3 | 0
2021-06-21 | 13 | Jun-21 | East 2 | DPF | CI/SI LP 8" | 275.8 | 0
2021-06-28 | 14 | Jun-21 | East 2 | DPF | CI/SI LP 8" | 472.5 | 0
2021-07-05 | 15 | Jul-21 | East 2 | DPF | CI/SI LP 8" | 354 | 0
2021-07-12 | 16 | Jul-21 | East 2 | DPF | CI/SI LP 8" | 434 | 0
2021-07-19 | 17 | Jul-21 | East 2 | DPF | CI/SI LP 8" | 158 | 0
2021-07-26 | 18 | Jul-21 | East 2 | DPF | CI/SI LP 8" | 677 | 0
2021-08-02 | 19 | Aug-21 | East 2 | DPF | CI/SI LP 8" | 579 | 0
2021-08-09 | 20 | Aug-21 | East 2 | DPF | CI/SI LP 8" | 262 | 0
2021-08-16 | 21 | Aug-21 | East 2 | DPF | CI/SI LP 8" | 362 | 0
2021-08-23 | 22 | Aug-21 | East 2 | DPF | CI/SI LP 8" | 625.7 | 0
2021-08-30 | 23 | Aug-21 | East 2 | DPF | CI/SI LP 8" | 235 | 0
2021-09-06 | 24 | Sep-21 | East 2 | DPF | CI/SI LP 8" | 551 | 0
2021-09-13 | 25 | Sep-21 | East 2 | DPF | CI/SI LP 8" | 156 | 0
2021-09-20 | 26 | Sep-21 | East 2 | DPF | CI/SI LP 8" | 473.2 | 0
2021-09-27 | 27 | Sep-21 | East 2 | DPF | CI/SI LP 8" | 338 | 0
2021-10-04 | 28 | Oct-21 | East 2 | DPF | CI/SI LP 8" | 160 | 0
2021-10-11 | 29 | Oct-21 | East 2 | DPF | CI/SI LP 8" | 287 | 0
2021-10-18 | 30 | Oct-21 | East 2 | DPF | CI/SI LP 8" | 159 | 0
2021-10-25 | 31 | Oct-21 | East 2 | DPF | CI/SI LP 8" | 276 | 0
2021-11-01 | 32 | Nov-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-11-08 | 33 | Nov-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-11-15 | 34 | Nov-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-11-22 | 35 | Nov-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-11-29 | 36 | Nov-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-12-06 | 37 | Dec-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-12-13 | 38 | Dec-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-12-20 | 39 | Dec-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-12-27 | 40 | Dec-21 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-01-03 | 41 | Jan-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-01-10 | 42 | Jan-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-01-17 | 43 | Jan-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-01-24 | 44 | Jan-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-01-31 | 45 | Jan-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-02-07 | 46 | Feb-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-02-14 | 47 | Feb-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-02-21 | 48 | Feb-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-02-28 | 49 | Feb-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-03-07 | 50 | Mar-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-03-14 | 51 | Mar-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-03-21 | 52 | Mar-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2022-03-28 | 53 | Mar-22 | East 2 | DPF | CI/SI LP 8" | 0 | 0
2021-03-29 | 1 | Mar-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-04-05 | 2 | Apr-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-04-12 | 3 | Apr-21 |  | OMJ | DI LP 4"-5" | 484 | 0
2021-04-19 | 4 | Apr-21 |  | OMJ | DI LP 4"-5" | 610 | 0
2021-04-26 | 5 | Apr-21 |  | OMJ | DI LP 4"-5" | 340 | 0
2021-05-03 | 6 | May-21 |  | OMJ | DI LP 4"-5" | 631 | 0
2021-05-10 | 7 | May-21 |  | OMJ | DI LP 4"-5" | 491 | 0
2021-05-17 | 8 | May-21 |  | OMJ | DI LP 4"-5" | 424 | 0
2021-05-24 | 9 | May-21 |  | OMJ | DI LP 4"-5" | 391 | 0
2021-05-31 | 10 | May-21 |  | OMJ | DI LP 4"-5" | 309 | 0
2021-06-07 | 11 | Jun-21 |  | OMJ | DI LP 4"-5" | 684 | 0
2021-06-14 | 12 | Jun-21 |  | OMJ | DI LP 4"-5" | 692 | 0
2021-06-21 | 13 | Jun-21 |  | OMJ | DI LP 4"-5" | 571 | 0
2021-06-28 | 14 | Jun-21 |  | OMJ | DI LP 4"-5" | 401 | 0
2021-07-05 | 15 | Jul-21 |  | OMJ | DI LP 4"-5" | 613 | 0
2021-07-12 | 16 | Jul-21 |  | OMJ | DI LP 4"-5" | 779 | 0
2021-07-19 | 17 | Jul-21 |  | OMJ | DI LP 4"-5" | 334 | 0
2021-07-26 | 18 | Jul-21 |  | OMJ | DI LP 4"-5" | 685 | 0
2021-08-02 | 19 | Aug-21 |  | OMJ | DI LP 4"-5" | 459 | 0
2021-08-09 | 20 | Aug-21 |  | OMJ | DI LP 4"-5" | 255 | 0
2021-08-16 | 21 | Aug-21 |  | OMJ | DI LP 4"-5" | 424 | 0
2021-08-23 | 22 | Aug-21 |  | OMJ | DI LP 4"-5" | 533 | 0
2021-08-30 | 23 | Aug-21 |  | OMJ | DI LP 4"-5" | 440 | 0
2021-09-06 | 24 | Sep-21 |  | OMJ | DI LP 4"-5" | 333.7 | 0
2021-09-13 | 25 | Sep-21 |  | OMJ | DI LP 4"-5" | 675 | 0
2021-09-20 | 26 | Sep-21 |  | OMJ | DI LP 4"-5" | 601 | 0
2021-09-27 | 27 | Sep-21 |  | OMJ | DI LP 4"-5" | 264 | 0
2021-10-04 | 28 | Oct-21 |  | OMJ | DI LP 4"-5" | 393 | 0
2021-10-11 | 29 | Oct-21 |  | OMJ | DI LP 4"-5" | 553 | 0
2021-10-18 | 30 | Oct-21 |  | OMJ | DI LP 4"-5" | 450 | 0
2021-10-25 | 31 | Oct-21 |  | OMJ | DI LP 4"-5" | 803 | 0
2021-11-01 | 32 | Nov-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-11-08 | 33 | Nov-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-11-15 | 34 | Nov-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-11-22 | 35 | Nov-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-11-29 | 36 | Nov-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-12-06 | 37 | Dec-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-12-13 | 38 | Dec-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-12-20 | 39 | Dec-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-12-27 | 40 | Dec-21 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-01-03 | 41 | Jan-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-01-10 | 42 | Jan-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-01-17 | 43 | Jan-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-01-24 | 44 | Jan-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-01-31 | 45 | Jan-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-02-07 | 46 | Feb-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-02-14 | 47 | Feb-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-02-21 | 48 | Feb-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-02-28 | 49 | Feb-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-03-07 | 50 | Mar-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-03-14 | 51 | Mar-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-03-21 | 52 | Mar-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2022-03-28 | 53 | Mar-22 |  | OMJ | DI LP 4"-5" | 0 | 0
2021-03-29 | 1 | Mar-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-04-05 | 2 | Apr-21 |  | DHB UTILITIES | DI LP 6"-7" | 410 | 0
2021-04-12 | 3 | Apr-21 |  | DHB UTILITIES | DI LP 6"-7" | 1092 | 0
2021-04-19 | 4 | Apr-21 |  | DHB UTILITIES | DI LP 6"-7" | 1121 | 0
2021-04-26 | 5 | Apr-21 |  | DHB UTILITIES | DI LP 6"-7" | 896 | 0
2021-05-03 | 6 | May-21 |  | DHB UTILITIES | DI LP 6"-7" | 1046 | 0
2021-05-10 | 7 | May-21 |  | DHB UTILITIES | DI LP 6"-7" | 883 | 0
2021-05-17 | 8 | May-21 |  | DHB UTILITIES | DI LP 6"-7" | 1505 | 0
2021-05-24 | 9 | May-21 |  | DHB UTILITIES | DI LP 6"-7" | 927 | 0
2021-05-31 | 10 | May-21 |  | DHB UTILITIES | DI LP 6"-7" | 1192 | 0
2021-06-07 | 11 | Jun-21 |  | DHB UTILITIES | DI LP 6"-7" | 1401 | 0
2021-06-14 | 12 | Jun-21 |  | DHB UTILITIES | DI LP 6"-7" | 885 | 0
2021-06-21 | 13 | Jun-21 |  | DHB UTILITIES | DI LP 6"-7" | 698 | 0
2021-06-28 | 14 | Jun-21 |  | DHB UTILITIES | DI LP 6"-7" | 1243 | 0
2021-07-05 | 15 | Jul-21 |  | DHB UTILITIES | DI LP 6"-7" | 1341 | 0
2021-07-12 | 16 | Jul-21 |  | DHB UTILITIES | DI LP 6"-7" | 918 | 0
2021-07-19 | 17 | Jul-21 |  | DHB UTILITIES | DI LP 6"-7" | 956 | 0
2021-07-26 | 18 | Jul-21 |  | DHB UTILITIES | DI LP 6"-7" | 697 | 0
2021-08-02 | 19 | Aug-21 |  | DHB UTILITIES | DI LP 6"-7" | 737 | 0
2021-08-09 | 20 | Aug-21 |  | DHB UTILITIES | DI LP 6"-7" | 826 | 0
2021-08-16 | 21 | Aug-21 |  | DHB UTILITIES | DI LP 6"-7" | 809 | 0
2021-08-23 | 22 | Aug-21 |  | DHB UTILITIES | DI LP 6"-7" | 893 | 0
2021-08-30 | 23 | Aug-21 |  | DHB UTILITIES | DI LP 6"-7" | 674 | 0
2021-09-06 | 24 | Sep-21 |  | DHB UTILITIES | DI LP 6"-7" | 980.3 | 0
2021-09-13 | 25 | Sep-21 |  | DHB UTILITIES | DI LP 6"-7" | 1124 | 0
2021-09-20 | 26 | Sep-21 |  | DHB UTILITIES | DI LP 6"-7" | 694 | 0
2021-09-27 | 27 | Sep-21 |  | DHB UTILITIES | DI LP 6"-7" | 766 | 0
2021-10-04 | 28 | Oct-21 |  | DHB UTILITIES | DI LP 6"-7" | 1051 | 0
2021-10-11 | 29 | Oct-21 |  | DHB UTILITIES | DI LP 6"-7" | 409 | 0
2021-10-18 | 30 | Oct-21 |  | DHB UTILITIES | DI LP 6"-7" | 1159 | 0
2021-10-25 | 31 | Oct-21 |  | DHB UTILITIES | DI LP 6"-7" | 1003 | 0
2021-11-01 | 32 | Nov-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-11-08 | 33 | Nov-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-11-15 | 34 | Nov-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-11-22 | 35 | Nov-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-11-29 | 36 | Nov-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-12-06 | 37 | Dec-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-12-13 | 38 | Dec-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-12-20 | 39 | Dec-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-12-27 | 40 | Dec-21 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-01-03 | 41 | Jan-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-01-10 | 42 | Jan-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-01-17 | 43 | Jan-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-01-24 | 44 | Jan-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-01-31 | 45 | Jan-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-02-07 | 46 | Feb-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-02-14 | 47 | Feb-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-02-21 | 48 | Feb-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-02-28 | 49 | Feb-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-03-07 | 50 | Mar-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-03-14 | 51 | Mar-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-03-21 | 52 | Mar-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2022-03-28 | 53 | Mar-22 |  | DHB UTILITIES | DI LP 6"-7" | 0 | 0
2021-03-29 | 1 | Mar-21 |  | JDT | DI LP 8" | 0 | 0
2021-04-05 | 2 | Apr-21 |  | JDT | DI LP 8" | 0 | 0
2021-04-12 | 3 | Apr-21 |  | JDT | DI LP 8" | 475 | 0
2021-04-19 | 4 | Apr-21 |  | JDT | DI LP 8" | 553 | 0
2021-04-26 | 5 | Apr-21 |  | JDT | DI LP 8" | 463 | 0
2021-05-03 | 6 | May-21 |  | JDT | DI LP 8" | 693.5 | 0
2021-05-10 | 7 | May-21 |  | JDT | DI LP 8" | 827 | 0
2021-05-17 | 8 | May-21 |  | JDT | DI LP 8" | 672.5 | 0
2021-05-24 | 9 | May-21 |  | JDT | DI LP 8" | 414 | 0
2021-05-31 | 10 | May-21 |  | JDT | DI LP 8" | 1128 | 0
2021-06-07 | 11 | Jun-21 |  | JDT | DI LP 8" | 562 | 0
2021-06-14 | 12 | Jun-21 |  | JDT | DI LP 8" | 641 | 0
2021-06-21 | 13 | Jun-21 |  | JDT | DI LP 8" | 426 | 0
2021-06-28 | 14 | Jun-21 |  | JDT | DI LP 8" | 869.5 | 0
2021-07-05 | 15 | Jul-21 |  | JDT | DI LP 8" | 589.3 | 0
2021-07-12 | 16 | Jul-21 |  | JDT | DI LP 8" | 312.5 | 0
2021-07-19 | 17 | Jul-21 |  | JDT | DI LP 8" | 690 | 0
2021-07-26 | 18 | Jul-21 |  | JDT | DI LP 8" | 559.8 | 0
2021-08-02 | 19 | Aug-21 |  | JDT | DI LP 8" | 858 | 0
2021-08-09 | 20 | Aug-21 |  | JDT | DI LP 8" | 493 | 0
2021-08-16 | 21 | Aug-21 |  | JDT | DI LP 8" | 470 | 0
2021-08-23 | 22 | Aug-21 |  | JDT | DI LP 8" | 687.5 | 0
2021-08-30 | 23 | Aug-21 |  | JDT | DI LP 8" | 476.7 | 0
2021-09-06 | 24 | Sep-21 |  | JDT | DI LP 8" | 814.2 | 0
2021-09-13 | 25 | Sep-21 |  | JDT | DI LP 8" | 1319.7 | 0
2021-09-20 | 26 | Sep-21 |  | JDT | DI LP 8" | 844.7 | 0
2021-09-27 | 27 | Sep-21 |  | JDT | DI LP 8" | 760.2 | 0
2021-10-04 | 28 | Oct-21 |  | JDT | DI LP 8" | 1018 | 0
2021-10-11 | 29 | Oct-21 |  | JDT | DI LP 8" | 1328.7 | 0
2021-10-18 | 30 | Oct-21 |  | JDT | DI LP 8" | 1212.5 | 0
2021-10-25 | 31 | Oct-21 |  | JDT | DI LP 8" | 913 | 0
2021-11-01 | 32 | Nov-21 |  | JDT | DI LP 8" | 0 | 0
2021-11-08 | 33 | Nov-21 |  | JDT | DI LP 8" | 0 | 0
2021-11-15 | 34 | Nov-21 |  | JDT | DI LP 8" | 0 | 0
2021-11-22 | 35 | Nov-21 |  | JDT | DI LP 8" | 0 | 0
2021-11-29 | 36 | Nov-21 |  | JDT | DI LP 8" | 0 | 0
2021-12-06 | 37 | Dec-21 |  | JDT | DI LP 8" | 0 | 0
2021-12-13 | 38 | Dec-21 |  | JDT | DI LP 8" | 0 | 0
2021-12-20 | 39 | Dec-21 |  | JDT | DI LP 8" | 0 | 0
2021-12-27 | 40 | Dec-21 |  | JDT | DI LP 8" | 0 | 0
2022-01-03 | 41 | Jan-22 |  | JDT | DI LP 8" | 0 | 0
2022-01-10 | 42 | Jan-22 |  | JDT | DI LP 8" | 0 | 0
2022-01-17 | 43 | Jan-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | CI/SI LP <=3"
2022-01-24 | 44 | Jan-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | CI/SI LP 4"-5"
2022-01-31 | 45 | Jan-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | CI/SI LP 6"-7"
2022-02-07 | 46 | Feb-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | CI/SI LP 8"
2022-02-14 | 47 | Feb-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | CI/SI MP 8"
2022-02-21 | 48 | Feb-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | ST LP <=3"
2022-02-28 | 49 | Feb-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | ST LP 4"-5"
2022-03-07 | 50 | Mar-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | ST LP 6"-7"
2022-03-14 | 51 | Mar-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | ST LP 8"
2022-03-21 | 52 | Mar-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | ST MP 8"
2022-03-28 | 53 | Mar-22 |  | JDT | DI LP 8" | 0 | 0 |  |  | DI LP <=3"
2021-03-29 | 1 | Mar-21 |  | MURRAY | T2/3 | 0 | 0 |  |  | DI LP 4"-5"
2021-04-05 | 2 | Apr-21 |  | MURRAY | T2/3 | 358 | 0 |  |  | DI LP 6"-7"
2021-04-12 | 3 | Apr-21 |  | MURRAY | T2/3 | 416 | 0 |  |  | DI LP 8"
2021-04-19 | 4 | Apr-21 |  | MURRAY | T2/3 | 454 | 0 |  |  | T2/3
2021-04-26 | 5 | Apr-21 |  | MURRAY | T2/3 | 297 | 0 |  |  | 2" ST
2021-05-03 | 6 | May-21 |  | MURRAY | T2/3 | 648 | 0
2021-05-10 | 7 | May-21 |  | MURRAY | T2/3 | 613.9 | 0
2021-05-17 | 8 | May-21 |  | MURRAY | T2/3 | 251 | 0
2021-05-24 | 9 | May-21 |  | MURRAY | T2/3 | 442 | 0
2021-05-31 | 10 | May-21 |  | MURRAY | T2/3 | 216 | 0
2021-06-07 | 11 | Jun-21 |  | MURRAY | T2/3 | 444 | 0
2021-06-14 | 12 | Jun-21 |  | MURRAY | T2/3 | 350 | 0
2021-06-21 | 13 | Jun-21 |  | MURRAY | T2/3 | 376 | 0
2021-06-28 | 14 | Jun-21 |  | MURRAY | T2/3 | 530 | 0
2021-07-05 | 15 | Jul-21 |  | MURRAY | T2/3 | 397 | 0
2021-07-12 | 16 | Jul-21 |  | MURRAY | T2/3 | 430 | 0
2021-07-19 | 17 | Jul-21 |  | MURRAY | T2/3 | 233.7 | 0
2021-07-26 | 18 | Jul-21 |  | MURRAY | T2/3 | 658 | 0
2021-08-02 | 19 | Aug-21 |  | MURRAY | T2/3 | 724 | 0
2021-08-09 | 20 | Aug-21 |  | MURRAY | T2/3 | 395 | 0
2021-08-16 | 21 | Aug-21 |  | MURRAY | T2/3 | 171 | 0
2021-08-23 | 22 | Aug-21 |  | MURRAY | T2/3 | 326 | 0
2021-08-30 | 23 | Aug-21 |  | MURRAY | T2/3 | 347 | 0
2021-09-06 | 24 | Sep-21 |  | MURRAY | T2/3 | 384 | 0
2021-09-13 | 25 | Sep-21 |  | MURRAY | T2/3 | 516 | 0
2021-09-20 | 26 | Sep-21 |  | MURRAY | T2/3 | 466.8 | 0
2021-09-27 | 27 | Sep-21 |  | MURRAY | T2/3 | 255.2 | 0
2021-10-04 | 28 | Oct-21 |  | MURRAY | T2/3 | 811.1 | 0
2021-10-11 | 29 | Oct-21 |  | MURRAY | T2/3 | 1104 | 0
2021-10-18 | 30 | Oct-21 |  | MURRAY | T2/3 | 739.1 | 0
2021-10-25 | 31 | Oct-21 |  | MURRAY | T2/3 | 880 | 0
2021-11-01 | 32 | Nov-21 |  | MURRAY | T2/3 | 0 | 0
2021-11-08 | 33 | Nov-21 |  | MURRAY | T2/3 | 0 | 0
2021-11-15 | 34 | Nov-21 |  | MURRAY | T2/3 | 0 | 0
2021-11-22 | 35 | Nov-21 |  | MURRAY | T2/3 | 0 | 0
2021-11-29 | 36 | Nov-21 |  | MURRAY | T2/3 | 0 | 0
2021-12-06 | 37 | Dec-21 |  | MURRAY | T2/3 | 0 | 0
2021-12-13 | 38 | Dec-21 |  | MURRAY | T2/3 | 0 | 0
2021-12-20 | 39 | Dec-21 |  | MURRAY | T2/3 | 0 | 0
2021-12-27 | 40 | Dec-21 |  | MURRAY | T2/3 | 0 | 0
2022-01-03 | 41 | Jan-22 |  | MURRAY | T2/3 | 0 | 0
2022-01-10 | 42 | Jan-22 |  | MURRAY | T2/3 | 0 | 0
2022-01-17 | 43 | Jan-22 |  | MURRAY | T2/3 | 0 | 0
2022-01-24 | 44 | Jan-22 |  | MURRAY | T2/3 | 0 | 0
2022-01-31 | 45 | Jan-22 |  | MURRAY | T2/3 | 0 | 0
2022-02-07 | 46 | Feb-22 |  | MURRAY | T2/3 | 0 | 0
2022-02-14 | 47 | Feb-22 |  | MURRAY | T2/3 | 0 | 0
2022-02-21 | 48 | Feb-22 |  | MURRAY | T2/3 | 0 | 0
2022-02-28 | 49 | Feb-22 |  | MURRAY | T2/3 | 0 | 0
2022-03-07 | 50 | Mar-22 |  | MURRAY | T2/3 | 0 | 0
2022-03-14 | 51 | Mar-22 |  | MURRAY | T2/3 | 0 | 0
2022-03-21 | 52 | Mar-22 |  | MURRAY | T2/3 | 0 | 0
2022-03-28 | 53 | Mar-22 |  | MURRAY | T2/3 | 0 | 0
2021-03-29 | 1 | Mar-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-04-05 | 2 | Apr-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-04-12 | 3 | Apr-21 |  | DIRECT MOLE | 2" ST | 320 | 0
2021-04-19 | 4 | Apr-21 |  | DIRECT MOLE | 2" ST | 50 | 68
2021-04-26 | 5 | Apr-21 |  | DIRECT MOLE | 2" ST | 260 | 49
2021-05-03 | 6 | May-21 |  | DIRECT MOLE | 2" ST | 367 | 48.3
2021-05-10 | 7 | May-21 |  | DIRECT MOLE | 2" ST | 348 | 0
2021-05-17 | 8 | May-21 |  | DIRECT MOLE | 2" ST | 217 | 30
2021-05-24 | 9 | May-21 |  | DIRECT MOLE | 2" ST | 408 | 0
2021-05-31 | 10 | May-21 |  | DIRECT MOLE | 2" ST | 117 | 31
2021-06-07 | 11 | Jun-21 |  | DIRECT MOLE | 2" ST | 289 | 22.8
2021-06-14 | 12 | Jun-21 |  | DIRECT MOLE | 2" ST | 146 | 9
2021-06-21 | 13 | Jun-21 |  | DIRECT MOLE | 2" ST | 174 | 31
2021-06-28 | 14 | Jun-21 |  | DIRECT MOLE | 2" ST | 0 | 33
2021-07-05 | 15 | Jul-21 |  | DIRECT MOLE | 2" ST | 206 | 42
2021-07-12 | 16 | Jul-21 |  | DIRECT MOLE | 2" ST | 190 | 0
2021-07-19 | 17 | Jul-21 |  | DIRECT MOLE | 2" ST | 81 | 52
2021-07-26 | 18 | Jul-21 |  | DIRECT MOLE | 2" ST | 159 | 0
2021-08-02 | 19 | Aug-21 |  | DIRECT MOLE | 2" ST | 0 | 41
2021-08-09 | 20 | Aug-21 |  | DIRECT MOLE | 2" ST | 91 | 42
2021-08-16 | 21 | Aug-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-08-23 | 22 | Aug-21 |  | DIRECT MOLE | 2" ST | 266 | 0
2021-08-30 | 23 | Aug-21 |  | DIRECT MOLE | 2" ST | 143 | 0
2021-09-06 | 24 | Sep-21 |  | DIRECT MOLE | 2" ST | 116 | 0
2021-09-13 | 25 | Sep-21 |  | DIRECT MOLE | 2" ST | 185 | 0
2021-09-20 | 26 | Sep-21 |  | DIRECT MOLE | 2" ST | 241 | 87.9
2021-09-27 | 27 | Sep-21 |  | DIRECT MOLE | 2" ST | 50 | 12.7
2021-10-04 | 28 | Oct-21 |  | DIRECT MOLE | 2" ST | 363 | 48
2021-10-11 | 29 | Oct-21 |  | DIRECT MOLE | 2" ST | 53 | 49.3
2021-10-18 | 30 | Oct-21 |  | DIRECT MOLE | 2" ST | 113 | 0
2021-10-25 | 31 | Oct-21 |  | DIRECT MOLE | 2" ST | 256 | 91
2021-11-01 | 32 | Nov-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-11-08 | 33 | Nov-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-11-15 | 34 | Nov-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-11-22 | 35 | Nov-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-11-29 | 36 | Nov-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-12-06 | 37 | Dec-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-12-13 | 38 | Dec-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-12-20 | 39 | Dec-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-12-27 | 40 | Dec-21 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-01-03 | 41 | Jan-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-01-10 | 42 | Jan-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-01-17 | 43 | Jan-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-01-24 | 44 | Jan-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-01-31 | 45 | Jan-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-02-07 | 46 | Feb-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-02-14 | 47 | Feb-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-02-21 | 48 | Feb-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-02-28 | 49 | Feb-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-03-07 | 50 | Mar-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-03-14 | 51 | Mar-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-03-21 | 52 | Mar-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2022-03-28 | 53 | Mar-22 |  | DIRECT MOLE | 2" ST | 0 | 0
2021-03-29 | 1 | Mar-21 |  | SQS | Connected ST | 0 | 0
2021-04-05 | 2 | Apr-21 |  | SQS | Connected ST | 175 | 0
2021-04-12 | 3 | Apr-21 |  | SQS | Connected ST | 740 | 0
2021-04-19 | 4 | Apr-21 |  | SQS | Connected ST | 693 | 0
2021-04-26 | 5 | Apr-21 |  | SQS | Connected ST | 759 | 0
2021-05-03 | 6 | May-21 |  | SQS | Connected ST | 946 | 0
2021-05-10 | 7 | May-21 |  | SQS | Connected ST | 522 | 0
2021-05-17 | 8 | May-21 |  | SQS | Connected ST | 711 | 0
2021-05-24 | 9 | May-21 |  | SQS | Connected ST | 595 | 0
2021-05-31 | 10 | May-21 |  | SQS | Connected ST | 415 | 0
2021-06-07 | 11 | Jun-21 |  | SQS | Connected ST | 587 | 0
2021-06-14 | 12 | Jun-21 |  | SQS | Connected ST | 238 | 0
2021-06-21 | 13 | Jun-21 |  | SQS | Connected ST | 747 | 0
2021-06-28 | 14 | Jun-21 |  | SQS | Connected ST | 816 | 0
2021-07-05 | 15 | Jul-21 |  | SQS | Connected ST | 521 | 0
2021-07-12 | 16 | Jul-21 |  | SQS | Connected ST | 684 | 0
2021-07-19 | 17 | Jul-21 |  | SQS | Connected ST | 537 | 0
2021-07-26 | 18 | Jul-21 |  | SQS | Connected ST | 475 | 0
2021-08-02 | 19 | Aug-21 |  | SQS | Connected ST | 242 | 0
2021-08-09 | 20 | Aug-21 |  | SQS | Connected ST | 627 | 0
2021-08-16 | 21 | Aug-21 |  | SQS | Connected ST | 607 | 0
2021-08-23 | 22 | Aug-21 |  | SQS | Connected ST | 730 | 0
2021-08-30 | 23 | Aug-21 |  | SQS | Connected ST | 861 | 0
2021-09-06 | 24 | Sep-21 |  | SQS | Connected ST | 1192 | 0
2021-09-13 | 25 | Sep-21 |  | SQS | Connected ST | 786 | 0
2021-09-20 | 26 | Sep-21 |  | SQS | Connected ST | 993 | 0
2021-09-27 | 27 | Sep-21 |  | SQS | Connected ST | 804 | 0
2021-10-04 | 28 | Oct-21 |  | SQS | Connected ST | 738 | 0
2021-10-11 | 29 | Oct-21 |  | SQS | Connected ST | 1193 | 0
2021-10-18 | 30 | Oct-21 |  | SQS | Connected ST | 459 | 0
2021-10-25 | 31 | Oct-21 |  | SQS | Connected ST | 906 | 0
2021-11-01 | 32 | Nov-21 |  | SQS | Connected ST | 0 | 0
2021-11-08 | 33 | Nov-21 |  | SQS | Connected ST | 0 | 0
2021-11-15 | 34 | Nov-21 |  | SQS | Connected ST | 0 | 0
2021-11-22 | 35 | Nov-21 |  | SQS | Connected ST | 0 | 0
2021-11-29 | 36 | Nov-21 |  | SQS | Connected ST | 0 | 0
2021-12-06 | 37 | Dec-21 |  | SQS | Connected ST | 0 | 0
2021-12-13 | 38 | Dec-21 |  | SQS | Connected ST | 0 | 0
2021-12-20 | 39 | Dec-21 |  | SQS | Connected ST | 0 | 0
2021-12-27 | 40 | Dec-21 |  | SQS | Connected ST | 0 | 0
2022-01-03 | 41 | Jan-22 |  | SQS | Connected ST | 0 | 0
2022-01-10 | 42 | Jan-22 |  | SQS | Connected ST | 0 | 0
2022-01-17 | 43 | Jan-22 |  | SQS | Connected ST | 0 | 0
2022-01-24 | 44 | Jan-22 |  | SQS | Connected ST | 0 | 0
2022-01-31 | 45 | Jan-22 |  | SQS | Connected ST | 0 | 0
2022-02-07 | 46 | Feb-22 |  | SQS | Connected ST | 0 | 0
2022-02-14 | 47 | Feb-22 |  | SQS | Connected ST | 0 | 0
2022-02-21 | 48 | Feb-22 |  | SQS | Connected ST | 0 | 0
2022-02-28 | 49 | Feb-22 |  | SQS | Connected ST | 0 | 0
2022-03-07 | 50 | Mar-22 |  | SQS | Connected ST | 0 | 0
2022-03-14 | 51 | Mar-22 |  | SQS | Connected ST | 0 | 0
2022-03-21 | 52 | Mar-22 |  | SQS | Connected ST | 0 | 0
2022-03-28 | 53 | Mar-22 |  | SQS | Connected ST | 0 | 0

## CMO Input
PON | Network | Area | Month | Week | A / F | PM | SM | Project | Street | PON | PON Type | Risk Score | Policy / Non Policy | Diameter | Material | Metrage | Units | Concatenate | Banding | Tier | Material 2 | Concatenate 2 | Contains "LA" | OM Cross Check | Restructure | MR3 Score | Carry Over | Area2 | Project2 | Street2 | Local Authority | Sub Area | Realigned Y / N | PAST | LDP | Full PON Type | Resource | Pressure | New World Priority | Diameter2 | Diameter 2 | Pressure3 | Policy | Tier4 | Material5 | Category | Month6
510894344 | Carryover | Central | April | 2 | A | Trevor Trent | Wayne Passingham | IMGA201003 | PORTOBELLO ROAD | 510894344 | T3 CBA | 7.2 | Policy | 18 | CI | 65 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0.468 | 0 | Central | IMGA201003 | PORTOBELLO ROAD | #N/A | Central | TRUE |  | KLT | T3 CBA SPECIFIED | tRIIO CAREY, Tony | LP | ENM T3 | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | April
510838369 | Carryover | Central | April | 3 | A | Shaun Melluish | Chris Brittin | IMGA183207 | GOLDERS GREEN CRESCENT | 510838369 | T2 PAST | 286.6 | Policy | 14 | CI | 34 | inch | 14inch | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 9.7444 | Y | Central | IMGA183207 | GOLDERS GREEN CRESCENT | #N/A | Central | TRUE | PAST | Terra Firma | T2 RAT | CMO HORGAN, Liam | #N/A | RAT | >12-17” | 14 |  | Policy | Tier 2 | CI | T2A | April
510852949 | Carryover | Central | April | 3 | A | Shaun Melluish | Chris Brittin | IMGA183207 | HODFORD ROAD | 510852949 | T2 PAST | 590.1 | Policy | 14 | CI | 55.7 | inch | 14inch | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 32.8686 | Y | Central | IMGA183207 | HODFORD ROAD | #N/A | Central | TRUE | PAST | Terra Firma | T2 RAT | CMO HORGAN, Liam | #N/A | RAT | >12-17” | 14 |  | Policy | Tier 2 | CI | T2A | April
200018405398 | Carryover | Central | April | 3 | A | Steve Edwards | Adam Fletcher | IMGA191103 | FENCHURCH STREET | 200018405398 | T3 CBA | 0 | Policy | 18 | CI | 118 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0 | Y | Central | IMGA191103 | FENCHURCH STREET | #N/A | Central | TRUE |  | Terra Firma |  | STAFF FRANCIS, Darren | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | April
DR4 Requested | Carryover | Central | April | 3 | A | Shaun Melluish | Chris Brittin | IMGA183207 | GOLDERS GREEN CRESCENT | DR4 Requested | T2 PAST | 0 | Policy | 14 | CI | 13 | inch | 14inch | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0 | Y | Central | IMGA183207 | GOLDERS GREEN CRESCENT | #N/A | Central | TRUE | PAST | Terra Firma | T2 RAT | CMO HORGAN, Liam | #N/A | #N/A | >12-17” | 14 |  | Policy | Tier 2 | CI | T2A | April
510874819 | Carryover | Central | April | 4 | A | Tim Butler | TBA - Lon | IMGA140131 | Marylebone Road | 510874819 | T1 PAST | 290.8 | Policy | 8 | DI | 11 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1988 | 0 | Central | IMGA140131 | Marylebone Road | #N/A | Central | TRUE | PAST | Terra Firma | T1 ALARP | CMO TILBURY, Clive | LP | ALARP | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | April
510906073 | Carryover | Central | April | 4 | A | Trevor Trent | Chris Smith | IMGA201004 | ST GEORGE'S DRIVE | 510906073 | T3 CBA | 105.9 | Policy | 24 | CI | 32 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 3.3888 | 0 | Central | IMGA201004 | ST GEORGE'S DRIVE | #N/A | Central | TRUE |  | Forefront | T3 CBA CANDIDATE | tRIIO O'DEA, Gerald | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | April
510906074 | Carryover | Central | April | 4 | A | Trevor Trent | Chris Smith | IMGA201004 | ST GEORGE'S DRIVE | 510906074 | T3 CBA | 78 | Policy | 24 | CI | 398 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 31.044 | 0 | Central | IMGA201004 | ST GEORGE'S DRIVE | #N/A | Central | TRUE |  | Forefront | T3 CBA CANDIDATE | tRIIO O'DEA, Gerald | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | April
510831309 | Carryover | Central | April | 4 | A | Steve Edwards | Adam Fletcher | IMGA191103 | FENCHURCH STREET | 510831309 | T3 CBA | 33.7 | Policy | 18 | CI | 118 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 3.9766 | Y | Central | IMGA191103 | FENCHURCH STREET | #N/A | Central | TRUE |  | Terra Firma |  | STAFF FRANCIS, Darren | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | April
200018405398 | Carryover | Central | April | 4 | A | Steve Edwards | Adam Fletcher | IMGA191103 | FENCHURCH STREET | 200018405398 | T3 CBA | 0 | Policy | 18 | CI | -118 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0 | Y | Central | IMGA191103 | FENCHURCH STREET | #N/A | Central | TRUE |  | Terra Firma |  | STAFF FRANCIS, Darren | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | April
510909357 | Carryover | Central | April | 5 | A | Steve Edwards | Adam Fletcher | IMGA191103 | SEETHING LANE | 510909357 | T3 CBA | 234.1 | Policy | 24 | CI | 88 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 20.6008 | Y | Central | IMGA191103 | SEETHING LANE | #N/A | Central | TRUE |  | Terra Firma | T3 CBA CANDIDATE | CMO RUTKOWSKI, Slawomir | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | April
510802432 | Carryover | Central | April | 5 | A | Trevor Trent | Chris Smith | IMGA191091 | CANONBURY ROAD | 510802432 | T3 CBA | 101.1 | Policy | 24 | CI | 13 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 1.3143 | 0 | Central | IMGA191091 | CANONBURY ROAD | #N/A | Central | TRUE |  | KLT |  | CMO CLARK KLT, Darren | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | April
510802433 | Carryover | Central | April | 5 | A | Trevor Trent | Chris Smith | IMGA191091 | CANONBURY ROAD | 510802433 | T3 CBA | 122.7 | Policy | 18 | CI | 55 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 6.7485 | 0 | Central | IMGA191091 | CANONBURY ROAD | #N/A | Central | TRUE |  | KLT |  | CMO CLARK KLT, Darren | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | April
220001627760 | Carryover | Central | April | 5 | A | Trevor Trent | Chris Smith | IMGA191091 | CANONBURY ROAD | 220001627760 | T3 CBA | 0 | Policy | 36 | CI | 62 | inch | 36inch | Abandonment >24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | Central | IMGA191091 | CANONBURY ROAD | #N/A | Central | TRUE |  | KLT |  | CMO CLARK KLT, Darren | #N/A | #N/A | >24” | 36 |  | Policy | Tier 3 | CI | T3 | April
510802419 | Carryover | Central | April | 5 | A | Trevor Trent | Chris Smith | IMGA191091 | CANONBURY ROAD | 510802419 | T3 CBA | 41.5 | Policy | 24 | CI | 12 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0.498 | 0 | Central | IMGA191091 | CANONBURY ROAD | #N/A | Central | TRUE |  | KLT | T2 CBA CANDIDATE | CMO CLARK KLT, Darren | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | April
510894344 | Carryover | Central | April | 5 | A | Trevor Trent | Wayne Passingham | IMGA201003 | PORTOBELLO ROAD | 510894344 | T3 CBA | 7.2 | Policy | 18 | CI | 45 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0.324 | 0 | Central | IMGA201003 | PORTOBELLO ROAD | #N/A | Central | TRUE |  | KLT | T3 CBA SPECIFIED | CMO CAREY KLT, Anthony | LP | ENM T3 | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | April
side street | Carryover | Central | April | 5 | A | Trevor Trent | Wayne Passingham | IMGA201003 | PORTOBELLO ROAD | side street | T1 Policy | 0 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | Central | IMGA201003 | PORTOBELLO ROAD | #N/A | Central | TRUE |  | KLT |  | CMO CAREY KLT, Anthony | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510802419 | Carryover | Central | May | 6 | A | Trevor Trent | Chris Smith | IMGA191091 | CANONBURY ROAD | 510802419 | T3 CBA | 41.5 | Policy | 24 | CI | -12 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | -0.498 | 0 | Central | IMGA191091 | CANONBURY ROAD | #N/A | Central | TRUE |  | KLT | T2 CBA CANDIDATE | CMO CLARK KLT, Darren | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | May
510802419 | Carryover | Central | May | 6 | A | Trevor Trent | Chris Smith | IMGA191091 | CANONBURY ROAD | 510802419 | T2 CBA | 41.5 | Policy | 12 | CI | 12 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0.498 | 0 | Central | IMGA191091 | CANONBURY ROAD | #N/A | Central | TRUE |  | KLT | T2 CBA CANDIDATE | CMO CLARK KLT, Darren | #N/A | #N/A | 10-12” | 12 |  | Policy | Tier 2 | CI | T2A | May
510906074 | Carryover | Central | May | 8 | A | Trevor Trent | Chris Smith | IMGA201004 | ST GEORGE'S DRIVE | 510906074 | T3 CBA | 78 | Policy | 24 | CI | 40 | inch | 24inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 3.12 | 0 | Central | IMGA201004 | ST GEORGE'S DRIVE | #N/A | Central | TRUE |  | Forefront | T3 CBA CANDIDATE | tRIIO O'DEA, Gerald | #N/A | #N/A | 18-24” | 24 |  | Policy | Tier 3 | CI | T3 | May
510831309 | Carryover | Central | May | 9 | A | Steve Edwards | Adam Fletcher | IMGA191103 | FENCHURCH STREET | 510831309 | T3 CBA | 33.7 | Policy | 18 | CI | 116 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 3.9092 | Y | Central | IMGA191103 | FENCHURCH STREET | #N/A | Central | TRUE |  | Terra Firma | T3 CBA CANDIDATE | tRIIO LAWRENCE, Neil | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | May
612104784 | Carryover | Central | June | 12 | A | Steve Edwards | Adam Fletcher | IMGA191103 | FENCHURCH STREET | 612104784 | T1 PAST | 99.2 | Policy | 4 | CI | 5.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.53568 | Y | Central | IMGA191103 | FENCHURCH STREET | #N/A | Central | TRUE | PAST | Terra Firma | T1 SEED | tRIIO LAWRENCE, Neil | #N/A | SEED | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220000068504 | Carryover | East | April | 5 | A | TBA - Lon | Robert Ashdown | IMGA183256 | Heath Road 2 Y8 | 220000068504 | Condition | 0 | Non Policy | 6 | ST | 180 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | Y | East | IMGA183256 | Heath Road 2 Y8 | #N/A | East | TRUE |  | Forefront |  | CMO ABBOTT , Tim | #N/A | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | April
- | Carryover | East | April | 5 | A | TBA - Lon | Robert Ashdown | IMGA183256 | Heath Road 2 Y8 | - | Condition | 0 | Non Policy | 6 | ST | 29 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | Y | East | IMGA183256 | Heath Road 2 Y8 | #N/A | East | TRUE |  | Forefront | T1 CONNECTED | CMO ABBOTT , Tim | #N/A | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | April
510819993 | Carryover | West | April | 3 | A | Mark Prothero | Liam Davies | IMGA202295 | DEAN CLOSE | 510819993 | T1 Policy | 24.3 | Policy | 4 | CI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.916 | 0 | West | IMGA202295 | DEAN CLOSE | #N/A | West | TRUE |  | DPF | T1 SECONDARY | CMO TURNER, James | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510786574 | Carryover | West | April | 4 | A | Bernie Ridsdale | Mick Bradley | IMGA202317 | AINSWORTH CLOSE | 510786574 | T1 Policy | 0.7 | Policy | 6 | DI | 4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0028 | 0 | West | IMGA202317 | AINSWORTH CLOSE | #N/A | West | TRUE |  | KLT |  | CMO MCPADDEN KLT, Mick | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510786575 | Carryover | West | April | 4 | A | Bernie Ridsdale | Mick Bradley | IMGA202317 | AINSWORTH CLOSE | 510786575 | T2 CBA | 2.3 | Policy | 12 | DI | 22 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0.0506 | 0 | West | IMGA202317 | AINSWORTH CLOSE | #N/A | West | TRUE |  | KLT |  | CMO MCPADDEN KLT, Mick | #N/A | #N/A | 10-12” | 12 |  | Policy | Tier 2 | DI | T2A | April
510787389 | Carryover | West | April | 4 | A | Mark Prothero |  | IMGA202295 | Baronsmead Road Part 3 | 510787389 | T1 Policy | 42.8 | Policy | 4 | CI | 119 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.0932 | 0 | West | IMGA202295 | Baronsmead Road Part 3 | #N/A | West | TRUE |  | DPF |  | CMO GRANTHAM, Colin | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510787389 | Carryover | West | May | 6 | A | Mark Prothero |  | IMGA202295 | Baronsmead Road Part 3 | 510787389 | T1 Policy | 42.8 | Policy | 4 | CI | 119 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.0932 | 0 | West | IMGA202295 | Baronsmead Road Part 3 | #N/A | West | TRUE |  | DPF |  | CMO GRANTHAM, Colin | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510786571 | Carryover | West | June | 10 | A | Bernie Ridsdale | Mick Bradley | IMGA202317 | AINSWORTH CLOSE | 510786571 | T1 Policy | 12.4 | Policy | 4 | DI | 38 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4712 | 0 | West | IMGA202317 | AINSWORTH CLOSE | #N/A | West | TRUE |  | KLT | T1 SECONDARY | tRIIO VAN DER HAVE, John | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510893123 | Carryover | West | September | 24 | A | Gary Conway | Natasha Barrett | IMGA192129 | PINNER ROAD | 510893123 | T1 PAST | 0 | Policy | 6 | CI | 22.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | West | IMGA192129 | PINNER ROAD | #N/A | West | TRUE | PAST | KLT | T1 SEED | CMO ANTHONY SNR, Russell | #N/A | SEED | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510893123 | Carryover | West | September | 24 | A | Gary Conway | Natasha Barrett | IMGA192129 | PINNER ROAD | 510893123 | T1 PAST | 0 | Policy | 6 | SI | 27 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | West | IMGA192129 | PINNER ROAD | #N/A | West | TRUE | PAST | KLT | T1 SEED | CMO ANTHONY SNR, Russell | #N/A | SEED | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510951105 | Carryover | West | September | 24 | A | TBA - Lon | TBA - Lon | IMGA192270 | MAYFIELD CLOSE | 510951105 | T1 PAST | 0 | Policy | 6 | SI | 5.7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | West | IMGA192270 | MAYFIELD CLOSE | #N/A | West | TRUE | PAST | OMJ | T1 SEED | CMO COLLINS (OMJ), Patrick | #N/A | SEED | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510944381 | Carryover | West | September | 24 | A | TBA - Lon | TBA - Lon | IMGA212285 | CONWAY DRIVE | 510944381 | T1 Policy | 0 | Policy | 4 | SI | 67.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | West | IMGA212285 | CONWAY DRIVE | #N/A | West | TRUE |  | DHB Utilities | T1 SECONDARY | tRIIO CUTHBERTSON, Steve | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510921974 | Carryover | West | September | 27 | A | Nick Granger | William Madge | IMGA182093 | THE AVENUE | 510921974 | T1 Policy | 0 | Policy | 6 | CI | 76.1 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | West | IMGA182093 | THE AVENUE | #N/A | West | TRUE |  | KLT | T1 SECONDARY | Richard, Balldock | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510921974 | Carryover | West | October | 29 | A | Nick Granger |  | IMGA182093 | THE AVENUE (YR 6) | 510921974 | T1 Policy | 0 | Policy | 6 | CI | 96 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | West | IMGA182093 | THE AVENUE (YR 6) | #N/A | West | TRUE |  | KLT |  | STAFF HILLS, Scott | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510984117 | CMO | CMO East 1 | April | 2 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 510984117 | T1 Policy | 0 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARK, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510984117 | CMO | CMO East 1 | April | 2 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 510984117 | T1 Policy | 0 | Policy | 6 | SI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARK, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510970495 | CMO | CMO East 1 | April | 2 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 510970495 | T1 Policy | 58.4 | Policy | 8 | SI | 353 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 20.6152 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARK, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | April
220000364995 | CMO | CMO East 1 | April | 2 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 220000364995 | T1 Policy | 0 | Policy | 6 | SI | 1 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARK, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510877419 | CMO | CMO East 1 | April | 3 | A | Joshua Overfield | John Burns | IMGA223190 | MILL RIDGE | 510877419 | T1 Policy | 23.5 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.82 | 0 | CMO East 1 | IMGA223190 | MILL RIDGE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO HILL, Matthew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510937961 | CMO | CMO East 1 | April | 3 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937961 | T1 Policy | 19.4 | Policy | 4 | CI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.649 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510827806 | CMO | CMO East 1 | April | 3 | A | Joshua Overfield | Wayne Garland | IMGA223329 | ELWIN STREET | 510827806 | T1 Policy | 0.5 | Policy | 4 | DI | 62 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.031 | 0 | CMO East 1 | IMGA223329 | ELWIN STREET | Tower Hamlets Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO HAGUES, Chris | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510832923 | CMO | CMO East 1 | April | 3 | A | Joshua Overfield | Wayne Garland | IMGA223314 | FLORENCE ROAD | 510832923 | T1 Policy | 4.7 | Policy | 6 | DI | 94 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4418 | 0 | CMO East 1 | IMGA223314 | FLORENCE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510984117 | CMO | CMO East 1 | April | 3 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 510984117 | T1 Policy | 0 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510970495 | CMO | CMO East 1 | April | 3 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 510970495 | T1 Policy | 58.4 | Policy | 8 | CI | 346 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 20.2064 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
- | CMO | CMO East 1 | April | 3 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | - | T1 Policy | 0 | Policy | 8 | CI | 68 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510877419 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | John Burns | IMGA223190 | MILL RIDGE | 510877419 | T1 Policy | 23.5 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.82 | 0 | CMO East 1 | IMGA223190 | MILL RIDGE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO HILL, Matthew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510866724 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | LINDEN LEA | 510866724 | T1 Policy | 16.3 | Policy | 6 | CI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0815 | 0 | CMO East 1 | IMGA223196 | LINDEN LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510937957 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937957 | T1 Policy | 5 | Policy | 6 | DI | 13 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.065 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510937958 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937958 | T1 Policy | 1.9 | Policy | 6 | DI | 55 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1045 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510937961 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937961 | T1 Policy | 19.4 | Policy | 4 | CI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1164 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510962007 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | Wayne Garland | IMGA223315 | MORTLAKE ROAD | 510962007 | T1 Policy | 0.3 | Policy | 4 | DI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0105 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
606714434 | CMO | CMO East 1 | April | 4 | A | Joshua Overfield | Wayne Garland | IMGA223315 | MORTLAKE ROAD | 606714434 | T1 Policy | 0.7 | Policy | 4 | DI | 44 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0308 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510970501 | CMO | CMO East 1 | April | 4 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 510970501 | T1 Policy | 17.2 | Policy | 4 | SI | 51 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8772 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
622287848 | CMO | CMO East 1 | April | 4 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 622287848 | T1 Policy | 14.3 | Policy | 8 | CI | 399 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.7057 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
- | CMO | CMO East 1 | April | 4 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | - | T1 Policy | 0 | Policy | 4 | SI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510944068 | CMO | CMO East 1 | April | 5 | A | Joshua Overfield | John Burns | IMGA223189 | MANNS ROAD | 510944068 | T1 Policy | 0.7 | Policy | 4 | DI | 98 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0686 | 0 | CMO East 1 | IMGA223189 | MANNS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO RADA, Besim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510877419 | CMO | CMO East 1 | April | 5 | A | Joshua Overfield | John Burns | IMGA223190 | MILL RIDGE | 510877419 | T1 Policy | 23.5 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.82 | 0 | CMO East 1 | IMGA223190 | MILL RIDGE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO HILL, Matthew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510866724 | CMO | CMO East 1 | April | 5 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | LINDEN LEA | 510866724 | T1 Policy | 16.3 | Policy | 6 | CI | 93 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5159 | 0 | CMO East 1 | IMGA223196 | LINDEN LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510937961 | CMO | CMO East 1 | April | 5 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937961 | T1 Policy | 19.4 | Policy | 4 | CI | 76.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4841 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510825171 | CMO | CMO East 1 | April | 5 | A | Joshua Overfield | Herbie Thomas | IMGA223203 | EASTSIDE ROAD | 510825171 | T1 Policy | 30.9 | Policy | 6 | CI | 85 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.6265 | 0 | CMO East 1 | IMGA223203 | EASTSIDE ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BEARDSELL, Brian | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
606714434 | CMO | CMO East 1 | April | 5 | A | Joshua Overfield | Wayne Garland | IMGA223315 | MORTLAKE ROAD | 606714434 | T1 Policy | 0.7 | Policy | 6 | DI | 51 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0357 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
622287848 | CMO | CMO East 1 | April | 5 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | 622287848 | T1 Policy | 14.3 | Policy | 8 | CI | 99 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4157 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
- | CMO | CMO East 1 | April | 5 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | - | T1 Policy | 0 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
- | CMO | CMO East 1 | April | 5 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | - | T1 Policy | 0 | Policy | 6 | CI | 97 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
- | CMO | CMO East 1 | April | 5 | A | Phil Whitlock | Robert Ashdown | IMGA223229 | FULLWELL AVENUE | - | T1 Policy | 0 | Policy | 8 | CI | 98 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie |  | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510877419 | CMO | CMO East 1 | May | 6 | A | Joshua Overfield | John Burns | IMGA223190 | MILL RIDGE | 510877419 | T1 Policy | 23.5 | Policy | 4 | SI | 55 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2925 | 0 | CMO East 1 | IMGA223190 | MILL RIDGE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO HILL, Matthew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510962006 | CMO | CMO East 1 | May | 6 | A | Joshua Overfield | Wayne Garland | IMGA223315 | MORTLAKE ROAD | 510962006 | T1 PAST | 1.7 | Policy | 6 | DI | 58 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0986 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | CMO NOLAN, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510962014 | CMO | CMO East 1 | May | 6 | A | Joshua Overfield | Wayne Garland | IMGA223315 | MORTLAKE ROAD | 510962014 | T1 Policy | 1.1 | Policy | 4 | DI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0814 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510827806 | CMO | CMO East 1 | May | 6 | A | Joshua Overfield | Wayne Garland | IMGA223329 | ELWIN STREET | 510827806 | T1 Policy | 0.5 | Policy | 100 | DI | 63 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0315 | 0 | CMO East 1 | IMGA223329 | ELWIN STREET | Tower Hamlets Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510897464 | CMO | CMO East 1 | May | 6 | A | Joshua Overfield | Wayne Garland | IMGA223329 | QUILTER STREET | 510897464 | T1 Policy | 0.3 | Policy | 100 | DI | 28 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0084 | 0 | CMO East 1 | IMGA223329 | QUILTER STREET | Tower Hamlets Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510872769 | CMO | CMO East 1 | May | 6 | A | Phil Whitlock | Robert Ashdown | IMGA223217 | MANOR ROAD | 510872769 | T1 Policy | 11.8 | Policy | 8 | CI | 140 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.652 | 0 | CMO East 1 | IMGA223217 | MANOR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510801321 | CMO | CMO East 1 | May | 6 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | CALNE AVENUE | 510801321 | T1 Policy | 16.9 | Policy | 6 | CI | 160 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.704 | 0 | CMO East 1 | IMGA223228 | CALNE AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510898564 | CMO | CMO East 1 | May | 6 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | RAVENSBOURNE GARDENS | 510898564 | T1 Policy | 14.9 | Policy | 6 | CI | 193 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.8757 | 0 | CMO East 1 | IMGA223228 | RAVENSBOURNE GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510855454 | CMO | CMO East 1 | May | 6 | A | Phil Whitlock | Robert Ashdown | IMGA223230 | HUMPHREY CLOSE | 510855454 | T1 Policy | 26.9 | Policy | 4 | SI | 77.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0848 | 0 | CMO East 1 | IMGA223230 | HUMPHREY CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510900366 | CMO | CMO East 1 | May | 6 | A | Phil Whitlock | Robert Ashdown | IMGA223230 | REPTON GROVE | 510900366 | T1 Policy | 16.7 | Policy | 4 | SI | 77.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2942 | 0 | CMO East 1 | IMGA223230 | REPTON GROVE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510825171 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | Herbie Thomas | IMGA223203 | EASTSIDE ROAD | 510825171 | T1 Policy | 30.9 | Policy | 6 | CI | 163 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.0367 | 0 | CMO East 1 | IMGA223203 | EASTSIDE ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BEARDSELL, Brian | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510866724 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | LINDEN LEA | 510866724 | T1 Policy | 16.3 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.63 | 0 | CMO East 1 | IMGA223196 | LINDEN LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510872769 | CMO | CMO East 1 | May | 7 | A | Phil Whitlock | Robert Ashdown | IMGA223217 | MANOR ROAD | 510872769 | T1 Policy | 11.8 | Policy | 8 | SI | 105 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.239 | 0 | CMO East 1 | IMGA223217 | MANOR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | May
510897465 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | Wayne Garland | IMGA223329 | QUILTER STREET | 510897465 | T1 Policy | 14.4 | Policy | 100 | DI | 86 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2384 | 0 | CMO East 1 | IMGA223329 | QUILTER STREET | Tower Hamlets Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510898564 | CMO | CMO East 1 | May | 7 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | RAVENSBOURNE GARDENS | 510898564 | T1 Policy | 14.9 | Policy | 6 | CI | 68.4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0192 | 0 | CMO East 1 | IMGA223228 | RAVENSBOURNE GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510898566 | CMO | CMO East 1 | May | 7 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | RAVENSBOURNE GARDENS | 510898566 | T1 Policy | 24.8 | Policy | 4 | SI | 201 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.9848 | 0 | CMO East 1 | IMGA223228 | RAVENSBOURNE GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510898567 | CMO | CMO East 1 | May | 7 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | RAVENSBOURNE GARDENS | 510898567 | T1 Policy | 27.7 | Policy | 4 | SI | 66 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.8282 | 0 | CMO East 1 | IMGA223228 | RAVENSBOURNE GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510898568 | CMO | CMO East 1 | May | 7 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | RAVENSBOURNE GARDENS | 510898568 | T1 Policy | 21.5 | Policy | 4 | SI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.9025 | 0 | CMO East 1 | IMGA223228 | RAVENSBOURNE GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510898571 | CMO | CMO East 1 | May | 7 | A | Phil Whitlock | Robert Ashdown | IMGA223228 | RAVENSBOURNE GARDENS | 510898571 | T1 Policy | 32.8 | Policy | 4 | SI | 38.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2628 | 0 | CMO East 1 | IMGA223228 | RAVENSBOURNE GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510937958 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937958 | T1 Policy | 1.9 | Policy | 6 | DI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.19 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510944068 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | John Burns | IMGA223189 | MANNS ROAD | 510944068 | T1 Policy | 0.7 | Policy | 4 | DI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0252 | 0 | CMO East 1 | IMGA223189 | MANNS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO RADA, Besim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510944980 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | John Burns | IMGA223189 | GARDEN CITY | 510944980 | T1 Policy | 0.7 | Policy | 4 | DI | 76 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0532 | 0 | CMO East 1 | IMGA223189 | GARDEN CITY | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO RADA, Besim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
606714425 | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | John Burns | IMGA223189 | GARDEN CITY | 606714425 | T1 Policy | 0.7 | Policy | 4 | DI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0049 | 0 | CMO East 1 | IMGA223189 | GARDEN CITY | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO RADA, Besim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
DAF TO BE SUBMITTED | CMO | CMO East 1 | May | 7 | A | Joshua Overfield | Herbie Thomas | IMGA223203 | EASTSIDE ROAD | DAF TO BE SUBMITTED | T1 Policy | 0 | Policy | 4 | CI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223203 | EASTSIDE ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO BEARDSELL, Brian |  | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510808158 | CMO | CMO East 1 | May | 8 | A | Joshua Overfield | John Burns | IMGA223189 | CHILTON ROAD | 510808158 | T1 Policy | 1.5 | Policy | 4 | DI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0945 | 0 | CMO East 1 | IMGA223189 | CHILTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO RADA, Besim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510943983 | CMO | CMO East 1 | May | 8 | A | Joshua Overfield | Peter Rattigan | IMGA223192 | HIGHVIEW AVENUE | 510943983 | T1 Policy | 25.7 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.084 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510855741 | CMO | CMO East 1 | May | 8 | A | Joshua Overfield | Herbie Thomas | IMGA223203 | EASTSIDE ROAD | 510855741 | T1 Policy | 0 | Policy | 4 | CI | 17 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223203 | EASTSIDE ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO BEARDSELL, Brian | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510855746 | CMO | CMO East 1 | May | 8 | A | Joshua Overfield | Herbie Thomas | IMGA223203 | EASTSIDE ROAD | 510855746 | T1 Policy | 0 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223203 | EASTSIDE ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO BEARDSELL, Brian | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510825171 | CMO | CMO East 1 | May | 8 | A | Joshua Overfield | Herbie Thomas | IMGA223203 | EASTSIDE ROAD | 510825171 | T1 Policy | 30.9 | Policy | 6 | CI | 15 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4635 | 0 | CMO East 1 | IMGA223203 | EASTSIDE ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BEARDSELL, Brian | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510897465 | CMO | CMO East 1 | May | 8 | A | Joshua Overfield | Wayne Garland | IMGA223329 | QUILTER STREET | 510897465 | T1 Policy | 14.4 | Policy | 100 | DI | 80 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.152 | 0 | CMO East 1 | IMGA223329 | QUILTER STREET | Tower Hamlets Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510830195 | CMO | CMO East 1 | May | 8 | A | Matt Payne | Robert Ashdown | IMGA223217 | MANOR ROAD | 510830195 | T1 Policy | 53.6 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.36 | 0 | CMO East 1 | IMGA223217 | MANOR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510778302 | CMO | CMO East 1 | May | 8 | A | Matt Payne | Robert Ashdown | IMGA223247 | ABBOTSFORD GARDENS | 510778302 | T1 Policy | 23.4 | Policy | 6 | CI | 151 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.5334 | 0 | CMO East 1 | IMGA223247 | ABBOTSFORD GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510851298 | CMO | CMO East 1 | May | 9 | A | Steve Edwards | Chris Brittin | IMGA221026 | HIGHBURY PLACE | 510851298 | T1 Policy | 45 | Policy | 8 | CI | 126 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.67 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Steven | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510937958 | CMO | CMO East 1 | May | 9 | A | Joshua Overfield | Herbie Thomas | IMGA223202 | WICKLIFFE AVENUE | 510937958 | T1 Policy | 1.9 | Policy | 6 | DI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.171 | 0 | CMO East 1 | IMGA223202 | WICKLIFFE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510872769 | CMO | CMO East 1 | May | 9 | A | Matt Payne | Robert Ashdown | IMGA223217 | MANOR ROAD | 510872769 | T1 Policy | 11.8 | Policy | 8 | CI | 90 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.062 | 0 | CMO East 1 | IMGA223217 | MANOR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510819461 | CMO | CMO East 1 | May | 9 | A | Matt Payne | Robert Ashdown | IMGA223247 | ROKEBY GARDENS | 510819461 | T1 Policy | 22.5 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.135 | 0 | CMO East 1 | IMGA223247 | ROKEBY GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510902372 | CMO | CMO East 1 | May | 9 | A | Matt Payne | Robert Ashdown | IMGA223247 | ROKEBY GARDENS | 510902372 | T1 Policy | 34.9 | Policy | 4 | CI | 133 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.6417 | 0 | CMO East 1 | IMGA223247 | ROKEBY GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510902373 | CMO | CMO East 1 | May | 9 | A | Matt Payne | Robert Ashdown | IMGA223247 | ROKEBY GARDENS | 510902373 | T1 Policy | 19.8 | Policy | 6 | CI | 208 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.1184 | 0 | CMO East 1 | IMGA223247 | ROKEBY GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510833356 | CMO | CMO East 1 | May | 9 | A | Matt Payne | Robert Ashdown | IMGA223247 | ROKEBY GARDENS | 510833356 | T1 Policy | 0 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223247 | ROKEBY GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
220001382168 | CMO | CMO East 1 | May | 9 | A | Matt Payne | Robert Ashdown | IMGA223247 | ROKEBY GARDENS | 220001382168 | T1 Policy | 0 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223247 | ROKEBY GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510813633 | CMO | CMO East 1 | June | 10 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COMPTON AVENUE | 510813633 | T1 Policy | 66.8 | Policy | 6 | CI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.676 | 0 | CMO East 1 | IMGA223309 | COMPTON AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510872769 | CMO | CMO East 1 | June | 10 | A | Matt Payne | Robert Ashdown | IMGA223217 | MANOR ROAD | 510872769 | T1 Policy | 11.8 | Policy | 8 | CI | 30 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.354 | 0 | CMO East 1 | IMGA223217 | MANOR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510845984 | CMO | CMO East 1 | June | 10 | A | Matt Payne | Robert Ashdown | IMGA223247 | DARNLEY ROAD | 510845984 | T1 Policy | 23.5 | Policy | 4 | CI | 73 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7155 | 0 | CMO East 1 | IMGA223247 | DARNLEY ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510819460 | CMO | CMO East 1 | June | 10 | A | Matt Payne | Robert Ashdown | IMGA223247 | DARNLEY ROAD | 510819460 | T1 Policy | 16.5 | Policy | 6 | CI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1155 | 0 | CMO East 1 | IMGA223247 | DARNLEY ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510819461 | CMO | CMO East 1 | June | 10 | A | Matt Payne | Robert Ashdown | IMGA223247 | DARNLEY ROAD | 510819461 | T1 Policy | 22.5 | Policy | 6 | CI | 106 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.385 | 0 | CMO East 1 | IMGA223247 | DARNLEY ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510851298 | CMO | CMO East 1 | June | 11 | A | Steve Edwards | Chris Brittin | IMGA221026 | HIGHBURY PLACE | 510851298 | T1 Policy | 45 | Policy | 8 | CI | 60.5 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7225 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Shaun | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
612791714 | CMO | CMO East 1 | June | 11 | A | Steve Edwards | Chris Brittin | IMGA221026 | HIGHBURY PLACE | 612791714 | T1 Policy | 100.5 | Policy | 4 | CI | 4.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4422 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Shaun | LP | SEED | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510943983 | CMO | CMO East 1 | June | 11 | A | Joshua Overfield | Peter Rattigan | IMGA223192 | HIGHVIEW AVENUE | 510943983 | T1 Policy | 25.7 | Policy | 6 | CI | 92 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3644 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510813633 | CMO | CMO East 1 | June | 11 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COMPTON AVENUE | 510813633 | T1 Policy | 66.8 | Policy | 6 | CI | 195 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.026 | 0 | CMO East 1 | IMGA223309 | COMPTON AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510872769 | CMO | CMO East 1 | June | 11 | A | Matt Payne | Robert Ashdown | IMGA223217 | MANOR ROAD | 510872769 | T1 Policy | 11.8 | Policy | 8 | CI | 75 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.885 | 0 | CMO East 1 | IMGA223217 | MANOR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510783058 | CMO | CMO East 1 | June | 11 | A | Matt Payne | Steve Moscrop | IMGA223247 | ARLINGTON ROAD | 510783058 | T1 Policy | 31.2 | Policy | 4 | CI | 118 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.6816 | 0 | CMO East 1 | IMGA223247 | ARLINGTON ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510819460 | CMO | CMO East 1 | June | 11 | A | Matt Payne | Steve Moscrop | IMGA223247 | DARNLEY ROAD | 510819460 | T1 Policy | 16.5 | Policy | 6 | CI | 83 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3695 | 0 | CMO East 1 | IMGA223247 | DARNLEY ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510845984 | CMO | CMO East 1 | June | 11 | A | Matt Payne | Steve Moscrop | IMGA223247 | HAROLD ROAD | 510845984 | T1 Policy | 23.5 | Policy | 4 | CI | 56 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.316 | 0 | CMO East 1 | IMGA223247 | HAROLD ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510972057 | CMO | CMO East 1 | June | 11 | A | Matt Payne | Steve Moscrop | IMGA223247 | SOMERSET CLOSE | 510972057 | T1 Policy | 0.3 | Policy | 4 | CI | 76 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0228 | 0 | CMO East 1 | IMGA223247 | SOMERSET CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510972058 | CMO | CMO East 1 | June | 11 | A | Matt Payne | Steve Moscrop | IMGA223247 | SOMERSET CLOSE | 510972058 | T1 Policy | 0.2 | Policy | 4 | CI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0072 | 0 | CMO East 1 | IMGA223247 | SOMERSET CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510853639 | CMO | CMO East 1 | June | 12 | A | Shaun Melluish | Chris Brittin | IMGA221001 | HOLLY TERRACE | 510853639 | T1 Policy | 16.8 | Policy | 4 | CI | 10.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1764 | 0 | CMO East 1 | IMGA221001 | HOLLY TERRACE | Camden Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510851649 | CMO | CMO East 1 | June | 12 | A | Shaun Melluish | Chris Brittin | IMGA221001 | HOLLY TERRACE | 510851649 | T2 CBA | 34.3 | Policy | 10 | CI | 0.7 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0.02401 | 0 | CMO East 1 | IMGA221001 | HOLLY TERRACE | Camden Council | East 1 | FALSE |  | Terra Firma |  | CMO KULZCEWSK, Pawel | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | CI | T2A | June
220000250442 | CMO | CMO East 1 | June | 12 | A | Joshua Overfield | Herbie Thomas | IMGA223366 | HEATH CLOSE | 220000250442 | T1 Policy | 31.1 | Policy | 4 | CI | 101 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1411 | 0 | CMO East 1 | IMGA223366 | HEATH CLOSE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 CBA | CMO HILL, Matthew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510804136 | CMO | CMO East 1 | June | 12 | A | Matt Payne | Steve Moscrop | IMGA223247 | CAVENDISH AVENUE | 510804136 | T1 Policy | 35.2 | Policy | 4 | CI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.344 | 0 | CMO East 1 | IMGA223247 | CAVENDISH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510813633 | CMO | CMO East 1 | June | 12 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COMPTON AVENUE | 510813633 | T1 Policy | 66.8 | Policy | 6 | CI | 55 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.674 | 0 | CMO East 1 | IMGA223309 | COMPTON AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510819460 | CMO | CMO East 1 | June | 12 | A | Matt Payne | Steve Moscrop | IMGA223247 | DARNLEY ROAD | 510819460 | T1 Policy | 16.5 | Policy | 6 | CI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2375 | 0 | CMO East 1 | IMGA223247 | DARNLEY ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510858211 | CMO | CMO East 1 | June | 12 | A | Matt Payne | Steve Moscrop | IMGA223255 | KELVEDON WAY | 510858211 | T1 Policy | 55.3 | Policy | 6 | CI | 45 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4885 | 0 | CMO East 1 | IMGA223255 | KELVEDON WAY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510896225 | CMO | CMO East 1 | June | 12 | A | Matt Payne | Steve Moscrop | IMGA223255 | PURLEIGH AVENUE | 510896225 | T1 Policy | 66.2 | Policy | 6 | CI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 8.937 | 0 | CMO East 1 | IMGA223255 | PURLEIGH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510833489 | CMO | CMO East 1 | June | 12 | A | Matt Payne | Robert Ashdown | IMGA223380 | FOREST ROAD | 510833489 | T1 Policy | 24.4 | Policy | 6 | CI | 145 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.538 | 0 | CMO East 1 | IMGA223380 | FOREST ROAD | Waltham Forest London Borough Council | East 1 | FALSE |  | Terra Firma | T1 CBA | tRIIO GRANT, Colin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
606689458 | CMO | CMO East 1 | June | 12 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COMPTON AVENUE | 606689458 | T1 Policy | 34.1 | Policy | 6 | CI | 172 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.8652 | 0 | CMO East 1 | IMGA223309 | COMPTON AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
DR4 Requested | CMO | CMO East 1 | June | 12 | A | Joshua Overfield | John Burns | IMGA223213 | ALLINGTON ROAD | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223213 | ALLINGTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO GRANTHAM, Colin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO East 1 | June | 12 | A | Joshua Overfield | John Burns | IMGA223213 | ALLINGTON ROAD | DR4 Requested | T1 Policy | 0 | Policy | 4 | DI | 61.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223213 | ALLINGTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO GRANTHAM, Colin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO East 1 | June | 12 | A | Joshua Overfield | John Burns | IMGA223213 | ALLINGTON ROAD | DR4 Requested | Condition | 0 | Non Policy | 4 | ST | 71 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223213 | ALLINGTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO GRANTHAM, Colin | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | June
510947263 | CMO | CMO East 1 | June | 13 | A | Shaun Melluish | Chris Brittin | IMGA221002 | WEST HILL PARK | 510947263 | T1 PAST | 9.7 | Policy | 100 | DI | 128 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2416 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLEE, Mark | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510851298 | CMO | CMO East 1 | June | 13 | A | Steve Edwards | Chris Brittin | IMGA221026 | HIGHBURY PLACE | 510851298 | T1 Policy | 45 | Policy | 8 | CI | 96 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.32 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Steven | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510903814 | CMO | CMO East 1 | June | 13 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | ROWAN WALK | 510903814 | T1 Policy | 60.6 | Policy | 6 | CI | 98 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.9388 | 0 | CMO East 1 | IMGA223196 | ROWAN WALK | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510836872 | CMO | CMO East 1 | June | 13 | A | Joshua Overfield | Wayne Garland | IMGA223302 | BERGER ROAD | 510836872 | T1 PAST | 0.3 | Policy | 4 | DI | 38.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01167 | 0 | CMO East 1 | IMGA223302 | BERGER ROAD | Hackney London Borough Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | CMO TILBURY, Clive | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510871513 | CMO | CMO East 1 | June | 13 | A | Joshua Overfield | Wayne Garland | IMGA223316 | MAFEKING AVENUE | 510871513 | T1 Policy | 18.8 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.94 | 0 | CMO East 1 | IMGA223316 | MAFEKING AVENUE | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO RUTKOWSKI, Slawomir | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510819460 | CMO | CMO East 1 | June | 13 | A | Matt Payne | Mark Pittman | IMGA223247 | BEVERLEY CRESCENT | 510819460 | T1 Policy | 16.5 | Policy | 6 | CI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2275 | 0 | CMO East 1 | IMGA223247 | BEVERLEY CRESCENT | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510804136 | CMO | CMO East 1 | June | 13 | A | Matt Payne | Mark Pittman | IMGA223247 | CAVENDISH AVENUE | 510804136 | T1 Policy | 35.2 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.76 | 0 | CMO East 1 | IMGA223247 | CAVENDISH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510847740 | CMO | CMO East 1 | June | 13 | A | Matt Payne | Mark Pittman | IMGA223255 | PURLEIGH AVENUE | 510847740 | T1 Policy | 140.7 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9849 | 0 | CMO East 1 | IMGA223255 | PURLEIGH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | SEED | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510896222 | CMO | CMO East 1 | June | 13 | A | Matt Payne | Mark Pittman | IMGA223255 | PURLEIGH AVENUE | 510896222 | T1 Policy | 46.9 | Policy | 4 | SI | 103 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.8307 | 0 | CMO East 1 | IMGA223255 | PURLEIGH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510896223 | CMO | CMO East 1 | June | 13 | A | Matt Payne | Mark Pittman | IMGA223255 | PURLEIGH AVENUE | 510896223 | T1 Policy | 19.6 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.98 | 0 | CMO East 1 | IMGA223255 | PURLEIGH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO East 1 | June | 13 | A | Joshua Overfield | John Burns | IMGA223213 | ALLINGTON ROAD | DR4 Requested | T1 Policy | 0 | Policy | 4 | DI | 76 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223213 | ALLINGTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF |  | CMO HILL, Matthew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
- | CMO | CMO East 1 | June | 13 | A | Matt Payne | Mark Pittman | IMGA223255 | PURLEIGH AVENUE | - | Condition | 0 | Non Policy | 2 | ST | 31 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223255 | PURLEIGH AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO COLLINS, Joe | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | June
631202054 | CMO | CMO East 1 | June | 14 | A | Matt Payne | Mark Pittman | IMGA223255 | KELVEDON WAY | 631202054 | T1 Policy | 196 | Policy | 4 | SI | 1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.196 | 0 | CMO East 1 | IMGA223255 | KELVEDON WAY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510866724 | CMO | CMO East 1 | June | 14 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | LINDEN LEA | 510866724 | T1 Policy | 16.3 | Policy | 6 | CI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3423 | 0 | CMO East 1 | IMGA223196 | LINDEN LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510903814 | CMO | CMO East 1 | June | 14 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | ROWAN WALK | 510903814 | T1 Policy | 60.6 | Policy | 6 | CI | 9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5454 | 0 | CMO East 1 | IMGA223196 | ROWAN WALK | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220000659633 | CMO | CMO East 1 | June | 14 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659633 | T1 Policy | 0 | Policy | 6 | CI | 109 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220000659639 | CMO | CMO East 1 | June | 14 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659639 | T1 Policy | 0 | Policy | 6 | CI | 30.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
637323351 | CMO | CMO East 1 | June | 14 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | HAMPSTEAD LANE | 637323351 | Condition | 0 | Non Policy | 6 | SI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223309 | HAMPSTEAD LANE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510791373 | CMO | CMO East 1 | June | 14 | A | Matt Payne | Mark Pittman | IMGA223247 | BEVERLEY CRESCENT | 510791373 | T1 Policy | 19.1 | Policy | 6 | CI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.674 | 0 | CMO East 1 | IMGA223247 | BEVERLEY CRESCENT | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510836350 | CMO | CMO East 1 | June | 14 | A | Matt Payne | Mark Pittman | IMGA223254 | GAYNES HILL ROAD | 510836350 | T1 Policy | 14.6 | Policy | 6 | CI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.022 | 0 | CMO East 1 | IMGA223254 | GAYNES HILL ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510858211 | CMO | CMO East 1 | June | 14 | A | Matt Payne | Mark Pittman | IMGA223255 | KELVEDON WAY | 510858211 | T1 Policy | 55.3 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.765 | 0 | CMO East 1 | IMGA223255 | KELVEDON WAY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510781151 | CMO | CMO East 1 | June | 14 | A | Joshua Overfield | Dai John | IMGA223213 | ALLINGTON ROAD | 510781151 | T1 Policy | 20.8 | Policy | 8 | CI | 98 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0384 | 0 | CMO East 1 | IMGA223213 | ALLINGTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510817584 | CMO | CMO East 1 | June | 14 | A | Matt Payne | Mark Pittman | IMGA223253 | CROSS ROAD | 510817584 | T1 Policy | 16.1 | Policy | 8 | SI | 173 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7853 | 0 | CMO East 1 | IMGA223253 | CROSS ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | June
510836349 | CMO | CMO East 1 | June | 14 | A | Matt Payne | Mark Pittman | IMGA223254 | GAYNES HILL ROAD | 510836349 | T1 Policy | 0.6 | Policy | 8 | DI | 96 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0576 | 0 | CMO East 1 | IMGA223254 | GAYNES HILL ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | June
606689458 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COMPTON AVENUE | 606689458 | T1 Policy | 34.1 | Policy | 6 | CI | -172 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | -5.8652 | 0 | CMO East 1 | IMGA223309 | COMPTON AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510813633 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | COMPTON AVENUE | 510813633 | T1 Policy | 66.8 | Policy | 6 | CI | 172 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.4896 | 0 | CMO East 1 | IMGA223309 | COMPTON AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510866722 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | LINDEN LEA | 510866722 | T1 Policy | 70.8 | Policy | 6 | CI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.416 | 0 | CMO East 1 | IMGA223196 | LINDEN LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | SEED | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510866724 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Peter Rattigan | IMGA223196 | LINDEN LEA | 510866724 | T1 Policy | 16.3 | Policy | 6 | CI | 160 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.608 | 0 | CMO East 1 | IMGA223196 | LINDEN LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510781151 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Dai John | IMGA223213 | ALLINGTON ROAD | 510781151 | T1 Policy | 20.8 | Policy | 8 | CI | 45 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.936 | 0 | CMO East 1 | IMGA223213 | ALLINGTON ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510891478 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Wayne Garland | IMGA223300 | PEMBURY ROAD | 510891478 | T1 Policy | 0.1 | Policy | 100 | DI | 113 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0113 | 0 | CMO East 1 | IMGA223300 | PEMBURY ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TILBURY, Clive | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510962009 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Wayne Garland | IMGA223315 | MORTLAKE ROAD | 510962009 | T1 Policy | 0.5 | Policy | 4 | DI | 42 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.021 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510871513 | CMO | CMO East 1 | July | 15 | A | Joshua Overfield | Wayne Garland | IMGA223316 | MAFEKING AVENUE | 510871513 | T1 Policy | 18.8 | Policy | 6 | CI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.564 | 0 | CMO East 1 | IMGA223316 | MAFEKING AVENUE | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO RUTKOWSKI, Slawomir | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510798794 | CMO | CMO East 1 | July | 15 | A | Matt Payne | Mark Pittman | IMGA223232 | BRUNSWICK GARDENS | 510798794 | T1 Policy | 47 | Policy | 4 | CI | 138 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.486 | 0 | CMO East 1 | IMGA223232 | BRUNSWICK GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510817584 | CMO | CMO East 1 | July | 15 | A | Matt Payne | Mark Pittman | IMGA223253 | CROSS ROAD | 510817584 | T1 Policy | 16.1 | Policy | 8 | SI | 90 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.449 | 0 | CMO East 1 | IMGA223253 | CROSS ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | July
510836349 | CMO | CMO East 1 | July | 15 | A | Matt Payne | Mark Pittman | IMGA223254 | GAYNES HILL ROAD | 510836349 | T1 Policy | 0.6 | Policy | 8 | DI | 165 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.099 | 0 | CMO East 1 | IMGA223254 | GAYNES HILL ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | July
510902077 | CMO | CMO East 1 | July | 15 | A | Matt Payne | Mark Pittman | IMGA223254 | RODING AVENUE | 510902077 | T1 Policy | 45.1 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1804 | 0 | CMO East 1 | IMGA223254 | RODING AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
Side Street | CMO | CMO East 1 | July | 15 | A | Matt Payne | Robert Ashdown | IMGA223420 | SOUTH GROVE | Side Street | T1 Policy | 0 | Policy | 4 | CI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223420 | SOUTH GROVE | Waltham Forest London Borough Council | East 1 | FALSE |  | Forefront | T1 SECONDARY | tRIIO O'DEA, Gerald | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510913018 | CMO | CMO East 1 | July | 15 | A | Matt Payne | Robert Ashdown | IMGA223420 | SOUTH GROVE | 510913018 | T2 CBA | 108 | Policy | 10 | SI | 153 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 16.524 | 0 | CMO East 1 | IMGA223420 | SOUTH GROVE | Waltham Forest London Borough Council | East 1 | FALSE |  | Forefront | T2 CBA CANDIDATE | tRIIO O'DEA, Gerald | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | SI | T2A | July
635646924 | CMO | CMO East 1 | July | 15 | A | Matt Payne | Robert Ashdown | IMGA223420 | ST JAMES PATH | 635646924 | T2 CBA | 96.7 | Policy | 10 | CI | 33 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 3.1911 | 0 | CMO East 1 | IMGA223420 | ST JAMES PATH | Waltham Forest London Borough Council | East 1 | FALSE |  | Forefront | T2 CBA CANDIDATE | tRIIO O'DEA, Gerald | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | CI | T2A | July
510913018 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Robert Ashdown | IMGA223420 | SOUTH GROVE | 510913018 | T2 CBA | 108 | Policy | 10 | SI | -153 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | -16.524 | 0 | CMO East 1 | IMGA223420 | SOUTH GROVE | Waltham Forest London Borough Council | East 1 | FALSE |  | Forefront | T2 CBA CANDIDATE | tRIIO O'DEA, Gerald | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | SI | T2A | July
510913018 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Robert Ashdown | IMGA223420 | SOUTH GROVE | 510913018 | T2 PAST | 230 | Policy | 10 | SI | 153 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 35.19 | 0 | CMO East 1 | IMGA223420 | SOUTH GROVE | Waltham Forest London Borough Council | East 1 | FALSE | PAST | Forefront | T2 CBA CANDIDATE | tRIIO O'DEA, Gerald | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | SI | T2A | July
510845220 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Vic Roxborough | IMGA223232 | HANOVER GARDENS | 510845220 | T1 Policy | 4.7 | Policy | 6 | CI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.658 | 0 | CMO East 1 | IMGA223232 | HANOVER GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510845221 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Vic Roxborough | IMGA223232 | HANOVER GARDENS | 510845221 | T1 Policy | 19 | Policy | 6 | CI | 152 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.888 | 0 | CMO East 1 | IMGA223232 | HANOVER GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510836348 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Vic Roxborough | IMGA223254 | GAYNES HILL ROAD | 510836348 | T1 Policy | 11.7 | Policy | 6 | CI | 66 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7722 | 0 | CMO East 1 | IMGA223254 | GAYNES HILL ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510902077 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Vic Roxborough | IMGA223254 | RODING AVENUE | 510902077 | T1 Policy | 5.8 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.406 | 0 | CMO East 1 | IMGA223254 | RODING AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510902078 | CMO | CMO East 1 | July | 16 | A | Matt Payne | Vic Roxborough | IMGA223254 | RODING AVENUE | 510902078 | T1 Policy | 8.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0178 | 0 | CMO East 1 | IMGA223254 | RODING AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510839691 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | Paul Cafferkey | IMGA223213 | GRAHAM ROAD | 510839691 | T1 Policy | 18.3 | Policy | 4 | CI | 128 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3424 | 0 | CMO East 1 | IMGA223213 | GRAHAM ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220000659639 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659639 | T1 Policy | 1.9 | Policy | 6 | CI | 98 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1862 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510962006 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | James Cox | IMGA223315 | MORTLAKE ROAD | 510962006 | T1 PAST | 367.4 | Policy | 6 | DI | 74 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 27.1876 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | CMO KULZCEWSK, Pawel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510962009 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | James Cox | IMGA223315 | MORTLAKE ROAD | 510962009 | T1 Policy | 25.7 | Policy | 4 | DI | 41 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0537 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510962011 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | James Cox | IMGA223315 | MORTLAKE ROAD | 510962011 | T1 Policy | 27.3 | Policy | 4 | DI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2558 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
606715325 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | James Cox | IMGA223315 | MORTLAKE ROAD | 606715325 | T1 Policy | 27.3 | Policy | 4 | DI | 1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0273 | 0 | CMO East 1 | IMGA223315 | MORTLAKE ROAD | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510871513 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | James Cox | IMGA223316 | MAFEKING AVENUE | 510871513 | T1 Policy | 4 | Policy | 6 | CI | 37 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.148 | 0 | CMO East 1 | IMGA223316 | MAFEKING AVENUE | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO RUTKOWSKI, Slawomir | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510821856 | CMO | CMO East 1 | July | 16 | A | Michael Solomon | Herbie Thomas | IMGA223367 | DOLLIS ROAD | 510821856 | T1 Policy | 2 | Policy | 8 | CI | 130 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.26 | 0 | CMO East 1 | IMGA223367 | DOLLIS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO HILL, Matthew | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510817586 | CMO | CMO East 1 | July | 17 | A | Matt Payne | Vic Roxborough | IMGA223253 | CROSS ROAD | 510817586 | T1 Policy | 2.3 | Policy | 4 | CI | 39 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0897 | 0 | CMO East 1 | IMGA223253 | CROSS ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510886037 | CMO | CMO East 1 | July | 17 | A | Matt Payne | Vic Roxborough | IMGA223254 | OAKWOOD CLOSE | 510886037 | T1 Policy | 5.8 | Policy | 4 | CI | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.435 | 0 | CMO East 1 | IMGA223254 | OAKWOOD CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510886038 | CMO | CMO East 1 | July | 17 | A | Matt Payne | Vic Roxborough | IMGA223254 | OAKWOOD CLOSE | 510886038 | T1 Policy | 11.8 | Policy | 4 | CI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3186 | 0 | CMO East 1 | IMGA223254 | OAKWOOD CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510845220 | CMO | CMO East 1 | July | 17 | A | Matt Payne | Vic Roxborough | IMGA223232 | HANOVER GARDENS | 510845220 | T1 Policy | 4.7 | Policy | 6 | CI | 92.7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.43569 | 0 | CMO East 1 | IMGA223232 | HANOVER GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510871513 | CMO | CMO East 1 | July | 17 | A | Michael Solomon | James Cox | IMGA223316 | MAFEKING AVENUE | 510871513 | T1 Policy | 4 | Policy | 6 | CI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.084 | 0 | CMO East 1 | IMGA223316 | MAFEKING AVENUE | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO SULLENS, Dave | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510883514 | CMO | CMO East 1 | July | 17 | A | Michael Solomon | Peter Rattigan | IMGA223196 | NORRICE LEA | 510883514 | T1 Policy | 2.9 | Policy | 6 | CI | 43 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1247 | 0 | CMO East 1 | IMGA223196 | NORRICE LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220000659639 | CMO | CMO East 1 | July | 17 | A | Michael Solomon | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659639 | T1 Policy | 1.9 | Policy | 6 | CI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.133 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510839692 | CMO | CMO East 1 | July | 17 | A | Michael Solomon | Paul Cafferkey | IMGA223213 | GRAHAM ROAD | 510839692 | T1 Policy | 7.5 | Policy | 8 | CI | 45 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3375 | 0 | CMO East 1 | IMGA223213 | GRAHAM ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510851298 | CMO | CMO East 1 | July | 17 | A | TBA - Lon | TBA - Lon | IMGA221026 | HIGHBURY PLACE | 510851298 | T1 Policy | 84.8 | Policy | 8 | CI | 47 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.9856 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | STAFF CORRIGAN, Drew | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510913018 | CMO | CMO East 1 | July | 17 | A | Matt Payne | Kevin Lawlor | IMGA223420 | SOUTH GROVE | 510913018 | T2 PAST | 230 | Policy | 10 | SI | 18 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 4.14 | 0 | CMO East 1 | IMGA223420 | SOUTH GROVE | Waltham Forest London Borough Council | East 1 | FALSE | PAST | Forefront | T2 CBA CANDIDATE | tRIIO O'DEA, Gerald | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | SI | T2A | July
510943983 | CMO | CMO East 1 | July | 18 | A | Joshua Overfield | Peter Rattigan | IMGA223192 | HIGHVIEW AVENUE | 510943983 | T1 Policy | 8.4 | Policy | 6 | CI | 220 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.848 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510972088 | CMO | CMO East 1 | July | 18 | A | Matt Payne | Vic Roxborough | IMGA223232 | BENREK CLOSE | 510972088 | T1 Policy | 5.4 | Policy | 100 | DI | 101 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5454 | 0 | CMO East 1 | IMGA223232 | BENREK CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510813300 | CMO | CMO East 1 | July | 18 | A | Matt Payne | Vic Roxborough | IMGA223232 | COLVIN GARDENS | 510813300 | T1 Policy | 2.5 | Policy | 6 | CI | 204 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO East 1 | IMGA223232 | COLVIN GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220001811028 | CMO | CMO East 1 | July | 18 | A | Matt Payne | Vic Roxborough | IMGA223234 | TOMSWOOD HILL | 220001811028 | T1 Policy | 0 | Policy | 4 | CI | 128 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223234 | TOMSWOOD HILL | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510817586 | CMO | CMO East 1 | July | 18 | A | Matt Payne | Vic Roxborough | IMGA223253 | CROSS ROAD | 510817586 | T1 Policy | 2.3 | Policy | 4 | CI | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3312 | 0 | CMO East 1 | IMGA223253 | CROSS ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510841438 | CMO | CMO East 1 | July | 18 | A | Matt Payne | Vic Roxborough | IMGA223254 | GREEN WALK | 510841438 | T1 Policy | 1.8 | Policy | 4 | CI | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.135 | 0 | CMO East 1 | IMGA223254 | GREEN WALK | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510886037 | CMO | CMO East 1 | July | 18 | A | Matt Payne | Vic Roxborough | IMGA223254 | OAKWOOD CLOSE | 510886037 | T1 Policy | 5.8 | Policy | 4 | CI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0348 | 0 | CMO East 1 | IMGA223254 | OAKWOOD CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO COLLINS, Joe | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510883514 | CMO | CMO East 1 | July | 18 | A | Michael Solomon | Peter Rattigan | IMGA223196 | NORRICE LEA | 510883514 | T1 Policy | 2.9 | Policy | 6 | CI | 125 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3625 | 0 | CMO East 1 | IMGA223196 | NORRICE LEA | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510839691 | CMO | CMO East 1 | July | 18 | A | Michael Solomon | Paul Cafferkey | IMGA223213 | GRAHAM ROAD | 510839691 | T1 Policy | 18.3 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0366 | 0 | CMO East 1 | IMGA223213 | GRAHAM ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510839692 | CMO | CMO East 1 | July | 18 | A | Michael Solomon | Paul Cafferkey | IMGA223213 | GRAHAM ROAD | 510839692 | T1 Policy | 7.5 | Policy | 8 | CI | 58 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.435 | 0 | CMO East 1 | IMGA223213 | GRAHAM ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
220000659639 | CMO | CMO East 1 | July | 18 | A | Michael Solomon | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659639 | T1 Policy | 1.9 | Policy | 6 | CI | 188 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3572 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510871513 | CMO | CMO East 1 | July | 18 | A | Michael Solomon | James Cox | IMGA223316 | MAFEKING AVENUE | 510871513 | T1 Policy | 4 | Policy | 6 | CI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO East 1 | IMGA223316 | MAFEKING AVENUE | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO SULLENS, Dave | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
637323351 | CMO | CMO East 1 | August | 19 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | HAMPSTEAD LANE | 637323351 | Condition | 0 | Non Policy | 6 | SI | -135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223309 | HAMPSTEAD LANE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
637323351 | CMO | CMO East 1 | August | 19 | A | Joshua Overfield | Herbie Thomas | IMGA223309 | HAMPSTEAD LANE | 637323351 | T1 Policy | 0 | Policy | 6 | SI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223309 | HAMPSTEAD LANE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510817322 | CMO | CMO East 1 | August | 19 | A | Michael Solomon | Paul Cafferkey | IMGA223195 | CROMWELL CLOSE | 510817322 | T1 Policy | 4.4 | Policy | 4 | CI | 178 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7832 | 0 | CMO East 1 | IMGA223195 | CROMWELL CLOSE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510823034 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223236 | DRYDEN CLOSE | 510823034 | T1 Policy | 10.5 | Policy | 4 | CI | 244 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.562 | 0 | CMO East 1 | IMGA223236 | DRYDEN CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510915728 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223254 | RODING LANE NORTH | 510915728 | T1 Policy | 3.2 | Policy | 4 | CI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.112 | 0 | CMO East 1 | IMGA223254 | RODING LANE NORTH | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 ENM CONDITION SPECIFIED | CMO COLLINS, Joe | LP | ENM P3 | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
633252142 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223232 | COLVIN GARDENS | 633252142 | T1 Policy | 8.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0178 | 0 | CMO East 1 | IMGA223232 | COLVIN GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
633252143 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223232 | COLVIN GARDENS | 633252143 | T1 Policy | 8.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0178 | 0 | CMO East 1 | IMGA223232 | COLVIN GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220001811028 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223234 | TOMSWOOD HILL | 220001811028 | T1 Policy | 0 | Policy | 4 | CI | 195 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223234 | TOMSWOOD HILL | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510813300 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223232 | COLVIN GARDENS | 510813300 | T1 Policy | 2.5 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.25 | 0 | CMO East 1 | IMGA223232 | COLVIN GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510871513 | CMO | CMO East 1 | August | 19 | A | Michael Solomon | James Cox | IMGA223316 | MAFEKING AVENUE | 510871513 | T1 Policy | 4 | Policy | 6 | CI | 38 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.152 | 0 | CMO East 1 | IMGA223316 | MAFEKING AVENUE | Newham London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO SULLENS, Dave | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510902779 | CMO | CMO East 1 | August | 19 | A | TBA - Lon | TBA - Lon | IMGA221026 | HIGHBURY PLACE | 510902779 | T1 Policy | 22.7 | Policy | 6 | DI | 93 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1111 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma |  | tRIIO CUMMINS, Shaun | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510915728 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223254 | RODING LANE NORTH | 510915728 | T1 Policy | 3.2 | Policy | 6 | CI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.288 | 0 | CMO East 1 | IMGA223254 | RODING LANE NORTH | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 ENM CONDITION SPECIFIED | CMO COLLINS, Joe | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220000659633 | CMO | CMO East 1 | August | 19 | A | Michael Solomon | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659633 | T1 Policy | 1.8 | Policy | 6 | CI | 240 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.432 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220001511495 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Vic Roxborough | IMGA223232 | COLVIN GARDENS | 220001511495 | T1 Policy | 3.7 | Policy | 6 | CI | 56 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2072 | 0 | CMO East 1 | IMGA223232 | COLVIN GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510821856 | CMO | CMO East 1 | August | 19 | A | Michael Solomon | Herbie Thomas | IMGA223367 | DOLLIS ROAD | 510821856 | T1 Policy | 2 | Policy | 8 | CI | 60 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO East 1 | IMGA223367 | DOLLIS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO HILL, Matthew | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510913018 | CMO | CMO East 1 | August | 19 | A | Matt Payne | Kevin Lawlor | IMGA223420 | SOUTH GROVE | 510913018 | T2 PAST | 230 | Policy | 10 | DI | 120 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 27.6 | 0 | CMO East 1 | IMGA223420 | SOUTH GROVE | Waltham Forest London Borough Council | East 1 | FALSE | PAST | Forefront | T2 CBA CANDIDATE | CMO GILBERT, Daniel | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | August
510853825 | CMO | CMO East 1 | August | 20 | A | Michael Solomon | Peter Rattigan | IMGA223196 | HOLNE CHASE | 510853825 | T1 Policy | 3.9 | Policy | 8 | CI | 85 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3315 | 0 | CMO East 1 | IMGA223196 | HOLNE CHASE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510821856 | CMO | CMO East 1 | August | 20 | A | Michael Solomon | Herbie Thomas | IMGA223367 | DOLLIS ROAD | 510821856 | T1 Policy | 2 | Policy | 8 | SI | 73 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.146 | 0 | CMO East 1 | IMGA223367 | DOLLIS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510994341 | CMO | CMO East 1 | August | 20 | A | Michael Solomon | Herbie Thomas | IMGA223367 | DOLLIS ROAD | 510994341 | T1 Policy | 2 | Policy | 8 | SI | 34 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.068 | 0 | CMO East 1 | IMGA223367 | DOLLIS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 CBA | CMO CRUZ, Abel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510845221 | CMO | CMO East 1 | August | 20 | A | Steve Edwards | Vic Roxborough | IMGA223232 | HANOVER GARDENS | 510845221 | T1 Policy | 19 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.038 | 0 | CMO East 1 | IMGA223232 | HANOVER GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510925945 | CMO | CMO East 1 | August | 20 | A | Steve Edwards | Vic Roxborough | IMGA223234 | TOMSWOOD HILL | 510925945 | T1 Policy | 14.1 | Policy | 4 | CI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4675 | 0 | CMO East 1 | IMGA223234 | TOMSWOOD HILL | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510823033 | CMO | CMO East 1 | August | 20 | A | Steve Edwards | Vic Roxborough | IMGA223236 | DRYDEN CLOSE | 510823033 | T1 Policy | 27 | Policy | 4 | CI | 218 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.886 | 0 | CMO East 1 | IMGA223236 | DRYDEN CLOSE | Redbridge London Borough Council | East 1 | FALSE |  | Murray |  | CMO McGowan, Rory | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510851298 | CMO | CMO East 1 | August | 20 | A | TBA - Lon | TBA - Lon | IMGA221026 | HIGHBURY PLACE | 510851298 | T1 Policy | 84.8 | Policy | 8 | CI | 49 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.1552 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Shaun | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
220000834170 | CMO | CMO East 1 | August | 20 | A | TBA - Lon | TBA - Lon | IMGA221026 | HIGHBURY PLACE | 220000834170 | T1 PAST | 358.5 | Policy | 100 | DI | 0.3 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.10755 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | tRIIO CUMMINS, Shaun | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
220001188941 | CMO | CMO East 1 | August | 20 | A | TBA - Lon | TBA - Lon | IMGA221026 | HIGHBURY PLACE | 220001188941 | T1 Policy | 6.8 | Policy | 8 | SI | 3 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0204 | 0 | CMO East 1 | IMGA221026 | HIGHBURY PLACE | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Shaun | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510781036 | CMO | CMO East 1 | August | 21 | A | Michael Solomon | Paul Cafferkey | IMGA223201 | ALLANDALE AVENUE | 510781036 | T1 Policy | 3 | Policy | 6 | CI | 220 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.66 | 0 | CMO East 1 | IMGA223201 | ALLANDALE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
- | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Drew Corrigan | IMGA223221 | BEEHIVE LANE | - | T1 Policy | 0 | Policy | 6 | CI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223221 | BEEHIVE LANE | Redbridge London Borough Council | East 1 | FALSE |  | Terra Firma |  | tRIIO CLEE, Richard | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
daf | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Drew Corrigan | IMGA223221 | BEEHIVE LANE | daf | T1 Policy | 0 | Policy | 6 | CI | 17.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223221 | BEEHIVE LANE | Redbridge London Borough Council | East 1 | FALSE |  | Terra Firma |  | tRIIO CLEE, Richard | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
DR4 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Drew Corrigan | IMGA223221 | BEEHIVE LANE | DR4 | T1 Policy | 0 | Policy | 9 | CI | 3 | inch | 9inch | Abandonment 9” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223221 | BEEHIVE LANE | Redbridge London Borough Council | East 1 | FALSE |  | Terra Firma |  | tRIIO CLEE, Richard | LP | #N/A | 9” | 9 |  | Policy | Tier 2 | CI | T2A | August
510789658 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Drew Corrigan | IMGA223221 | BEEHIVE LANE | 510789658 | T1 Policy | 1.5 | Policy | 6 | CI | 192 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.288 | 0 | CMO East 1 | IMGA223221 | BEEHIVE LANE | Redbridge London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CLEE, Richard | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510819737 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Vic Roxborough | IMGA223235 | DAVIDS WAY | 510819737 | T1 Policy | 28.6 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.43 | 0 | CMO East 1 | IMGA223235 | DAVIDS WAY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510819738 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Vic Roxborough | IMGA223235 | DAVIDS WAY | 510819738 | T1 Policy | 9.7 | Policy | 4 | SI | 76 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7372 | 0 | CMO East 1 | IMGA223235 | DAVIDS WAY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510823033 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Vic Roxborough | IMGA223236 | DRYDEN CLOSE BACK ALLEY | 510823033 | T1 Policy | 27 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.27 | 0 | CMO East 1 | IMGA223236 | DRYDEN CLOSE BACK ALLEY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO McGowan, Rory | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510845984 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Vic Roxborough | IMGA223247 | HAROLD ROAD | 510845984 | T1 Policy | 10.8 | Policy | 4 | CI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.378 | 0 | CMO East 1 | IMGA223247 | HAROLD ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510883501 | CMO | CMO East 1 | August | 21 | A | Steve Edwards | Kevin Lawlor | IMGA223281 | NORMANTON PARK | 510883501 | T1 Policy | 3.2 | Policy | 8 | CI | 93 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2976 | 0 | CMO East 1 | IMGA223281 | NORMANTON PARK | Waltham Forest London Borough Council | East 1 | FALSE |  | KLT | T1 SECONDARY | CMO WHEELER, Liam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510881467 | CMO | CMO East 1 | August | 22 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881467 | T1 Policy | 10.6 | Policy | 6 | DI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.848 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO COONEY, Martin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510870133 | CMO | CMO East 1 | August | 22 | A | Michael Solomon | Paul Cafferkey | IMGA223212 | EATON ROAD | 510870133 | T1 PAST | 423.3 | Policy | 4 | DI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 40.2135 | 0 | CMO East 1 | IMGA223212 | EATON ROAD | Barnet London Borough Council | East 1 | FALSE | PAST | DPF | T1 PAST | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510819006 | CMO | CMO East 1 | August | 22 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 510819006 | T1 Policy | 20.8 | Policy | 6 | CI | 96 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9968 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220000659633 | CMO | CMO East 1 | August | 22 | A | Michael Solomon | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659633 | T1 Policy | 1.8 | Policy | 6 | CI | 50.4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.09072 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF |  | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220000659639 | CMO | CMO East 1 | August | 22 | A | Michael Solomon | Herbie Thomas | IMGA223309 | COURTENAY AVENUE | 220000659639 | T1 Policy | 1.9 | Policy | 6 | CI | 14.3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02717 | 0 | CMO East 1 | IMGA223309 | COURTENAY AVENUE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510938033 | CMO | CMO East 1 | August | 22 | A | Michael Solomon | Herbie Thomas | IMGA223312 | WIGHTMAN ROAD | 510938033 | T2 PAST | 242.9 | Policy | 400 | DI | 115 | mm | 400mm | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 27.9335 | 0 | CMO East 1 | IMGA223312 | WIGHTMAN ROAD | Haringey Council | East 1 | FALSE | PAST | DPF | T2 PAST | CMO BARAKU, Zenel | LP | #N/A | >12-17” | 400 |  | Policy | Tier 2 | DI | T2A | August
510902779 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Drew Corrigan | IMGA221026 | HIGHBURY CRESCENT | 510902779 | T1 Policy | 22.7 | Policy | 6 | DI | 66 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4982 | 0 | CMO East 1 | IMGA221026 | HIGHBURY CRESCENT | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Shaun | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
DR4 Requested | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Drew Corrigan | IMGA221026 | HIGHBURY CRESCENT | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA221026 | HIGHBURY CRESCENT | Islington Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO CUMMINS, Shaun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510931706 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Vic Roxborough | IMGA223235 | WALDEN WAY | 510931706 | T1 Policy | 44.6 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.46 | 0 | CMO East 1 | IMGA223235 | WALDEN WAY | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510894813 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Vic Roxborough | IMGA223238 | PRESTON DRIVE | 510894813 | T1 Policy | 4.6 | Policy | 4 | CI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.437 | 0 | CMO East 1 | IMGA223238 | PRESTON DRIVE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510810638 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Vic Roxborough | IMGA223246 | CLARISSA ROAD | 510810638 | T1 Policy | 5.5 | Policy | 4 | CI | 131 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7205 | 0 | CMO East 1 | IMGA223246 | CLARISSA ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510883501 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Kevin Lawlor | IMGA223281 | NORMANTON PARK | 510883501 | T1 Policy | 3.2 | Policy | 8 | CI | 178 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5696 | 0 | CMO East 1 | IMGA223281 | NORMANTON PARK | Waltham Forest London Borough Council | East 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
DR4 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Drew Corrigan | IMGA223221 | BEEHIVE LANE | DR4 | T1 Policy | 0 | Policy | 9 | CI | -3 | inch | 9inch | Abandonment 9” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223221 | BEEHIVE LANE | Redbridge London Borough Council | East 1 | FALSE |  | Terra Firma |  | tRIIO CLEE, Richard | LP | #N/A | 9” | 9 |  | Policy | Tier 2 | CI | T2A | August
DR4 | CMO | CMO East 1 | August | 22 | A | Steve Edwards | Drew Corrigan | IMGA223221 | BEEHIVE LANE | DR4 | T2 CBA | 0 | Policy | 9 | CI | 3 | inch | 9inch | Abandonment 9” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223221 | BEEHIVE LANE | Redbridge London Borough Council | East 1 | FALSE |  | Terra Firma |  | tRIIO CLEE, Richard | LP | #N/A | 9” | 9 |  | Policy | Tier 2 | CI | T2A | August
510853825 | CMO | CMO East 1 | September | 23 | A | Michael Solomon | Peter Rattigan | IMGA223196 | HOLNE CHASE | 510853825 | T1 Policy | 3.9 | Policy | 8 | CI | 106 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4134 | 0 | CMO East 1 | IMGA223196 | HOLNE CHASE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510965086 | CMO | CMO East 1 | September | 23 | A | Michael Solomon | Herbie Thomas | IMGA223197 | ASHBURNHAM CLOSE | 510965086 | T1 Policy | 37.9 | Policy | 100 | DI | 23 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8717 | 0 | CMO East 1 | IMGA223197 | ASHBURNHAM CLOSE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510965087 | CMO | CMO East 1 | September | 23 | A | Michael Solomon | Herbie Thomas | IMGA223197 | ASHBURNHAM CLOSE | 510965087 | T1 Policy | 8.5 | Policy | 100 | DI | 58 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.493 | 0 | CMO East 1 | IMGA223197 | ASHBURNHAM CLOSE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510819006 | CMO | CMO East 1 | September | 23 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 510819006 | T1 Policy | 20.8 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1248 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510889813 | CMO | CMO East 1 | September | 23 | A | Michael Solomon | Peter Rattigan | IMGA223214 | PARK ROAD | 510889813 | Condition | 0 | Non Policy | 8 | ST | 22 | inch | 8inch | Abandonment 8” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223214 | PARK ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 CONNECTED | CMO ZHUKA, Romeo | LP | #N/A | 8” | 8 |  | Non Policy | Tier 1 | ST | ST LP 8" | September
510889843 | CMO | CMO East 1 | September | 23 | A | Michael Solomon | Peter Rattigan | IMGA223214 | PARK ROAD | 510889843 | Condition | 0 | Non Policy | 200 | ST | 20 | mm | 200mm | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223214 | PARK ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 CONNECTED | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 200 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | September
510784730 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Vic Roxborough | IMGA223230 | FULLWELL AVENUE | 510784730 | T1 Policy | 13 | Policy | 200 | DI | 37 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.481 | 0 | CMO East 1 | IMGA223230 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
631175290 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Vic Roxborough | IMGA223230 | FULLWELL AVENUE | 631175290 | T1 Policy | 6 | Policy | 4 | CI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.09 | 0 | CMO East 1 | IMGA223230 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510970496 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Vic Roxborough | IMGA223230 | FULLWELL AVENUE | 510970496 | T1 Policy | 2.1 | Policy | 8 | CI | 48 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1008 | 0 | CMO East 1 | IMGA223230 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510894812 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Vic Roxborough | IMGA223238 | PRESTON DRIVE | 510894812 | T1 Policy | 10 | Policy | 100 | DI | 125 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.25 | 0 | CMO East 1 | IMGA223238 | PRESTON DRIVE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO DARBY, Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510894813 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Vic Roxborough | IMGA223238 | PRESTON DRIVE | 510894813 | T1 Policy | 4.6 | Policy | 4 | CI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.184 | 0 | CMO East 1 | IMGA223238 | PRESTON DRIVE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO DARBY, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510810638 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Vic Roxborough | IMGA223246 | CLARISSA ROAD | 510810638 | T1 Policy | 5.5 | Policy | 4 | CI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.451 | 0 | CMO East 1 | IMGA223246 | CLARISSA ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510883502 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Kevin Lawlor | IMGA223281 | NORMANTON PARK | 510883502 | T1 Policy | 5.3 | Policy | 8 | CI | 61 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3233 | 0 | CMO East 1 | IMGA223281 | NORMANTON PARK | Waltham Forest London Borough Council | East 1 | FALSE |  | KLT | T1 SECONDARY | CMO WHEELER, Liam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
638623423 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Kevin Lawlor | IMGA223281 | NORMANTON PARK | 638623423 | T1 Policy | 11.5 | Policy | 8 | CI | 1 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0115 | 0 | CMO East 1 | IMGA223281 | NORMANTON PARK | Waltham Forest London Borough Council | East 1 | FALSE |  | KLT | T1 SECONDARY | CMO WHEELER, Liam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
220001280302 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Kevin Lawlor | IMGA223281 | NORMANTON PARK | 220001280302 | T1 Policy | 8.9 | Policy | 4 | CI | 1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0089 | 0 | CMO East 1 | IMGA223281 | NORMANTON PARK | Waltham Forest London Borough Council | East 1 | FALSE |  | KLT | T1 SECONDARY | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001280306 | CMO | CMO East 1 | September | 23 | A | Steve Edwards | Kevin Lawlor | IMGA223281 | NORMANTON PARK | 220001280306 | T1 Policy | 8.9 | Policy | 4 | CI | 1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0089 | 0 | CMO East 1 | IMGA223281 | NORMANTON PARK | Waltham Forest London Borough Council | East 1 | FALSE |  | KLT | T1 SECONDARY | CMO WHEELER, Liam | LP | SEED | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510881472 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881472 | T1 Policy | 21.4 | Policy | 6 | CI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.605 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SEED | CMO BARAKU, Zenel | LP | SEED | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510781036 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Paul Cafferkey | IMGA223201 | ALLANDALE AVENUE | 510781036 | T1 Policy | 3 | Policy | 6 | CI | 130 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.39 | 0 | CMO East 1 | IMGA223201 | ALLANDALE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510781038 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Paul Cafferkey | IMGA223201 | ALLANDALE AVENUE | 510781038 | T1 Policy | 8.1 | Policy | 6 | CI | 45 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3645 | 0 | CMO East 1 | IMGA223201 | ALLANDALE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510870133 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Paul Cafferkey | IMGA223212 | EATON ROAD | 510870133 | T1 PAST | 423.3 | Policy | 4 | DI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 21.165 | 0 | CMO East 1 | IMGA223212 | EATON ROAD | Barnet London Borough Council | East 1 | FALSE | PAST | DPF | T1 PAST | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
606693079 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Paul Cafferkey | IMGA223212 | NEW BRENT STREET | 606693079 | T1 Policy | 14.7 | Policy | 4 | DI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0882 | 0 | CMO East 1 | IMGA223212 | NEW BRENT STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510819006 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 510819006 | T1 Policy | 20.8 | Policy | 6 | CI | 94 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9552 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220001444976 | CMO | CMO East 1 | September | 24 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 220001444976 | T1 Policy | 6 | Policy | 6 | CI | 4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.024 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510947263 | CMO | CMO East 1 | September | 24 | A | Steve Edwards | Drew Corrigan | IMGA221002 | WEST HILL PARK | 510947263 | T1 PAST | 222.1 | Policy | 100 | DI | 24 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.3304 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | tRIIO GRANT, Colin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510783524 | CMO | CMO East 1 | September | 24 | A | Steve Edwards | Vic Roxborough | IMGA223246 | ARTHUR ROAD | 510783524 | T1 Policy | 7.3 | Policy | 4 | CI | 117 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8541 | 0 | CMO East 1 | IMGA223246 | ARTHUR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510783525 | CMO | CMO East 1 | September | 24 | A | Steve Edwards | Vic Roxborough | IMGA223246 | ARTHUR ROAD | 510783525 | T1 Policy | 5.9 | Policy | 4 | CI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1534 | 0 | CMO East 1 | IMGA223246 | ARTHUR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510810638 | CMO | CMO East 1 | September | 24 | A | Steve Edwards | Vic Roxborough | IMGA223246 | CLARISSA ROAD | 510810638 | T1 Policy | 5.5 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0385 | 0 | CMO East 1 | IMGA223246 | CLARISSA ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510878296 | CMO | CMO East 1 | September | 24 | A | Steve Edwards | Vic Roxborough | IMGA223250 | MONKHAMS AVENUE | 510878296 | T1 Policy | 3.2 | Policy | 6 | CI | 97 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3104 | 0 | CMO East 1 | IMGA223250 | MONKHAMS AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
603478885 | CMO | CMO East 1 | September | 24 | A | TBA - Lon | Drew Corrigan | IMGA223419 | STATION ROAD | 603478885 | T3 CBA | 0 | Policy | 18 | CI | 26.8 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223419 | STATION ROAD | Barnet London Borough Council | East 1 | FALSE |  | Terra Firma |  | CMO NOLAN, Daniel | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | September
605250352 | CMO | CMO East 1 | September | 24 | A | TBA - Lon | Drew Corrigan | IMGA223419 | STATION ROAD | 605250352 | T3 CBA | 0 | Policy | 18 | CI | 22.7 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223419 | STATION ROAD | Barnet London Borough Council | East 1 | FALSE |  | Terra Firma |  | CMO NOLAN, Daniel | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | September
220001993825 | CMO | CMO East 1 | September | 24 | A | TBA - Lon | Drew Corrigan | IMGA223419 | STATION ROAD | 220001993825 | T3 CBA | 0 | Policy | 18 | CI | 25.6 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223419 | STATION ROAD | Barnet London Borough Council | East 1 | FALSE |  | Terra Firma |  | CMO NOLAN, Daniel | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | September
604094147 | CMO | CMO East 1 | September | 24 | A | TBA - Lon | Drew Corrigan | IMGA223419 | STATION ROAD | 604094147 | T3 PAST | 563 | Policy | 18 | DI | 41.5 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 23.3645 | 0 | CMO East 1 | IMGA223419 | STATION ROAD | Barnet London Borough Council | East 1 | FALSE | PAST | Terra Firma | T3 DIMP | CMO NOLAN, Daniel | MP | #N/A | 18-24” | 18 |  | Policy | Tier 3 | DI | T3 | September
510783525 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223246 | ARTHUR ROAD | 510783525 | T1 Policy | 5.9 | Policy | 4 | CI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0885 | 0 | CMO East 1 | IMGA223246 | ARTHUR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510825696 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223246 | EDGAR ROAD | 510825696 | T1 Policy | 6.4 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.32 | 0 | CMO East 1 | IMGA223246 | EDGAR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510829145 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223246 | EVA ROAD | 510829145 | T1 Policy | 5.5 | Policy | 4 | CI | 106 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.583 | 0 | CMO East 1 | IMGA223246 | EVA ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510855769 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223250 | Hutton Close | 510855769 | T1 Policy | 23.2 | Policy | 4 | DI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.16 | 0 | CMO East 1 | IMGA223250 | Hutton Close | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510877263 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223252 | MILKWELL GARDENS | 510877263 | T1 Policy | 11.5 | Policy | 4 | CI | 92 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.058 | 0 | CMO East 1 | IMGA223252 | MILKWELL GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO DARBY, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510877264 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223252 | MILKWELL GARDENS | 510877264 | T1 Policy | 12.5 | Policy | 4 | CI | 33 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4125 | 0 | CMO East 1 | IMGA223252 | MILKWELL GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO DARBY, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510943986 | CMO | CMO East 1 | September | 25 | A | Michael Solomon | Peter Rattigan | IMGA223192 | HIGHVIEW GARDENS | 510943986 | T1 Policy | 3.7 | Policy | 6 | CI | 71 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2627 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW GARDENS | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510881473 | CMO | CMO East 1 | September | 25 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881473 | T1 Policy | 6.3 | Policy | 6 | CI | 28 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1764 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BARAKU, Zenel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510881765 | CMO | CMO East 1 | September | 25 | A | Michael Solomon | Peter Rattigan | IMGA223212 | NEW BRENT STREET | 510881765 | T1 Policy | 7 | Policy | 6 | SI | 42 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.294 | 0 | CMO East 1 | IMGA223212 | NEW BRENT STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510878294 | CMO | CMO East 1 | September | 25 | A | Steve Edwards | Vic Roxborough | IMGA223250 | MONKHAMS AVENUE | 510878294 | T1 Policy | 3.1 | Policy | 6 | CI | 62 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1922 | 0 | CMO East 1 | IMGA223250 | MONKHAMS AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510780084 | CMO | CMO East 1 | September | 25 | A | Michael Solomon | James Cox | IMGA223304 | ALBION ROAD | 510780084 | T1 Policy | 10.5 | Policy | 8 | CI | 14 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.147 | 0 | CMO East 1 | IMGA223304 | ALBION ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO RUTKOWSKI, Slawomir | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510943986 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Peter Rattigan | IMGA223192 | HIGHVIEW GARDENS | 510943986 | T1 Policy | 3.7 | Policy | 6 | CI | 31 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1147 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW GARDENS | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510781035 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Herbie Thomas | IMGA223201 | ALLANDALE AVENUE | 510781035 | T1 Policy | 4.4 | Policy | 8 | CI | 140 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.616 | 0 | CMO East 1 | IMGA223201 | ALLANDALE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510781036 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Herbie Thomas | IMGA223201 | ALLANDALE AVENUE | 510781036 | T1 Policy | 3 | Policy | 6 | CI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.009 | 0 | CMO East 1 | IMGA223201 | ALLANDALE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
613761296 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Herbie Thomas | IMGA223201 | ALLANDALE AVENUE | 613761296 | T1 Policy | 9.5 | Policy | 6 | CI | 5.2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0494 | 0 | CMO East 1 | IMGA223201 | ALLANDALE AVENUE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | SEED | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510921257 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Paul Cafferkey | IMGA223208 | TEMPLE FORTUNE LANE | 510921257 | T1 Policy | 1.8 | Policy | 6 | CI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.135 | 0 | CMO East 1 | IMGA223208 | TEMPLE FORTUNE LANE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510881765 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Peter Rattigan | IMGA223212 | NEW BRENT STREET | 510881765 | T1 Policy | 7 | Policy | 6 | CI | 43 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.301 | 0 | CMO East 1 | IMGA223212 | NEW BRENT STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510819006 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 510819006 | T1 Policy | 20.8 | Policy | 6 | CI | 96 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9968 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510819381 | CMO | CMO East 1 | September | 26 | A | Michael Solomon | Paul Cafferkey | IMGA223215 | DANIEL PLACE | 510819381 | T1 Policy | 14.1 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.128 | 0 | CMO East 1 | IMGA223215 | DANIEL PLACE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510947263 | CMO | CMO East 1 | September | 26 | A | Steve Edwards | Drew Corrigan | IMGA221002 | WEST HILL PARK | 510947263 | T1 PAST | 222.1 | Policy | 100 | DI | 10 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.221 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | tRIIO GRANT, Colin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
220001950165 | CMO | CMO East 1 | September | 26 | A | Steve Edwards | Vic Roxborough | IMGA223229 | FULLWELL AVENUE | 220001950165 | T1 Policy | 0 | Policy | 4 | CI | 14 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223229 | FULLWELL AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510805937 | CMO | CMO East 1 | September | 26 | A | Steve Edwards | Vic Roxborough | IMGA223246 | CHARLES ROAD | 510805937 | T1 Policy | 6.1 | Policy | 4 | CI | 106 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6466 | 0 | CMO East 1 | IMGA223246 | CHARLES ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510825944 | CMO | CMO East 1 | September | 26 | A | Steve Edwards | Vic Roxborough | IMGA223246 | EDITH ROAD | 510825944 | T1 Policy | 6 | Policy | 4 | CI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.384 | 0 | CMO East 1 | IMGA223246 | EDITH ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510877263 | CMO | CMO East 1 | September | 26 | A | Steve Edwards | Vic Roxborough | IMGA223252 | MILKWELL GARDENS | 510877263 | T1 Policy | 11.5 | Policy | 4 | CI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0575 | 0 | CMO East 1 | IMGA223252 | MILKWELL GARDENS | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO DARBY, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001249617 | CMO | CMO East 1 | September | 26 | A | Steve Edwards | Vic Roxborough | IMGA223252 | ST BARNABAS ROAD | 220001249617 | T1 Policy | 2.9 | Policy | 6 | CI | 106 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3074 | 0 | CMO East 1 | IMGA223252 | ST BARNABAS ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO DARBY, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510943986 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | Peter Rattigan | IMGA223192 | HIGHVIEW GARDENS | 510943986 | T1 Policy | 3.7 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.148 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW GARDENS | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510881473 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881473 | T1 Policy | 6.3 | Policy | 6 | CI | 45 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2835 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BARAKU, Zenel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510921257 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | Paul Cafferkey | IMGA223208 | TEMPLE FORTUNE LANE | 510921257 | T1 Policy | 1.8 | Policy | 6 | CI | 132 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2376 | 0 | CMO East 1 | IMGA223208 | TEMPLE FORTUNE LANE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510819006 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 510819006 | T1 Policy | 20.8 | Policy | 6 | CI | 81 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6848 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510819381 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | Paul Cafferkey | IMGA223215 | DANIEL PLACE | 510819381 | T1 Policy | 14.1 | Policy | 4 | CI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.564 | 0 | CMO East 1 | IMGA223215 | DANIEL PLACE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO TURNER, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510842281 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | James Cox | IMGA223303 | GROOMBRIDGE ROAD | 510842281 | T1 Policy | 22.2 | Policy | 150 | DI | 55 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.221 | 0 | CMO East 1 | IMGA223303 | GROOMBRIDGE ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510780080 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | James Cox | IMGA223304 | ALBION ROAD | 510780080 | T1 Policy | 0 | Policy | 4 | CI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223304 | ALBION ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma |  | CMO RUTKOWSKI, Slawomir | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001280427 | CMO | CMO East 1 | September | 27 | A | Michael Solomon | James Cox | IMGA223304 | WINSTON ROAD | 220001280427 | T1 Policy | 41.7 | Policy | 4 | CI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3336 | 0 | CMO East 1 | IMGA223304 | WINSTON ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO RUTKOWSKI, Slawomir | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510825697 | CMO | CMO East 1 | September | 27 | A | Steve Edwards | Vic Roxborough | IMGA223246 | EDGAR ROAD | 510825697 | T1 Policy | 7.5 | Policy | 4 | CI | 92 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.69 | 0 | CMO East 1 | IMGA223246 | EDGAR ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510825944 | CMO | CMO East 1 | September | 27 | A | Steve Edwards | Vic Roxborough | IMGA223246 | EDITH ROAD | 510825944 | T1 Policy | 6 | Policy | 4 | CI | 18 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.108 | 0 | CMO East 1 | IMGA223246 | EDITH ROAD | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO HAILSTONE, Darren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510943986 | CMO | CMO East 1 | October | 28 | A | Michael Solomon | Peter Rattigan | IMGA223192 | HIGHVIEW GARDENS | 510943986 | T1 Policy | 3.7 | Policy | 6 | CI | 42 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1554 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW GARDENS | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510780662 | CMO | CMO East 1 | October | 28 | A | Michael Solomon | Peter Rattigan | IMGA223194 | ALEXANDRA GROVE | 510780662 | T1 Policy | 4.2 | Policy | 8 | CI | 55 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.231 | 0 | CMO East 1 | IMGA223194 | ALEXANDRA GROVE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO GRANTHAM, Colin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510881473 | CMO | CMO East 1 | October | 28 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881473 | T1 Policy | 6.3 | Policy | 6 | CI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0504 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BARAKU, Zenel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510819007 | CMO | CMO East 1 | October | 28 | A | Michael Solomon | Peter Rattigan | IMGA223214 | DALLAS ROAD | 510819007 | T1 Policy | 13 | Policy | 150 | DI | 55 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.715 | 0 | CMO East 1 | IMGA223214 | DALLAS ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
220001342129 | CMO | CMO East 1 | October | 28 | A | Michael Solomon | James Cox | IMGA223301 | SOUTHWOLD ROAD | 220001342129 | T1 Policy | 4.2 | Policy | 6 | CI | 103 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4326 | 0 | CMO East 1 | IMGA223301 | SOUTHWOLD ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLEE, Mark | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510947263 | CMO | CMO East 1 | October | 28 | A | Steve Edwards | Drew Corrigan | IMGA221002 | WEST HILL PARK | 510947263 | T1 PAST | 222.1 | Policy | 100 | DI | 63 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.9923 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE | PAST | Terra Firma | T1 PAST | tRIIO GRANT, Colin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510947264 | CMO | CMO East 1 | October | 28 | A | Steve Edwards | Drew Corrigan | IMGA221002 | WEST HILL PARK | 510947264 | T1 Policy | 51.1 | Policy | 100 | DI | 45 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2995 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO GRANT, Colin | LP | SEED | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510947269 | CMO | CMO East 1 | October | 28 | A | Steve Edwards | Drew Corrigan | IMGA221002 | WEST HILL PARK | 510947269 | Condition | 0 | Non Policy | 50 | ST | 23 | mm | 50mm | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE |  | Terra Firma | T1 CONNECTED | tRIIO GRANT, Colin | LP | #N/A | 2” | 50 |  | Non Policy | Tier 1 | ST | 2" ST | October
510878293 | CMO | CMO East 1 | October | 28 | A | Steve Edwards | Vic Roxborough | IMGA223250 | MONKHAMS AVENUE | 510878293 | T1 Policy | 13.4 | Policy | 6 | CI | 160 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.144 | 0 | CMO East 1 | IMGA223250 | MONKHAMS AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510878293 | CMO | CMO East 1 | October | 29 | A | Steve Edwards | Vic Roxborough | IMGA223250 | MONKHAMS AVENUE | 510878293 | T1 Policy | 13.4 | Policy | 6 | CI | 220 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.948 | 0 | CMO East 1 | IMGA223250 | MONKHAMS AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510915725 | CMO | CMO East 1 | October | 29 | A | Steve Edwards | Vic Roxborough | IMGA223248 | RODING LANE NORTH | 510915725 | T1 Policy | 8.5 | Policy | 6 | CI | 260 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.21 | 0 | CMO East 1 | IMGA223248 | RODING LANE NORTH | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 ENM CONDITION SPECIFIED | CMO HAILSTONE, Darren | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510921257 | CMO | CMO East 1 | October | 29 | A | Michael Solomon | Paul Cafferkey | IMGA223208 | TEMPLE FORTUNE LANE | 510921257 | T1 Policy | 1.8 | Policy | 6 | CI | 106 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1908 | 0 | CMO East 1 | IMGA223208 | TEMPLE FORTUNE LANE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510881480 | CMO | CMO East 1 | October | 29 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881480 | T1 Policy | 7.9 | Policy | 8 | CI | 85 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6715 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BARAKU, Zenel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510786390 | CMO | CMO East 1 | October | 29 | A | Michael Solomon | James Cox | IMGA223303 | BANBURY ROAD | 510786390 | T1 Policy | 11.9 | Policy | 100 | DI | 45 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5355 | 0 | CMO East 1 | IMGA223303 | BANBURY ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510842281 | CMO | CMO East 1 | October | 29 | A | Michael Solomon | James Cox | IMGA223303 | GROOMBRIDGE ROAD | 510842281 | T1 Policy | 22.2 | Policy | 150 | DI | 18 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3996 | 0 | CMO East 1 | IMGA223303 | GROOMBRIDGE ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510943986 | CMO | CMO East 1 | October | 30 | A | Michael Solomon | Paul Cafferkey | IMGA223192 | HIGHVIEW GARDENS | 510943986 | T1 Policy | 3.7 | Policy | 6 | CI | 65 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2405 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW GARDENS | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510881480 | CMO | CMO East 1 | October | 30 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881480 | T1 Policy | 7.9 | Policy | 8 | CI | 25 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1975 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BARAKU, Zenel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510864454 | CMO | CMO East 1 | October | 30 | A | Michael Solomon | Peter Rattigan | IMGA223214 | LAYFIELD ROAD | 510864454 | T1 Policy | 7.2 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.288 | 0 | CMO East 1 | IMGA223214 | LAYFIELD ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510915725 | CMO | CMO East 1 | October | 30 | A | Steve Edwards | Vic Roxborough | IMGA223248 | RODING LANE NORTH | 510915725 | T1 Policy | 8.5 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.85 | 0 | CMO East 1 | IMGA223248 | RODING LANE NORTH | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 ENM CONDITION SPECIFIED | CMO HAILSTONE, Darren | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
220001384707 | CMO | CMO East 1 | October | 30 | A | Steve Edwards | Vic Roxborough | IMGA223250 | THE GREEN | 220001384707 | T1 Policy | 3.1 | Policy | 6 | CI | 138 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4278 | 0 | CMO East 1 | IMGA223250 | THE GREEN | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510885421 | CMO | CMO East 1 | October | 30 | A | Steve Edwards | Kevin Lawlor | IMGA223294 | OAK HILL | 510885421 | T1 Policy | 4.2 | Policy | 8 | CI | 106 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4452 | 0 | CMO East 1 | IMGA223294 | OAK HILL | Waltham Forest London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO JONES, Dean | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510889420 | CMO | CMO East 1 | October | 31 | A | Steve Edwards | Vic Roxborough | IMGA223250 | PARK AVENUE | 510889420 | T1 Policy | 16.7 | Policy | 4 | CI | 262 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.3754 | 0 | CMO East 1 | IMGA223250 | PARK AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510996775 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Paul Cafferkey | IMGA223193 | BROCKLEY HILL | 510996775 | T1 CONNECTED | 0 | Non Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 1 | IMGA223193 | BROCKLEY HILL | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 CONNECTED | CMO HOXHAJ, Aurel | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510813133 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Herbie Thomas | IMGA223307 | COLNEY HATCH LANE | 510813133 | T1 Policy | 10.2 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO East 1 | IMGA223307 | COLNEY HATCH LANE | Haringey Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO PARKER, Matthew | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510853534 | CMO | CMO East 1 | October | 31 | A | Steve Edwards | Kevin Lawlor | IMGA223294 | HOLLY CRESCENT | 510853534 | T1 Policy | 7.4 | Policy | 6 | CI | 87 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6438 | 0 | CMO East 1 | IMGA223294 | HOLLY CRESCENT | Waltham Forest London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | tRIIO JONES, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510864455 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Peter Rattigan | IMGA223214 | LAYFIELD ROAD | 510864455 | T1 Policy | 9.6 | Policy | 6 | CI | 55 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.528 | 0 | CMO East 1 | IMGA223214 | LAYFIELD ROAD | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO ZHUKA, Romeo | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510878293 | CMO | CMO East 1 | October | 31 | A | Steve Edwards | Vic Roxborough | IMGA223250 | MONKHAMS AVENUE | 510878293 | T1 Policy | 13.4 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.67 | 0 | CMO East 1 | IMGA223250 | MONKHAMS AVENUE | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 SECONDARY | CMO CLARKE, Charlie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510915725 | CMO | CMO East 1 | October | 31 | A | Steve Edwards | Vic Roxborough | IMGA223248 | RODING LANE NORTH | 510915725 | T1 Policy | 8.5 | Policy | 6 | CI | 99 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8415 | 0 | CMO East 1 | IMGA223248 | RODING LANE NORTH | Redbridge London Borough Council | East 1 | FALSE |  | Murray | T1 ENM CONDITION SPECIFIED | CMO HAILSTONE, Darren | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510921257 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Paul Cafferkey | IMGA223208 | TEMPLE FORTUNE LANE | 510921257 | T1 Policy | 1.8 | Policy | 6 | CI | 47 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0846 | 0 | CMO East 1 | IMGA223208 | TEMPLE FORTUNE LANE | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO CRUZ, Abel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510943986 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Paul Cafferkey | IMGA223192 | HIGHVIEW GARDENS | 510943986 | T1 Policy | 3.7 | Policy | 6 | CI | 17 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0629 | 0 | CMO East 1 | IMGA223192 | HIGHVIEW GARDENS | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO JOSEPH, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510881480 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Paul Cafferkey | IMGA223199 | NETHER STREET | 510881480 | T1 Policy | 7.9 | Policy | 8 | DI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.79 | 0 | CMO East 1 | IMGA223199 | NETHER STREET | Barnet London Borough Council | East 1 | FALSE |  | DPF | T1 SECONDARY | CMO BARAKU, Zenel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | October
510947267 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | Drew Corrigan | IMGA221002 | WEST HILL PARK | 510947267 | T1 Policy | 33 | Policy | 100 | DI | 43 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.419 | 0 | CMO East 1 | IMGA221002 | WEST HILL PARK | Camden Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO GRANT, Colin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510914113 | CMO | CMO East 1 | October | 31 | A | Michael Solomon | James Cox | IMGA223301 | SOUTHWOLD ROAD | 510914113 | T1 Policy | 12.5 | Policy | 200 | DI | 15 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1875 | 0 | CMO East 1 | IMGA223301 | SOUTHWOLD ROAD | Hackney London Borough Council | East 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TILBURY, Clive | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
634566416 | CMO | CMO East 2 | April | 2 | A | Stuart Griffiths | Bob Sawyer | IMGA223067 | BOSCOMBE ROAD | 634566416 | T1 Policy | 30.6 | Policy | 4 | CI | 146 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.4676 | 0 | CMO East 2 | IMGA223067 | BOSCOMBE ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510941811 | CMO | CMO East 2 | April | 3 | A | Alex Wright | Dan Wigfall | IMGA223184 | WOODWARD ROAD | 510941811 | T1 Policy | 19.4 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0582 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510903850 | CMO | CMO East 2 | April | 3 | A | Alex Wright | Jake Parry | IMGA223188 | ROWDOWNS ROAD | 510903850 | T1 Policy | 16.8 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.344 | 0 | CMO East 2 | IMGA223188 | ROWDOWNS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510921484 | CMO | CMO East 2 | April | 3 | A | Dave Bamber | Chris McVeigh | IMGA223016 | TENNYSON ROAD | 510921484 | T1 Policy | 26.2 | Policy | 4 | SI | 111 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.9082 | 0 | CMO East 2 | IMGA223016 | TENNYSON ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
634566416 | CMO | CMO East 2 | April | 3 | A | Stuart Griffiths | Bob Sawyer | IMGA223067 | BOSCOMBE ROAD | 634566416 | T1 Policy | 30.6 | Policy | 4 | CI | 141 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.3146 | 0 | CMO East 2 | IMGA223067 | BOSCOMBE ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510837669 | CMO | CMO East 2 | April | 3 | A | TBA - Lon | Bob Sawyer | IMGA223066 | GLENMORE STREET | 510837669 | T1 Policy | 0.5 | Policy | 4 | DI | 22 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.011 | 0 | CMO East 2 | IMGA223066 | GLENMORE STREET | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510845007 | CMO | CMO East 2 | April | 3 | A | TBA - Lon | TBA - Lon | IMGA223066 | HAMSTEL ROAD | 510845007 | T1 Policy | 37.4 | Policy | 4 | SI | 33 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2342 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510959103 | CMO | CMO East 2 | April | 3 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959103 | T1 Policy | 6.8 | Policy | 6 | CI | 156 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0608 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
220001472367 | CMO | CMO East 2 | April | 3 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 220001472367 | T1 Policy | 0 | Policy | 6 | CI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510846120 | CMO | CMO East 2 | April | 3 | A | Stuart Griffiths | Chris Southam | IMGA223008 | HARRODS COURT | 510846120 | T1 Policy | 0.7 | Policy | 6 | DI | 111 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0777 | 0 | CMO East 2 | IMGA223008 | HARRODS COURT | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO STONEMAN, Thomas | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510888171 | CMO | CMO East 2 | April | 3 | A | Stuart Griffiths | Chris Southam | IMGA223008 | OUTWOOD COMMON ROAD | 510888171 | T1 Policy | 0.3 | Policy | 6 | DI | 42 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0126 | 0 | CMO East 2 | IMGA223008 | OUTWOOD COMMON ROAD | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO STONEMAN, Thomas | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510904827 | CMO | CMO East 2 | April | 3 | A | Dave Bamber | Mick Linwood | IMGA223261 | RUSSELL ROAD | 510904827 | T1 Policy | 42.8 | Policy | 7 | CI | 104 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.4512 | 0 | CMO East 2 | IMGA223261 | RUSSELL ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510941808 | CMO | CMO East 2 | April | 3 | A | Alex Wright | Dan Wigfall | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 96 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7184 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
220001728165 | CMO | CMO East 2 | April | 3 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728165 | T1 Policy | 0 | Policy | 8 | CI | 87 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510961724 | CMO | CMO East 2 | April | 3 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961724 | T1 Policy | 0.5 | Policy | 100 | DI | 96 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.048 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510904969 | CMO | CMO East 2 | April | 3 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | CAMBRIDGE GARDENS | 510904969 | T1 Policy | 0.2 | Policy | 4 | DI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0108 | 0 | CMO East 2 | IMGA223048 | CAMBRIDGE GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
220001322153 | CMO | CMO East 2 | April | 3 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | CAMBRIDGE GARDENS | 220001322153 | T1 Policy | 0 | Policy | 4 | DI | 71 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223048 | CAMBRIDGE GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510801485 | CMO | CMO East 2 | April | 3 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | CAMBRIDGE GARDENS | 510801485 | T1 Policy | 0.5 | Policy | 6 | DI | 17 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0085 | 0 | CMO East 2 | IMGA223048 | CAMBRIDGE GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
- | CMO | CMO East 2 | April | 3 | A | Dave Bamber | Chris McVeigh | IMGA223016 | TENNYSON ROAD | - | Condition | 0 | Non Policy | 6 | ST | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223016 | TENNYSON ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront |  | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | April
510959117 | CMO | CMO East 2 | April | 4 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959117 | T1 Policy | 9.9 | Policy | 6 | SI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3365 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510909069 | CMO | CMO East 2 | April | 4 | A | Alex Wright | James Cox | IMGA223180 | SEABROOK ROAD | 510909069 | T1 Policy | 26.4 | Policy | 4 | CI | 126 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.3264 | 0 | CMO East 2 | IMGA223180 | SEABROOK ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510941808 | CMO | CMO East 2 | April | 4 | A | Alex Wright | Dan Wigfall | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 137 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4523 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510903848 | CMO | CMO East 2 | April | 4 | A | Alex Wright | Jake Parry | IMGA223188 | ROWDOWNS ROAD | 510903848 | T1 Policy | 27.2 | Policy | 4 | CI | 155 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.216 | 0 | CMO East 2 | IMGA223188 | ROWDOWNS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510921484 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223016 | TENNYSON ROAD | 510921484 | T1 Policy | 26.2 | Policy | 4 | SI | 111 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.9082 | 0 | CMO East 2 | IMGA223016 | TENNYSON ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510888152 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223027 | OUTINGS LANE | 510888152 | T1 PAST | 1.2 | Policy | 4 | DI | 16 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0192 | 0 | CMO East 2 | IMGA223027 | OUTINGS LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | tRIIO BAXTER, Curtis | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510888153 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223027 | OUTINGS LANE | 510888153 | T1 PAST | 1.2 | Policy | 6 | DI | 41.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.05016 | 0 | CMO East 2 | IMGA223027 | OUTINGS LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | tRIIO BAXTER, Curtis | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510914489 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223027 | SPILLBUTTERS | 510914489 | T1 Policy | 1.7 | Policy | 4 | DI | 86.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14756 | 0 | CMO East 2 | IMGA223027 | SPILLBUTTERS | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO BAXTER, Curtis | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510914490 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223027 | SPILLBUTTERS | 510914490 | T1 Policy | 0.6 | Policy | 4 | DI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.069 | 0 | CMO East 2 | IMGA223027 | SPILLBUTTERS | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO BAXTER, Curtis | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510961723 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961723 | T1 Policy | 0.6 | Policy | 100 | DI | 69.1 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.04146 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510961724 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961724 | T1 Policy | 0.5 | Policy | 100 | DI | 6 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.003 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510961725 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961725 | Condition | 0 | Non Policy | 2 | ST | 22 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | CMO MARSH, Dan | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | April
220001348980 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Mick Hoden | IMGA223124 | CORRINGHAM ROAD | 220001348980 | T1 Policy | 0 | Policy | 6 | CI | 27 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510815222 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Mick Hoden | IMGA223124 | THE SORRELLS | 510815222 | T1 Policy | 13.9 | Policy | 6 | SI | 48 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6672 | 0 | CMO East 2 | IMGA223124 | THE SORRELLS | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
606677955 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Mick Hoden | IMGA223128 | NURSERY ROAD | 606677955 | T1 Policy | 33.1 | Policy | 8 | CI | 63 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0853 | 0 | CMO East 2 | IMGA223128 | NURSERY ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO CHAPMAN, Joe | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510904827 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Mick Linwood | IMGA223261 | RUSSELL ROAD | 510904827 | T1 Policy | 42.8 | Policy | 4 | CI | 112 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.7936 | 0 | CMO East 2 | IMGA223261 | RUSSELL ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510965744 | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Mick Linwood | IMGA223263 | NORTHDENE | 510965744 | T1 Policy | 18.4 | Policy | 8 | DI | 82 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5088 | 0 | CMO East 2 | IMGA223263 | NORTHDENE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | April
607346746 | CMO | CMO East 2 | April | 4 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 607346746 | Condition | 0 | Non Policy | 4 | ST | 235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | April
602634584 | CMO | CMO East 2 | April | 4 | A | Stuart Griffiths | Bob Sawyer | IMGA223072 | THE WILLOWS | 602634584 | T1 Policy | 0.3 | Policy | 4 | DI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0147 | 0 | CMO East 2 | IMGA223072 | THE WILLOWS | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
220000863634 | CMO | CMO East 2 | April | 4 | A | Stuart Griffiths | Bob Sawyer | IMGA223072 | THE WILLOWS | 220000863634 | T1 Policy | 0 | Policy | 4 | DI | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223072 | THE WILLOWS | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
- | CMO | CMO East 2 | April | 4 | A | Dave Bamber | Mick Linwood | IMGA223261 | RUSSELL ROAD | - | T1 Policy | 0 | Policy | 4 | CI | 2.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223261 | RUSSELL ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510959117 | CMO | CMO East 2 | April | 5 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959117 | T1 Policy | 9.9 | Policy | 6 | SI | 94 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9306 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
220001472367 | CMO | CMO East 2 | April | 5 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 220001472367 | T1 Policy | 0 | Policy | 6 | SI | 194 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510941808 | CMO | CMO East 2 | April | 5 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 50 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.895 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510903848 | CMO | CMO East 2 | April | 5 | A | Alex Wright | Jake Parry | IMGA223188 | ROWDOWNS ROAD | 510903848 | T1 Policy | 27.2 | Policy | 4 | CI | 125 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.4 | 0 | CMO East 2 | IMGA223188 | ROWDOWNS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510800768 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Chris McVeigh | IMGA223016 | BYRON ROAD | 510800768 | Condition | 0 | Non Policy | 6 | ST | 42 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223016 | BYRON ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | April
635775873 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Chris McVeigh | IMGA223016 | BYRON ROAD | 635775873 | Condition | 0 | Non Policy | 6 | ST | 4.4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223016 | BYRON ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | April
510861167 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Chris McVeigh | IMGA223016 | KINGSLEY ROAD | 510861167 | Condition | 0 | Non Policy | 6 | ST | 90.9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223016 | KINGSLEY ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 PAST | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | April
510921484 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Chris McVeigh | IMGA223016 | TENNYSON ROAD | 510921484 | T1 Policy | 26.2 | Policy | 4 | SI | 12.2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.31964 | 0 | CMO East 2 | IMGA223016 | TENNYSON ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510855142 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Mick Hoden | IMGA223100 | HOWELL ROAD | 510855142 | T1 PAST | 2 | Policy | 4 | DI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.092 | 0 | CMO East 2 | IMGA223100 | HOWELL ROAD | Thurrock Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510937479 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Mick Hoden | IMGA223124 | WHITFIELDS | 510937479 | T1 Policy | 29.5 | Policy | 4 | SI | 177 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.2215 | 0 | CMO East 2 | IMGA223124 | WHITFIELDS | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
220001728165 | CMO | CMO East 2 | April | 5 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728165 | T1 Policy | 0 | Policy | 8 | CI | 63 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510837493 | CMO | CMO East 2 | April | 5 | A | Stuart Griffiths | Chris Southam | IMGA223004 | FOXHUNTER WALK | 510837493 | T1 Policy | 0.3 | Policy | 4 | DI | 34 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0102 | 0 | CMO East 2 | IMGA223004 | FOXHUNTER WALK | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO AGUIS, P | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510837494 | CMO | CMO East 2 | April | 5 | A | Stuart Griffiths | Chris Southam | IMGA223004 | GLENCREE | 510837494 | T1 Policy | 0.2 | Policy | 4 | DI | 81 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0162 | 0 | CMO East 2 | IMGA223004 | GLENCREE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO AGUIS, P | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510852318 | CMO | CMO East 2 | April | 5 | A | Stuart Griffiths | Chris Southam | IMGA223010 | HILLHOUSE DRIVE | 510852318 | Condition | 0 | Non Policy | 4 | ST | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223010 | HILLHOUSE DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 PAST | CMO SMYTH, Billy | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | April
510801485 | CMO | CMO East 2 | April | 5 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | CAMBRIDGE GARDENS | 510801485 | T1 Policy | 0.5 | Policy | 6 | DI | 154 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.077 | 0 | CMO East 2 | IMGA223048 | CAMBRIDGE GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510822885 | CMO | CMO East 2 | April | 5 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | HAMSTEL ROAD | 510822885 | T1 Policy | 24 | Policy | 4 | SI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.144 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510845007 | CMO | CMO East 2 | April | 5 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | HAMSTEL ROAD | 510845007 | T1 Policy | 37.4 | Policy | 4 | SI | 133 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.9742 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510872365 | CMO | CMO East 2 | May | 6 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510872365 | T1 Policy | 17.6 | Policy | 4 | CI | 125.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2088 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510959118 | CMO | CMO East 2 | May | 6 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959118 | T1 Policy | 14.3 | Policy | 6 | CI | 95 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3585 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
220001472368 | CMO | CMO East 2 | May | 6 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 220001472368 | T1 Policy | 0 | Policy | 6 | CI | 298 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510941808 | CMO | CMO East 2 | May | 6 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 6 | CI | 12 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2148 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510941808 | CMO | CMO East 2 | May | 6 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 33 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5907 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510903848 | CMO | CMO East 2 | May | 6 | A | Alex Wright | Jake Parry | IMGA223188 | ROWDOWNS ROAD | 510903848 | T1 Policy | 27.2 | Policy | 4 | CI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.536 | 0 | CMO East 2 | IMGA223188 | ROWDOWNS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510961721 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961721 | T1 Policy | 1.3 | Policy | 100 | DI | 62.5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.08125 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510961722 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961722 | Condition | 0 | Non Policy | 2 | ST | 30.3 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | CMO MARSH, Dan | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | May
510961724 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961724 | T1 Policy | 0.5 | Policy | 100 | DI | 45.4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0227 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510855142 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Mick Hoden | IMGA223100 | HOWELL ROAD | 510855142 | T1 PAST | 2 | Policy | 4 | DI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.098 | 0 | CMO East 2 | IMGA223100 | HOWELL ROAD | Thurrock Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001348977 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Mick Hoden | IMGA223124 | CORRINGHAM ROAD | 220001348977 | T1 Policy | 0 | Policy | 6 | CI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510885248 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Mick Hoden | IMGA223128 | NURSERY ROAD | 510885248 | T1 Policy | 49.2 | Policy | 8 | CI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.444 | 0 | CMO East 2 | IMGA223128 | NURSERY ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510904827 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Mick Linwood | IMGA223261 | RUSSELL ROAD | 510904827 | T1 Policy | 42.8 | Policy | 7 | CI | 49 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0972 | 0 | CMO East 2 | IMGA223261 | RUSSELL ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
220001728165 | CMO | CMO East 2 | May | 6 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728165 | T1 Policy | 0 | Policy | 8 | CI | 56 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510785390 | CMO | CMO East 2 | May | 6 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 510785390 | Condition | 0 | Non Policy | 4 | ST | 207 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
607346746 | CMO | CMO East 2 | May | 6 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 607346746 | Condition | 0 | Non Policy | 4 | ST | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510956434 | CMO | CMO East 2 | May | 6 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | DORSET GARDENS | 510956434 | T1 Policy | 0.2 | Policy | 100 | DI | 100 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO East 2 | IMGA223048 | DORSET GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510785390 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510785390 | Condition | 0 | Non Policy | 4 | ST | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma |  | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510804725 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | DORSET GARDENS | 510804725 | T1 Policy | 0.3 | Policy | 200 | DI | 3 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0009 | 0 | CMO East 2 | IMGA223048 | DORSET GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510822885 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | DROITWICH AVENUE | 510822885 | T1 Policy | 24 | Policy | 4 | SI | 57 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.368 | 0 | CMO East 2 | IMGA223066 | DROITWICH AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510822885 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | HAMSTEL ROAD | 510822885 | T1 Policy | 24 | Policy | 4 | SI | 87 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.088 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510838674 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | GOLF RIDE | 510838674 | Condition | 0 | Non Policy | 4 | ST | 66 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | GOLF RIDE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510855142 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Hoden | IMGA223100 | HOWELL ROAD | 510855142 | T1 PAST | 2 | Policy | 4 | DI | 61 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.122 | 0 | CMO East 2 | IMGA223100 | HOWELL ROAD | Thurrock Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510872365 | CMO | CMO East 2 | May | 7 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510872365 | T1 Policy | 17.6 | Policy | 4 | CI | 119 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0944 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510885248 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Hoden | IMGA223128 | NURSERY ROAD | 510885248 | T1 Policy | 49.2 | Policy | 8 | CI | 95 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.674 | 0 | CMO East 2 | IMGA223128 | NURSERY ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510903850 | CMO | CMO East 2 | May | 7 | A | Alex Wright | Jake Parry | IMGA223188 | ROWDOWNS ROAD | 510903850 | T1 Policy | 16.8 | Policy | 4 | CI | 88 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4784 | 0 | CMO East 2 | IMGA223188 | ROWDOWNS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510903850 | CMO | CMO East 2 | May | 7 | A | Alex Wright | Jake Parry | IMGA223188 | ROWDOWNS ROAD | 510903850 | T1 Policy | 16.8 | Policy | 6 | CI | 72 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2096 | 0 | CMO East 2 | IMGA223188 | ROWDOWNS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510925235 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510929373 | CMO | CMO East 2 | May | 7 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 510929373 | T1 Policy | 14.5 | Policy | 6 | CI | 196 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.842 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510941808 | CMO | CMO East 2 | May | 7 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 267 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.7793 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510956433 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | DORSET GARDENS | 510956433 | T1 Policy | 0.5 | Policy | 200 | DI | 113 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0565 | 0 | CMO East 2 | IMGA223048 | DORSET GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510956434 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | DORSET GARDENS | 510956434 | T1 Policy | 0.2 | Policy | 100 | DI | 3 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0006 | 0 | CMO East 2 | IMGA223048 | DORSET GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510959131 | CMO | CMO East 2 | May | 7 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959131 | T1 Policy | 35.1 | Policy | 6 | CI | 85 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.9835 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510961719 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961719 | T1 Policy | 0.5 | Policy | 150 | DI | 71 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0355 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510961721 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961721 | T1 Policy | 1.3 | Policy | 100 | DI | 5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0065 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510965744 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Linwood | IMGA223263 | NORTHDENE | 510965744 | T1 Policy | 18.4 | Policy | 4 | DI | 33.6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.61824 | 0 | CMO East 2 | IMGA223263 | NORTHDENE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510965744 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Linwood | IMGA223263 | NORTHDENE | 510965744 | T1 Policy | 18.4 | Policy | 8 | DI | 13.6 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.25024 | 0 | CMO East 2 | IMGA223263 | NORTHDENE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | May
602629187 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | DROITWICH AVENUE | 602629187 | T1 Policy | 42.3 | Policy | 4 | SI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1269 | 0 | CMO East 2 | IMGA223066 | DROITWICH AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
607277012 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 607277012 | Condition | 0 | Non Policy | 4 | ST | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
220001187686 | CMO | CMO East 2 | May | 7 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 220001187686 | Condition | 0 | Non Policy | 4 | ST | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
220001562958 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Chris McVeigh | IMGA223014 | KILMINGTON CLOSE | 220001562958 | T1 Policy | 0 | Policy | 4 | DI | 49.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223014 | KILMINGTON CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001563888 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Chris McVeigh | IMGA223014 | KILMINGTON CLOSE | 220001563888 | T1 Policy | 0 | Policy | 6 | DI | 87.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223014 | KILMINGTON CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
220001728164 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728164 | T1 Policy | 0 | Policy | 8 | CI | 37 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
220001728165 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728165 | T1 Policy | 0 | Policy | 8 | CI | 61 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
220001822181 | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Hoden | IMGA223128 | CORNWELL CRESCENT | 220001822181 | T1 Policy | 34.3 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.058 | 0 | CMO East 2 | IMGA223128 | CORNWELL CRESCENT | Thurrock Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | tRIIO WASSELL, Mark | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
DAF TO BE SUBMITTED | CMO | CMO East 2 | May | 7 | A | Dave Bamber | Mick Linwood | IMGA223263 | NORTHDENE | DAF TO BE SUBMITTED | T1 Policy | 0 | Policy | 8 | DI | 7.5 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223263 | NORTHDENE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront |  | CMO SMITH , Lloyd | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | May
510859382 | CMO | CMO East 2 | May | 8 | A | Alex Wright | Jake Parry | IMGA223159 | KERSHAW ROAD | 510859382 | T1 PAST | 27.4 | Policy | 4 | CI | 152 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.1648 | 0 | CMO East 2 | IMGA223159 | KERSHAW ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE | PAST | JDT | T1 PAST | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510833221 | CMO | CMO East 2 | May | 8 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0876 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510872365 | CMO | CMO East 2 | May | 8 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510872365 | T1 Policy | 17.6 | Policy | 4 | CI | 53.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9416 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510959131 | CMO | CMO East 2 | May | 8 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959131 | T1 Policy | 35.1 | Policy | 6 | CI | 148 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.1948 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
607505615 | CMO | CMO East 2 | May | 8 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 607505615 | T1 Policy | 14.5 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.029 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510929373 | CMO | CMO East 2 | May | 8 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 510929373 | T1 Policy | 14.5 | Policy | 6 | CI | 244 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.538 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510941808 | CMO | CMO East 2 | May | 8 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.253 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510855142 | CMO | CMO East 2 | May | 8 | A | Dave Bamber | Mick Hoden | IMGA223100 | HOWELL ROAD | 510855142 | T1 PAST | 2 | Policy | 4 | DI | 71 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.142 | 0 | CMO East 2 | IMGA223100 | HOWELL ROAD | Thurrock Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001348977 | CMO | CMO East 2 | May | 8 | A | Dave Bamber | Mick Hoden | IMGA223124 | CORRINGHAM ROAD | 220001348977 | T1 Policy | 0 | Policy | 6 | CI | 130 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510885248 | CMO | CMO East 2 | May | 8 | A | Dave Bamber | Mick Hoden | IMGA223128 | NURSERY ROAD | 510885248 | T1 Policy | 49.2 | Policy | 8 | CI | 24 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1808 | 0 | CMO East 2 | IMGA223128 | NURSERY ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510928626 | CMO | CMO East 2 | May | 8 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 510928626 | T1 Policy | 1.3 | Policy | 100 | DI | 8 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0104 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront |  | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001728164 | CMO | CMO East 2 | May | 8 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728164 | T1 Policy | 0 | Policy | 8 | CI | 83 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
607277012 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 607277012 | Condition | 0 | Non Policy | 4 | ST | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma |  | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510925235 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | 170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510912528 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Bob Sawyer | IMGA223061 | SNAKES LANE | 510912528 | T1 Policy | 17.7 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0354 | 0 | CMO East 2 | IMGA223061 | SNAKES LANE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 ENM CONDITION SPECIFIED | CMO MILES, Lee | LP | ENM P2 | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510844997 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | HAMSTEL ROAD | 510844997 | T1 Policy | 0.2 | Policy | 4 | DI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.001 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510845007 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | HAMSTEL ROAD | 510845007 | T1 Policy | 37.4 | Policy | 4 | SI | 19 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7106 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510918012 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 0.5 | Policy | 4 | DI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.003 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510909185 | CMO | CMO East 2 | May | 8 | A | Stuart Griffiths | Paul Illingworth | IMGA223140 | SEAVIEW ROAD | 510909185 | Condition | 0 | Non Policy | 4 | ST | 277 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223140 | SEAVIEW ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510859382 | CMO | CMO East 2 | May | 9 | A | Alex Wright | Jake Parry | IMGA223159 | KERSHAW ROAD | 510859382 | T1 PAST | 27.4 | Policy | 4 | CI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.603 | 0 | CMO East 2 | IMGA223159 | KERSHAW ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE | PAST | JDT | T1 PAST | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510833221 | CMO | CMO East 2 | May | 9 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510833221 | T1 Policy | 29.2 | Policy | 4 | CI | 69 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0148 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510833221 | CMO | CMO East 2 | May | 9 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 48 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4016 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510941808 | CMO | CMO East 2 | May | 9 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0358 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510941808 | CMO | CMO East 2 | May | 9 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 200 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.58 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510794404 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223014 | BOWHAY | 510794404 | T1 Policy | 0.3 | Policy | 4 | DI | 29.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.00894 | 0 | CMO East 2 | IMGA223014 | BOWHAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510794405 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223014 | BOWHAY | 510794405 | T1 Policy | 0.1 | Policy | 4 | DI | 16.6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.00166 | 0 | CMO East 2 | IMGA223014 | BOWHAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510794407 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223014 | BOWHAY | 510794407 | T1 Policy | 0.2 | Policy | 4 | DI | 66.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01336 | 0 | CMO East 2 | IMGA223014 | BOWHAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510794408 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223014 | BOWHAY | 510794408 | T1 Policy | 0.2 | Policy | 4 | DI | 61.1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01222 | 0 | CMO East 2 | IMGA223014 | BOWHAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220000466548 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223014 | BOWHAY | 220000466548 | T1 Policy | 0 | Policy | 6 | DI | 178.4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223014 | BOWHAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510888152 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223027 | OUTINGS LANE | 510888152 | T1 PAST | 1.2 | Policy | 4 | DI | 32.7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.03924 | 0 | CMO East 2 | IMGA223027 | OUTINGS LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | tRIIO LOCKERBY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
602478725 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223027 | OUTINGS LANE | 602478725 | T1 Policy | 25.6 | Policy | 4 | SI | 50.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2928 | 0 | CMO East 2 | IMGA223027 | OUTINGS LANE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO LOCKERBY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510961718 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961718 | T1 Policy | 0.6 | Policy | 100 | DI | 38.5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0231 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510961719 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961719 | T1 Policy | 0.5 | Policy | 150 | DI | 18.6 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0093 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510961720 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961720 | T1 Policy | 0.4 | Policy | 100 | DI | 31.5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0126 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510819771 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Hoden | IMGA223093 | DAVIS ROAD | 510819771 | T1 Policy | 15.4 | Policy | 4 | SI | 43 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6622 | 0 | CMO East 2 | IMGA223093 | DAVIS ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510827163 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Hoden | IMGA223093 | ELM ROAD | 510827163 | T1 Policy | 26.2 | Policy | 4 | SI | 72 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.8864 | 0 | CMO East 2 | IMGA223093 | ELM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510855142 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Hoden | IMGA223100 | HOWELL ROAD | 510855142 | T1 PAST | 2 | Policy | 100 | DI | 115 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.23 | 0 | CMO East 2 | IMGA223100 | HOWELL ROAD | Thurrock Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510815220 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Hoden | IMGA223124 | CORRINGHAM ROAD | 510815220 | T1 Policy | 5.4 | Policy | 4 | CI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.162 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
220001348977 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Hoden | IMGA223124 | CORRINGHAM ROAD | 220001348977 | T1 Policy | 0 | Policy | 6 | CI | 11 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
220000763579 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Hoden | IMGA223124 | RAINBOW LANE | 220000763579 | T1 Policy | 0 | Policy | 4 | CI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | RAINBOW LANE | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510904827 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Linwood | IMGA223261 | RUSSELL ROAD | 510904827 | T1 Policy | 42.8 | Policy | 7 | CI | 66 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.8248 | 0 | CMO East 2 | IMGA223261 | RUSSELL ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510849506 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 510849506 | T1 Policy | 8.9 | Policy | 4 | CI | 67 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5963 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront |  | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
220001728164 | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728164 | T1 Policy | 0 | Policy | 8 | CI | 21 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510834277 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Chris Southam | IMGA223004 | FOXHUNTER WALK | 510834277 | T1 Policy | 0.6 | Policy | 6 | DI | 54 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0324 | 0 | CMO East 2 | IMGA223004 | FOXHUNTER WALK | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO HOLPIN, Stacey | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510783721 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Chris Southam | IMGA223008 | ASH GREEN | 510783721 | T1 Policy | 13.7 | Policy | 6 | DI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2877 | 0 | CMO East 2 | IMGA223008 | ASH GREEN | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510783722 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Chris Southam | IMGA223008 | ASH GREEN | 510783722 | T1 Policy | 11.2 | Policy | 6 | SI | 43 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4816 | 0 | CMO East 2 | IMGA223008 | ASH GREEN | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510925235 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | 156 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | May
510804723 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | CENTRAL AVENUE | 510804723 | T1 Policy | 1.1 | Policy | 200 | DI | 32 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0352 | 0 | CMO East 2 | IMGA223048 | CENTRAL AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510804725 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | DORSET GARDENS | 510804725 | T1 Policy | 0.3 | Policy | 200 | DI | 65 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0195 | 0 | CMO East 2 | IMGA223048 | DORSET GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510804724 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | PRINCESS GARDENS | 510804724 | T1 Policy | 0.4 | Policy | 200 | DI | 32 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0128 | 0 | CMO East 2 | IMGA223048 | PRINCESS GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma |  | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510895509 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | PRINCESS GARDENS | 510895509 | T1 Policy | 0.3 | Policy | 200 | DI | 30 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.009 | 0 | CMO East 2 | IMGA223048 | PRINCESS GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
220000632430 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Bob Sawyer | IMGA223061 | BRENDON WAY | 220000632430 | T1 Policy | 0 | Policy | 6 | CI | 11 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223061 | BRENDON WAY | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510912528 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Bob Sawyer | IMGA223061 | SNAKES LANE | 510912528 | T1 Policy | 17.7 | Policy | 6 | SI | 250 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.425 | 0 | CMO East 2 | IMGA223061 | SNAKES LANE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 ENM CONDITION SPECIFIED | CMO MILES, Lee | LP | ENM P2 | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510918012 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 0.5 | Policy | 4 | DI | 53 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0265 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
606442791 | CMO | CMO East 2 | May | 9 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 606442791 | T1 Policy | 1.3 | Policy | 4 | DI | 1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0013 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
DR4 Requested | CMO | CMO East 2 | May | 9 | A | Dave Bamber | Chris McVeigh | IMGA223027 | OUTINGS LANE | DR4 Requested | T1 Policy | 0 | Policy | 4 | SI | 2.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223027 | OUTINGS LANE | Brentwood Borough Council | East 2 | FALSE |  | Forefront |  | tRIIO LOCKERBY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510791320 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223150 | BEVAN AVENUE | 510791320 | T1 Policy | 29.2 | Policy | 6 | CI | 242 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.0664 | 0 | CMO East 2 | IMGA223150 | BEVAN AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510858086 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223150 | KEIR HARDIE WAY | 510858086 | T1 Policy | 18.5 | Policy | 6 | SI | 184 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.404 | 0 | CMO East 2 | IMGA223150 | KEIR HARDIE WAY | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
630909720 | CMO | CMO East 2 | June | 10 | A | Alex Wright | Jake Parry | IMGA223159 | KERSHAW ROAD | 630909720 | T1 Policy | 5 | Policy | 6 | SI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.04 | 0 | CMO East 2 | IMGA223159 | KERSHAW ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO PAVITT, Nick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510859382 | CMO | CMO East 2 | June | 10 | A | Alex Wright | Jake Parry | IMGA223159 | KERSHAW ROAD | 510859382 | T1 PAST | 27.4 | Policy | 4 | SI | 14 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3836 | 0 | CMO East 2 | IMGA223159 | KERSHAW ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE | PAST | JDT | T1 PAST | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510833221 | CMO | CMO East 2 | June | 10 | A | Alex Wright | Jake Parry | IMGA223167 | FORD ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 59 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7228 | 0 | CMO East 2 | IMGA223167 | FORD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510959117 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959117 | T1 Policy | 9.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0198 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510959117 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959117 | T1 Policy | 9.9 | Policy | 6 | CI | 149 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4751 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510929373 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 510929373 | T1 Policy | 14.5 | Policy | 6 | CI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.29 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220001472368 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 220001472368 | T1 Policy | 0 | Policy | 6 | CI | 114 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220001742338 | CMO | CMO East 2 | June | 10 | A | Alex Wright | James Cox | IMGA223180 | VALENCE AVENUE | 220001742338 | T1 Policy | 0 | Policy | 6 | CI | 276 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223180 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510941808 | CMO | CMO East 2 | June | 10 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 60 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.074 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510904827 | CMO | CMO East 2 | June | 10 | A | Dave Bamber | Mick Linwood | IMGA223261 | AMBERLEY ROAD | 510904827 | T1 Policy | 42.8 | Policy | 7 | CI | 12 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5136 | 0 | CMO East 2 | IMGA223261 | AMBERLEY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront |  | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
621124058 | CMO | CMO East 2 | June | 10 | A | Dave Bamber | Mick Linwood | IMGA223261 | AMBERLEY ROAD | 621124058 | T1 Policy | 65.7 | Policy | 4 | CI | 4.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.29565 | 0 | CMO East 2 | IMGA223261 | AMBERLEY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
634112800 | CMO | CMO East 2 | June | 10 | A | Dave Bamber | Mick Linwood | IMGA223261 | AMBERLEY ROAD | 634112800 | T1 Policy | 17.1 | Policy | 4 | CI | 58.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.99864 | 0 | CMO East 2 | IMGA223261 | AMBERLEY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001728164 | CMO | CMO East 2 | June | 10 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728164 | T1 Policy | 0 | Policy | 8 | CI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510925235 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | 102 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | June
510895508 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | PRINCESS GARDENS | 510895508 | T1 Policy | 0.3 | Policy | 200 | DI | 50 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.015 | 0 | CMO East 2 | IMGA223048 | PRINCESS GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510895509 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | PRINCESS GARDENS | 510895509 | T1 Policy | 0.3 | Policy | 200 | DI | 70 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.021 | 0 | CMO East 2 | IMGA223048 | PRINCESS GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510970457 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | FYFIELD PATH | 510970457 | T1 Policy | 1.2 | Policy | 100 | DI | 4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0048 | 0 | CMO East 2 | IMGA223059 | FYFIELD PATH | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510970457 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | FYFIELD PATH | 510970457 | T1 Policy | 1.2 | Policy | 200 | DI | 120 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.144 | 0 | CMO East 2 | IMGA223059 | FYFIELD PATH | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510970456 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | TILLINGHAM WAY | 510970456 | T1 Policy | 0.9 | Policy | 200 | DI | 14 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0126 | 0 | CMO East 2 | IMGA223059 | TILLINGHAM WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510844997 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | HAMSTEL ROAD | 510844997 | T1 Policy | 0.2 | Policy | 4 | DI | 9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0018 | 0 | CMO East 2 | IMGA223066 | HAMSTEL ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
635638182 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 635638182 | T1 Policy | 0 | Policy | 125 | CI | 2 | mm | 125mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO MILES, Lee | LP | #N/A | 4-5” | 125 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
636168810 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 636168810 | T1 Policy | 23.2 | Policy | 6 | CI | 82 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9024 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220000313267 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 220000313267 | T1 Policy | 0 | Policy | 6 | CI | 86 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510802558 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | CANVEY ROAD | 510802558 | T1 Policy | 15.6 | Policy | 4 | SI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.5616 | 0 | CMO East 2 | IMGA223134 | CANVEY ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma |  | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510802545 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | CANVEY ROAD | 510802545 | T1 Policy | 3.8 | Policy | 4 | SI | 33 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.1254 | 0 | CMO East 2 | IMGA223134 | CANVEY ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510802546 | CMO | CMO East 2 | June | 10 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | CANVEY ROAD | 510802546 | T1 Policy | 42.3 | Policy | 4 | SI | 22 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.9306 | 0 | CMO East 2 | IMGA223134 | CANVEY ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510790420 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223150 | BEN TILLET CLOSE | 510790420 | T1 Policy | 9.4 | Policy | 4 | SI | 103 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9682 | 0 | CMO East 2 | IMGA223150 | BEN TILLET CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510790421 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223150 | BEN TILLET CLOSE | 510790421 | T1 Policy | 11.8 | Policy | 4 | SI | 98 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1564 | 0 | CMO East 2 | IMGA223150 | BEN TILLET CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510791330 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223150 | BEN TILLET CLOSE | 510791330 | T1 Policy | 6.5 | Policy | 6 | SI | 13 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0845 | 0 | CMO East 2 | IMGA223150 | BEN TILLET CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510858086 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223150 | KEIR HARDIE WAY | 510858086 | T1 Policy | 18.5 | Policy | 4 | SI | 18 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.333 | 0 | CMO East 2 | IMGA223150 | KEIR HARDIE WAY | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510833221 | CMO | CMO East 2 | June | 11 | A | Alex Wright | Jake Parry | IMGA223167 | FORD ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 56 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6352 | 0 | CMO East 2 | IMGA223167 | FORD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510797534 | CMO | CMO East 2 | June | 11 | A | Alex Wright | Jake Parry | IMGA223175 | BROMHALL ROAD | 510797534 | T1 Policy | 31.8 | Policy | 4 | CI | 108 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.4344 | 0 | CMO East 2 | IMGA223175 | BROMHALL ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001594981 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 220001594981 | T1 Policy | 0 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510856117 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 16.3 | Policy | 6 | CI | 129 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1027 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510941808 | CMO | CMO East 2 | June | 11 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 17.9 | Policy | 8 | CI | 20 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.358 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510941809 | CMO | CMO East 2 | June | 11 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 13 | Policy | 6 | CI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.104 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510852657 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Chris McVeigh | IMGA223018 | HILLWOOD GROVE | 510852657 | T1 Policy | 13.1 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.441 | 0 | CMO East 2 | IMGA223018 | HILLWOOD GROVE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510961720 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961720 | T1 Policy | 0.4 | Policy | 150 | DI | 76 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0304 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510961726 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 510961726 | Condition | 0 | Non Policy | 2 | ST | 16.9 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | CMO MARSH, Dan | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | June
601468395 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Chris McVeigh | IMGA223033 | VIKING WAY | 601468395 | Condition | 0 | Non Policy | 2 | ST | 5.9 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223033 | VIKING WAY | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 CONNECTED | CMO MARSH, Dan | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | June
510819769 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Hoden | IMGA223093 | DAVIS ROAD | 510819769 | T1 Policy | 16 | Policy | 6 | SI | 125 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2 | 0 | CMO East 2 | IMGA223093 | DAVIS ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510778389 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Hoden | IMGA223124 | ABBOTTS HALL CHASE | 510778389 | T1 Policy | 25.7 | Policy | 4 | CI | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9275 | 0 | CMO East 2 | IMGA223124 | ABBOTTS HALL CHASE | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510778390 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Hoden | IMGA223124 | ABBOTTS HALL CHASE | 510778390 | T1 Policy | 25.3 | Policy | 4 | CI | 42 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0626 | 0 | CMO East 2 | IMGA223124 | ABBOTTS HALL CHASE | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510815221 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Hoden | IMGA223124 | CORRINGHAM ROAD | 510815221 | T1 Policy | 27 | Policy | 4 | CI | 47.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2825 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510933805 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Hoden | IMGA223124 | WEBSTER ROAD | 510933805 | T1 Policy | 16.3 | Policy | 4 | CI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4075 | 0 | CMO East 2 | IMGA223124 | WEBSTER ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510965744 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Linwood | IMGA223263 | NORTHDENE | 510965744 | T1 Policy | 18.4 | Policy | 8 | DI | 56 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0304 | 0 | CMO East 2 | IMGA223263 | NORTHDENE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO O'DEA, Gerald | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | June
510928626 | CMO | CMO East 2 | June | 11 | A | Dave Bamber | Mick Linwood | IMGA223274 | HAZELWOOD | 510928626 | T1 Policy | 1.3 | Policy | 100 | DI | 90 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.117 | 0 | CMO East 2 | IMGA223274 | HAZELWOOD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510783722 | CMO | CMO East 2 | June | 11 | A | Stuart Griffiths | Chris Southam | IMGA223008 | ASH GREEN | 510783722 | T1 Policy | 11.2 | Policy | 6 | SI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.84 | 0 | CMO East 2 | IMGA223008 | ASH GREEN | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510970456 | CMO | CMO East 2 | June | 11 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | TILLINGHAM WAY | 510970456 | T1 Policy | 0.9 | Policy | 200 | DI | 47 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0423 | 0 | CMO East 2 | IMGA223059 | TILLINGHAM WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510918350 | CMO | CMO East 2 | June | 11 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918350 | T1 Policy | 0 | Policy | 100 | DI | 10 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510856164 | CMO | CMO East 2 | June | 11 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510856164 | T1 Policy | 0.4 | Policy | 100 | DI | 62 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0248 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
636168810 | CMO | CMO East 2 | June | 11 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 636168810 | T1 Policy | 23.2 | Policy | 6 | CI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.088 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510858089 | CMO | CMO East 2 | June | 11 | A | Alex Wright | James Cox | IMGA223150 | BEN TILLET CLOSE | 510858089 | T1 Policy | 10.1 | Policy | 6 | SI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0707 | 0 | CMO East 2 | IMGA223150 | BEN TILLET CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
602686207 | CMO | CMO East 2 | June | 11 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 602686207 | T1 Policy | 0 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510833221 | CMO | CMO East 2 | June | 12 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510833221 | T1 Policy | 29.2 | Policy | 2 | CI | 3 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0876 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | CI | CI/SI/DI LP <=3" | June
510833221 | CMO | CMO East 2 | June | 12 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510833221 | T1 Policy | 29.2 | Policy | 3 | CI | 3 | inch | 3inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0876 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | <=3” | 3 |  | Policy | Tier 1 | CI | CI/SI/DI LP <=3" | June
510791320 | CMO | CMO East 2 | June | 12 | A | Alex Wright | James Cox | IMGA223150 | BEVAN AVENUE | 510791320 | T1 Policy | 29.2 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0584 | 0 | CMO East 2 | IMGA223150 | BEVAN AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510791331 | CMO | CMO East 2 | June | 12 | A | Alex Wright | James Cox | IMGA223150 | BEVAN AVENUE | 510791331 | T1 Policy | 19 | Policy | 4 | SI | 192 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.648 | 0 | CMO East 2 | IMGA223150 | BEVAN AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510797534 | CMO | CMO East 2 | June | 12 | A | Alex Wright | Jake Parry | IMGA223175 | BROMHALL ROAD | 510797534 | T1 Policy | 31.8 | Policy | 4 | CI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.657 | 0 | CMO East 2 | IMGA223175 | BROMHALL ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001594996 | CMO | CMO East 2 | June | 12 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 220001594996 | T1 Policy | 0 | Policy | 4 | CI | 16 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510941809 | CMO | CMO East 2 | June | 12 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 13 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.026 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510933805 | CMO | CMO East 2 | June | 12 | A | Dave Bamber | Mick Hoden | IMGA223124 | WEBSTER ROAD | 510933805 | T1 Policy | 16.3 | Policy | 4 | CI | 126 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0538 | 0 | CMO East 2 | IMGA223124 | WEBSTER ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
633005945 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Paul Illingworth | IMGA223042 | HALL CRESCENT | 633005945 | Condition | 0 | Non Policy | 4 | ST | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223042 | HALL CRESCENT | Canvey Island | East 2 | FALSE |  | Terra Firma |  | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | June
628368510 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Paul Illingworth | IMGA223042 | HALL CRESCENT | 628368510 | Condition | 0 | Non Policy | 4 | ST | 224 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223042 | HALL CRESCENT | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | June
635723117 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | MEADWAY | 635723117 | T1 Policy | 0 | Policy | 4 | CI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223073 | MEADWAY | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO AGUIS, P | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510802558 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | CANVEY ROAD | 510802558 | T1 Policy | 15.6 | Policy | 4 | SI | 81 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.2636 | 0 | CMO East 2 | IMGA223134 | CANVEY ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510833221 | CMO | CMO East 2 | June | 12 | A | Alex Wright | Jake Parry | IMGA223167 | MANNING ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 26 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7592 | 0 | CMO East 2 | IMGA223167 | MANNING ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510856117 | CMO | CMO East 2 | June | 12 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 16.3 | Policy | 6 | CI | 92 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4996 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510941809 | CMO | CMO East 2 | June | 12 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 13 | Policy | 6 | CI | 190 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.47 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510992543 | CMO | CMO East 2 | June | 12 | A | Dave Bamber | Mick Hoden | IMGA223099 | THE MANORWAY | 510992543 | T1 Policy | 5.2 | Policy | 6 | CI | 62.1 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.32292 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO LAFLEUR, Ricky | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510992544 | CMO | CMO East 2 | June | 12 | A | Dave Bamber | Mick Hoden | IMGA223099 | THE MANORWAY | 510992544 | T1 Policy | 3.5 | Policy | 6 | CI | 67.4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2359 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO LAFLEUR, Ricky | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510992555 | CMO | CMO East 2 | June | 12 | A | Dave Bamber | Mick Hoden | IMGA223099 | THE MANORWAY | 510992555 | T1 Policy | 3.6 | Policy | 6 | CI | 124.2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.44712 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO LAFLEUR, Ricky | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510992557 | CMO | CMO East 2 | June | 12 | A | Dave Bamber | Mick Hoden | IMGA223099 | THE MANORWAY | 510992557 | T1 Policy | 4.1 | Policy | 6 | CI | 117.3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.48093 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO LAFLEUR, Ricky | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510783721 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Chris Southam | IMGA223008 | ASH GREEN | 510783721 | T1 Policy | 13.7 | Policy | 6 | SI | 82 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1234 | 0 | CMO East 2 | IMGA223008 | ASH GREEN | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
636168810 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 636168810 | T1 Policy | 23.2 | Policy | 6 | CI | 98 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2736 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO AGUIS, P | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510965744 | CMO | CMO East 2 | June | 12 | A | Dave Bamber | Mick Linwood | IMGA223263 | NORTHDENE | 510965744 | T1 Policy | 18.4 | Policy | 8 | DI | 40 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.736 | 0 | CMO East 2 | IMGA223263 | NORTHDENE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO GRIMWOOD, Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | June
510895508 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | RECTORY AVENUE | 510895508 | T1 Policy | 0.3 | Policy | 200 | DI | 68 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0204 | 0 | CMO East 2 | IMGA223048 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma |  | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510899277 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | RECTORY AVENUE | 510899277 | T1 Policy | 0.2 | Policy | 200 | DI | 72 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0144 | 0 | CMO East 2 | IMGA223048 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
621261091 | CMO | CMO East 2 | June | 12 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | RECTORY AVENUE | 621261091 | T1 Policy | 0.1 | Policy | 200 | DI | 26 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0026 | 0 | CMO East 2 | IMGA223048 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510791331 | CMO | CMO East 2 | June | 13 | A | Alex Wright | James Cox | IMGA223150 | BEVAN AVENUE | 510791331 | T1 Policy | 19 | Policy | 4 | SI | 101.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9285 | 0 | CMO East 2 | IMGA223150 | BEVAN AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510863530 | CMO | CMO East 2 | June | 13 | A | Alex Wright | James Cox | IMGA223150 | LANSBURY AVENUE | 510863530 | T1 Policy | 19.8 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.98 | 0 | CMO East 2 | IMGA223150 | LANSBURY AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510833221 | CMO | CMO East 2 | June | 13 | A | Alex Wright | Jake Parry | IMGA223167 | FORD ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 84.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4674 | 0 | CMO East 2 | IMGA223167 | FORD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510797534 | CMO | CMO East 2 | June | 13 | A | Alex Wright | Jake Parry | IMGA223175 | BROMHALL ROAD | 510797534 | T1 Policy | 31.8 | Policy | 4 | CI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.477 | 0 | CMO East 2 | IMGA223175 | BROMHALL ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510856117 | CMO | CMO East 2 | June | 13 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 16.3 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.815 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510940494 | CMO | CMO East 2 | June | 13 | A | Alex Wright | Jake Parry | IMGA223187 | WOOD LANE | 510940494 | T1 Policy | 21.9 | Policy | 4 | CI | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6425 | 0 | CMO East 2 | IMGA223187 | WOOD LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510845070 | CMO | CMO East 2 | June | 13 | A | Dave Bamber | Mick Hoden | IMGA223093 | HANFORD ROAD | 510845070 | T1 Policy | 31 | Policy | 4 | SI | 125 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.875 | 0 | CMO East 2 | IMGA223093 | HANFORD ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510992544 | CMO | CMO East 2 | June | 13 | A | Dave Bamber | Mick Hoden | IMGA223099 | THE GEERINGS | 510992544 | T1 Policy | 3.5 | Policy | 6 | SI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4725 | 0 | CMO East 2 | IMGA223099 | THE GEERINGS | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO LAFLEUR, Ricky | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
220001207794 | CMO | CMO East 2 | June | 13 | A | Dave Bamber | Mick Hoden | IMGA223124 | LEVETT ROAD | 220001207794 | T1 Policy | 0 | Policy | 6 | CI | 25 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | LEVETT ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510933805 | CMO | CMO East 2 | June | 13 | A | Dave Bamber | Mick Hoden | IMGA223124 | WEBSTER ROAD | 510933805 | T1 Policy | 16.3 | Policy | 4 | CI | 127 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0701 | 0 | CMO East 2 | IMGA223124 | WEBSTER ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510957266 | CMO | CMO East 2 | June | 13 | A | Stuart Griffiths | Paul Illingworth | IMGA223044 | HAZELWOOD | 510957266 | T1 Policy | 0.3 | Policy | 4 | DI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0012 | 0 | CMO East 2 | IMGA223044 | HAZELWOOD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510916165 | CMO | CMO East 2 | June | 13 | A | Stuart Griffiths | Paul Illingworth | IMGA223044 | STANSFIELD ROAD | 510916165 | T1 Policy | 0.3 | Policy | 100 | DI | 72 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0216 | 0 | CMO East 2 | IMGA223044 | STANSFIELD ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
220001194062 | CMO | CMO East 2 | June | 13 | A | Stuart Griffiths | Paul Illingworth | IMGA223044 | STANSFIELD ROAD | 220001194062 | T1 Policy | 0 | Policy | 4 | SI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223044 | STANSFIELD ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510918012 | CMO | CMO East 2 | June | 13 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 0.5 | Policy | 100 | DI | 52 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.026 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
635723117 | CMO | CMO East 2 | June | 13 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | MEADWAY | 635723117 | T1 Policy | 0 | Policy | 4 | CI | 192 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223073 | MEADWAY | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510791320 | CMO | CMO East 2 | June | 14 | A | Alex Wright | James Cox | IMGA223150 | BEVAN AVENUE | 510791320 | T1 Policy | 29.2 | Policy | 4 | SI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.796 | 0 | CMO East 2 | IMGA223150 | BEVAN AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510791321 | CMO | CMO East 2 | June | 14 | A | Alex Wright | James Cox | IMGA223150 | BEVAN AVENUE | 510791321 | T1 Policy | 16.8 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.84 | 0 | CMO East 2 | IMGA223150 | BEVAN AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510863309 | CMO | CMO East 2 | June | 14 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 22.3 | Policy | 4 | CI | 58 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2934 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510941809 | CMO | CMO East 2 | June | 14 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 13 | Policy | 4 | CI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.585 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510940494 | CMO | CMO East 2 | June | 14 | A | Alex Wright | Jake Parry | IMGA223187 | WOOD LANE | 510940494 | T1 Policy | 21.9 | Policy | 4 | CI | 163 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.5697 | 0 | CMO East 2 | IMGA223187 | WOOD LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510852657 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Chris McVeigh | IMGA223018 | HILLWOOD GROVE | 510852657 | T1 Policy | 13.1 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.441 | 0 | CMO East 2 | IMGA223018 | HILLWOOD GROVE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510819770 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Mick Hoden | IMGA223093 | DAVIS ROAD | 510819770 | T1 Policy | 27.3 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.911 | 0 | CMO East 2 | IMGA223093 | DAVIS ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
220001786233 | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | CANVEY ROAD | 220001786233 | T1 Policy | 0 | Policy | 4 | SI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223134 | CANVEY ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510833221 | CMO | CMO East 2 | June | 14 | A | Alex Wright | Jake Parry | IMGA223167 | FORD ROAD | 510833221 | T1 Policy | 29.2 | Policy | 6 | CI | 37.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.095 | 0 | CMO East 2 | IMGA223167 | FORD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510856117 | CMO | CMO East 2 | June | 14 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 16.3 | Policy | 6 | CI | 185 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.0155 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510941802 | CMO | CMO East 2 | June | 14 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941802 | T1 Policy | 23.2 | Policy | 6 | CI | 201 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.6632 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510780825 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Mick Hoden | IMGA223093 | ALFRED ROAD | 510780825 | T1 Policy | 27.3 | Policy | 6 | SI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1638 | 0 | CMO East 2 | IMGA223093 | ALFRED ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
220001207794 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Mick Hoden | IMGA223124 | LEVETT ROAD | 220001207794 | T1 Policy | 0 | Policy | 6 | SI | 81 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | LEVETT ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
603360826 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 6.3 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.315 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510834277 | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Chris Southam | IMGA223004 | FOXHUNTER WALK | 510834277 | T1 Policy | 0.6 | Policy | 6 | DI | 125 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.075 | 0 | CMO East 2 | IMGA223004 | FOXHUNTER WALK | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO HOLPIN, Stacey | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
220001728164 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Mick Linwood | IMGA223274 | UPPER PARK | 220001728164 | T1 Policy | 0 | Policy | 8 | CI | 45 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223274 | UPPER PARK | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510970456 | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | TILLINGHAM WAY | 510970456 | T1 Policy | 0.9 | Policy | 100 | DI | 61 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0549 | 0 | CMO East 2 | IMGA223059 | TILLINGHAM WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510918012 | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 0.5 | Policy | 100 | DI | 50 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.025 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510802557 | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | CANVEY ROAD | 510802557 | T1 Policy | 15.1 | Policy | 100 | DI | 120.8 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.8241 | 0 | CMO East 2 | IMGA223134 | CANVEY ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510885228 | CMO | CMO East 2 | June | 14 | A | Dave Bamber | Mick Linwood | IMGA223274 | NURSERY ROAD | 510885228 | T1 Policy | 5 | Policy | 180 | CI | 48 | mm | 180mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.24 | 0 | CMO East 2 | IMGA223274 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 180 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
621261090 | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Paul Illingworth | IMGA223048 | RECTORY AVENUE | 621261090 | T1 Policy | 0.1 | Policy | 200 | DI | 68 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0068 | 0 | CMO East 2 | IMGA223048 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
- | CMO | CMO East 2 | June | 14 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | - | T1 Policy | 0 | Policy | 100 | DI | 12 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
607346746 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 607346746 | Condition | 0 | Non Policy | 4 | ST | -235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 510785390 | T1 PAST | 289.1 | Policy | 4 | ST | 235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelPolicy | FALSE | FALSE | CMO East 2 | 67.9385 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | ST | ST LP 4"-5" | July
510863308 | CMO | CMO East 2 | July | 15 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863308 | T1 Policy | 18 | Policy | 4 | CI | 41 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.738 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510959120 | CMO | CMO East 2 | July | 15 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959120 | T1 Policy | 25.8 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.806 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510959131 | CMO | CMO East 2 | July | 15 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959131 | T1 Policy | 35.1 | Policy | 4 | CI | 78 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7378 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510959132 | CMO | CMO East 2 | July | 15 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959132 | T1 Policy | 11.8 | Policy | 6 | CI | 41 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4838 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510856117 | CMO | CMO East 2 | July | 15 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 16.3 | Policy | 6 | CI | 84 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3692 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510941801 | CMO | CMO East 2 | July | 15 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD GARDENS | 510941801 | T1 Policy | 28.2 | Policy | 4 | SI | 98 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7636 | 0 | CMO East 2 | IMGA223184 | WOODWARD GARDENS | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510941809 | CMO | CMO East 2 | July | 15 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 13 | Policy | 6 | CI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.273 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
Side Street | CMO | CMO East 2 | July | 15 | A | Alex Wright | Jake Parry | IMGA223187 | WOOD LANE | Side Street | T1 Policy | 0 | Policy | 4 | CI | 5.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223187 | WOOD LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510940494 | CMO | CMO East 2 | July | 15 | A | Alex Wright | Jake Parry | IMGA223187 | WOOD LANE | 510940494 | T1 Policy | 21.9 | Policy | 4 | CI | 41 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8979 | 0 | CMO East 2 | IMGA223187 | WOOD LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510940501 | CMO | CMO East 2 | July | 15 | A | Alex Wright | Jake Parry | IMGA223187 | WOOD LANE | 510940501 | T1 Policy | 41.9 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.609 | 0 | CMO East 2 | IMGA223187 | WOOD LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510852656 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Chris McVeigh | IMGA223018 | HILLWOOD CLOSE | 510852656 | T1 Policy | 20.1 | Policy | 4 | SI | 161 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.2361 | 0 | CMO East 2 | IMGA223018 | HILLWOOD CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510815219 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Darren Francis | IMGA223124 | CORRINGHAM ROAD | 510815219 | T1 Policy | 8.9 | Policy | 4 | SI | 62 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5518 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
638178696 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Darren Francis | IMGA223124 | CORRINGHAM ROAD | 638178696 | T1 Policy | 10.1 | Policy | 4 | SI | 125 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2625 | 0 | CMO East 2 | IMGA223124 | CORRINGHAM ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220001207794 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Darren Francis | IMGA223124 | LEVETT ROAD | 220001207794 | T1 Policy | 0 | Policy | 6 | SI | 16 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223124 | LEVETT ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
603360826 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 6.3 | Policy | 6 | CI | 62.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.39564 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510928626 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Mick Linwood | IMGA223274 | HAZELWOOD | 510928626 | T1 Policy | 1.3 | Policy | 100 | DI | 11 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0143 | 0 | CMO East 2 | IMGA223274 | HAZELWOOD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510965621 | CMO | CMO East 2 | July | 15 | A | Dave Bamber | Mick Linwood | IMGA223274 | HAZELWOOD | 510965621 | T1 Policy | 0.3 | Policy | 150 | DI | 49 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0147 | 0 | CMO East 2 | IMGA223274 | HAZELWOOD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510821085 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | DEVON GARDENS | 510821085 | T1 Policy | 0.6 | Policy | 4 | DI | 156 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0936 | 0 | CMO East 2 | IMGA223051 | DEVON GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510899275 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510899275 | T1 Policy | 0.2 | Policy | 100 | DI | 71 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0142 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510899280 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510899280 | T1 Policy | 0.5 | Policy | 4 | DI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.018 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
Side Street | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | TILLINGHAM WAY | Side Street | T1 Policy | 0 | Policy | 100 | DI | 8 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223059 | TILLINGHAM WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510970456 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | TILLINGHAM WAY | 510970456 | T1 Policy | 0.9 | Policy | 200 | DI | 37 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0333 | 0 | CMO East 2 | IMGA223059 | TILLINGHAM WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510918012 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 0.5 | Policy | 100 | DI | 73 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0365 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510956463 | CMO | CMO East 2 | July | 15 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST GEORGES WALK | 510956463 | T1 Policy | 25.7 | Policy | 4 | SI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.9018 | 0 | CMO East 2 | IMGA223134 | ST GEORGES WALK | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 510785390 | Condition | 0 | Non Policy | 4 | ST | -207 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 510785390 | T1 PAST | 0 | Non Policy | 4 | ST | 207 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
602686207 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 602686207 | T1 Policy | 0 | Policy | 6 | CI | -2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
602686027 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | LEASWAY | 602686027 | T1 Policy | 8.1 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0162 | 0 | CMO East 2 | IMGA223073 | LEASWAY | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510861167 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | Chris McVeigh | IMGA223016 | KINGSLEY ROAD | 510861167 | Condition | 0 | Non Policy | 6 | ST | -90.9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223016 | KINGSLEY ROAD | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 PAST | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | July
510852318 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Chris Southam | IMGA223010 | HILLHOUSE DRIVE | 510852318 | Condition | 0 | Non Policy | 4 | ST | -100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223010 | HILLHOUSE DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 PAST | CMO SMYTH, Billy | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510785390 | Condition | 0 | Non Policy | 4 | ST | -3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma |  | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | -144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | -170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | -156 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | Condition | 0 | Non Policy | 4 | ST | -102 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510909185 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223140 | SEAVIEW ROAD | 510909185 | Condition | 0 | Non Policy | 4 | ST | -277 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223140 | SEAVIEW ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
628368510 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223042 | HALL CRESCENT | 628368510 | Condition | 0 | Non Policy | 4 | ST | -224 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223042 | HALL CRESCENT | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510861167 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | Chris McVeigh | IMGA223016 | KINGSLEY ROAD | 510861167 | T1 PAST | 0 | Non Policy | 6 | ST | 90.9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223016 | KINGSLEY ROAD | Brentwood Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Non Policy | Tier 1 | ST | ST LP 6"-7" | July
510852318 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Chris Southam | IMGA223010 | HILLHOUSE DRIVE | 510852318 | T1 PAST | 0 | Non Policy | 4 | ST | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223010 | HILLHOUSE DRIVE | Basildon Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO SMYTH, Billy | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510785390 | T1 PAST | 0 | Non Policy | 4 | ST | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma |  | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | T1 PAST | 0 | Non Policy | 4 | ST | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | T1 PAST | 0 | Non Policy | 4 | ST | 170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | T1 PAST | 0 | Non Policy | 4 | ST | 156 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510925235 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | THUNDERSLEY PARK ROAD | 510925235 | T1 PAST | 0 | Non Policy | 4 | ST | 102 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | THUNDERSLEY PARK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510909185 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223140 | SEAVIEW ROAD | 510909185 | T1 PAST | 0 | Non Policy | 4 | ST | 277 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223140 | SEAVIEW ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO BRAY, Ben | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
628368510 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223042 | HALL CRESCENT | 628368510 | T1 PAST | 0 | Non Policy | 4 | ST | 224 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223042 | HALL CRESCENT | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
510786246 | CMO | CMO East 2 | July | 16 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 510786246 | T1 Policy | 8.9 | Policy | 4 | CI | 1.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01335 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220000813466 | CMO | CMO East 2 | July | 16 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 220000813466 | T1 Policy | 3.1 | Policy | 6 | CI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.062 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220000806668 | CMO | CMO East 2 | July | 16 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 220000806668 | T1 Policy | 3.6 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0072 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510863309 | CMO | CMO East 2 | July | 16 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 11 | Policy | 4 | CI | 67 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.737 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510959132 | CMO | CMO East 2 | July | 16 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959132 | T1 Policy | 5.7 | Policy | 6 | CI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.798 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510873869 | CMO | CMO East 2 | July | 16 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510873869 | T1 Policy | 0 | Policy | 6 | SI | 27 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510856117 | CMO | CMO East 2 | July | 16 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 7.1 | Policy | 6 | CI | 0 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510941802 | CMO | CMO East 2 | July | 16 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941802 | T1 Policy | 3 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.012 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510941803 | CMO | CMO East 2 | July | 16 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941803 | T1 Policy | 1.7 | Policy | 4 | CI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0765 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510941809 | CMO | CMO East 2 | July | 16 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0168 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510800903 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | James Cox | IMGA223088 | CADOGAN AVENUE | 510800903 | T1 Policy | 127.7 | Policy | 4 | DI | 145 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 18.5165 | 0 | CMO East 2 | IMGA223088 | CADOGAN AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
603360826 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 0.7 | Policy | 6 | CI | 201.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14126 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510965697 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | Mick Linwood | IMGA223263 | COPPERFIELD | 510965697 | T1 Policy | 4.8 | Policy | 4 | DI | 51 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2448 | 0 | CMO East 2 | IMGA223263 | COPPERFIELD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront |  | CMO GILBERT, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510965744 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | Mick Linwood | IMGA223263 | COPPERFIELD | 510965744 | T1 Policy | 36.9 | Policy | 8 | DI | 4 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1476 | 0 | CMO East 2 | IMGA223263 | COPPERFIELD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront |  | CMO GILBERT, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | July
510965705 | CMO | CMO East 2 | July | 16 | A | Dave Bamber | Mick Linwood | IMGA223263 | COPPERFIELD | 510965705 | T1 Policy | 6.6 | Policy | 8 | DI | 26 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1716 | 0 | CMO East 2 | IMGA223263 | COPPERFIELD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | July
510827001 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Chris Southam | IMGA223008 | ELM GREEN | 510827001 | T1 Policy | 10.1 | Policy | 4 | SI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4545 | 0 | CMO East 2 | IMGA223008 | ELM GREEN | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510899274 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510899274 | T1 Policy | 6.1 | Policy | 4 | DI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5185 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510970456 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | TILLINGHAM WAY | 510970456 | T1 Policy | 41.5 | Policy | 200 | DI | 53 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1995 | 0 | CMO East 2 | IMGA223059 | TILLINGHAM WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
220001725695 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | ILFRACOMBE ROAD | 220001725695 | T1 Policy | 0 | Policy | 100 | DI | 13 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223066 | ILFRACOMBE ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510856164 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510856164 | T1 Policy | 15.2 | Policy | 100 | DI | 17 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2584 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510918012 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 33 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.465 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510832429 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | FIRST AVENUE | 510832429 | T1 Policy | 5.3 | Policy | 4 | CI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5035 | 0 | CMO East 2 | IMGA223075 | FIRST AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510956462 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST GEORGES WALK | 510956462 | T1 Policy | 3.7 | Policy | 4 | SI | 13 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0481 | 0 | CMO East 2 | IMGA223134 | ST GEORGES WALK | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510956464 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST GEORGES WALK | 510956464 | T1 Policy | 6 | Policy | 4 | SI | 28 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.168 | 0 | CMO East 2 | IMGA223134 | ST GEORGES WALK | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510907413 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST PAULS ROAD | 510907413 | T1 Policy | 15.2 | Policy | 4 | SI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.532 | 0 | CMO East 2 | IMGA223134 | ST PAULS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220001276127 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST PAULS ROAD | 220001276127 | T1 Policy | 8.9 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0178 | 0 | CMO East 2 | IMGA223134 | ST PAULS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 510785390 | T1 PAST | 289.1 | Policy | 4 | ST | -235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelPolicy | FALSE | FALSE | CMO East 2 | -67.9385 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | ST | ST LP 4"-5" | July
510785390 | CMO | CMO East 2 | July | 16 | A | Stuart Griffiths | Paul Illingworth | IMGA223039 | AVONDALE ROAD | 510785390 | T1 PAST | 0 | Non Policy | 4 | ST | 235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223039 | AVONDALE ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | July
Side Street | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | LEAS GARDENS | Side Street | T1 Policy | 0 | Policy | 2 | SI | 68 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223075 | LEAS GARDENS | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | July
510800903 | CMO | CMO East 2 | July | 17 | A | Dave Bamber | James Cox | IMGA223088 | CADOGAN AVENUE | 510800903 | T1 Policy | 127.7 | Policy | 4 | DI | 131 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 16.7287 | 0 | CMO East 2 | IMGA223088 | CADOGAN AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510828612 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | ESPLANADE GARDENS | 510828612 | T1 Policy | 13.5 | Policy | 4 | CI | 44 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.594 | 0 | CMO East 2 | IMGA223075 | ESPLANADE GARDENS | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510831420 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510831420 | T1 Policy | 15 | Policy | 4 | DI | 24 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.36 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510852657 | CMO | CMO East 2 | July | 17 | A | Dave Bamber | Chris McVeigh | IMGA223018 | HILLWOOD GROVE | 510852657 | T1 Policy | 4.4 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.44 | 0 | CMO East 2 | IMGA223018 | HILLWOOD GROVE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510857370 | CMO | CMO East 2 | July | 17 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510857370 | T1 Policy | 7.7 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0539 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510861612 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510861612 | T1 Policy | 4 | Policy | 4 | CI | 260 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.04 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510861618 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510861618 | T1 Policy | 6.9 | Policy | 4 | SI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.3381 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510863309 | CMO | CMO East 2 | July | 17 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 11 | Policy | 4 | CI | 71 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.781 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510864798 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | LEAS GARDENS | 510864798 | T1 Policy | 14.1 | Policy | 4 | CI | 116 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6356 | 0 | CMO East 2 | IMGA223075 | LEAS GARDENS | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510956148 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510956148 | T1 Policy | 12.3 | Policy | 4 | SI | 38 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.4674 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510956437 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510956437 | T1 Policy | 14.1 | Policy | 4 | DI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.6627 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510956438 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510956438 | T1 Policy | 7.5 | Policy | 4 | SI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.195 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510959131 | CMO | CMO East 2 | July | 17 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959131 | T1 Policy | 4.8 | Policy | 4 | CI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.576 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
635869753 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | THE DRIVE | 635869753 | T1 Policy | 22.9 | Policy | 4 | CI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1374 | 0 | CMO East 2 | IMGA223073 | THE DRIVE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO FEARON, Tom (JUPP) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220001524411 | CMO | CMO East 2 | July | 17 | A | Alex Wright | Jake Parry | IMGA223158 | ROWLANDS ROAD | 220001524411 | T1 Policy | 8.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0178 | 0 | CMO East 2 | IMGA223158 | ROWLANDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510780058 | CMO | CMO East 2 | July | 17 | A | Dave Bamber | Mick Linwood | IMGA223273 | ALBION HILL | 510780058 | T1 Policy | 16.8 | Policy | 6 | SI | 102 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7136 | 0 | CMO East 2 | IMGA223273 | ALBION HILL | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510845069 | CMO | CMO East 2 | July | 17 | A | Dave Bamber | Darren Francis | IMGA223093 | HANFORD ROAD | 510845069 | T1 Policy | 2.9 | Policy | 6 | CI | 69 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2001 | 0 | CMO East 2 | IMGA223093 | HANFORD ROAD | Thurrock Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | tRIIO WASSELL, Mark | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510856117 | CMO | CMO East 2 | July | 17 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 7.1 | Policy | 6 | CI | 115 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8165 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510869481 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Chris Southam | IMGA223004 | LONGTAIL | 510869481 | T1 Policy | 24.8 | Policy | 6 | DI | 41 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0168 | 0 | CMO East 2 | IMGA223004 | LONGTAIL | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510903877 | CMO | CMO East 2 | July | 17 | A | Alex Wright | Jake Parry | IMGA223158 | ROWLANDS ROAD | 510903877 | T1 Policy | 2.5 | Policy | 6 | SI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.225 | 0 | CMO East 2 | IMGA223158 | ROWLANDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510941809 | CMO | CMO East 2 | July | 17 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 230 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.644 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
603360826 | CMO | CMO East 2 | July | 17 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 0.7 | Policy | 6 | CI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.063 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
636168810 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Bob Sawyer | IMGA223073 | KINGS ROAD | 636168810 | T1 Policy | 7.8 | Policy | 6 | CI | 263 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0514 | 0 | CMO East 2 | IMGA223073 | KINGS ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO FEARON, Tom (JUPP) | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220000806668 | CMO | CMO East 2 | July | 17 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 220000806668 | T1 Policy | 3.6 | Policy | 6 | CI | 46 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1656 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510888227 | CMO | CMO East 2 | July | 17 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 510888227 | T1 Policy | 2.8 | Policy | 8 | CI | 9 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0252 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510899282 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510899282 | T1 Policy | 8.3 | Policy | 8 | DI | 133 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1039 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | July
510918012 | CMO | CMO East 2 | July | 17 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 66 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.93 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510903877 | CMO | CMO East 2 | July | 18 | A | Alex Wright | Jake Parry | IMGA223158 | ROWLANDS ROAD | 510903877 | T1 Policy | 2.5 | Policy | 6 | CI | 82 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.205 | 0 | CMO East 2 | IMGA223158 | ROWLANDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510786224 | CMO | CMO East 2 | July | 18 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 510786224 | T1 Policy | 1 | Policy | 8 | CI | 30.5 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0305 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
220000813466 | CMO | CMO East 2 | July | 18 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 220000813466 | T1 Policy | 3.1 | Policy | 6 | CI | 10.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.03255 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510888227 | CMO | CMO East 2 | July | 18 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 510888227 | T1 Policy | 2.8 | Policy | 6 | CI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0392 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510888230 | CMO | CMO East 2 | July | 18 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 510888230 | T1 Policy | 6 | Policy | 6 | CI | 1.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.009 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220000806668 | CMO | CMO East 2 | July | 18 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 220000806668 | T1 Policy | 3.6 | Policy | 6 | CI | 57 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2052 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510863309 | CMO | CMO East 2 | July | 18 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 11 | Policy | 4 | CI | 48 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.528 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510959132 | CMO | CMO East 2 | July | 18 | A | Alex Wright | James Cox | IMGA223174 | GREEN LANE | 510959132 | T1 Policy | 5.7 | Policy | 6 | CI | 149 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8493 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220001433953 | CMO | CMO East 2 | July | 18 | A | Alex Wright | Jake Parry | IMGA223184 | CARROW ROAD | 220001433953 | T1 Policy | 2.3 | Policy | 4 | CI | 2.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.00529 | 0 | CMO East 2 | IMGA223184 | CARROW ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510941809 | CMO | CMO East 2 | July | 18 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 165 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.462 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510852657 | CMO | CMO East 2 | July | 18 | A | Dave Bamber | Chris McVeigh | IMGA223018 | HILLWOOD GROVE | 510852657 | T1 Policy | 4.4 | Policy | 4 | CI | 169 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7436 | 0 | CMO East 2 | IMGA223018 | HILLWOOD GROVE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510924794 | CMO | CMO East 2 | July | 18 | A | Dave Bamber | James Cox | IMGA223088 | THORNDON AVENUE | 510924794 | T1 PAST | 221.1 | Policy | 4 | DI | 143 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 31.6173 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
603360826 | CMO | CMO East 2 | July | 18 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 0.7 | Policy | 6 | CI | 118 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0826 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510780058 | CMO | CMO East 2 | July | 18 | A | Dave Bamber | Mick Linwood | IMGA223273 | ALBION HILL | 510780058 | T1 Policy | 16.8 | Policy | 6 | SI | 88 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4784 | 0 | CMO East 2 | IMGA223273 | ALBION HILL | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510823550 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Chris Southam | IMGA223004 | DUNFANE | 510823550 | T1 Policy | 7.4 | Policy | 4 | DI | 79 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5846 | 0 | CMO East 2 | IMGA223004 | DUNFANE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510823551 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Chris Southam | IMGA223004 | DUNFANE | 510823551 | T1 Policy | 5.1 | Policy | 4 | DI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2754 | 0 | CMO East 2 | IMGA223004 | DUNFANE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510827001 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Chris Southam | IMGA223008 | ELM GREEN | 510827001 | T1 Policy | 10.1 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.01 | 0 | CMO East 2 | IMGA223008 | ELM GREEN | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510801485 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510801485 | T1 Policy | 7.1 | Policy | 6 | DI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0142 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510899281 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510899281 | T1 Policy | 2.7 | Policy | 200 | DI | 65 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1755 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510899282 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 510899282 | T1 Policy | 8.3 | Policy | 200 | DI | 80 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.664 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
602621826 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | RECTORY AVENUE | 602621826 | T1 Policy | 4.4 | Policy | 200 | DI | 2 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0088 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | tRIIO COLWILL, Scott | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510828611 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | ESPLANADE GARDENS | 510828611 | T1 Policy | 3.2 | Policy | 6 | CI | 183 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5856 | 0 | CMO East 2 | IMGA223075 | ESPLANADE GARDENS | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510905836 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Chris Southam | IMGA223084 | ST CLERES CRESCENT | 510905836 | T1 Policy | 2.8 | Policy | 6 | SI | 109 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3052 | 0 | CMO East 2 | IMGA223084 | ST CLERES CRESCENT | Basildon Borough Council | East 2 | FALSE |  | Forefront |  | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510790919 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | BERKELEY LANE | 510790919 | T1 Policy | 4.3 | Policy | 4 | SI | 189 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.8127 | 0 | CMO East 2 | IMGA223133 | BERKELEY LANE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220001256954 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | BERKELEY LANE | 220001256954 | T1 Policy | 5.8 | Policy | 4 | SI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0696 | 0 | CMO East 2 | IMGA223133 | BERKELEY LANE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510861618 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223133 | KITKATTS ROAD | 510861618 | T1 Policy | 6.9 | Policy | 4 | SI | 20 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.138 | 0 | CMO East 2 | IMGA223133 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220001276127 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST JAMES CLOSE | 220001276127 | T1 Policy | 8.9 | Policy | 4 | SI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0267 | 0 | CMO East 2 | IMGA223134 | ST JAMES CLOSE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220001786689 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST JAMES CLOSE | 220001786689 | T1 Policy | 0 | Policy | 4 | SI | 44 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223134 | ST JAMES CLOSE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510907413 | CMO | CMO East 2 | July | 18 | A | Stuart Griffiths | Paul Illingworth | IMGA223134 | ST PAULS ROAD | 510907413 | T1 Policy | 15.2 | Policy | 4 | SI | 37 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.5624 | 0 | CMO East 2 | IMGA223134 | ST PAULS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510819711 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Steve Moscrop | IMGA223174 | GREEN LANE | 510819711 | T1 Policy | 8.9 | Policy | 4 | CI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0712 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510848264 | CMO | CMO East 2 | August | 19 | A | Alex Wright | James Cox | IMGA223176 | HEDINGHAM ROAD | 510848264 | T1 Policy | 4.1 | Policy | 4 | CI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4715 | 0 | CMO East 2 | IMGA223176 | HEDINGHAM ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510854086 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 510854086 | T1 Policy | 2.4 | Policy | 4 | CI | 37 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0888 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510856846 | CMO | CMO East 2 | August | 19 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856846 | T1 Policy | 9.5 | Policy | 4 | CI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2375 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510863304 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863304 | T1 Policy | 21.6 | Policy | 4 | CI | 14.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.30888 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510863306 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863306 | T1 Policy | 13.7 | Policy | 4 | CI | 42.2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.57814 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510863309 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 11 | Policy | 4 | CI | 54.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5995 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510924794 | CMO | CMO East 2 | August | 19 | A | Dave Bamber | James Cox | IMGA223088 | THORNDON AVENUE | 510924794 | T1 PAST | 221.1 | Policy | 4 | DI | 79 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 17.4669 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510924795 | CMO | CMO East 2 | August | 19 | A | Dave Bamber | James Cox | IMGA223088 | THORNDON AVENUE | 510924795 | T1 Policy | 27.4 | Policy | 4 | DI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7262 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510941805 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941805 | T1 Policy | 1.8 | Policy | 4 | CI | 32 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0576 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510941811 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941811 | T1 Policy | 2.3 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0046 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510956427 | CMO | CMO East 2 | August | 19 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | CORNWALL GARDENS | 510956427 | T1 Policy | 11.9 | Policy | 4 | DI | 69 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8211 | 0 | CMO East 2 | IMGA223051 | CORNWALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510956428 | CMO | CMO East 2 | August | 19 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | DEVON GARDENS | 510956428 | T1 Policy | 10.7 | Policy | 4 | DI | 38 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4066 | 0 | CMO East 2 | IMGA223051 | DEVON GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510956429 | CMO | CMO East 2 | August | 19 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | CORNWALL GARDENS | 510956429 | T1 Policy | 11.3 | Policy | 4 | DI | 16 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1808 | 0 | CMO East 2 | IMGA223051 | CORNWALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510956430 | CMO | CMO East 2 | August | 19 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | DEVON GARDENS | 510956430 | T1 Policy | 4.9 | Policy | 4 | DI | 11 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0539 | 0 | CMO East 2 | IMGA223051 | DEVON GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510956431 | CMO | CMO East 2 | August | 19 | A | Stuart Griffiths | Paul Illingworth | IMGA223051 | DEVON GARDENS | 510956431 | T1 Policy | 7.3 | Policy | 4 | DI | 38 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2774 | 0 | CMO East 2 | IMGA223051 | DEVON GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510780058 | CMO | CMO East 2 | August | 19 | A | Dave Bamber | Mick Linwood | IMGA223273 | ALBION HILL | 510780058 | T1 Policy | 16.8 | Policy | 6 | SI | 58 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9744 | 0 | CMO East 2 | IMGA223273 | ALBION HILL | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510856117 | CMO | CMO East 2 | August | 19 | A | Alex Wright | James Cox | IMGA223177 | ILCHESTER ROAD | 510856117 | T1 Policy | 7.1 | Policy | 6 | CI | 176 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2496 | 0 | CMO East 2 | IMGA223177 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510901018 | CMO | CMO East 2 | August | 19 | A | Alex Wright | James Cox | IMGA223165 | RIDGEWELL CLOSE | 510901018 | T1 Policy | 32.6 | Policy | 6 | DI | 119 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.8794 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510903877 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223158 | ROWLANDS ROAD | 510903877 | T1 Policy | 2.5 | Policy | 6 | CI | 37 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0925 | 0 | CMO East 2 | IMGA223158 | ROWLANDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510941809 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 35 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.098 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510959132 | CMO | CMO East 2 | August | 19 | A | Alex Wright | Steve Moscrop | IMGA223174 | GREEN LANE | 510959132 | T1 Policy | 5.7 | Policy | 6 | CI | 152 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8664 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
603360826 | CMO | CMO East 2 | August | 19 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 0.7 | Policy | 6 | CI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0049 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
Side Street | CMO | CMO East 2 | August | 19 | A | Alex Wright | Steve Moscrop | IMGA223174 | GREEN LANE | Side Street | T1 Policy | 0 | Policy | 6 | CI | 9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510809328 | CMO | CMO East 2 | August | 19 | A | Dave Bamber | Mick Linwood | IMGA223257 | CHURCH ROAD | 510809328 | T1 Policy | 4.4 | Policy | 7 | CI | 27 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1188 | 0 | CMO East 2 | IMGA223257 | CHURCH ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510918012 | CMO | CMO East 2 | August | 19 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 61 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.405 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
220001571826 | CMO | CMO East 2 | August | 20 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 220001571826 | T1 Policy | 4.1 | Policy | 4 | CI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2665 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510888227 | CMO | CMO East 2 | August | 20 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 510888227 | T1 Policy | 2.8 | Policy | 6 | CI | 9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0252 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510888227 | CMO | CMO East 2 | August | 20 | A | Alex Wright | James Cox | IMGA223165 | OVAL ROAD NORTH | 510888227 | T1 Policy | 2.8 | Policy | 8 | CI | 58 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1624 | 0 | CMO East 2 | IMGA223165 | OVAL ROAD NORTH | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510929363 | CMO | CMO East 2 | August | 20 | A | Alex Wright | Steve Moscrop | IMGA223174 | VALENCE AVENUE | 510929363 | T1 Policy | 2.8 | Policy | 6 | CI | 65 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.182 | 0 | CMO East 2 | IMGA223174 | VALENCE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510856846 | CMO | CMO East 2 | August | 20 | A | Alex Wright | James Cox | IMGA223176 | HEDINGHAM ROAD | 510856846 | T1 Policy | 9.5 | Policy | 4 | CI | 101 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9595 | 0 | CMO East 2 | IMGA223176 | HEDINGHAM ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
DR4 Requested | CMO | CMO East 2 | August | 20 | A | Alex Wright | James Cox | IMGA223176 | HEDINGHAM ROAD | DR4 Requested | Condition | 0 | Non Policy | 1.5 | ST | 20 | inch | 1.5inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223176 | HEDINGHAM ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | LP | #N/A | <=3” | 1.5 |  | Non Policy | Tier 1 | ST | ST LP <=3" | August
510848265 | CMO | CMO East 2 | August | 20 | A | Alex Wright | James Cox | IMGA223176 | HEDINGHAM ROAD | 510848265 | T1 Policy | 4.6 | Policy | 4 | CI | 94 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4324 | 0 | CMO East 2 | IMGA223176 | HEDINGHAM ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510941809 | CMO | CMO East 2 | August | 20 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 78 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2184 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510941810 | CMO | CMO East 2 | August | 20 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941810 | T1 Policy | 3.6 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0108 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510845157 | CMO | CMO East 2 | August | 20 | A | Dave Bamber | Chris McVeigh | IMGA223017 | HANGING HILL LANE | 510845157 | T1 PAST | 202.2 | Policy | 150 | DI | 40 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 8.088 | 0 | CMO East 2 | IMGA223017 | HANGING HILL LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO BRAY, Ben | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510845179 | CMO | CMO East 2 | August | 20 | A | Dave Bamber | Chris McVeigh | IMGA223017 | HANGING HILL LANE | 510845179 | T1 Policy | 3.8 | Policy | 6 | SI | 22 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0836 | 0 | CMO East 2 | IMGA223017 | HANGING HILL LANE | Brentwood Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO BRAY, Ben | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510800902 | CMO | CMO East 2 | August | 20 | A | Dave Bamber | James Cox | IMGA223088 | CADOGAN AVENUE | 510800902 | T1 Policy | 17.1 | Policy | 4 | DI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.565 | 0 | CMO East 2 | IMGA223088 | CADOGAN AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510899281 | CMO | CMO East 2 | August | 20 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | RECTORY AVENUE | 510899281 | T1 Policy | 2.7 | Policy | 8 | SI | 46 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1242 | 0 | CMO East 2 | IMGA223051 | RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510918012 | CMO | CMO East 2 | August | 20 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 60 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.3 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510905834 | CMO | CMO East 2 | August | 20 | A | Stuart Griffiths | Chris Southam | IMGA223084 | ST CLERES CRESCENT | 510905834 | T1 Policy | 2.1 | Policy | 8 | SI | 13 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0273 | 0 | CMO East 2 | IMGA223084 | ST CLERES CRESCENT | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510905835 | CMO | CMO East 2 | August | 20 | A | Stuart Griffiths | Chris Southam | IMGA223084 | ST CLERES CRESCENT | 510905835 | T1 Policy | 2 | Policy | 6 | SI | 48 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.096 | 0 | CMO East 2 | IMGA223084 | ST CLERES CRESCENT | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510905836 | CMO | CMO East 2 | August | 20 | A | Stuart Griffiths | Chris Southam | IMGA223084 | ST CLERES CRESCENT | 510905836 | T1 Policy | 2.8 | Policy | 6 | SI | 25 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.07 | 0 | CMO East 2 | IMGA223084 | ST CLERES CRESCENT | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510933955 | CMO | CMO East 2 | August | 20 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510933955 | T1 Policy | 9.9 | Policy | 4 | SI | 134 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.3266 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220001571826 | CMO | CMO East 2 | August | 21 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 220001571826 | T1 Policy | 4.1 | Policy | 4 | CI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4715 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510901019 | CMO | CMO East 2 | August | 21 | A | Alex Wright | James Cox | IMGA223165 | RIDGEWELL CLOSE | 510901019 | T1 Policy | 6.3 | Policy | 4 | DI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3402 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510863307 | CMO | CMO East 2 | August | 21 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863307 | T1 Policy | 14.6 | Policy | 4 | CI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6862 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510863309 | CMO | CMO East 2 | August | 21 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 11 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.11 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510863309 | CMO | CMO East 2 | August | 21 | A | Alex Wright | Jake Parry | IMGA223167 | LANGHORNE ROAD | 510863309 | T1 Policy | 11 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.11 | 0 | CMO East 2 | IMGA223167 | LANGHORNE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510959132 | CMO | CMO East 2 | August | 21 | A | Alex Wright | Steve Moscrop | IMGA223174 | GREEN LANE | 510959132 | T1 Policy | 5.7 | Policy | 6 | CI | 54 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3078 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510848265 | CMO | CMO East 2 | August | 21 | A | Alex Wright | James Cox | IMGA223176 | HEDINGHAM ROAD | 510848265 | T1 Policy | 4.6 | Policy | 4 | CI | 134 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6164 | 0 | CMO East 2 | IMGA223176 | HEDINGHAM ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510856846 | CMO | CMO East 2 | August | 21 | A | Alex Wright | James Cox | IMGA223176 | IVINGHOE ROAD | 510856846 | T1 Policy | 9.5 | Policy | 4 | CI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.342 | 0 | CMO East 2 | IMGA223176 | IVINGHOE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510941809 | CMO | CMO East 2 | August | 21 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.028 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510800902 | CMO | CMO East 2 | August | 21 | A | Dave Bamber | James Cox | IMGA223088 | CADOGAN AVENUE | 510800902 | T1 Policy | 17.1 | Policy | 4 | DI | 123 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1033 | 0 | CMO East 2 | IMGA223088 | CADOGAN AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
603360826 | CMO | CMO East 2 | August | 21 | A | Dave Bamber | Mick Linwood | IMGA223257 | EPPING NEW ROAD | 603360826 | T1 Policy | 0.7 | Policy | 6 | CI | 12 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0084 | 0 | CMO East 2 | IMGA223257 | EPPING NEW ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510780060 | CMO | CMO East 2 | August | 21 | A | Dave Bamber | Mick Linwood | IMGA223273 | ALBION HILL | 510780060 | T1 PAST | 150.3 | Policy | 6 | DI | 59 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 8.8677 | 0 | CMO East 2 | IMGA223273 | ALBION HILL | Epping Forest District Council (Lower) | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510956427 | CMO | CMO East 2 | August | 21 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | CORNWALL GARDENS | 510956427 | T1 Policy | 11.9 | Policy | 4 | DI | 81 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9639 | 0 | CMO East 2 | IMGA223051 | CORNWALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510956432 | CMO | CMO East 2 | August | 21 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | FOOTPATH NORTH FROM CORNWALL GARDENS TO RECTORY AVENUE | 510956432 | T1 Policy | 8.4 | Policy | 4 | DI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3948 | 0 | CMO East 2 | IMGA223051 | FOOTPATH NORTH FROM CORNWALL GARDENS TO RECTORY AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510882544 | CMO | CMO East 2 | August | 21 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | NEWELL AVENUE | 510882544 | T1 Policy | 9.5 | Policy | 4 | CI | 155 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4725 | 0 | CMO East 2 | IMGA223070 | NEWELL AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510832428 | CMO | CMO East 2 | August | 21 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | FIRST AVENUE | 510832428 | T1 Policy | 3.2 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.384 | 0 | CMO East 2 | IMGA223075 | FIRST AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510832429 | CMO | CMO East 2 | August | 21 | A | Stuart Griffiths | Bob Sawyer | IMGA223075 | FIRST AVENUE | 510832429 | T1 Policy | 5.3 | Policy | 4 | CI | 79 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4187 | 0 | CMO East 2 | IMGA223075 | FIRST AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510866907 | CMO | CMO East 2 | August | 21 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866907 | T1 PAST | 250.6 | Policy | 6 | DI | 94 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 23.5564 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | tRIIO FEARON, Tom (JUPP) | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510789102 | CMO | CMO East 2 | August | 22 | A | Alex Wright | Jake Parry | IMGA223158 | BECONTREE AVENUE | 510789102 | T1 Policy | 4.3 | Policy | 4 | CI | 220 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.946 | 0 | CMO East 2 | IMGA223158 | BECONTREE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510786224 | CMO | CMO East 2 | August | 22 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 510786224 | T1 Policy | 1 | Policy | 8 | CI | 46 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.046 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
220000775593 | CMO | CMO East 2 | August | 22 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 220000775593 | T1 Policy | 5.6 | Policy | 4 | CI | 21 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1176 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220000775595 | CMO | CMO East 2 | August | 22 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 220000775595 | T1 Policy | 4.9 | Policy | 4 | CI | 20 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.098 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510870802 | CMO | CMO East 2 | August | 22 | A | Alex Wright | Steve Moscrop | IMGA223170 | LYMINGTON ROAD | 510870802 | T1 Policy | 0 | Policy | 6 | CI | 91.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510959118 | CMO | CMO East 2 | August | 22 | A | Alex Wright | Steve Moscrop | IMGA223174 | GREEN LANE | 510959118 | T1 Policy | 6.9 | Policy | 6 | CI | 29 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2001 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510959131 | CMO | CMO East 2 | August | 22 | A | Alex Wright | Steve Moscrop | IMGA223174 | GREEN LANE | 510959131 | T1 Policy | 4.8 | Policy | 6 | CI | 29 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1392 | 0 | CMO East 2 | IMGA223174 | GREEN LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510846124 | CMO | CMO East 2 | August | 22 | A | Alex Wright | James Cox | IMGA223176 | HARROLD ROAD | 510846124 | T1 Policy | 5.2 | Policy | 4 | CI | 66 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3432 | 0 | CMO East 2 | IMGA223176 | HARROLD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510846125 | CMO | CMO East 2 | August | 22 | A | Alex Wright | James Cox | IMGA223176 | HARROLD ROAD | 510846125 | T1 Policy | 5 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5 | 0 | CMO East 2 | IMGA223176 | HARROLD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510856846 | CMO | CMO East 2 | August | 22 | A | Alex Wright | James Cox | IMGA223176 | IVINGHOE ROAD | 510856846 | T1 Policy | 9.5 | Policy | 4 | CI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4275 | 0 | CMO East 2 | IMGA223176 | IVINGHOE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220001521686 | CMO | CMO East 2 | August | 22 | A | Alex Wright | Jake Parry | IMGA223181 | GRAFTON ROAD | 220001521686 | T1 Policy | 12 | Policy | 8 | CI | 20 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.24 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510845157 | CMO | CMO East 2 | August | 22 | A | Dave Bamber | Chris McVeigh | IMGA223017 | HANGING HILL LANE | 510845157 | T1 PAST | 202.2 | Policy | 150 | DI | 92 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 18.6024 | 0 | CMO East 2 | IMGA223017 | HANGING HILL LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO BRAY, Ben | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510800902 | CMO | CMO East 2 | August | 22 | A | Dave Bamber | James Cox | IMGA223088 | CADOGAN AVENUE | 510800902 | T1 Policy | 17.1 | Policy | 4 | DI | 68 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1628 | 0 | CMO East 2 | IMGA223088 | CADOGAN AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510965630 | CMO | CMO East 2 | August | 22 | A | Dave Bamber | Mick Linwood | IMGA223273 | POLLARDS CLOSE | 510965630 | T1 Policy | 10.1 | Policy | 4 | SI | 76 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7676 | 0 | CMO East 2 | IMGA223273 | POLLARDS CLOSE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510853923 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Chris Southam | IMGA223004 | HOLLYFORD | 510853923 | T1 Policy | 8.2 | Policy | 8 | DI | 62 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5084 | 0 | CMO East 2 | IMGA223004 | HOLLYFORD | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | August
510869481 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Chris Southam | IMGA223004 | LONGTAIL | 510869481 | T1 Policy | 24.8 | Policy | 6 | DI | 53 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3144 | 0 | CMO East 2 | IMGA223004 | LONGTAIL | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510786308 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Chris Southam | IMGA223008 | BALMORAL CLOSE | 510786308 | T1 Policy | 14.1 | Policy | 4 | SI | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4805 | 0 | CMO East 2 | IMGA223008 | BALMORAL CLOSE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510857043 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Chris Southam | IMGA223008 | JAMES SQUARE | 510857043 | T1 Policy | 6.2 | Policy | 4 | SI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1674 | 0 | CMO East 2 | IMGA223008 | JAMES SQUARE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510857044 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Chris Southam | IMGA223008 | JAMES SQUARE | 510857044 | T1 Policy | 9.2 | Policy | 4 | SI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4232 | 0 | CMO East 2 | IMGA223008 | JAMES SQUARE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510918012 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 60 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.3 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510803712 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | CASTLE CLOSE | 510803712 | T1 Policy | 28.6 | Policy | 4 | SI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.288 | 0 | CMO East 2 | IMGA223070 | CASTLE CLOSE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510891111 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | PEEL AVENUE | 510891111 | T1 Policy | 6.8 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.34 | 0 | CMO East 2 | IMGA223070 | PEEL AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510788726 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Chris Southam | IMGA223084 | BEAUCHAMPS DRIVE | 510788726 | T1 Policy | 2.2 | Policy | 8 | SI | 102 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2244 | 0 | CMO East 2 | IMGA223084 | BEAUCHAMPS DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510904450 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510904450 | T1 Policy | 13.1 | Policy | 200 | DI | 22 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.2882 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510933954 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510933954 | T1 Policy | 5 | Policy | 8 | SI | 60 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.3 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510933955 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510933955 | T1 Policy | 9.9 | Policy | 4 | SI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0495 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510933956 | CMO | CMO East 2 | August | 22 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510933956 | T1 Policy | 13.4 | Policy | 200 | DI | 40 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.536 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
Side Street | CMO | CMO East 2 | September | 23 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | Side Street | T1 Policy | 0 | Policy | 8 | CI | 1.4 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510786224 | CMO | CMO East 2 | September | 23 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 510786224 | T1 Policy | 1 | Policy | 8 | CI | 152.5 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1525 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
220000776470 | CMO | CMO East 2 | September | 23 | A | Alex Wright | James Cox | IMGA223165 | BALLARDS ROAD | 220000776470 | T1 Policy | 3.5 | Policy | 4 | SI | 6.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0238 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510846124 | CMO | CMO East 2 | September | 23 | A | Alex Wright | James Cox | IMGA223176 | HARROLD ROAD | 510846124 | T1 Policy | 5.2 | Policy | 4 | CI | 163 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8476 | 0 | CMO East 2 | IMGA223176 | HARROLD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510846125 | CMO | CMO East 2 | September | 23 | A | Alex Wright | James Cox | IMGA223176 | HARROLD ROAD | 510846125 | T1 Policy | 5 | Policy | 4 | CI | 9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.045 | 0 | CMO East 2 | IMGA223176 | HARROLD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510941808 | CMO | CMO East 2 | September | 23 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941808 | T1 Policy | 5.9 | Policy | 8 | CI | 87 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5133 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510941809 | CMO | CMO East 2 | September | 23 | A | Alex Wright | Jake Parry | IMGA223184 | WOODWARD ROAD | 510941809 | T1 Policy | 2.8 | Policy | 6 | CI | 57 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1596 | 0 | CMO East 2 | IMGA223184 | WOODWARD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510835077 | CMO | CMO East 2 | September | 23 | A | Dave Bamber | Chris McVeigh | IMGA223035 | FRYERNING LANE | 510835077 | T1 Policy | 1.7 | Policy | 6 | CI | 480 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.816 | 0 | CMO East 2 | IMGA223035 | FRYERNING LANE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO DAUGHTERS-WRIGHT, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510809327 | CMO | CMO East 2 | September | 23 | A | Dave Bamber | Mick Linwood | IMGA223257 | CHURCH ROAD | 510809327 | T1 Policy | 17.5 | Policy | 7 | CI | 48.1 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.84175 | 0 | CMO East 2 | IMGA223257 | CHURCH ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510809328 | CMO | CMO East 2 | September | 23 | A | Dave Bamber | Mick Linwood | IMGA223257 | CHURCH ROAD | 510809328 | T1 Policy | 4.4 | Policy | 7 | CI | 81.8 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.35992 | 0 | CMO East 2 | IMGA223257 | CHURCH ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510786308 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Chris Southam | IMGA223008 | BALMORAL CLOSE | 510786308 | T1 Policy | 14.1 | Policy | 4 | SI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1562 | 0 | CMO East 2 | IMGA223008 | BALMORAL CLOSE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
220000688437 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Chris Southam | IMGA223008 | STUART WAY | 220000688437 | T1 Policy | 20.4 | Policy | 4 | SI | 66 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3464 | 0 | CMO East 2 | IMGA223008 | STUART WAY | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO ABBOTT , Tim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510821085 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | DEVON GARDENS | 510821085 | T1 Policy | 10.7 | Policy | 4 | DI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5778 | 0 | CMO East 2 | IMGA223051 | DEVON GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
602621816 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | DEVON GARDENS | 602621816 | T1 Policy | 10.6 | Policy | 4 | DI | 14 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1484 | 0 | CMO East 2 | IMGA223051 | DEVON GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510899508 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | RECTORY ROAD | 510899508 | T1 Policy | 11.9 | Policy | 100 | DI | 47 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5593 | 0 | CMO East 2 | IMGA223051 | RECTORY ROAD | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510899509 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Robert Ashdown | IMGA223051 | RECTORY ROAD | 510899509 | T1 Policy | 127.7 | Policy | 4 | DI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.4695 | 0 | CMO East 2 | IMGA223051 | RECTORY ROAD | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510893500 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Bob Sawyer | IMGA223053 | PLUMBEROW AVENUE | 510893500 | T1 PAST | 0 | Non Policy | 4 | ST | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | September
510918012 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 75 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.875 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510788726 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Chris Southam | IMGA223084 | BEAUCHAMPS DRIVE | 510788726 | T1 Policy | 2.2 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.22 | 0 | CMO East 2 | IMGA223084 | BEAUCHAMPS DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866905 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866905 | T1 Policy | 4.3 | Policy | 8 | DI | 60 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.258 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | September
510866906 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866906 | T1 Policy | 2.5 | Policy | 8 | SI | 4 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.01 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866907 | CMO | CMO East 2 | September | 23 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866907 | T1 PAST | 250.6 | Policy | 6 | DI | 18 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 4.5108 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510809327 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | Mick Linwood | IMGA223257 | CHURCH ROAD | 510809327 | T1 Policy | 17.5 | Policy | 7 | CI | -48.1 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | -0.84175 | 0 | CMO East 2 | IMGA223257 | CHURCH ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510809328 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | Mick Linwood | IMGA223257 | CHURCH ROAD | 510809328 | T1 Policy | 4.4 | Policy | 7 | CI | 48.1 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.21164 | 0 | CMO East 2 | IMGA223257 | CHURCH ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510789102 | CMO | CMO East 2 | September | 24 | A | Alex Wright | Jake Parry | IMGA223158 | BECONTREE AVENUE | 510789102 | T1 Policy | 4.3 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.43 | 0 | CMO East 2 | IMGA223158 | BECONTREE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510903877 | CMO | CMO East 2 | September | 24 | A | Alex Wright | Jake Parry | IMGA223158 | ROWLANDS ROAD | 510903877 | T1 Policy | 2.5 | Policy | 6 | CI | 63 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1575 | 0 | CMO East 2 | IMGA223158 | ROWLANDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510786224 | CMO | CMO East 2 | September | 24 | A | Alex Wright | Andy Bond | IMGA223165 | BALLARDS ROAD | 510786224 | T1 Policy | 1 | Policy | 8 | CI | 299 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.299 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510901019 | CMO | CMO East 2 | September | 24 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901019 | T1 Policy | 6.3 | Policy | 4 | SI | 32 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2016 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
Side Street | CMO | CMO East 2 | September | 24 | A | Alex Wright | Jake Parry | IMGA223170 | LYMINGTON ROAD | Side Street | T1 Policy | 0 | Policy | 4 | CI | 1.2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
Side Street | CMO | CMO East 2 | September | 24 | A | Alex Wright | Jake Parry | IMGA223170 | LYMINGTON ROAD | Side Street | T1 Policy | 0 | Policy | 100 | DI | 1.9 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | #N/A | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510870802 | CMO | CMO East 2 | September | 24 | A | Alex Wright | Jake Parry | IMGA223170 | LYMINGTON ROAD | 510870802 | T1 Policy | 0 | Policy | 6 | CI | 217.1 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220001521686 | CMO | CMO East 2 | September | 24 | A | Alex Wright | Andy Bond | IMGA223181 | GRAFTON ROAD | 220001521686 | T1 Policy | 12 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510845157 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | Chris McVeigh | IMGA223017 | HANGING HILL LANE | 510845157 | T1 PAST | 202.2 | Policy | 150 | DI | 79 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 15.9738 | 0 | CMO East 2 | IMGA223017 | HANGING HILL LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO BRAY, Ben | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510845179 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | Chris McVeigh | IMGA223017 | HANGING HILL LANE | 510845179 | T1 Policy | 3.8 | Policy | 6 | CI | 36 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1368 | 0 | CMO East 2 | IMGA223017 | HANGING HILL LANE | Brentwood Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO BRAY, Ben | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220000661505 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WESTWOOD AVENUE | 220000661505 | T1 Policy | 8 | Policy | 6 | CI | 137 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.096 | 0 | CMO East 2 | IMGA223023 | WESTWOOD AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510924795 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | James Cox | IMGA223088 | THORNDON AVENUE | 510924795 | T1 Policy | 27.4 | Policy | 4 | DI | 159 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.3566 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510809327 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | TBA - Lon | IMGA223257 | CHURCH ROAD | 510809327 | T1 Policy | 17.5 | Policy | 4 | CI | 87 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5225 | 0 | CMO East 2 | IMGA223257 | CHURCH ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510780060 | CMO | CMO East 2 | September | 24 | A | Dave Bamber | Mick Linwood | IMGA223273 | ALBION HILL | 510780060 | T1 PAST | 150.3 | Policy | 6 | DI | 160.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 24.1232 | 0 | CMO East 2 | IMGA223273 | ALBION HILL | Epping Forest District Council (Lower) | East 2 | FALSE | PAST | Forefront | T1 PAST | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510946186 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Chris Southam | IMGA223004 | DOUBLET MEWS | 510946186 | T1 Policy | 4.3 | Policy | 150 | DI | 118 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5074 | 0 | CMO East 2 | IMGA223004 | DOUBLET MEWS | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510893500 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Bob Sawyer | IMGA223053 | PLUMBEROW AVENUE | 510893500 | T1 PAST | 0 | Policy | 4 | ST | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | ST | ST LP 4"-5" | September
510955673 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | BARDFIELD WAY | 510955673 | T1 Policy | 13.1 | Policy | 200 | DI | 76 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9956 | 0 | CMO East 2 | IMGA223059 | BARDFIELD WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510891111 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | PEEL AVENUE | 510891111 | T1 Policy | 6.8 | Policy | 4 | SI | 84 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5712 | 0 | CMO East 2 | IMGA223070 | PEEL AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510916934 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Robert Ashdown | IMGA223071 | STATION ROAD | 510916934 | T1 Policy | 5.5 | Policy | 6 | CI | 78 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.429 | 0 | CMO East 2 | IMGA223071 | STATION ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220001917333 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | KITKATTS ROAD | 220001917333 | T1 Policy | 0 | Policy | 4 | SI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223136 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
606866741 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | KITKATTS ROAD | 606866741 | T1 Policy | 20.3 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0406 | 0 | CMO East 2 | IMGA223136 | KITKATTS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510933954 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510933954 | T1 Policy | 5 | Policy | 8 | SI | 210 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.05 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
220001973015 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 220001973015 | T1 Policy | 0 | Policy | 8 | SI | 1 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | #N/A | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
220001973017 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 220001973017 | T1 Policy | 0 | Policy | 6 | SI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001973018 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 220001973018 | T1 Policy | 0 | Policy | 4 | SI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510866904 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866904 | T1 Policy | 3.1 | Policy | 8 | SI | 92 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.2852 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866905 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866905 | T1 Policy | 4.3 | Policy | 8 | SI | 42 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.1806 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510875815 | CMO | CMO East 2 | September | 24 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | MEADOW VIEW WALK | 510875815 | T1 Policy | 0 | Policy | 4 | DI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223142 | MEADOW VIEW WALK | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510893500 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Bob Sawyer | IMGA223053 | PLUMBEROW AVENUE | 510893500 | T1 PAST | 0 | Policy | 4 | ST | -65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | ST | ST LP 4"-5" | September
510893500 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Bob Sawyer | IMGA223053 | PLUMBEROW AVENUE | 510893500 | T1 PAST | 0 | Non Policy | 4 | ST | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | September
510789102 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Jake Parry | IMGA223158 | BECONTREE AVENUE | 510789102 | T1 Policy | 4.3 | Policy | 4 | CI | 103.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.44677 | 0 | CMO East 2 | IMGA223158 | BECONTREE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510901019 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901019 | T1 Policy | 6.3 | Policy | 4 | DI | 4.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02835 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510901020 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901020 | T1 Policy | 5.4 | Policy | 4 | DI | 55 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.297 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510901021 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901021 | T1 Policy | 5.4 | Policy | 4 | DI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3402 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510901022 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901022 | T1 Policy | 4.8 | Policy | 4 | DI | 1.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0072 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
636005098 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Jake Parry | IMGA223178 | LODGE AVENUE | 636005098 | T1 Policy | 4.4 | Policy | 4 | CI | 370 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.628 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001456792 | CMO | CMO East 2 | September | 25 | A | Alex Wright | TBA - Lon | IMGA223352 | NORWOOD AVENUE | 220001456792 | T1 Policy | 4.9 | Policy | 4 | DI | 241 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1809 | 0 | CMO East 2 | IMGA223352 | NORWOOD AVENUE | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO HUGHES, Shaun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510924795 | CMO | CMO East 2 | September | 25 | A | Dave Bamber | James Cox | IMGA223088 | THORNDON AVENUE | 510924795 | T1 Policy | 27.4 | Policy | 4 | DI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.11 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510885226 | CMO | CMO East 2 | September | 25 | A | Dave Bamber | Mick Linwood | IMGA223273 | NURSERY ROAD | 510885226 | T1 Policy | 4.1 | Policy | 4 | CI | 120.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.49364 | 0 | CMO East 2 | IMGA223273 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510893500 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Robert Ashdown | IMGA223053 | PLUMBEROW AVENUE | 510893500 | T1 PAST | 0 | Non Policy | 4 | ST | 162 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | September
510891111 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | PEEL AVENUE | 510891111 | T1 Policy | 6.8 | Policy | 4 | SI | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.714 | 0 | CMO East 2 | IMGA223070 | PEEL AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510901018 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901018 | T1 Policy | 32.6 | Policy | 6 | DI | 1.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.05868 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510870802 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Jake Parry | IMGA223170 | LYMINGTON ROAD | 510870802 | T1 Policy | 0 | Policy | 6 | CI | 98 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220000661505 | CMO | CMO East 2 | September | 25 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WESTWOOD AVENUE | 220000661505 | T1 Policy | 8 | Policy | 6 | CI | 108 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.864 | 0 | CMO East 2 | IMGA223023 | WESTWOOD AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510869481 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Chris Southam | IMGA223004 | LONGTAIL | 510869481 | T1 Policy | 24.8 | Policy | 6 | DI | 85 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.108 | 0 | CMO East 2 | IMGA223004 | LONGTAIL | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
Side Street | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | Side Street | T1 Policy | 0 | Policy | 6 | SI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510786224 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223165 | BALLARDS ROAD | 510786224 | T1 Policy | 1 | Policy | 8 | CI | 180 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.18 | 0 | CMO East 2 | IMGA223165 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510788726 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Chris Southam | IMGA223084 | BEAUCHAMPS DRIVE | 510788726 | T1 Policy | 2.2 | Policy | 8 | SI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.154 | 0 | CMO East 2 | IMGA223084 | BEAUCHAMPS DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866900 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866900 | T1 Policy | 2.6 | Policy | 8 | SI | 66 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.1716 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866901 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866901 | T1 Policy | 2.7 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.27 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866904 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866904 | T1 Policy | 3.1 | Policy | 8 | SI | 3 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0093 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510936144 | CMO | CMO East 2 | September | 25 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936144 | T1 Policy | 158.7 | Policy | 100 | DI | 201 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 31.8987 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510918012 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Bob Sawyer | IMGA223066 | STORNOWAY ROAD | 510918012 | T1 Policy | 105 | Policy | 100 | DI | 63.8 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.699 | 0 | CMO East 2 | IMGA223066 | STORNOWAY ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510875501 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | MAYLAND AVENUE | 510875501 | T1 Policy | 5.9 | Policy | 200 | DI | 48 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.2832 | 0 | CMO East 2 | IMGA223136 | MAYLAND AVENUE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510904450 | CMO | CMO East 2 | September | 25 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510904450 | T1 Policy | 13.1 | Policy | 200 | DI | 10 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.131 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510936144 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936144 | T1 Policy | 158.7 | Policy | 100 | DI | 204 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 32.3748 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510854085 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 510854085 | T1 Policy | 7.5 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.03 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510854086 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 510854086 | T1 Policy | 2.4 | Policy | 4 | CI | 34 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0816 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001571826 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 220001571826 | T1 Policy | 4.1 | Policy | 4 | CI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2583 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510786198 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510786198 | T1 Policy | 7.8 | Policy | 4 | DI | 14 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1092 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510901022 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Andy Bond | IMGA223165 | RIDGEWELL CLOSE | 510901022 | T1 Policy | 4.8 | Policy | 4 | DI | 31 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1488 | 0 | CMO East 2 | IMGA223165 | RIDGEWELL CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510870802 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Jake Parry | IMGA223170 | LYMINGTON ROAD | 510870802 | T1 Policy | 0 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
636005098 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Jake Parry | IMGA223178 | LODGE AVENUE | 636005098 | T1 Policy | 4.4 | Policy | 4 | CI | 149 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6556 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
Side Street | CMO | CMO East 2 | September | 26 | A | Alex Wright | Andy Bond | IMGA223181 | GRAFTON ROAD | Side Street | T1 Policy | 0 | Policy | 4 | CI | 3.7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001521686 | CMO | CMO East 2 | September | 26 | A | Alex Wright | Andy Bond | IMGA223181 | GRAFTON ROAD | 220001521686 | T1 Policy | 12 | Policy | 8 | CI | 121 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.452 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
220001456792 | CMO | CMO East 2 | September | 26 | A | Alex Wright | TBA - Lon | IMGA223352 | NORWOOD AVENUE | 220001456792 | T1 Policy | 4.9 | Policy | 4 | DI | 101 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4949 | 0 | CMO East 2 | IMGA223352 | NORWOOD AVENUE | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO HUGHES, Shaun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510872814 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223023 | MANOR WAY | 510872814 | T1 Policy | 13.2 | Policy | 4 | CI | 50.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.67188 | 0 | CMO East 2 | IMGA223023 | MANOR WAY | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510872815 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223023 | MANOR WAY | 510872815 | T1 Policy | 9.9 | Policy | 4 | CI | 53.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.53361 | 0 | CMO East 2 | IMGA223023 | MANOR WAY | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510936233 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WESTWOOD AVENUE | 510936233 | T1 Policy | 11.3 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.678 | 0 | CMO East 2 | IMGA223023 | WESTWOOD AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220000661505 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WESTWOOD AVENUE | 220000661505 | T1 Policy | 8 | Policy | 6 | CI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.056 | 0 | CMO East 2 | IMGA223023 | WESTWOOD AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510963688 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223031 | ST ANDREWS PLACE | 510963688 | Condition | 0 | Non Policy | 2 | ST | 67.9 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223031 | ST ANDREWS PLACE | Brentwood Borough Council | East 2 | FALSE |  | KLT | T1 CONNECTED | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | September
510963689 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223031 | ST ANDREWS PLACE | 510963689 | T1 Policy | 4.2 | Policy | 100 | DI | 18.6 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.07812 | 0 | CMO East 2 | IMGA223031 | ST ANDREWS PLACE | Brentwood Borough Council | East 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510963690 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223031 | ST ANDREWS PLACE | 510963690 | T1 Policy | 3.7 | Policy | 100 | DI | 201.9 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.74703 | 0 | CMO East 2 | IMGA223031 | ST ANDREWS PLACE | Brentwood Borough Council | East 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510963691 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223031 | ST ANDREWS PLACE | 510963691 | T1 Policy | 8.7 | Policy | 100 | DI | 118 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0266 | 0 | CMO East 2 | IMGA223031 | ST ANDREWS PLACE | Brentwood Borough Council | East 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510924795 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Chris McVeigh | IMGA223088 | THORNDON AVENUE | 510924795 | T1 Policy | 27.4 | Policy | 4 | DI | 93 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.5482 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510887889 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Mick Linwood | IMGA223257 | OSBORNE ROAD | 510887889 | T1 Policy | 16.9 | Policy | 4 | SI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0816 | 0 | CMO East 2 | IMGA223257 | OSBORNE ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510885227 | CMO | CMO East 2 | September | 26 | A | Dave Bamber | Mick Linwood | IMGA223273 | NURSERY ROAD | 510885227 | T1 Policy | 4.2 | Policy | 6 | CI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.63 | 0 | CMO East 2 | IMGA223273 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510958321 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Chris Southam | IMGA223004 | MERCER ROAD | 510958321 | T1 Policy | 4.7 | Policy | 6 | DI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.376 | 0 | CMO East 2 | IMGA223004 | MERCER ROAD | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510958323 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Chris Southam | IMGA223004 | MERCER ROAD | 510958323 | T1 Policy | 4.6 | Policy | 6 | DI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.092 | 0 | CMO East 2 | IMGA223004 | MERCER ROAD | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510882847 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 510882847 | T1 Policy | 4.7 | Policy | 4 | SI | 69 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3243 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Iusco, Ioan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510882848 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 510882848 | Condition | 0 | Non Policy | 4 | ST | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO Iusco, Ioan | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | September
510882849 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 510882849 | T1 Policy | 4.2 | Policy | 4 | SI | 22 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0924 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Iusco, Ioan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510955675 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | BARDFIELD WAY | 510955675 | T1 Policy | 8.6 | Policy | 200 | DI | 65.2 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.56072 | 0 | CMO East 2 | IMGA223059 | BARDFIELD WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510891111 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | PEEL AVENUE | 510891111 | T1 Policy | 6.8 | Policy | 4 | SI | 137 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9316 | 0 | CMO East 2 | IMGA223070 | PEEL AVENUE | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510792493 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | SERVICE ROAD FOR 9 TO 29 BLACKGATE ROAD | 510792493 | T1 Policy | 4.6 | Policy | 4 | SI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.828 | 0 | CMO East 2 | IMGA223070 | SERVICE ROAD FOR 9 TO 29 BLACKGATE ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510916934 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Robert Ashdown | IMGA223071 | STATION ROAD | 510916934 | T1 Policy | 5.5 | Policy | 6 | CI | 114.3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.62865 | 0 | CMO East 2 | IMGA223071 | STATION ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510788726 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Chris Southam | IMGA223084 | BEAUCHAMPS DRIVE | 510788726 | T1 Policy | 2.2 | Policy | 8 | SI | 40 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.088 | 0 | CMO East 2 | IMGA223084 | BEAUCHAMPS DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510933955 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Paul Illingworth | IMGA223136 | WELBECK ROAD | 510933955 | T1 Policy | 9.9 | Policy | 4 | SI | 38 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.3762 | 0 | CMO East 2 | IMGA223136 | WELBECK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510883491 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Paul Illingworth | IMGA223139 | NORMANS ROAD | 510883491 | T1 Policy | 6.4 | Policy | 4 | SI | 232 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 1.4848 | 0 | CMO East 2 | IMGA223139 | NORMANS ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
220001973017 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 220001973017 | T1 Policy | 0 | Policy | 6 | SI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510866899 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866899 | T1 Policy | 1.6 | Policy | 8 | SI | 37 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0592 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510866901 | CMO | CMO East 2 | September | 26 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866901 | T1 Policy | 2.7 | Policy | 8 | SI | 62 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.1674 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510936144 | CMO | CMO East 2 | September | 27 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936144 | T1 Policy | 158.7 | Policy | 100 | DI | 135 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 21.4245 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
Side Street | CMO | CMO East 2 | September | 27 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | Side Street | T1 Policy | 0 | Policy | 100 | DI | 2.7 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T3 SECONDARY | CMO PAVITT, Nick | #N/A | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
220001571826 | CMO | CMO East 2 | September | 27 | A | Alex Wright | Jake Parry | IMGA223158 | HOMESTEAD ROAD | 220001571826 | T1 Policy | 4.1 | Policy | 4 | CI | 72 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2952 | 0 | CMO East 2 | IMGA223158 | HOMESTEAD ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510786226 | CMO | CMO East 2 | September | 27 | A | Alex Wright | Andy Bond | IMGA223166 | CHURCH LANE | 510786226 | T1 Policy | 3.6 | Policy | 8 | SI | 273 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9828 | 0 | CMO East 2 | IMGA223166 | CHURCH LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
Side Street | CMO | CMO East 2 | September | 27 | A | Alex Wright | Allan Mount | IMGA223170 | FRESHWATER ROAD | Side Street | Condition | 0 | Non Policy | 2 | ST | 2 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | FRESHWATER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 CONNECTED | CMO LINWOOD, Billy | #N/A | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | September
510834687 | CMO | CMO East 2 | September | 27 | A | Alex Wright | Allan Mount | IMGA223170 | FRESHWATER ROAD | 510834687 | T1 Policy | 6 | Policy | 6 | CI | 180.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.083 | 0 | CMO East 2 | IMGA223170 | FRESHWATER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510870802 | CMO | CMO East 2 | September | 27 | A | Alex Wright | Allan Mount | IMGA223170 | LYMINGTON ROAD | 510870802 | T1 Policy | 0 | Policy | 6 | CI | 13 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223170 | LYMINGTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220001456792 | CMO | CMO East 2 | September | 27 | A | Alex Wright | TBA - Lon | IMGA223352 | NORWOOD AVENUE | 220001456792 | T1 Policy | 4.9 | Policy | 4 | DI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4018 | 0 | CMO East 2 | IMGA223352 | NORWOOD AVENUE | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO HUGHES, Shaun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
220000871923 | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WEST PARK HILL | 220000871923 | T1 Policy | 5.6 | Policy | 4 | CI | 9.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0532 | 0 | CMO East 2 | IMGA223023 | WEST PARK HILL | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
Side Street | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WEST WAY | Side Street | Condition | 0 | Non Policy | 2 | ST | 10.7 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223023 | WEST WAY | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 CONNECTED | tRIIO NORRIS, Sam | #N/A | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | September
510961687 | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WEST WAY | 510961687 | T1 Policy | 11.4 | Policy | 4 | CI | 90.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0317 | 0 | CMO East 2 | IMGA223023 | WEST WAY | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510936233 | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WESTWOOD AVENUE | 510936233 | T1 Policy | 11.3 | Policy | 4 | CI | 4.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.05424 | 0 | CMO East 2 | IMGA223023 | WESTWOOD AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220000661505 | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223023 | WESTWOOD AVENUE | 220000661505 | T1 Policy | 8 | Policy | 6 | CI | 29.7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2376 | 0 | CMO East 2 | IMGA223023 | WESTWOOD AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510924786 | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223088 | THORNDON AVENUE | 510924786 | T1 Policy | 35.5 | Policy | 4 | DI | 146 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.183 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510924788 | CMO | CMO East 2 | September | 27 | A | Dave Bamber | Chris McVeigh | IMGA223088 | THORNDON AVENUE | 510924788 | T1 Policy | 3.2 | Policy | 6 | DI | 19.2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06144 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510958938 | CMO | CMO East 2 | September | 27 | A | Stuart Griffiths | Chris Southam | IMGA223004 | MERCER ROAD | 510958938 | T1 Policy | 2.1 | Policy | 6 | DI | 15 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0315 | 0 | CMO East 2 | IMGA223004 | MERCER ROAD | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO GILBERT, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510882849 | CMO | CMO East 2 | September | 27 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 510882849 | T1 Policy | 4.2 | Policy | 4 | SI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2268 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Iusco, Ioan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510923689 | CMO | CMO East 2 | September | 27 | A | Stuart Griffiths | Bob Sawyer | IMGA223052 | THE WESTERINGS | 510923689 | T1 PAST | 0 | Non Policy | 4 | ST | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223052 | THE WESTERINGS | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | September
510835579 | CMO | CMO East 2 | September | 27 | A | Stuart Griffiths | Paul Illingworth | IMGA223138 | FURTHERWICK ROAD | 510835579 | T1 Policy | 4.1 | Policy | 4 | SI | 151 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.6191 | 0 | CMO East 2 | IMGA223138 | FURTHERWICK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510936144 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936144 | T1 Policy | 158.7 | Policy | 4 | DI | 16.2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.5709 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510936149 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936149 | T1 Policy | 8.3 | Policy | 8 | SI | 42.2 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.35026 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
630961044 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 630961044 | T1 Policy | 8.6 | Policy | 6 | SI | 21.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.18748 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510939969 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Jake Parry | IMGA223154 | WINSTEAD GARDENS | 510939969 | T1 Policy | 15.2 | Policy | 4 | CI | 77 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1704 | 0 | CMO East 2 | IMGA223154 | WINSTEAD GARDENS | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510856117 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Allan Mount | IMGA223178 | ILCHESTER ROAD | 510856117 | T1 Policy | 7.1 | Policy | 6 | CI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0994 | 0 | CMO East 2 | IMGA223178 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
606496190 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 606496190 | T1 Policy | 10.2 | Policy | 4 | CI | 128 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3056 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
636005097 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 636005097 | T1 Policy | 5.6 | Policy | 4 | CI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3024 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
636005098 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 636005098 | T1 Policy | 4.4 | Policy | 4 | CI | 257.7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1339 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
220001521686 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Allan Mount | IMGA223181 | GRAFTON ROAD | 220001521686 | T1 Policy | 12 | Policy | 8 | CI | 94 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.128 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510959391 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Steve Moscrop | IMGA223345 | NORTHOLT WAY | 510959391 | T1 Policy | 4.2 | Policy | 4 | DI | 34.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14658 | 0 | CMO East 2 | IMGA223345 | NORTHOLT WAY | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO CLEMENTS , Andy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
220001605272 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Steve Moscrop | IMGA223345 | NORTHOLT WAY | 220001605272 | T1 Policy | 0 | Policy | 4 | DI | 77.2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223345 | NORTHOLT WAY | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO CLEMENTS , Andy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510899340 | CMO | CMO East 2 | October | 28 | A | Alex Wright | Steve Moscrop | IMGA223361 | RECTORY GARDENS | 510899340 | T1 PAST | 213 | Policy | 100 | DI | 201 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 42.813 | 0 | CMO East 2 | IMGA223361 | RECTORY GARDENS | Havering London Borough Council | East 2 | FALSE | PAST | JDT | T1 PAST | tRIIO MADDOCKS, Lee (SQS) | #N/A | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510941458 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Chris McVeigh | IMGA223025 | WOODMAN ROAD | 510941458 | T1 Policy | 202.1 | Policy | 6 | DI | 210 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 42.441 | 0 | CMO East 2 | IMGA223025 | WOODMAN ROAD | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510887433 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Chris McVeigh | IMGA223032 | ORCHARD LANE | 510887433 | T1 PAST | 0 | Non Policy | 4 | ST | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223032 | ORCHARD LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Murray | T1 PAST | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
631086806 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Chris McVeigh | IMGA223032 | ORCHARD LANE | 631086806 | T1 Policy | 30.1 | Policy | 4 | SI | 2.1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06321 | 0 | CMO East 2 | IMGA223032 | ORCHARD LANE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220000650961 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Darren Francis | IMGA223099 | GIFFORDS CROSS ROAD | 220000650961 | T1 Policy | 3.3 | Policy | 6 | CI | 137 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4521 | 0 | CMO East 2 | IMGA223099 | GIFFORDS CROSS ROAD | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
220000621316 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Darren Francis | IMGA223099 | GOLDSMITHS AVENUE | 220000621316 | T1 Policy | 1.6 | Policy | 2 | SI | 2 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0032 | 0 | CMO East 2 | IMGA223099 | GOLDSMITHS AVENUE | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | October
220000621316 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Darren Francis | IMGA223099 | GOLDSMITHS AVENUE | 220000621316 | T1 Policy | 1.6 | Policy | 4 | SI | 16 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0256 | 0 | CMO East 2 | IMGA223099 | GOLDSMITHS AVENUE | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
DR4 Requested | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Darren Francis | IMGA223099 | SPRINGHOUSE ROAD | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223099 | SPRINGHOUSE ROAD | Thurrock Council | East 2 | FALSE |  | Murray |  | tRIIO CLARKE, Stuart | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
220000639614 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Darren Francis | IMGA223099 | SPRINGHOUSE ROAD | 220000639614 | T1 Policy | 3.9 | Policy | 4 | SI | 134 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5226 | 0 | CMO East 2 | IMGA223099 | SPRINGHOUSE ROAD | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510851740 | CMO | CMO East 2 | October | 28 | A | Dave Bamber | Mick Linwood | IMGA223273 | HIGHVIEW CLOSE | 510851740 | T1 Policy | 14.4 | Policy | 4 | SI | 122.6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7654 | 0 | CMO East 2 | IMGA223273 | HIGHVIEW CLOSE | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510784589 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | ASSANDUNE CLOSE | 510784589 | T1 Policy | 4.5 | Policy | 4 | SI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.36 | 0 | CMO East 2 | IMGA223049 | ASSANDUNE CLOSE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Iusco, Ioan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510916934 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Robert Ashdown | IMGA223071 | STATION ROAD | 510916934 | T1 Policy | 5.5 | Policy | 6 | CI | 59.8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3289 | 0 | CMO East 2 | IMGA223071 | STATION ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Winter, Harry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510788726 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Chris Southam | IMGA223084 | BEAUCHAMPS DRIVE | 510788726 | T1 Policy | 2.2 | Policy | 8 | SI | 40 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.088 | 0 | CMO East 2 | IMGA223084 | BEAUCHAMPS DRIVE | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SKINNER, Jason | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
220001264902 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223138 | CLEVELAND ROAD | 220001264902 | T1 Policy | 2 | Policy | 4 | SI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.024 | 0 | CMO East 2 | IMGA223138 | CLEVELAND ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510835579 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223138 | FURTHERWICK ROAD | 510835579 | T1 Policy | 4.1 | Policy | 4 | SI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.1886 | 0 | CMO East 2 | IMGA223138 | FURTHERWICK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510920267 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223138 | SYLVAN CLOSE | 510920267 | T1 Policy | 9.8 | Policy | 4 | SI | 76 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.7448 | 0 | CMO East 2 | IMGA223138 | SYLVAN CLOSE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510920268 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223138 | SYLVAN CLOSE | 510920268 | T1 Policy | 20.3 | Policy | 4 | SI | 24 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.4872 | 0 | CMO East 2 | IMGA223138 | SYLVAN CLOSE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO CLARKE, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510873167 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510873167 | T1 Policy | 4 | Policy | 8 | SI | 150 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.6 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | #N/A | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
510866898 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866898 | T1 Policy | 2.9 | Policy | 4 | SI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.0348 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510866899 | CMO | CMO East 2 | October | 28 | A | Stuart Griffiths | Paul Illingworth | IMGA223142 | LINK ROAD | 510866899 | T1 Policy | 1.6 | Policy | 8 | SI | 56.1 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.08976 | 0 | CMO East 2 | IMGA223142 | LINK ROAD | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
602801208 | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 602801208 | Condition | 0 | Non Policy | 2 | ST | 3.4 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO Iusco, Ioan | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
607100683 | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 607100683 | Condition | 0 | Non Policy | 2 | ST | 4.4 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO Iusco, Ioan | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
DR4 Requested | CMO | CMO East 2 | October | 29 | A | Alex Wright | Andy Bond | IMGA223166 | FARM CLOSE | DR4 Requested | Condition | 0 | Non Policy | 2 | ST | 20 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223166 | FARM CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | tRIIO BEARD, Daniel | #N/A | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
DR4 Requested | CMO | CMO East 2 | October | 29 | A | Alex Wright | Andy Bond | IMGA223166 | FARM CLOSE | DR4 Requested | Condition | 0 | Non Policy | 2 | ST | 21.5 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223166 | FARM CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | tRIIO BEARD, Daniel | #N/A | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
510782509 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223025 | ARBOUR CLOSE | 510782509 | T1 Policy | 15.7 | Policy | 4 | DI | 65.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0252 | 0 | CMO East 2 | IMGA223025 | ARBOUR CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510782510 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223025 | ARBOUR CLOSE | 510782510 | T1 Policy | 30.9 | Policy | 4 | DI | 74.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3113 | 0 | CMO East 2 | IMGA223025 | ARBOUR CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510830583 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Andy Bond | IMGA223166 | FARM CLOSE | 510830583 | T1 Policy | 7 | Policy | 4 | SI | 81 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.567 | 0 | CMO East 2 | IMGA223166 | FARM CLOSE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510831572 | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Paul Illingworth | IMGA223040 | FERNLEA ROAD | 510831572 | T1 PAST | 0 | Non Policy | 4 | ST | 103 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223040 | FERNLEA ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510882849 | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Robert Ashdown | IMGA223049 | NEWTON HALL GARDENS | 510882849 | T1 Policy | 4.2 | Policy | 4 | SI | 68 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2856 | 0 | CMO East 2 | IMGA223049 | NEWTON HALL GARDENS | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO Iusco, Ioan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510887433 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223032 | ORCHARD LANE | 510887433 | T1 PAST | 0 | Non Policy | 4 | ST | 173 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223032 | ORCHARD LANE | Brentwood Borough Council | East 2 | FALSE | PAST | Murray | T1 PAST | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510923622 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Steve Moscrop | IMGA223361 | THE MEADS | 510923622 | T1 Policy | 9.5 | Policy | 4 | SI | 78 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.741 | 0 | CMO East 2 | IMGA223361 | THE MEADS | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MADDOCKS, Lee (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510924786 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223088 | THORNDON AVENUE | 510924786 | T1 Policy | 35.5 | Policy | 4 | DI | 153 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.4315 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510939969 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Jake Parry | IMGA223154 | WINSTEAD GARDENS | 510939969 | T1 Policy | 15.2 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.52 | 0 | CMO East 2 | IMGA223154 | WINSTEAD GARDENS | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
606496190 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 606496190 | T1 Policy | 10.2 | Policy | 4 | CI | 20 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.204 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
631111430 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223032 | ORCHARD LANE | 631111430 | T1 Policy | 30.1 | Policy | 4 | SI | 2.1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06321 | 0 | CMO East 2 | IMGA223032 | ORCHARD LANE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220000241232 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Steve Moscrop | IMGA223343 | WYCH ELM ROAD | 220000241232 | T1 Policy | 25.2 | Policy | 4 | SI | 300 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.56 | 0 | CMO East 2 | IMGA223343 | WYCH ELM ROAD | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO HUGHES, Shaun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220000658323 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Darren Francis | IMGA223099 | THAMES HAVEN ROAD | 220000658323 | T1 Policy | 2 | Policy | 4 | CI | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.182 | 0 | CMO East 2 | IMGA223099 | THAMES HAVEN ROAD | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
220001577707 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223025 | WOODMAN ROAD | 220001577707 | T1 Policy | 5.6 | Policy | 4 | SI | 2.6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01456 | 0 | CMO East 2 | IMGA223025 | WOODMAN ROAD | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | SEED | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220001591071 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Allan Mount | IMGA223181 | BOULTON ROAD | 220001591071 | T1 Policy | 8.9 | Policy | 4 | SI | 1.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01602 | 0 | CMO East 2 | IMGA223181 | BOULTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220001776551 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Andy Bond | IMGA223166 | BOLEYN GARDENS | 220001776551 | T1 Policy | 2 | Policy | 4 | SI | 1.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0038 | 0 | CMO East 2 | IMGA223166 | BOLEYN GARDENS | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
DR4 Requested | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Bob Sawyer | IMGA223070 | SERVICE ROAD FOR 9 TO 29 BLACKGATE ROAD | DR4 Requested | Condition | 0 | Non Policy | 4 | ST | 109 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223070 | SERVICE ROAD FOR 9 TO 29 BLACKGATE ROAD | Southend-on-Sea Borough Council | East 2 | FALSE |  | Terra Firma |  | CMO SMITH , Lloyd | #N/A | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
Side Street | CMO | CMO East 2 | October | 29 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | Side Street | T1 Policy | 0 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO WILDER, Jamie | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510786225 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Andy Bond | IMGA223166 | BALLARDS ROAD | 510786225 | T1 Policy | 3 | Policy | 6 | SI | 42.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1275 | 0 | CMO East 2 | IMGA223166 | BALLARDS ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510866907 | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Paul Illingworth | IMGA223143 | LINK ROAD | 510866907 | T1 PAST | 250.6 | Policy | 6 | DI | 149 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 37.3394 | 0 | CMO East 2 | IMGA223143 | LINK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510885227 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Mick Linwood | IMGA223273 | NURSERY ROAD | 510885227 | T1 Policy | 4.2 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.42 | 0 | CMO East 2 | IMGA223273 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510941458 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Chris McVeigh | IMGA223025 | WOODMAN ROAD | 510941458 | T1 Policy | 202.1 | Policy | 6 | DI | 150.2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 30.3554 | 0 | CMO East 2 | IMGA223025 | WOODMAN ROAD | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510992543 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Darren Francis | IMGA223099 | THE MANORWAY | 510992543 | T1 Policy | 2.6 | Policy | 6 | CI | 28 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0728 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
DR4 Requested | CMO | CMO East 2 | October | 29 | A | Alex Wright | Allan Mount | IMGA223171 | TURNAGE ROAD | DR4 Requested | T1 Policy | 0 | Policy | 6 | CI | 152 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223171 | TURNAGE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO LINWOOD, Billy | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510936149 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936149 | T1 Policy | 8.3 | Policy | 8 | SI | 157 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3031 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
510970741 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 510970741 | T1 Policy | 5.7 | Policy | 8 | CI | 200 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.14 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510992557 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Darren Francis | IMGA223099 | THE MANORWAY | 510992557 | T1 Policy | 2.1 | Policy | 8 | CI | 8 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0168 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO CLARKE, Stuart | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
220001521686 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Allan Mount | IMGA223181 | GRAFTON ROAD | 220001521686 | T1 Policy | 12 | Policy | 8 | CI | 63 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.756 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
606549188 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Darren Francis | IMGA223099 | THE MANORWAY | 606549188 | T3 CBA | 1 | Policy | 18 | CI | 6 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0.006 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Murray |  | tRIIO CLARKE, Stuart | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | October
220000479804 | CMO | CMO East 2 | October | 29 | A | Dave Bamber | Darren Francis | IMGA223099 | THE MANORWAY | 220000479804 | T3 CBA | 1 | Policy | 18 | CI | 23 | inch | 18inch | Abandonment 18-24” | Tier 3 | Iron | Tier 3IronPolicy | FALSE | FALSE | #N/A | 0.023 | 0 | CMO East 2 | IMGA223099 | THE MANORWAY | Thurrock Council | East 2 | FALSE |  | Murray | T3 SECONDARY | tRIIO CLARKE, Stuart | #N/A | #N/A | 18-24” | 18 |  | Policy | Tier 3 | CI | T3 | October
510946324 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Steve Moscrop | IMGA223345 | DETLING CLOSE | 510946324 | T1 Policy | 4.9 | Policy | 100 | DI | 55 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2695 | 0 | CMO East 2 | IMGA223345 | DETLING CLOSE | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO CLEMENTS , Andy | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510946325 | CMO | CMO East 2 | October | 29 | A | Alex Wright | Steve Moscrop | IMGA223345 | DETLING CLOSE | 510946325 | T1 Policy | 6.7 | Policy | 100 | DI | 32 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2144 | 0 | CMO East 2 | IMGA223345 | DETLING CLOSE | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO CLEMENTS , Andy | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510955675 | CMO | CMO East 2 | October | 29 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | BARDFIELD WAY | 510955675 | T1 Policy | 8.6 | Policy | 200 | DI | 62 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5332 | 0 | CMO East 2 | IMGA223059 | BARDFIELD WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510936149 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936149 | T1 Policy | 8.3 | Policy | 8 | SI | 112 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9296 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
510834278 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Jake Parry | IMGA223154 | FOXLANDS CRESCENT | 510834278 | T1 Policy | 11.4 | Policy | 4 | CI | 128.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4649 | 0 | CMO East 2 | IMGA223154 | FOXLANDS CRESCENT | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510939969 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Jake Parry | IMGA223154 | WINSTEAD GARDENS | 510939969 | T1 Policy | 15.2 | Policy | 4 | CI | 2.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.038 | 0 | CMO East 2 | IMGA223154 | WINSTEAD GARDENS | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
Side Street | CMO | CMO East 2 | October | 30 | A | Alex Wright | Andy Bond | IMGA223157 | FRIZLANDS LANE | Side Street | T1 Policy | 0 | Policy | 4 | CI | 1.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223157 | FRIZLANDS LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510834888 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Andy Bond | IMGA223157 | FRIZLANDS LANE | 510834888 | T1 Policy | 5.7 | Policy | 6 | CI | 18 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1026 | 0 | CMO East 2 | IMGA223157 | FRIZLANDS LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO BEARD, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
DR4 Requested | CMO | CMO East 2 | October | 30 | A | Alex Wright | Allan Mount | IMGA223171 | TURNAGE ROAD | DR4 Requested | T1 Policy | 0 | Policy | 6 | CI | 183 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223171 | TURNAGE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO LINWOOD, Billy | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510856117 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Allan Mount | IMGA223178 | ILCHESTER ROAD | 510856117 | T1 Policy | 7.1 | Policy | 6 | CI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.142 | 0 | CMO East 2 | IMGA223178 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510970741 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 510970741 | T1 Policy | 5.7 | Policy | 8 | CI | 96 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5472 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
DR4 Requested | CMO | CMO East 2 | October | 30 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 116 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
220001521686 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Allan Mount | IMGA223181 | GRAFTON ROAD | 220001521686 | T1 Policy | 12 | Policy | 8 | CI | 74 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.888 | 0 | CMO East 2 | IMGA223181 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WEBB, Sam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510959399 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Steve Moscrop | IMGA223345 | WEST MALLING WAY | 510959399 | T1 Policy | 6.6 | Policy | 100 | DI | 132 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8712 | 0 | CMO East 2 | IMGA223345 | WEST MALLING WAY | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO CLEMENTS , Andy | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510923623 | CMO | CMO East 2 | October | 30 | A | Alex Wright | Steve Moscrop | IMGA223361 | THE MEADS | 510923623 | T1 Policy | 10.7 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.535 | 0 | CMO East 2 | IMGA223361 | THE MEADS | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MADDOCKS, Lee (SQS) | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510843050 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Chris McVeigh | IMGA223025 | GUARDSMAN CLOSE | 510843050 | T1 Policy | 18.4 | Policy | 4 | DI | 62.2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1445 | 0 | CMO East 2 | IMGA223025 | GUARDSMAN CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510843051 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Chris McVeigh | IMGA223025 | GUARDSMAN CLOSE | 510843051 | T1 Policy | 13.9 | Policy | 4 | DI | 22.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.31692 | 0 | CMO East 2 | IMGA223025 | GUARDSMAN CLOSE | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510941458 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Chris McVeigh | IMGA223025 | WOODMAN ROAD | 510941458 | T1 Policy | 202.1 | Policy | 6 | DI | 166 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 33.5486 | 0 | CMO East 2 | IMGA223025 | WOODMAN ROAD | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510961739 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | TBA - Lon | IMGA223032 | ONGAR ROAD | 510961739 | T1 Policy | 17 | Policy | 4 | DI | 144.1 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4497 | 0 | CMO East 2 | IMGA223032 | ONGAR ROAD | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO NORRIS, Sam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510924786 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Chris McVeigh | IMGA223088 | THORNDON AVENUE | 510924786 | T1 Policy | 35.5 | Policy | 4 | DI | 151 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.3605 | 0 | CMO East 2 | IMGA223088 | THORNDON AVENUE | Brentwood Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO MARSH, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510870942 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Darren Francis | IMGA223097 | LYNDHURST ROAD | 510870942 | T1 Policy | 3.6 | Policy | 8 | CI | 69 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2484 | 0 | CMO East 2 | IMGA223097 | LYNDHURST ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510796375 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Darren Francis | IMGA223113 | BRIDGE ROAD | 510796375 | T1 Policy | 2.3 | Policy | 8 | CI | 73 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1679 | 0 | CMO East 2 | IMGA223113 | BRIDGE ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO PILKINGTON, Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510882157 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Darren Francis | IMGA223113 | NEW ROAD | 510882157 | T1 Policy | 1.7 | Policy | 6 | DI | 132 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2244 | 0 | CMO East 2 | IMGA223113 | NEW ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO PILKINGTON, Paul | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
220001459073 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Darren Francis | IMGA223113 | NEW ROAD | 220001459073 | T1 Policy | 12.7 | Policy | 6 | DI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0635 | 0 | CMO East 2 | IMGA223113 | NEW ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO PILKINGTON, Paul | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510885227 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Mick Linwood | IMGA223273 | NURSERY ROAD | 510885227 | T1 Policy | 4.2 | Policy | 6 | CI | 4.2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01764 | 0 | CMO East 2 | IMGA223273 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510885234 | CMO | CMO East 2 | October | 30 | A | Dave Bamber | Mick Linwood | IMGA223273 | NURSERY ROAD | 510885234 | T1 Policy | 2.3 | Policy | 8 | CI | 7.8 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.01794 | 0 | CMO East 2 | IMGA223273 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510893500 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | TBA - Lon | IMGA223053 | PLUMBEROW AVENUE | 510893500 | Condition | 0 | Non Policy | 4 | ST | 265 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
602858126 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | TBA - Lon | IMGA223053 | PLUMBEROW AVENUE | 602858126 | Condition | 0 | Non Policy | 4 | ST | 3.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223053 | PLUMBEROW AVENUE | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510955675 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | BARDFIELD WAY | 510955675 | T1 Policy | 8.6 | Policy | 200 | DI | 50 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.43 | 0 | CMO East 2 | IMGA223059 | BARDFIELD WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510853284 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Bob Sawyer | IMGA223132 | HOLLAND AVENUE | 510853284 | T1 Policy | 4.4 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.066 | 0 | CMO East 2 | IMGA223132 | HOLLAND AVENUE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510853285 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Bob Sawyer | IMGA223132 | HOLLAND AVENUE | 510853285 | Condition | 0 | Non Policy | 4 | ST | 55 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223132 | HOLLAND AVENUE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510853286 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Bob Sawyer | IMGA223132 | HOLLAND AVENUE | 510853286 | T1 Policy | 3.9 | Policy | 4 | SI | 33 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.1287 | 0 | CMO East 2 | IMGA223132 | HOLLAND AVENUE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510853287 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Bob Sawyer | IMGA223132 | HOLLAND AVENUE | 510853287 | Condition | 0 | Non Policy | 4 | ST | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | CMO East 2 | 0 | 0 | CMO East 2 | IMGA223132 | HOLLAND AVENUE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 CONNECTED | CMO TONGE, Martin | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510866907 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Paul Illingworth | IMGA223143 | LINK ROAD | 510866907 | T1 PAST | 250.6 | Policy | 4 | DI | 2.3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.57638 | 0 | CMO East 2 | IMGA223143 | LINK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510866907 | CMO | CMO East 2 | October | 30 | A | Stuart Griffiths | Paul Illingworth | IMGA223143 | LINK ROAD | 510866907 | T1 PAST | 250.6 | Policy | 6 | DI | 104 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 26.0624 | 0 | CMO East 2 | IMGA223143 | LINK ROAD | Canvey Island | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510821078 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Mick Linwood | IMGA223258 | DEVON CLOSE | 510821078 | T1 Policy | 9 | Policy | 4 | SI | 267.7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4093 | 0 | CMO East 2 | IMGA223258 | DEVON CLOSE | Epping Forest District Council (Lower) | East 2 | FALSE |  | KLT | T1 SECONDARY | CMO KENNELLY, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510821079 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Mick Linwood | IMGA223258 | DEVON CLOSE | 510821079 | T1 Policy | 13.5 | Policy | 4 | SI | 7.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0999 | 0 | CMO East 2 | IMGA223258 | DEVON CLOSE | Epping Forest District Council (Lower) | East 2 | FALSE |  | KLT | T1 SECONDARY | CMO KENNELLY, Dan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510836288 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Jake Parry | IMGA223154 | GAY GARDENS | 510836288 | T1 Policy | 18.3 | Policy | 4 | CI | 90 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.647 | 0 | CMO East 2 | IMGA223154 | GAY GARDENS | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO PAVITT, Nick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510839611 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Allan Mount | IMGA223171 | GRAFTON ROAD | 510839611 | T1 Policy | 4.2 | Policy | 4 | CI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.168 | 0 | CMO East 2 | IMGA223171 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO LINWOOD, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510842906 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Robert Ashdown | IMGA223055 | GROVE ROAD | 510842906 | T1 PAST | 0 | Non Policy | 4 | ST | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223055 | GROVE ROAD | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510844395 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Peter Try | IMGA223056 | HAMBRO AVENUE | 510844395 | T1 PAST | 0 | Non Policy | 4 | ST | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223056 | HAMBRO AVENUE | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO MILES, Lee | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510899340 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Steve Moscrop | IMGA223361 | RECTORY GARDENS | 510899340 | T1 PAST | 0 | Non Policy | 4 | ST | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223361 | RECTORY GARDENS | Havering London Borough Council | East 2 | FALSE | PAST | JDT | T1 PAST | tRIIO MADDOCKS, Lee (SQS) | #N/A | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
510923622 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Steve Moscrop | IMGA223361 | THE MEADS | 510923622 | T1 Policy | 9.5 | Policy | 4 | SI | 66 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.627 | 0 | CMO East 2 | IMGA223361 | THE MEADS | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MADDOCKS, Lee (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510924692 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Paul Illingworth | IMGA223141 | THOMPSON AVENUE | 510924692 | T1 Policy | 4.9 | Policy | 4 | SI | 173 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | CMO East 2 | 0.8477 | 0 | CMO East 2 | IMGA223141 | THOMPSON AVENUE | Canvey Island | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO SMITH , Lloyd | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
606402519 | CMO | CMO East 2 | October | 31 | A | Bernie Parrott | TBA - Lon | IMGA223401 | LONDON ROAD | 606402519 | T1 PAST | 0 | Non Policy | 4 | ST | 101.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223401 | LONDON ROAD | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO RUTKOWSKI, Slawomir | MP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
635804310 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Robert Ashdown | IMGA223055 | GROVE ROAD | 635804310 | T1 PAST | 0 | Non Policy | 4 | ST | 36.4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223055 | GROVE ROAD | Rochford District Council | East 2 | FALSE | PAST | Terra Firma | T1 PAST | CMO Winter, Harry | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
220000241232 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Steve Moscrop | IMGA223343 | WYCH ELM ROAD | 220000241232 | T1 Policy | 25.2 | Policy | 4 | SI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.252 | 0 | CMO East 2 | IMGA223343 | WYCH ELM ROAD | Havering London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO CLEMENTS , Andy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220000534644 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Chris Southam | IMGA223089 | CANEWDON GARDENS | 220000534644 | T1 PAST | 0 | Non Policy | 4 | ST | 86 | inch | 4inch | Abandonment 4-5” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223089 | CANEWDON GARDENS | Chelmsford Borough Council (Lower) | East 2 | FALSE | PAST | KLT | T1 PAST | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Non Policy | Tier 1 | ST | ST LP 4"-5" | October
Side Street | CMO | CMO East 2 | October | 31 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | Side Street | T1 Policy | 0 | Policy | 4 | CI | 2.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
Side Street | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Darren Francis | IMGA223097 | LYNDHURST ROAD | Side Street | T1 Policy | 0 | Policy | 4 | SI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223097 | LYNDHURST ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO FORGE, Nathan | #N/A | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510796601 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Chris Southam | IMGA223004 | BRIDLEWAY | 510796601 | T1 Policy | 1.7 | Policy | 6 | DI | 28 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0476 | 0 | CMO East 2 | IMGA223004 | BRIDLEWAY | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510834886 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Andy Bond | IMGA223157 | FRIZLANDS LANE | 510834886 | T1 Policy | 8.7 | Policy | 6 | CI | 47 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4089 | 0 | CMO East 2 | IMGA223157 | FRIZLANDS LANE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO MORGAN, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510856117 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Allan Mount | IMGA223178 | ILCHESTER ROAD | 510856117 | T1 Policy | 7.1 | Policy | 6 | CI | 4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0284 | 0 | CMO East 2 | IMGA223178 | ILCHESTER ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510920612 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Chris Southam | IMGA223004 | TALISMAN WALK | 510920612 | T1 Policy | 2.8 | Policy | 6 | DI | 11 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0308 | 0 | CMO East 2 | IMGA223004 | TALISMAN WALK | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510958324 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Chris Southam | IMGA223004 | BRIDLEWAY | 510958324 | T1 Policy | 2 | Policy | 6 | DI | 16 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.032 | 0 | CMO East 2 | IMGA223004 | BRIDLEWAY | Basildon Borough Council | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
621583676 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Chris McVeigh | IMGA223025 | WOODMAN ROAD | 621583676 | T1 Policy | 204.2 | Policy | 6 | DI | 382 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 78.0044 | 0 | CMO East 2 | IMGA223025 | WOODMAN ROAD | Brentwood Borough Council | East 2 | FALSE |  | Murray | T1 SECONDARY | tRIIO KAMENTSCHUK, Luke | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
DR4 Requested | CMO | CMO East 2 | October | 31 | A | Alex Wright | Allan Mount | IMGA223171 | GRAFTON ROAD | DR4 Requested | T1 Policy | 0 | Policy | 6 | CI | 93 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223171 | GRAFTON ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO LINWOOD, Billy | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
DR4 Requested | CMO | CMO East 2 | October | 31 | A | Alex Wright | Allan Mount | IMGA223171 | TURNAGE ROAD | DR4 Requested | T1 Policy | 0 | Policy | 6 | CI | 7.5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223171 | TURNAGE ROAD | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT |  | CMO LINWOOD, Billy | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510870942 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Darren Francis | IMGA223097 | LYNDHURST ROAD | 510870942 | T1 Policy | 3.6 | Policy | 8 | CI | 64 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2304 | 0 | CMO East 2 | IMGA223097 | LYNDHURST ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO FORGE, Nathan | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510885234 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Mick Linwood | IMGA223273 | NURSERY ROAD | 510885234 | T1 Policy | 2.3 | Policy | 8 | CI | 89.5 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.20585 | 0 | CMO East 2 | IMGA223273 | NURSERY ROAD | Epping Forest District Council (Lower) | East 2 | FALSE |  | Forefront | T1 SECONDARY | CMO BRACKETT, Warren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510936149 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Andy Bond | IMGA223153 | WESTROW DRIVE | 510936149 | T1 Policy | 8.3 | Policy | 8 | SI | 55 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4565 | 0 | CMO East 2 | IMGA223153 | WESTROW DRIVE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO BUTLER, Lee | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | October
510970741 | CMO | CMO East 2 | October | 31 | A | Alex Wright | Allan Mount | IMGA223178 | LODGE AVENUE | 510970741 | T1 Policy | 5.7 | Policy | 8 | CI | 207 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1799 | 0 | CMO East 2 | IMGA223178 | LODGE AVENUE | Barking and Dagenham London Borough Council | East 2 | FALSE |  | JDT | T1 SECONDARY | CMO WILDER, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
Side Street | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Darren Francis | IMGA223113 | EXMOUTH ROAD | Side Street | T1 Policy | 0 | Policy | 100 | DI | 2 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO East 2 | IMGA223113 | EXMOUTH ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO PILKINGTON, Paul (SQS) | #N/A | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510882156 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Darren Francis | IMGA223113 | EXMOUTH ROAD | 510882156 | T1 Policy | 3.8 | Policy | 150 | DI | 24 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0912 | 0 | CMO East 2 | IMGA223113 | EXMOUTH ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO PILKINGTON, Paul (SQS) | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510991664 | CMO | CMO East 2 | October | 31 | A | Dave Bamber | Darren Francis | IMGA223113 | EXMOUTH ROAD | 510991664 | T1 Policy | 8.2 | Policy | 150 | DI | 86 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7052 | 0 | CMO East 2 | IMGA223113 | EXMOUTH ROAD | Thurrock Council | East 2 | FALSE |  | JDT | T1 SECONDARY | tRIIO PILKINGTON, Paul (SQS) | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510955675 | CMO | CMO East 2 | October | 31 | A | Stuart Griffiths | Bob Sawyer | IMGA223059 | BARDFIELD WAY | 510955675 | T1 Policy | 8.6 | Policy | 200 | DI | 60 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.516 | 0 | CMO East 2 | IMGA223059 | BARDFIELD WAY | Rochford District Council | East 2 | FALSE |  | Terra Firma | T1 SECONDARY | CMO WILDER, Dean | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510937664 | CMO | CMO West 1 | April | 2 | A | Nick Granger | TBA - Lon | IMGA222059 | WHITTON AVENUE EAST | 510937664 | T1 Policy | 19.5 | Policy | 4 | SI | 20 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.39 | 0 | CMO West 1 | IMGA222059 | WHITTON AVENUE EAST | Ealing Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | tRIIO BLAKE, Aaron | LP | ENM P3 | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510937664 | CMO | CMO West 1 | April | 2 | A | Nick Granger | TBA - Lon | IMGA222059 | WHITTON AVENUE EAST | 510937664 | T1 Policy | 19.5 | Policy | 6 | SI | 64 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.248 | 0 | CMO West 1 | IMGA222059 | WHITTON AVENUE EAST | Ealing Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | tRIIO BLAKE, Aaron | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510799966 | CMO | CMO West 1 | April | 3 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | BURNELL AVENUE | 510799966 | T1 Policy | 24.3 | Policy | 4 | CI | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.4992 | 0 | CMO West 1 | IMGA222211 | BURNELL AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510932688 | CMO | CMO West 1 | April | 3 | A | Bernie Ridsdale | TBA - Lon | IMGA222225 | WARREN ROAD | 510932688 | T1 Policy | 18.1 | Policy | 4 | SI | 176 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1856 | 0 | CMO West 1 | IMGA222225 | WARREN ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510910219 | CMO | CMO West 1 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222192 | SHAKESPEARE AVENUE | 510910219 | T1 Policy | 25.4 | Policy | 4 | CI | 195 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.953 | 0 | CMO West 1 | IMGA222192 | SHAKESPEARE AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510931652 | CMO | CMO West 1 | April | 3 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 510931652 | T1 Policy | 37.5 | Policy | 4 | SI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.3125 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510937713 | CMO | CMO West 1 | April | 3 | A | Nick Granger | TBA - Lon | IMGA222059 | WHITTON CLOSE | 510937713 | T1 Policy | 39 | Policy | 4 | SI | 73 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.847 | 0 | CMO West 1 | IMGA222059 | WHITTON CLOSE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510907702 | CMO | CMO West 1 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222169 | ST THOMAS' DRIVE | 510907702 | T1 Policy | 10.1 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.404 | 0 | CMO West 1 | IMGA222169 | ST THOMAS' DRIVE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510882099 | CMO | CMO West 1 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882099 | T1 Policy | 20.8 | Policy | 6 | CI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.12 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | TRIIO TAYLOR, JAMIE | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510937664 | CMO | CMO West 1 | April | 3 | A | Nick Granger | TBA - Lon | IMGA222059 | WHITTON AVENUE EAST | 510937664 | T1 Policy | 19.5 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.95 | 0 | CMO West 1 | IMGA222059 | WHITTON AVENUE EAST | Ealing Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | tRIIO BLAKE, Aaron | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510897581 | CMO | CMO West 1 | April | 4 | A | Bernie Ridsdale | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 20 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.732 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510799966 | CMO | CMO West 1 | April | 4 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | BURNELL AVENUE | 510799966 | T1 Policy | 24.3 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.215 | 0 | CMO West 1 | IMGA222211 | BURNELL AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510872819 | CMO | CMO West 1 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 4 | SI | 400 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510872819 | CMO | CMO West 1 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 6 | SI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510882099 | CMO | CMO West 1 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882099 | T1 Policy | 20.8 | Policy | 6 | CI | 149 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.0992 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510970210 | CMO | CMO West 1 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222182 | TUNSTALL WALK | 510970210 | Condition | 0 | Non Policy | 2 | ST | 46 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222182 | TUNSTALL WALK | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 CONNECTED | tRIIO VAN DER HAVE, John | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | April
220001559051 | CMO | CMO West 1 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222192 | BURNS AVENUE | 220001559051 | T1 Policy | 0 | Policy | 4 | SI | 93 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222192 | BURNS AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510931652 | CMO | CMO West 1 | April | 4 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 510931652 | T1 Policy | 37.5 | Policy | 4 | CI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4375 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510937664 | CMO | CMO West 1 | April | 4 | A | Nick Granger | TBA - Lon | IMGA222059 | WHITTON AVENUE EAST | 510937664 | T1 Policy | 19.5 | Policy | 6 | SI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.925 | 0 | CMO West 1 | IMGA222059 | WHITTON AVENUE EAST | Ealing Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | tRIIO BLAKE, Aaron | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510816022 | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222148 | CRABTREE LANE | 510816022 | T1 Policy | 26.8 | Policy | 8 | DI | 40 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.072 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | April
510788795 | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | BEAUFORT ROAD | 510788795 | T1 Policy | 12.5 | Policy | 6 | SI | 56 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7 | 0 | CMO West 1 | IMGA222211 | BEAUFORT ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510799966 | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | BURNELL AVENUE | 510799966 | T1 Policy | 24.3 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.944 | 0 | CMO West 1 | IMGA222211 | BURNELL AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510862678 | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | LAMMAS ROAD | 510862678 | T1 Policy | 21.7 | Policy | 6 | SI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.519 | 0 | CMO West 1 | IMGA222211 | LAMMAS ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510973297 | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222212 | HAM CLOSE | 510973297 | T1 PAST | 1.2 | Policy | 4 | DI | 18 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0216 | 0 | CMO West 1 | IMGA222212 | HAM CLOSE | Richmond upon Thames London Borough Council | West 1 | FALSE | PAST | Direct Mole | T1 PAST | CMO CANT, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510932688 | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222225 | WARREN ROAD | 510932688 | T1 Policy | 18.1 | Policy | 4 | SI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6516 | 0 | CMO West 1 | IMGA222225 | WARREN ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510907705 | CMO | CMO West 1 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222169 | ST THOMAS' DRIVE | 510907705 | T1 Policy | 6.7 | Policy | 4 | CI | 68 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4556 | 0 | CMO West 1 | IMGA222169 | ST THOMAS' DRIVE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510882099 | CMO | CMO West 1 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882099 | T1 Policy | 20.8 | Policy | 6 | CI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.248 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510970207 | CMO | CMO West 1 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222182 | EALING ROAD | 510970207 | Condition | 0 | Non Policy | 2 | ST | 49 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222182 | EALING ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 CONNECTED | tRIIO VAN DER HAVE, John | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | April
510910219 | CMO | CMO West 1 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222192 | SHAKESPEARE AVENUE | 510910219 | T1 Policy | 25.4 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.27 | 0 | CMO West 1 | IMGA222192 | SHAKESPEARE AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510871154 | CMO | CMO West 1 | April | 5 | A | Nick Granger | TBA - Lon | IMGA222044 | LYON PARK AVENUE | 510871154 | T1 Policy | 1.5 | Policy | 100 | DI | 45 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0675 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510931653 | CMO | CMO West 1 | April | 5 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 510931653 | T1 Policy | 25.8 | Policy | 6 | CI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.322 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510841565 | CMO | CMO West 1 | April | 5 | A | Nick Granger | TBA - Lon | IMGA222067 | GREENFORD AVENUE | 510841565 | T1 Policy | 2 | Policy | 6 | DI | 37 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.074 | 0 | CMO West 1 | IMGA222067 | GREENFORD AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WALKER, Ross | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
627496739 | CMO | CMO West 1 | April | 5 | A | Nick Granger | TBA - Lon | IMGA222067 | GREENFORD AVENUE | 627496739 | T1 Policy | 48.7 | Policy | 6 | CI | 15 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7305 | 0 | CMO West 1 | IMGA222067 | GREENFORD AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WALKER, Ross | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
627496740 | CMO | CMO West 1 | April | 5 | A | Nick Granger | TBA - Lon | IMGA222067 | GREENFORD AVENUE | 627496740 | T1 Policy | 36.4 | Policy | 6 | CI | 88 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.2032 | 0 | CMO West 1 | IMGA222067 | GREENFORD AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WALKER, Ross | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510822775 | CMO | CMO West 1 | April | 5 | A | Nick Granger | TBA - Lon | IMGA222079 | DRAYTON GARDENS | 510822775 | T1 Policy | 0.4 | Policy | 100 | DI | 100 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.04 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO PARRISH KLT, Dan | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
- | CMO | CMO West 1 | April | 5 | A | Bernie Ridsdale | TBA - Lon | IMGA222148 | CRABTREE LANE | - | T1 Policy | 0 | Policy | 4 | DI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510897581 | CMO | CMO West 1 | May | 6 | A | Bernie Ridsdale | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 20 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.732 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510862678 | CMO | CMO West 1 | May | 6 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | LAMMAS ROAD | 510862678 | T1 Policy | 21.7 | Policy | 6 | SI | 110 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.387 | 0 | CMO West 1 | IMGA222211 | LAMMAS ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
628341342 | CMO | CMO West 1 | May | 6 | A | Bernie Ridsdale | TBA - Lon | IMGA222211 | VANCOUVER ROAD | 628341342 | T1 Policy | 15.6 | Policy | 6 | SI | 79 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2324 | 0 | CMO West 1 | IMGA222211 | VANCOUVER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510861680 | CMO | CMO West 1 | May | 6 | A | Bernie Ridsdale | TBA - Lon | IMGA222225 | KNELLER ROAD | 510861680 | T1 Policy | 19.8 | Policy | 4 | CI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.792 | 0 | CMO West 1 | IMGA222225 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510932688 | CMO | CMO West 1 | May | 6 | A | Bernie Ridsdale | TBA - Lon | IMGA222225 | WARREN ROAD | 510932688 | T1 Policy | 18.1 | Policy | 4 | CI | 138 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4978 | 0 | CMO West 1 | IMGA222225 | WARREN ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510907702 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222169 | ST THOMAS' DRIVE | 510907702 | T1 Policy | 10.1 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.101 | 0 | CMO West 1 | IMGA222169 | ST THOMAS' DRIVE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510895892 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222172 | PRIORY WAY | 510895892 | T1 Policy | 31.8 | Policy | 4 | CI | 170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.406 | 0 | CMO West 1 | IMGA222172 | PRIORY WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510949092 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222181 | DORCHESTER DRIVE | 510949092 | T1 Policy | 29.2 | Policy | 4 | SI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.482 | 0 | CMO West 1 | IMGA222181 | DORCHESTER DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510824132 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222182 | EALING ROAD | 510824132 | T1 Policy | 26 | Policy | 4 | DI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.274 | 0 | CMO West 1 | IMGA222182 | EALING ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO VAN DER HAVE, John | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510910219 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222192 | SHAKESPEARE AVENUE | 510910219 | T1 Policy | 25.4 | Policy | 4 | SI | 109 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7686 | 0 | CMO West 1 | IMGA222192 | SHAKESPEARE AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510910220 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222192 | SHAKESPEARE AVENUE | 510910220 | T1 Policy | 38.8 | Policy | 4 | CI | 21 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8148 | 0 | CMO West 1 | IMGA222192 | SHAKESPEARE AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510854202 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222037 | HONEYWOOD ROAD | 510854202 | T1 Policy | 17.2 | Policy | 100 | DI | 116 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9952 | 0 | CMO West 1 | IMGA222037 | HONEYWOOD ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510871154 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222044 | LYON PARK AVENUE | 510871154 | T1 Policy | 1.5 | Policy | 100 | DI | 60 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.09 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510869366 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222054 | LONGFIELD ROAD | 510869366 | T1 Policy | 29.8 | Policy | 6 | CI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.47 | 0 | CMO West 1 | IMGA222054 | LONGFIELD ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510931653 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 510931653 | T1 Policy | 25.8 | Policy | 6 | CI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5418 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
606183202 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 606183202 | Condition | 0 | Non Policy | 2 | ST | 15 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION CANDIDATE | CMO FELLOWS, Stephen | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | May
607099739 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 607099739 | Condition | 0 | Non Policy | 2 | ST | 3 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION CANDIDATE | CMO FELLOWS, Stephen | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | May
612811643 | CMO | CMO West 1 | May | 6 | A | Nick Granger | TBA - Lon | IMGA222055 | WALDEGRAVE ROAD | 612811643 | T1 Policy | 37.8 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1134 | 0 | CMO West 1 | IMGA222055 | WALDEGRAVE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510882099 | CMO | CMO West 1 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882099 | T1 Policy | 20.8 | Policy | 6 | CI | 63 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3104 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510906930 | CMO | CMO West 1 | May | 7 | A | Shaun Melluish | John Moran | IMGA221041 | ST MARY ABBOT'S TERRACE | 510906930 | T1 Policy | 34.4 | Policy | 4 | SI | 9.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.34056 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220001448596 | CMO | CMO West 1 | May | 7 | A | Shaun Melluish | John Moran | IMGA221041 | ST MARY ABBOT'S TERRACE | 220001448596 | T1 Policy | 0 | Policy | 4 | DI | 9.9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510791225 | CMO | CMO West 1 | May | 7 | A | Mark Prothero | TBA - Lon | IMGA222181 | BETHANY WAYE | 510791225 | T1 Policy | 31.5 | Policy | 6 | SI | 124 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.906 | 0 | CMO West 1 | IMGA222181 | BETHANY WAYE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510816022 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222148 | CRABTREE LANE | 510816022 | T1 Policy | 26.8 | Policy | 150 | DI | 3 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0804 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510816027 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222148 | CRABTREE LANE | 510816027 | T1 Policy | 41.5 | Policy | 6 | CI | 18 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.747 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510824132 | CMO | CMO West 1 | May | 7 | A | Mark Prothero | TBA - Lon | IMGA222182 | EALING ROAD | 510824132 | T1 Policy | 26 | Policy | 100 | DI | 49 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.274 | 0 | CMO West 1 | IMGA222182 | EALING ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO VAN DER HAVE, John | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510827332 | CMO | CMO West 1 | May | 7 | A | Mark Prothero | TBA - Lon | IMGA222171 | ELMCROFT CRESCENT | 510827332 | T1 Policy | 25 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.5 | 0 | CMO West 1 | IMGA222171 | ELMCROFT CRESCENT | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510861680 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222225 | KNELLER ROAD | 510861680 | T1 Policy | 19.8 | Policy | 4 | SI | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.079 | 0 | CMO West 1 | IMGA222225 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510862677 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222211 | LAMMAS ROAD | 510862677 | T1 Policy | 11.6 | Policy | 6 | SI | 105 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.218 | 0 | CMO West 1 | IMGA222211 | LAMMAS ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510862678 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222211 | LAMMAS ROAD | 510862678 | T1 Policy | 21.7 | Policy | 4 | SI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7794 | 0 | CMO West 1 | IMGA222211 | LAMMAS ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510865904 | CMO | CMO West 1 | May | 7 | A | Trevor Trent | TBA - Lon | IMGA222049 | LEYTHE ROAD | 510865904 | T1 Policy | 41 | Policy | 4 | SI | 122 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.002 | 0 | CMO West 1 | IMGA222049 | LEYTHE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510877464 | CMO | CMO West 1 | May | 7 | A | Bernie Ridsdale | TBA - Lon | IMGA222223 | MILL ROAD | 510877464 | T1 Policy | 0 | Policy | 6 | DI | 13 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222223 | MILL ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO CANT, Steve | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510924278 | CMO | CMO West 1 | May | 7 | A | Trevor Trent | TBA - Lon | IMGA222048 | THIRD AVENUE | 510924278 | T1 PAST | 29.5 | Policy | 6 | CI | 314 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.263 | 0 | CMO West 1 | IMGA222048 | THIRD AVENUE | Ealing Council | West 1 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
601510308 | CMO | CMO West 1 | May | 7 | A | Bernie Ridsdale | TBA - Lon | IMGA222223 | MILL ROAD | 601510308 | T1 PAST | 1.2 | Policy | 6 | DI | 32 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0384 | 0 | CMO West 1 | IMGA222223 | MILL ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE | PAST | Direct Mole | T1 PAST | CMO CANT, Steve | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
606807576 | CMO | CMO West 1 | May | 7 | A | Trevor Trent | TBA - Lon | IMGA222048 | THIRD AVENUE | 606807576 | T1 Policy | 27.7 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0554 | 0 | CMO West 1 | IMGA222048 | THIRD AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
613750159 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222225 | KNELLER ROAD | 613750159 | T1 Policy | 42.3 | Policy | 4 | SI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1269 | 0 | CMO West 1 | IMGA222225 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
628341342 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222211 | VANCOUVER ROAD | 628341342 | T1 Policy | 15.6 | Policy | 6 | SI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1248 | 0 | CMO West 1 | IMGA222211 | VANCOUVER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
638650061 | CMO | CMO West 1 | May | 7 | A | TBA - Lon | TBA - Lon | IMGA222148 | WOODLAWN ROAD | 638650061 | T1 Policy | 26.2 | Policy | 8 | CI | 7 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1834 | 0 | CMO West 1 | IMGA222148 | WOODLAWN ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510895892 | CMO | CMO West 1 | May | 8 | A | Mark Prothero | TBA - Lon | IMGA222172 | PRIORY WAY | 510895892 | T1 Policy | 31.8 | Policy | 4 | CI | 126 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.0068 | 0 | CMO West 1 | IMGA222172 | PRIORY WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510882099 | CMO | CMO West 1 | May | 8 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882099 | T1 Policy | 20.8 | Policy | 6 | SI | 84 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7472 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510844436 | CMO | CMO West 1 | May | 8 | A | Mark Prothero | TBA - Lon | IMGA222183 | HAMILTON CLOSE | 510844436 | T1 Policy | 31.1 | Policy | 4 | SI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.598 | 0 | CMO West 1 | IMGA222183 | HAMILTON CLOSE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220001559052 | CMO | CMO West 1 | May | 8 | A | Mark Prothero | TBA - Lon | IMGA222192 | BURNS AVENUE | 220001559052 | T1 Policy | 0 | Policy | 6 | SI | 84 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222192 | BURNS AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510910220 | CMO | CMO West 1 | May | 8 | A | Mark Prothero | TBA - Lon | IMGA222192 | SHAKESPEARE AVENUE | 510910220 | T1 Policy | 38.8 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2716 | 0 | CMO West 1 | IMGA222192 | SHAKESPEARE AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510897581 | CMO | CMO West 1 | May | 8 | A | TBA - Lon | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 43 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5738 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510816027 | CMO | CMO West 1 | May | 8 | A | TBA - Lon | TBA - Lon | IMGA222148 | CRABTREE LANE | 510816027 | T1 Policy | 41.5 | Policy | 6 | CI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.332 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510862679 | CMO | CMO West 1 | May | 8 | A | TBA - Lon | TBA - Lon | IMGA222211 | LAMMAS ROAD | 510862679 | T1 Policy | 19.7 | Policy | 4 | SI | 61 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2017 | 0 | CMO West 1 | IMGA222211 | LAMMAS ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510861687 | CMO | CMO West 1 | May | 8 | A | TBA - Lon | TBA - Lon | IMGA222224 | KNELLER ROAD | 510861687 | T1 Policy | 5.3 | Policy | 6 | SI | 156 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8268 | 0 | CMO West 1 | IMGA222224 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510898306 | CMO | CMO West 1 | May | 8 | A | Trevor Trent | TBA - Lon | IMGA222037 | RANELAGH ROAD | 510898306 | T1 Policy | 0.5 | Policy | 100 | DI | 50 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.025 | 0 | CMO West 1 | IMGA222037 | RANELAGH ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510871154 | CMO | CMO West 1 | May | 8 | A | Trevor Trent | TBA - Lon | IMGA222044 | LYON PARK AVENUE | 510871154 | T1 Policy | 1.5 | Policy | 100 | DI | 60 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.09 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510865903 | CMO | CMO West 1 | May | 8 | A | Trevor Trent | TBA - Lon | IMGA222049 | LEYTHE ROAD | 510865903 | T1 Policy | 42.1 | Policy | 4 | SI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9366 | 0 | CMO West 1 | IMGA222049 | LEYTHE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510922028 | CMO | CMO West 1 | May | 8 | A | Trevor Trent | TBA - Lon | IMGA222400 | THE AVENUE | 510922028 | T1 Policy | 16.4 | Policy | 4 | CI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.952 | 0 | CMO West 1 | IMGA222400 | THE AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510827332 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222171 | ELMCROFT CRESCENT | 510827332 | T1 Policy | 25 | Policy | 4 | CI | 51 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.275 | 0 | CMO West 1 | IMGA222171 | ELMCROFT CRESCENT | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510895892 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222172 | PRIORY WAY | 510895892 | T1 Policy | 31.8 | Policy | 4 | CI | 127 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.0386 | 0 | CMO West 1 | IMGA222172 | PRIORY WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510895893 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222172 | PRIORY WAY | 510895893 | T1 Policy | 19.5 | Policy | 6 | CI | 43 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8385 | 0 | CMO West 1 | IMGA222172 | PRIORY WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510882100 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882100 | T1 Policy | 41.1 | Policy | 4 | CI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.576 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT |  | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510882103 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882103 | T1 Policy | 37.8 | Policy | 4 | CI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3024 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510844434 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222183 | HAMILTON CLOSE | 510844434 | T1 Policy | 30.8 | Policy | 4 | SI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.158 | 0 | CMO West 1 | IMGA222183 | HAMILTON CLOSE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510844437 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222183 | HAMILTON CLOSE | 510844437 | T1 Policy | 17.7 | Policy | 6 | SI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1416 | 0 | CMO West 1 | IMGA222183 | HAMILTON CLOSE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510844438 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222183 | HAMILTON CLOSE | 510844438 | T1 Policy | 33.9 | Policy | 4 | SI | 153 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.1867 | 0 | CMO West 1 | IMGA222183 | HAMILTON CLOSE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220001215290 | CMO | CMO West 1 | May | 9 | A | Mark Prothero | TBA - Lon | IMGA222183 | HAMILTON CLOSE | 220001215290 | T1 Policy | 0 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222183 | HAMILTON CLOSE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510894682 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222031 | POYNTZ ROAD | 510894682 | T1 Policy | 0.3 | Policy | 4 | DI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0255 | 0 | CMO West 1 | IMGA222031 | POYNTZ ROAD | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510897581 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 15 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.549 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510816027 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222148 | CRABTREE LANE | 510816027 | T1 Policy | 41.5 | Policy | 6 | CI | 65 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.6975 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510862677 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510862677 | T1 Policy | 11.6 | Policy | 6 | SI | 61 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7076 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole |  | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510862678 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510862678 | T1 Policy | 21.7 | Policy | 4 | SI | 16 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3472 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole |  | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510823987 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510823987 | T1 Policy | 23.8 | Policy | 4 | SI | 133 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1654 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510823990 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510823990 | T1 Policy | 22.6 | Policy | 4 | SI | 87 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9662 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510861687 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222224 | KNELLER ROAD | 510861687 | T1 Policy | 5.3 | Policy | 6 | SI | 65 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3445 | 0 | CMO West 1 | IMGA222224 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510898306 | CMO | CMO West 1 | May | 9 | A | Trevor Trent | TBA - Lon | IMGA222037 | RANELAGH ROAD | 510898306 | T1 Policy | 0.5 | Policy | 100 | DI | 40 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 1 | IMGA222037 | RANELAGH ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510865903 | CMO | CMO West 1 | May | 9 | A | Trevor Trent | TBA - Lon | IMGA222049 | LEYTHE ROAD | 510865903 | T1 Policy | 42.1 | Policy | 4 | SI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.6835 | 0 | CMO West 1 | IMGA222049 | LEYTHE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220001617746 | CMO | CMO West 1 | May | 9 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 220001617746 | T1 Policy | 0 | Policy | 6 | SI | 200 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510862679 | CMO | CMO West 1 | May | 9 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510862679 | T1 Policy | 19.7 | Policy | 4 | SI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9062 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole |  | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510827332 | CMO | CMO West 1 | June | 10 | A | Mark Prothero | TBA - Lon | IMGA222171 | ELMCROFT CRESCENT | 510827332 | T1 Policy | 25 | Policy | 4 | CI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.625 | 0 | CMO West 1 | IMGA222171 | ELMCROFT CRESCENT | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510882100 | CMO | CMO West 1 | June | 10 | A | Mark Prothero | TBA - Lon | IMGA222181 | NEW ROAD | 510882100 | T1 Policy | 41.1 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.521 | 0 | CMO West 1 | IMGA222181 | NEW ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001559051 | CMO | CMO West 1 | June | 10 | A | Mark Prothero | TBA - Lon | IMGA222192 | BURNS AVENUE | 220001559051 | T1 Policy | 0 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222192 | BURNS AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510910220 | CMO | CMO West 1 | June | 10 | A | Mark Prothero | TBA - Lon | IMGA222192 | SHAKESPEARE AVENUE | 510910220 | T1 Policy | 38.8 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.268 | 0 | CMO West 1 | IMGA222192 | SHAKESPEARE AVENUE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SHEPPARD, Ashley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510894682 | CMO | CMO West 1 | June | 10 | A | TBA - Lon | TBA - Lon | IMGA222031 | POYNTZ ROAD | 510894682 | T1 Policy | 0.3 | Policy | 4 | DI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0135 | 0 | CMO West 1 | IMGA222031 | POYNTZ ROAD | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510816027 | CMO | CMO West 1 | June | 10 | A | TBA - Lon | TBA - Lon | IMGA222148 | CRABTREE LANE | 510816027 | T1 Policy | 41.5 | Policy | 6 | CI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.32 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510823989 | CMO | CMO West 1 | June | 10 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510823989 | T1 Policy | 24.1 | Policy | 4 | SI | 92 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2172 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510861687 | CMO | CMO West 1 | June | 10 | A | TBA - Lon | TBA - Lon | IMGA222224 | KNELLER ROAD | 510861687 | T1 Policy | 5.3 | Policy | 6 | SI | 25 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1325 | 0 | CMO West 1 | IMGA222224 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510871158 | CMO | CMO West 1 | June | 10 | A | Trevor Trent | TBA - Lon | IMGA222044 | LYON PARK AVENUE | 510871158 | T1 Policy | 1.3 | Policy | 150 | DI | 68 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0884 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510790472 | CMO | CMO West 1 | June | 10 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 510790472 | T1 Policy | 14.7 | Policy | 6 | DI | 108 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5876 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510922028 | CMO | CMO West 1 | June | 10 | A | Trevor Trent | TBA - Lon | IMGA222400 | THE AVENUE | 510922028 | T1 Policy | 16.4 | Policy | 4 | CI | 39 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6396 | 0 | CMO West 1 | IMGA222400 | THE AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510922040 | CMO | CMO West 1 | June | 10 | A | Trevor Trent | TBA - Lon | IMGA222400 | THE AVENUE | 510922040 | T1 Policy | 9.7 | Policy | 4 | CI | 112 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0864 | 0 | CMO West 1 | IMGA222400 | THE AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510827332 | CMO | CMO West 1 | June | 11 | A | Mark Prothero | TBA - Lon | IMGA222171 | ELMCROFT CRESCENT | 510827332 | T1 Policy | 25 | Policy | 4 | CI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.625 | 0 | CMO West 1 | IMGA222171 | ELMCROFT CRESCENT | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510872819 | CMO | CMO West 1 | June | 11 | A | Mark Prothero | TBA - Lon | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
627630737 | CMO | CMO West 1 | June | 11 | A | Mark Prothero | TBA - Lon | IMGA222181 | PAGE ROAD | 627630737 | T1 Policy | 26.3 | Policy | 4 | SI | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9725 | 0 | CMO West 1 | IMGA222181 | PAGE ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
634624343 | CMO | CMO West 1 | June | 11 | A | Mark Prothero | TBA - Lon | IMGA222181 | PAGE ROAD | 634624343 | T1 Policy | 38.8 | Policy | 6 | SI | 109 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.2292 | 0 | CMO West 1 | IMGA222181 | PAGE ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510897581 | CMO | CMO West 1 | June | 11 | A | TBA - Lon | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 50 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.83 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510823989 | CMO | CMO West 1 | June | 11 | A | TBA - Lon | TBA - Lon | IMGA222211 | DYSART AVENUE | 510823989 | T1 Policy | 24.1 | Policy | 4 | CI | 225 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.4225 | 0 | CMO West 1 | IMGA222211 | DYSART AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510861673 | CMO | CMO West 1 | June | 11 | A | TBA - Lon | TBA - Lon | IMGA222224 | KNELLER ROAD | 510861673 | T1 Policy | 6.2 | Policy | 8 | CI | 64 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3968 | 0 | CMO West 1 | IMGA222224 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510898307 | CMO | CMO West 1 | June | 11 | A | Trevor Trent | TBA - Lon | IMGA222037 | RANELAGH ROAD | 510898307 | T1 Policy | 0.4 | Policy | 100 | DI | 50 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 1 | IMGA222037 | RANELAGH ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510865904 | CMO | CMO West 1 | June | 11 | A | Trevor Trent | TBA - Lon | IMGA222049 | LEYTHE ROAD | 510865904 | T1 Policy | 41 | Policy | 4 | SI | 21 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.861 | 0 | CMO West 1 | IMGA222049 | LEYTHE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
633280182 | CMO | CMO West 1 | June | 11 | A | Trevor Trent | TBA - Lon | IMGA222049 | LEYTHE ROAD | 633280182 | T1 Policy | 74.6 | Policy | 4 | SI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2984 | 0 | CMO West 1 | IMGA222049 | LEYTHE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | SEED | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510839136 | CMO | CMO West 1 | June | 11 | A | Trevor Trent | TBA - Lon | IMGA222054 | Gordon Road | 510839136 | T1 Policy | 10.3 | Policy | 4 | DI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.03 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MORGAN, Carl | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510790472 | CMO | CMO West 1 | June | 11 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 510790472 | T1 Policy | 14.7 | Policy | 6 | DI | 102 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4994 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510790473 | CMO | CMO West 1 | June | 11 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 510790473 | T1 Policy | 19.4 | Policy | 4 | SI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.649 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
220001448596 | CMO | CMO West 1 | June | 11 | A | Steve Edwards | Darren Francis | IMGA221041 | ST MARY ABBOT'S TERRACE | 220001448596 | T1 Policy | 0 | Policy | 4 | CI | 33 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001448596 | CMO | CMO West 1 | June | 12 | A | Shaun Melluish | John Moran | IMGA221041 | ST MARY ABBOT'S TERRACE | 220001448596 | T1 Policy | 0 | Policy | 4 | CI | 56 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510861879 | CMO | CMO West 1 | June | 12 | A | Peter Giannini | TBA - Lon | IMGA222031 | KNOWSLEY ROAD | 510861879 | T1 Policy | 0.3 | Policy | 4 | DI | 185 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0555 | 0 | CMO West 1 | IMGA222031 | KNOWSLEY ROAD | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510832392 | CMO | CMO West 1 | June | 12 | A | Peter Giannini | TBA - Lon | IMGA222214 | FIRST AVENUE | 510832392 | T1 Policy | 42.7 | Policy | 4 | CI | 146 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.2342 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO FAIRWEATHER, Adam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001887213 | CMO | CMO West 1 | June | 12 | A | Trevor Trent | TBA - Lon | IMGA222050 | BOLLO BRIDGE ROAD | 220001887213 | T1 Policy | 0 | Policy | 4 | CI | 51 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510839136 | CMO | CMO West 1 | June | 12 | A | Trevor Trent | TBA - Lon | IMGA222054 | Gordon Road | 510839136 | T1 Policy | 10.3 | Policy | 4 | DI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.03 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MORGAN, Carl | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
220001887213 | CMO | CMO West 1 | June | 12 | A | Trevor Trent | TBA - Lon | IMGA222050 | BOLLO BRIDGE ROAD | 220001887213 | T1 Policy | 0 | Policy | 6 | CI | 124 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510897581 | CMO | CMO West 1 | June | 12 | A | Roger Fearn | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 74 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7084 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510872819 | CMO | CMO West 1 | June | 12 | A | Trevor Trent | TBA - Lon | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510898307 | CMO | CMO West 1 | June | 12 | A | Trevor Trent | TBA - Lon | IMGA222037 | RANELAGH ROAD | 510898307 | T1 Policy | 0.4 | Policy | 100 | DI | 30 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.012 | 0 | CMO West 1 | IMGA222037 | RANELAGH ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510810527 | CMO | CMO West 1 | June | 13 | A | Shaun Melluish | John Moran | IMGA221035 | CLARENDON ROAD | 510810527 | T2 PAST | 38.8 | Policy | 12 | DI | 28 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 1.0864 | 0 | CMO West 1 | IMGA221035 | CLARENDON ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE | PAST | DPF | T2 PAST | CMO RADA, Besim | LP | #N/A | 10-12” | 12 |  | Policy | Tier 2 | DI | T2A | June
510906930 | CMO | CMO West 1 | June | 13 | A | Shaun Melluish | John Moran | IMGA221041 | ST MARY ABBOT'S TERRACE | 510906930 | T1 Policy | 34.4 | Policy | 4 | CI | 38.8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3347 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001860376 | CMO | CMO West 1 | June | 13 | A | Peter Giannini | TBA - Lon | IMGA222210 | EAST SHEEN AVENUE | 220001860376 | T1 Policy | 0 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510832392 | CMO | CMO West 1 | June | 13 | A | Peter Giannini | TBA - Lon | IMGA222214 | FIRST AVENUE | 510832392 | T1 Policy | 42.7 | Policy | 4 | CI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1598 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO STONEMAN, Thomas | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510897581 | CMO | CMO West 1 | June | 13 | A | Roger Fearn | TBA - Lon | IMGA222147 | RADIPOLE ROAD | 510897581 | T1 Policy | 36.6 | Policy | 8 | CI | 25 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.915 | 0 | CMO West 1 | IMGA222147 | RADIPOLE ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510871154 | CMO | CMO West 1 | June | 13 | A | Shaun Melluish | TBA - Lon | IMGA222044 | LYON PARK AVENUE | 510871154 | T1 Policy | 1.5 | Policy | 150 | DI | 67 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1005 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510871158 | CMO | CMO West 1 | June | 13 | A | Shaun Melluish | TBA - Lon | IMGA222044 | LYON PARK AVENUE | 510871158 | T1 Policy | 1.3 | Policy | 150 | DI | 41 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0533 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510870945 | CMO | CMO West 1 | June | 13 | A | Trevor Trent | TBA - Lon | IMGA222064 | LYNDHURST ROAD | 510870945 | T1 Policy | 33.5 | Policy | 4 | CI | 214 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.169 | 0 | CMO West 1 | IMGA222064 | LYNDHURST ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510790473 | CMO | CMO West 1 | June | 13 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 510790473 | T1 Policy | 19.4 | Policy | 4 | SI | 136 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.6384 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
220001617746 | CMO | CMO West 1 | June | 13 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 220001617746 | T1 Policy | 0 | Policy | 4 | SI | 75 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510822774 | CMO | CMO West 1 | June | 13 | A | Trevor Trent | TBA - Lon | IMGA222079 | DRAYTON GARDENS | 510822774 | T1 Policy | 0.6 | Policy | 4 | DI | 11 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0066 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510822775 | CMO | CMO West 1 | June | 13 | A | Trevor Trent | TBA - Lon | IMGA222079 | DRAYTON GARDENS | 510822775 | T1 Policy | 0.4 | Policy | 4 | DI | 148 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0592 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510827332 | CMO | CMO West 1 | June | 13 | A | Trevor Trent | TBA - Lon | IMGA222171 | ELMCROFT CRESCENT | 510827332 | T1 Policy | 25 | Policy | 4 | CI | 107 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.675 | 0 | CMO West 1 | IMGA222171 | ELMCROFT CRESCENT | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO West 1 | June | 13 | A | Roger Fearn | TBA - Lon | IMGA222148 | CRABTREE LANE | DR4 Requested | T1 Policy | 0 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF |  | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510820586 | CMO | CMO West 1 | June | 14 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820586 | T1 Policy | 29.9 | Policy | 4 | CI | 143 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.2757 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510914275 | CMO | CMO West 1 | June | 14 | A | Roger Fearn | Lee Blackmore | IMGA222190 | SPARROW FARM DRIVE | 510914275 | T1 Policy | 27.4 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.918 | 0 | CMO West 1 | IMGA222190 | SPARROW FARM DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510914535 | CMO | CMO West 1 | June | 14 | A | Roger Fearn | Lee Blackmore | IMGA222191 | SPINNEY DRIVE | 510914535 | T1 Policy | 16.9 | Policy | 4 | CI | 300 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.07 | 0 | CMO West 1 | IMGA222191 | SPINNEY DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220001887213 | CMO | CMO West 1 | June | 14 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001887213 | T1 Policy | 0 | Policy | 6 | CI | 155 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510872819 | CMO | CMO West 1 | June | 14 | A | Trevor Trent | Darren Smith | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 8 | DI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | June
510810527 | CMO | CMO West 1 | June | 14 | A | Shaun Melluish | Darren Francis | IMGA221035 | CLARENDON ROAD | 510810527 | T2 PAST | 38.8 | Policy | 12 | CI | 70 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 2.716 | 0 | CMO West 1 | IMGA221035 | CLARENDON ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE | PAST | DPF | T2 PAST | CMO RADA, Besim | LP | #N/A | 10-12” | 12 |  | Policy | Tier 2 | CI | T2A | June
510898307 | CMO | CMO West 1 | June | 14 | A | Shaun Melluish | Dominic St. John | IMGA222037 | RANELAGH ROAD | 510898307 | T1 Policy | 0.4 | Policy | 100 | DI | 76 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0304 | 0 | CMO West 1 | IMGA222037 | RANELAGH ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510871155 | CMO | CMO West 1 | June | 14 | A | Shaun Melluish | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510871155 | T1 Policy | 2 | Policy | 100 | DI | 70 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510839136 | CMO | CMO West 1 | June | 14 | A | Trevor Trent | Simon White | IMGA222054 | Gordon Road | 510839136 | T1 Policy | 10.3 | Policy | 100 | DI | 70 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.721 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MORGAN, Carl | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510824655 | CMO | CMO West 1 | July | 15 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 510824655 | T1 Policy | 21.8 | Policy | 4 | CI | 71 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5478 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220001860376 | CMO | CMO West 1 | July | 15 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 220001860376 | T1 Policy | 0 | Policy | 6 | CI | 116 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
220001860380 | CMO | CMO West 1 | July | 15 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 220001860380 | T1 Policy | 0 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510850965 | CMO | CMO West 1 | July | 15 | A | Peter Giannini | Mick Bradley | IMGA222226 | HIGH STREET | 510850965 | T1 Policy | 15.2 | Policy | 8 | CI | 17 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2584 | 0 | CMO West 1 | IMGA222226 | HIGH STREET | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO CANT, Steve | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510816027 | CMO | CMO West 1 | July | 15 | A | Roger Fearn | Ben Noble | IMGA222148 | CRABTREE LANE | 510816027 | T1 Policy | 41.5 | Policy | 6 | CI | 65 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.6975 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510975551 | CMO | CMO West 1 | July | 15 | A | Roger Fearn | Ben Noble | IMGA222148 | CRABTREE LANE | 510975551 | T1 Policy | 30.3 | Policy | 100 | DI | 10 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.303 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510914264 | CMO | CMO West 1 | July | 15 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510914264 | T1 Policy | 32.6 | Policy | 4 | SI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.238 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT |  | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510969517 | CMO | CMO West 1 | July | 15 | A | Roger Fearn | Lee Blackmore | IMGA222191 | WEST VIEW | 510969517 | T1 Policy | 15.4 | Policy | 6 | CI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.31 | 0 | CMO West 1 | IMGA222191 | WEST VIEW | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
DR4 Requested | CMO | CMO West 1 | July | 15 | A | Shaun Melluish | Darren Francis | IMGA221035 | CLARENDON ROAD | DR4 Requested | T1 Policy | 0 | Policy | 6 | CI | 16 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA221035 | CLARENDON ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF |  | CMO RADA, Besim | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
632060916 | CMO | CMO West 1 | July | 15 | A | Shaun Melluish | Darren Francis | IMGA221035 | CLARENDON ROAD | 632060916 | T1 Policy | 30.1 | Policy | 4 | CI | 13 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3913 | 0 | CMO West 1 | IMGA221035 | CLARENDON ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO RADA, Besim | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220001448600 | CMO | CMO West 1 | July | 15 | A | Shaun Melluish | Darren Francis | IMGA221041 | ST MARY ABBOT'S TERRACE | 220001448600 | T1 Policy | 0 | Policy | 4 | DI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510868084 | CMO | CMO West 1 | July | 15 | A | Shaun Melluish | Dominic St. John | IMGA222044 | LOMOND CLOSE | 510868084 | T1 Policy | 0.3 | Policy | 100 | DI | 136 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0408 | 0 | CMO West 1 | IMGA222044 | LOMOND CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510871155 | CMO | CMO West 1 | July | 15 | A | Shaun Melluish | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510871155 | T1 Policy | 2 | Policy | 150 | DI | 30 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510822774 | CMO | CMO West 1 | July | 15 | A | Trevor Trent | Paul Burke | IMGA222079 | DRAYTON GARDENS | 510822774 | T1 Policy | 0.6 | Policy | 100 | DI | 67 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0402 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510872819 | CMO | CMO West 1 | July | 15 | A | Trevor Trent | Darren Smith | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 6 | CI | 53 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT |  | tRIIO SMITH, Bradley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510872819 | CMO | CMO West 1 | July | 15 | A | Trevor Trent | Darren Smith | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 8 | CI | 105 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510841447 | CMO | CMO West 1 | July | 15 | A | Trevor Trent | Darren Smith | IMGA222179 | GREENACRES DRIVE | 510841447 | T1 Policy | 0.4 | Policy | 4 | DI | 260 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.104 | 0 | CMO West 1 | IMGA222179 | GREENACRES DRIVE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510872819 | CMO | CMO West 1 | July | 16 | A | Mark Prothero | TBA - Lon | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 4 | SI | -400 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510872820 | CMO | CMO West 1 | July | 16 | A | Mark Prothero | TBA - Lon | IMGA222172 | MANOR WAY | 510872820 | T1 Policy | 23.9 | Policy | 4 | CI | 400 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.56 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220001617746 | CMO | CMO West 1 | July | 16 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 220001617746 | T1 Policy | 0 | Policy | 6 | SI | -200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220000010575 | CMO | CMO West 1 | July | 16 | A | Trevor Trent | TBA - Lon | IMGA222068 | BENGARTH ROAD | 220000010575 | T1 Policy | 0 | Policy | 6 | SI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222068 | BENGARTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220001860379 | CMO | CMO West 1 | July | 16 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 220001860379 | T1 Policy | 4.1 | Policy | 6 | CI | 190 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.779 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510786622 | CMO | CMO West 1 | July | 16 | A | Roger Fearn | Ben Noble | IMGA222146 | BARCLAY CLOSE | 510786622 | T1 PAST | 145.3 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.265 | 0 | CMO West 1 | IMGA222146 | BARCLAY CLOSE | Hammersmith and Fulham London Borough Council | West 1 | FALSE | PAST | DPF | T1 PAST | CMO MASON, Alec | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510914534 | CMO | CMO West 1 | July | 16 | A | Roger Fearn | Lee Blackmore | IMGA222191 | SPINNEY DRIVE | 510914534 | T1 Policy | 8.8 | Policy | 4 | CI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.408 | 0 | CMO West 1 | IMGA222191 | SPINNEY DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
220001448596 | CMO | CMO West 1 | July | 16 | A | Shaun Melluish | Darren Francis | IMGA221041 | ST MARY ABBOT'S TERRACE | 220001448596 | T1 Policy | 140.7 | Policy | 4 | DI | 28 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.9396 | 0 | CMO West 1 | IMGA221041 | ST MARY ABBOT'S TERRACE | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
220000478713 | CMO | CMO West 1 | July | 16 | A | Shaun Melluish | Dominic St. John | IMGA222393 | DOLLIS HILL LANE | 220000478713 | T1 Policy | 5 | Policy | 8 | CI | 177 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.885 | 0 | CMO West 1 | IMGA222393 | DOLLIS HILL LANE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
220001887213 | CMO | CMO West 1 | July | 16 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001887213 | T1 Policy | 0 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510839136 | CMO | CMO West 1 | July | 16 | A | Trevor Trent | Simon White | IMGA222054 | Gordon Road | 510839136 | T1 Policy | 36 | Policy | 100 | DI | 82 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.952 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MORGAN, Carl | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510870944 | CMO | CMO West 1 | July | 16 | A | Trevor Trent | Paul Burke | IMGA222064 | LYNDHURST ROAD | 510870944 | T1 Policy | 5.3 | Policy | 4 | CI | 142 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7526 | 0 | CMO West 1 | IMGA222064 | LYNDHURST ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510904360 | CMO | CMO West 1 | July | 16 | A | Trevor Trent | Paul Burke | IMGA222064 | RUISLIP CLOSE | 510904360 | T1 Policy | 3.3 | Policy | 4 | CI | 125 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4125 | 0 | CMO West 1 | IMGA222064 | RUISLIP CLOSE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510820585 | CMO | CMO West 1 | July | 17 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820585 | T1 Policy | 14.4 | Policy | 4 | CI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9216 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | TRIIO TAYLOR, JAMIE | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510832392 | CMO | CMO West 1 | July | 17 | A | Peter Giannini | Mick Bradley | IMGA222214 | FIRST AVENUE | 510832392 | T1 Policy | 21.5 | Policy | 4 | CI | 11 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2365 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510832393 | CMO | CMO West 1 | July | 17 | A | Peter Giannini | Mick Bradley | IMGA222214 | FIRST AVENUE | 510832393 | T1 Policy | 21.6 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.512 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510861879 | CMO | CMO West 1 | July | 17 | A | Peter Giannini | Marc Alexander | IMGA222031 | KNOWSLEY ROAD | 510861879 | T1 Policy | 17.7 | Policy | 4 | DI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.177 | 0 | CMO West 1 | IMGA222031 | KNOWSLEY ROAD | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510903223 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Paul Burke | IMGA222075 | ROSECROFT ROAD | 510903223 | T1 Policy | 8.6 | Policy | 4 | SI | 216 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.8576 | 0 | CMO West 1 | IMGA222075 | ROSECROFT ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510914263 | CMO | CMO West 1 | July | 17 | A | Roger Fearn | Lee Blackmore | IMGA222190 | SPARROW FARM DRIVE | 510914263 | T1 Policy | 4.9 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.539 | 0 | CMO West 1 | IMGA222190 | SPARROW FARM DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | TRIIO TAYLOR, JAMIE | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510914534 | CMO | CMO West 1 | July | 17 | A | Roger Fearn | Lee Blackmore | IMGA222191 | SPINNEY DRIVE | 510914534 | T1 Policy | 8.8 | Policy | 4 | CI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.408 | 0 | CMO West 1 | IMGA222191 | SPINNEY DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510954498 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Darren Smith | IMGA222179 | SUNNINGDALE CLOSE | 510954498 | T1 Policy | 2.7 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0405 | 0 | CMO West 1 | IMGA222179 | SUNNINGDALE CLOSE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510838949 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838949 | T1 Policy | 2.3 | Policy | 6 | SI | 43 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0989 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510861880 | CMO | CMO West 1 | July | 17 | A | Peter Giannini | Marc Alexander | IMGA222031 | KNOWSLEY ROAD | 510861880 | T1 Policy | 31.5 | Policy | 6 | DI | 231 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.2765 | 0 | CMO West 1 | IMGA222031 | KNOWSLEY ROAD | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510954497 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Darren Smith | IMGA222179 | SUNNINGDALE CLOSE | 510954497 | T1 Policy | 8.7 | Policy | 6 | SI | 156 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3572 | 0 | CMO West 1 | IMGA222179 | SUNNINGDALE CLOSE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510954499 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Darren Smith | IMGA222179 | SUNNINGDALE CLOSE | 510954499 | T1 Policy | 3.4 | Policy | 6 | DI | 63 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2142 | 0 | CMO West 1 | IMGA222179 | SUNNINGDALE CLOSE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
612911075 | CMO | CMO West 1 | July | 17 | A | Peter Giannini | Marc Alexander | IMGA222031 | KNOWSLEY ROAD | 612911075 | T1 Policy | 18.9 | Policy | 6 | DI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0945 | 0 | CMO West 1 | IMGA222031 | KNOWSLEY ROAD | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO NOLAN, Daniel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
220001887222 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001887222 | T1 Policy | 0 | Policy | 6 | CI | 45 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510822774 | CMO | CMO West 1 | July | 17 | A | Trevor Trent | Paul Burke | IMGA222079 | DRAYTON GARDENS | 510822774 | T1 Policy | 20 | Policy | 100 | DI | 70 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510903878 | CMO | CMO West 1 | July | 17 | A | Roger Fearn | Dominic St. John | IMGA222044 | ROWLEY CLOSE | 510903878 | T1 Policy | 83.4 | Policy | 100 | DI | 110 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.174 | 0 | CMO West 1 | IMGA222044 | ROWLEY CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
220001860379 | CMO | CMO West 1 | July | 18 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 220001860379 | T1 Policy | 4.1 | Policy | 6 | CI | 63 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2583 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510832393 | CMO | CMO West 1 | July | 18 | A | Peter Giannini | Mick Bradley | IMGA222214 | FIRST AVENUE | 510832393 | T1 Policy | 21.6 | Policy | 4 | CI | 96 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0736 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510853443 | CMO | CMO West 1 | July | 18 | A | Roger Fearn | Mick Bradley | IMGA221039 | HOLLAND VILLAS ROAD | 510853443 | T1 PAST | 187.1 | Policy | 6 | DI | 84 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 15.7164 | 0 | CMO West 1 | IMGA221039 | HOLLAND VILLAS ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE | PAST | DPF | T1 PAST | CMO BARAKU, Zenel | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510903878 | CMO | CMO West 1 | July | 18 | A | Roger Fearn | Dominic St. John | IMGA222044 | ROWLEY CLOSE | 510903878 | T1 Policy | 83.4 | Policy | 100 | DI | 95 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.923 | 0 | CMO West 1 | IMGA222044 | ROWLEY CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510903879 | CMO | CMO West 1 | July | 18 | A | Roger Fearn | Dominic St. John | IMGA222044 | ROWLEY CLOSE | 510903879 | T1 Policy | 0 | Policy | 100 | DI | 4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222044 | ROWLEY CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510820587 | CMO | CMO West 1 | July | 18 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820587 | T1 Policy | 12.1 | Policy | 4 | SI | 11 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1331 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | TRIIO TAYLOR, JAMIE | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510820588 | CMO | CMO West 1 | July | 18 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820588 | T1 Policy | 5.1 | Policy | 4 | SI | 77 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3927 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | TRIIO TAYLOR, JAMIE | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220000478713 | CMO | CMO West 1 | July | 18 | A | Roger Fearn | Dominic St. John | IMGA222393 | DOLLIS HILL LANE | 220000478713 | T1 Policy | 5 | Policy | 8 | CI | 137 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.685 | 0 | CMO West 1 | IMGA222393 | DOLLIS HILL LANE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
220001896185 | CMO | CMO West 1 | July | 18 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001896185 | T1 Policy | 65.7 | Policy | 6 | CI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.913 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510884088 | CMO | CMO West 1 | July | 18 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 510884088 | T1 Policy | 59.5 | Policy | 8 | CI | 198 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.781 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
629790742 | CMO | CMO West 1 | July | 18 | A | Trevor Trent | Paul Burke | IMGA222158 | METHUEN ROAD | 629790742 | T1 Policy | 8 | Policy | 6 | SI | 85 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.68 | 0 | CMO West 1 | IMGA222158 | METHUEN ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO VAN DER HAVE, John | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510820587 | CMO | CMO West 1 | August | 19 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820587 | T1 Policy | 12.1 | Policy | 4 | SI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5687 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510822774 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Paul Burke | IMGA222079 | DRAYTON GARDENS | 510822774 | T1 Policy | 20 | Policy | 4 | DI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510873964 | CMO | CMO West 1 | August | 19 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | 510873964 | T1 Policy | 6.8 | Policy | 4 | CI | 97 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6596 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510903873 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Darren Smith | IMGA222167 | ROWLANDS AVENUE | 510903873 | T1 Policy | 1.8 | Policy | 4 | CI | 55 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.099 | 0 | CMO West 1 | IMGA222167 | ROWLANDS AVENUE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510975551 | CMO | CMO West 1 | August | 19 | A | Roger Fearn | Ben Noble | IMGA222148 | CRABTREE LANE | 510975551 | T1 Policy | 180.5 | Policy | 4 | DI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 14.801 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
220001246127 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Simon White | IMGA222074 | BURNS AVENUE | 220001246127 | T1 Policy | 4.7 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0188 | 0 | CMO West 1 | IMGA222074 | BURNS AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220001246130 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Simon White | IMGA222074 | BURNS AVENUE | 220001246130 | T1 Policy | 5.2 | Policy | 4 | CI | 32 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1664 | 0 | CMO West 1 | IMGA222074 | BURNS AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510969517 | CMO | CMO West 1 | August | 19 | A | Roger Fearn | Lee Blackmore | IMGA222191 | WEST VIEW | 510969517 | T1 Policy | 17.9 | Policy | 6 | CI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.685 | 0 | CMO West 1 | IMGA222191 | WEST VIEW | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
- | CMO | CMO West 1 | August | 19 | A | Roger Fearn | Ben Noble | IMGA222148 | CRABTREE LANE | - | T1 Policy | 0 | Policy | 6 | CI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510884088 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 510884088 | T1 Policy | 59.5 | Policy | 8 | CI | 72 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.284 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510903873 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Darren Smith | IMGA222167 | ROWLANDS AVENUE | 510903873 | T1 Policy | 1.8 | Policy | 8 | CI | 25 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.045 | 0 | CMO West 1 | IMGA222167 | ROWLANDS AVENUE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510838948 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | CI | 72 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 23.76 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | CMO WARD, Jamie | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | CI | T2A | August
510822775 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Paul Burke | IMGA222079 | DRAYTON GARDENS | 510822775 | T1 Policy | 15.5 | Policy | 100 | DI | 4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.062 | 0 | CMO West 1 | IMGA222079 | DRAYTON GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO COFFMAN, Richard | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510839136 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Simon White | IMGA222054 | Gordon Road | 510839136 | T1 Policy | 36 | Policy | 100 | DI | 94 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.384 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO LEGGATT, Terry | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510847104 | CMO | CMO West 1 | August | 19 | A | Trevor Trent | Simon White | IMGA222054 | HAVEN GREEN | 510847104 | T1 Policy | 7 | Policy | 100 | DI | 16 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.112 | 0 | CMO West 1 | IMGA222054 | HAVEN GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO LEGGATT, Terry | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510816022 | CMO | CMO West 1 | August | 19 | A | Roger Fearn | Ben Noble | IMGA222148 | CRABTREE LANE | 510816022 | T1 Policy | 20.7 | Policy | 150 | DI | 5 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1035 | 0 | CMO West 1 | IMGA222148 | CRABTREE LANE | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510784731 | CMO | CMO West 1 | August | 20 | A | Peter Giannini | Marc Alexander | IMGA222026 | ATHERTON STREET | 510784731 | T1 Policy | 115.4 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.924 | 0 | CMO West 1 | IMGA222026 | ATHERTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510832393 | CMO | CMO West 1 | August | 20 | A | Peter Giannini | Mick Bradley | IMGA222214 | FIRST AVENUE | 510832393 | T1 Policy | 21.6 | Policy | 4 | CI | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9656 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510853440 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Mick Bradley | IMGA221039 | HOLLAND VILLAS ROAD | 510853440 | T2 CBA | 20.9 | Policy | 10 | DI | 70 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 1.463 | 0 | CMO West 1 | IMGA221039 | HOLLAND VILLAS ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T2 CBA | CMO BARAKU, Zenel | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | August
510874221 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Dominic St. John | IMGA222044 | MARQUIS CLOSE | 510874221 | T1 Policy | 9.3 | Policy | 100 | DI | 228 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1204 | 0 | CMO West 1 | IMGA222044 | MARQUIS CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510874222 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Dominic St. John | IMGA222044 | MARQUIS CLOSE | 510874222 | T1 Policy | 9.2 | Policy | 100 | DI | 8 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0736 | 0 | CMO West 1 | IMGA222044 | MARQUIS CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510807866 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Lee Blackmore | IMGA222190 | CHICHESTER WAY | 510807866 | T1 Policy | 17.6 | Policy | 4 | SI | 68 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1968 | 0 | CMO West 1 | IMGA222190 | CHICHESTER WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510807867 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Lee Blackmore | IMGA222190 | CHICHESTER WAY | 510807867 | T1 Policy | 8.7 | Policy | 4 | SI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2349 | 0 | CMO West 1 | IMGA222190 | CHICHESTER WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510807868 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Lee Blackmore | IMGA222190 | CHICHESTER WAY | 510807868 | T1 Policy | 27 | Policy | 4 | SI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.998 | 0 | CMO West 1 | IMGA222190 | CHICHESTER WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510864790 | CMO | CMO West 1 | August | 20 | A | Roger Fearn | Dominic St. John | IMGA222393 | DOLLIS HILL LANE | 510864790 | T1 Policy | 40 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.24 | 0 | CMO West 1 | IMGA222393 | DOLLIS HILL LANE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220001896185 | CMO | CMO West 1 | August | 20 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001896185 | T1 Policy | 65.7 | Policy | 6 | CI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.913 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510839136 | CMO | CMO West 1 | August | 20 | A | Trevor Trent | Simon White | IMGA222054 | Gordon Road | 510839136 | T1 Policy | 36 | Policy | 100 | DI | 160 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.76 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO LEGGATT, Terry | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510884088 | CMO | CMO West 1 | August | 20 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 510884088 | T1 Policy | 59.5 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.95 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510903022 | CMO | CMO West 1 | August | 20 | A | Trevor Trent | Paul Burke | IMGA222075 | ROSE GARDENS | 510903022 | T1 Policy | 11.4 | Policy | 4 | SI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8436 | 0 | CMO West 1 | IMGA222075 | ROSE GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
- | CMO | CMO West 1 | August | 20 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | - | T1 Policy | 0 | Policy | 4 | DI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE |  | KLT |  | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510838948 | CMO | CMO West 1 | August | 20 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | DI | 163 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 53.79 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | CMO WARD, Jamie | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | August
510853440 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Mick Bradley | IMGA221039 | HOLLAND VILLAS ROAD | 510853440 | T2 CBA | 20.9 | Policy | 10 | DI | 80 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 1.672 | 0 | CMO West 1 | IMGA221039 | HOLLAND VILLAS ROAD | Kensington and Chelsea Royal Borough Council | West 1 | FALSE |  | DPF | T2 CBA | CMO BARAKU, Zenel | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | August
510868084 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Dominic St. John | IMGA222044 | LOMOND CLOSE | 510868084 | T1 Policy | 8.3 | Policy | 100 | DI | 20 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.166 | 0 | CMO West 1 | IMGA222044 | LOMOND CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510868085 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Dominic St. John | IMGA222044 | LOMOND CLOSE | 510868085 | T1 Policy | 6.8 | Policy | 100 | DI | 6 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0408 | 0 | CMO West 1 | IMGA222044 | LOMOND CLOSE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510783094 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 510783094 | T1 PAST | 337.8 | Policy | 4 | DI | 62 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 20.9436 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE | PAST | DPF | T1 PAST | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510873966 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | 510873966 | T1 Policy | 7.8 | Policy | 4 | SI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.312 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510873967 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | 510873967 | T1 Policy | 11 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.77 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510820585 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820585 | T1 Policy | 14.4 | Policy | 4 | SI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3744 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510820587 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222190 | DENHAM ROAD | 510820587 | T1 Policy | 12.1 | Policy | 4 | SI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.121 | 0 | CMO West 1 | IMGA222190 | DENHAM ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510914263 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222190 | SPARROW FARM DRIVE | 510914263 | T1 Policy | 4.9 | Policy | 4 | CI | 11 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0539 | 0 | CMO West 1 | IMGA222190 | SPARROW FARM DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510914264 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222190 | SPARROW FARM DRIVE | 510914264 | T1 Policy | 5.1 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0102 | 0 | CMO West 1 | IMGA222190 | SPARROW FARM DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220000447332 | CMO | CMO West 1 | August | 21 | A | Roger Fearn | Lee Blackmore | IMGA222190 | SPARROW FARM DRIVE | 220000447332 | T1 Policy | 5.6 | Policy | 4 | CI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.028 | 0 | CMO West 1 | IMGA222190 | SPARROW FARM DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510839137 | CMO | CMO West 1 | August | 21 | A | Trevor Trent | Simon White | IMGA222054 | Gordon Road | 510839137 | T1 PAST | 416.6 | Policy | 4 | DI | 143 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 59.5738 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE | PAST | KLT | T1 PAST | tRIIO LEGGATT, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510884088 | CMO | CMO West 1 | August | 21 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 510884088 | T1 Policy | 59.5 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.95 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510838948 | CMO | CMO West 1 | August | 21 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | CI | 77 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 25.41 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | CMO WARD, Jamie | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | CI | T2A | August
510822777 | CMO | CMO West 1 | August | 21 | A | Trevor Trent | Darren Smith | IMGA222398 | DRAYTON GREEN | 510822777 | T1 Policy | 13 | Policy | 150 | DI | 38 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.494 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WALKER, Ross | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510784731 | CMO | CMO West 1 | August | 22 | A | Peter Giannini | Marc Alexander | IMGA222026 | ATHERTON STREET | 510784731 | T1 Policy | 115.4 | Policy | 4 | CI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.2702 | 0 | CMO West 1 | IMGA222026 | ATHERTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510824655 | CMO | CMO West 1 | August | 22 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 510824655 | T1 Policy | 14.3 | Policy | 4 | CI | 230 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.289 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510832393 | CMO | CMO West 1 | August | 22 | A | Peter Giannini | Mick Bradley | IMGA222214 | FIRST AVENUE | 510832393 | T1 Policy | 21.6 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.216 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510909236 | CMO | CMO West 1 | August | 22 | A | Peter Giannini | Mick Bradley | IMGA222214 | SECOND AVENUE | 510909236 | T1 Policy | 26.2 | Policy | 4 | CI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6812 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510847988 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510847988 | T1 Policy | 15.2 | Policy | 100 | DI | 30 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.456 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510871155 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510871155 | T1 Policy | 42.9 | Policy | 100 | DI | 82 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.5178 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510871158 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510871158 | T1 Policy | 42 | Policy | 100 | DI | 18 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.756 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510871162 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510871162 | T1 Policy | 7.6 | Policy | 100 | DI | 10 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.076 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
220000857684 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 220000857684 | T1 Policy | 6 | Policy | 100 | DI | 2 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.012 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510845488 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Ben Noble | IMGA222149 | HARBORD STREET | 510845488 | T1 Policy | 4.2 | Policy | 8 | CI | 55 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.231 | 0 | CMO West 1 | IMGA222149 | HARBORD STREET | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO MASON, Alec | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510783095 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 510783095 | T1 Policy | 0 | Policy | 4 | DI | 116 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
220001187038 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Ben Noble | IMGA222151 | ETHELDEN ROAD | 220001187038 | T1 Policy | 85.6 | Policy | 100 | DI | 4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3424 | 0 | CMO West 1 | IMGA222151 | ETHELDEN ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510873964 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | 510873964 | T1 Policy | 6.8 | Policy | 6 | SI | 12 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0816 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510873965 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | 510873965 | T1 Policy | 7.9 | Policy | 4 | CI | 98 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7742 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510914263 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Lee Blackmore | IMGA222190 | SPARROW FARM DRIVE | 510914263 | T1 Policy | 4.9 | Policy | 4 | DI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1323 | 0 | CMO West 1 | IMGA222190 | SPARROW FARM DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | FFRONT TAYLOR, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510915443 | CMO | CMO West 1 | August | 22 | A | Roger Fearn | Lee Blackmore | IMGA222191 | STAINES ROAD | 510915443 | T1 Policy | 5.1 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO West 1 | IMGA222191 | STAINES ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
220001838427 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001838427 | T1 Policy | 8.9 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0356 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220001887213 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001887213 | T1 Policy | 0 | Policy | 6 | CI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220001887222 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001887222 | T1 Policy | 0 | Policy | 6 | CI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
220001887238 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001887238 | T1 Policy | 5 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220001896185 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Simon White | IMGA222050 | BOLLO BRIDGE ROAD | 220001896185 | T1 Policy | 65.7 | Policy | 6 | CI | 47 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.0879 | 0 | CMO West 1 | IMGA222050 | BOLLO BRIDGE ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO FELLOWS, Stephen | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510909429 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Paul Burke | IMGA222075 | SELBY GARDENS | 510909429 | T1 Policy | 13.4 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.072 | 0 | CMO West 1 | IMGA222075 | SELBY GARDENS | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510822776 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Darren Smith | IMGA222398 | DRAYTON GREEN | 510822776 | T1 Policy | 56 | Policy | 150 | DI | 34 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.904 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WALKER, Ross | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510872819 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Darren Smith | IMGA222172 | MANOR WAY | 510872819 | T1 Policy | 0 | Policy | 6 | CI | -53 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT |  | tRIIO SMITH, Bradley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510872821 | CMO | CMO West 1 | August | 22 | A | Trevor Trent | Darren Smith | IMGA222172 | MANOR WAY | 510872821 | T1 Policy | 10.6 | Policy | 6 | CI | 53 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5618 | 0 | CMO West 1 | IMGA222172 | MANOR WAY | Harrow Council | West 1 | FALSE |  | KLT |  | tRIIO SMITH, Bradley | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510871155 | CMO | CMO West 1 | September | 23 | A | Gary Conway | Dominic St. John | IMGA222044 | LYON PARK AVENUE | 510871155 | T1 Policy | 42.9 | Policy | 6 | DI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.287 | 0 | CMO West 1 | IMGA222044 | LYON PARK AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO BOORE, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510822776 | CMO | CMO West 1 | September | 23 | A | Gary Conway | Darren Smith | IMGA222398 | DRAYTON GREEN | 510822776 | T1 Policy | 56 | Policy | 150 | DI | 78 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.368 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
620654351 | CMO | CMO West 1 | September | 23 | A | Gary Conway | Darren Smith | IMGA222398 | DRAYTON GREEN | 620654351 | T1 Policy | 5 | Policy | 100 | DI | 5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.025 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510784731 | CMO | CMO West 1 | September | 23 | A | Peter Giannini | Marc Alexander | IMGA222026 | ATHERTON STREET | 510784731 | T1 Policy | 115.4 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8078 | 0 | CMO West 1 | IMGA222026 | ATHERTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Terra Firma | T1 SECONDARY | CMO KULZCEWSK, Pawel | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510930040 | CMO | CMO West 1 | September | 23 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE DRIVE | 510930040 | T1 Policy | 13 | Policy | 4 | SI | 43 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.559 | 0 | CMO West 1 | IMGA222210 | VICARAGE DRIVE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO CANT, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510909236 | CMO | CMO West 1 | September | 23 | A | Peter Giannini | Mick Bradley | IMGA222214 | SECOND AVENUE | 510909236 | T1 Policy | 26.2 | Policy | 4 | CI | 20 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.524 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510932686 | CMO | CMO West 1 | September | 23 | A | Peter Giannini | Mick Bradley | IMGA222225 | KNELLER ROAD | 510932686 | T1 PAST | 301.9 | Policy | 4 | DI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 24.152 | 0 | CMO West 1 | IMGA222225 | KNELLER ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE | PAST | Direct Mole | T1 PAST | CMO CANT, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510781827 | CMO | CMO West 1 | September | 23 | A | Roger Fearn | Lee Blackmore | IMGA222184 | AMESBURY ROAD | 510781827 | T1 Policy | 7.9 | Policy | 6 | SI | 44 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3476 | 0 | CMO West 1 | IMGA222184 | AMESBURY ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | CMO MEAR KLT, Rob | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510873964 | CMO | CMO West 1 | September | 23 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | 510873964 | T1 Policy | 6.8 | Policy | 6 | SI | 39 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2652 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510915443 | CMO | CMO West 1 | September | 23 | A | Roger Fearn | Lee Blackmore | IMGA222191 | STAINES ROAD | 510915443 | T1 Policy | 5.1 | Policy | 4 | CI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.612 | 0 | CMO West 1 | IMGA222191 | STAINES ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510884088 | CMO | CMO West 1 | September | 23 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 510884088 | T1 Policy | 59.5 | Policy | 8 | CI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.165 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
606689460 | CMO | CMO West 1 | September | 23 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 606689460 | T1 Policy | 10.8 | Policy | 8 | CI | 3 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0324 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
612943627 | CMO | CMO West 1 | September | 23 | A | Trevor Trent | Simon White | IMGA222074 | NORTH ROAD | 612943627 | T1 Policy | 4.4 | Policy | 4 | CI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0176 | 0 | CMO West 1 | IMGA222074 | NORTH ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510893127 | CMO | CMO West 1 | September | 23 | A | Trevor Trent | Darren Smith | IMGA222162 | PINNER VIEW | 510893127 | T1 Policy | 2.4 | Policy | 8 | CI | 78 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1872 | 0 | CMO West 1 | IMGA222162 | PINNER VIEW | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510839137 | CMO | CMO West 1 | September | 24 | A | Gary Conway | Simon White | IMGA222054 | Gordon Road | 510839137 | T1 PAST | 416.6 | Policy | 100 | DI | 95 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 39.577 | 0 | CMO West 1 | IMGA222054 | Gordon Road | Ealing Council | West 1 | FALSE | PAST | KLT | T1 PAST | tRIIO LEGGATT, Steve | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
220000478712 | CMO | CMO West 1 | September | 24 | A | Gary Conway | Dominic St. John | IMGA222393 | DOLLIS HILL LANE | 220000478712 | T1 Policy | 50 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5 | 0 | CMO West 1 | IMGA222393 | DOLLIS HILL LANE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
627854023 | CMO | CMO West 1 | September | 24 | A | Gary Conway | Simon White | IMGA222400 | SUTHERLAND AVENUE | 627854023 | T1 Policy | 24 | Policy | 4 | CI | 147 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.528 | 0 | CMO West 1 | IMGA222400 | SUTHERLAND AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510930040 | CMO | CMO West 1 | September | 24 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE DRIVE | 510930040 | T1 Policy | 13 | Policy | 4 | SI | 29 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.377 | 0 | CMO West 1 | IMGA222210 | VICARAGE DRIVE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO MCKENDRICK, Alex | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510930041 | CMO | CMO West 1 | September | 24 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE DRIVE | 510930041 | T1 Policy | 27.5 | Policy | 4 | SI | 29 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7975 | 0 | CMO West 1 | IMGA222210 | VICARAGE DRIVE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO MCKENDRICK, Alex | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510820299 | CMO | CMO West 1 | September | 24 | A | Peter Giannini | Mick Bradley | IMGA222213 | DEFOE AVENUE | 510820299 | T1 Policy | 8.5 | Policy | 4 | CI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.068 | 0 | CMO West 1 | IMGA222213 | DEFOE AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO CANT, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510909236 | CMO | CMO West 1 | September | 24 | A | Peter Giannini | Mick Bradley | IMGA222214 | SECOND AVENUE | 510909236 | T1 Policy | 26.2 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.31 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510783094 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 510783094 | T1 PAST | 337.8 | Policy | 4 | DI | 90 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 30.402 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE | PAST | DPF | T1 PAST | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510783095 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 510783095 | T1 Policy | 0 | Policy | 4 | DI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
220001187038 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Ben Noble | IMGA222151 | ETHELDEN ROAD | 220001187038 | T1 Policy | 85.6 | Policy | 4 | DI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.0232 | 0 | CMO West 1 | IMGA222151 | ETHELDEN ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510824803 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Lee Blackmore | IMGA222184 | EASTBOURNE ROAD | 510824803 | T1 Policy | 7.5 | Policy | 4 | SI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4725 | 0 | CMO West 1 | IMGA222184 | EASTBOURNE ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510914534 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Lee Blackmore | IMGA222191 | SPINNEY DRIVE | 510914534 | T1 Policy | 8.8 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0264 | 0 | CMO West 1 | IMGA222191 | SPINNEY DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SMITH KLT, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510914535 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Lee Blackmore | IMGA222191 | SPINNEY DRIVE | 510914535 | T1 Policy | 7.9 | Policy | 4 | CI | 23 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1817 | 0 | CMO West 1 | IMGA222191 | SPINNEY DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SMITH KLT, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510915443 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Lee Blackmore | IMGA222191 | STAINES ROAD | 510915443 | T1 Policy | 5.1 | Policy | 8 | CI | 75 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3825 | 0 | CMO West 1 | IMGA222191 | STAINES ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510969517 | CMO | CMO West 1 | September | 24 | A | Roger Fearn | Lee Blackmore | IMGA222191 | WEST VIEW | 510969517 | T1 Policy | 17.9 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.79 | 0 | CMO West 1 | IMGA222191 | WEST VIEW | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510838948 | CMO | CMO West 1 | September | 24 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | CI | 30 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 9.9 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | tRIIO BLAKE, Aaron | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | CI | T2A | September
510946562 | CMO | CMO West 1 | September | 24 | A | Trevor Trent | Darren Smith | IMGA222179 | LEAVESDEN ROAD | 510946562 | T1 Policy | 28.9 | Policy | 100 | DI | 62 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7918 | 0 | CMO West 1 | IMGA222179 | LEAVESDEN ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510946563 | CMO | CMO West 1 | September | 24 | A | Trevor Trent | Darren Smith | IMGA222179 | LEAVESDEN ROAD | 510946563 | T1 Policy | 114.6 | Policy | 100 | DI | 172 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 19.7112 | 0 | CMO West 1 | IMGA222179 | LEAVESDEN ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510824655 | CMO | CMO West 1 | September | 25 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 510824655 | T1 Policy | 14.3 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.43 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510930040 | CMO | CMO West 1 | September | 25 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE DRIVE | 510930040 | T1 Policy | 13 | Policy | 4 | SI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.338 | 0 | CMO West 1 | IMGA222210 | VICARAGE DRIVE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CSE GREEN, Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510820299 | CMO | CMO West 1 | September | 25 | A | Peter Giannini | Mick Bradley | IMGA222213 | DEFOE AVENUE | 510820299 | T1 Policy | 8.5 | Policy | 4 | SI | 23 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1955 | 0 | CMO West 1 | IMGA222213 | DEFOE AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO CANT, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510909236 | CMO | CMO West 1 | September | 25 | A | Peter Giannini | Mick Bradley | IMGA222214 | SECOND AVENUE | 510909236 | T1 Policy | 26.2 | Policy | 4 | CI | 36 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9432 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510783095 | CMO | CMO West 1 | September | 25 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 510783095 | T1 Policy | 0 | Policy | 4 | DI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510914535 | CMO | CMO West 1 | September | 25 | A | Roger Fearn | Lee Blackmore | IMGA222191 | SPINNEY DRIVE | 510914535 | T1 Policy | 7.9 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.474 | 0 | CMO West 1 | IMGA222191 | SPINNEY DRIVE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO SMITH KLT, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510969074 | CMO | CMO West 1 | September | 25 | A | Roger Fearn | Lee Blackmore | IMGA222203 | WEST WAY | 510969074 | T1 Policy | 5.4 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.054 | 0 | CMO West 1 | IMGA222203 | WEST WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510954500 | CMO | CMO West 1 | September | 25 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510954500 | T1 Policy | 2.8 | Policy | 4 | DI | 38 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1064 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO BLAKE, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510781827 | CMO | CMO West 1 | September | 25 | A | Roger Fearn | Lee Blackmore | IMGA222184 | AMESBURY ROAD | 510781827 | T1 Policy | 7.9 | Policy | 6 | CI | 37 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2923 | 0 | CMO West 1 | IMGA222184 | AMESBURY ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | CMO MEAR KLT, Rob | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510969075 | CMO | CMO West 1 | September | 25 | A | Roger Fearn | Lee Blackmore | IMGA222203 | WEST WAY | 510969075 | T1 Policy | 3.4 | Policy | 6 | CI | 243 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8262 | 0 | CMO West 1 | IMGA222203 | WEST WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510822776 | CMO | CMO West 1 | September | 25 | A | Gary Conway | Darren Smith | IMGA222398 | DRAYTON GREEN | 510822776 | T1 Policy | 56 | Policy | 150 | DI | 78 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.368 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO WALKER, Ross | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510813649 | CMO | CMO West 1 | September | 26 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 510813649 | T1 Policy | 6.4 | Policy | 4 | SI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.12 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510968698 | CMO | CMO West 1 | September | 26 | A | Gary Conway | Paul Burke | IMGA222084 | ARDEN ROAD | 510968698 | T1 PAST | 301.1 | Policy | 4 | DI | 39 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.7429 | 0 | CMO West 1 | IMGA222084 | ARDEN ROAD | Ealing Council | West 1 | FALSE | PAST | KLT | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510822775 | CMO | CMO West 1 | September | 26 | A | Gary Conway | Darren Smith | IMGA222398 | DRAYTON GREEN | 510822775 | T1 Policy | 15.5 | Policy | 100 | DI | 17 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2635 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510969075 | CMO | CMO West 1 | September | 26 | A | Roger Fearn | Lee Blackmore | IMGA222203 | WEST WAY | 510969075 | T1 Policy | 3.4 | Policy | 6 | CI | 200 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.68 | 0 | CMO West 1 | IMGA222203 | WEST WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510798461 | CMO | CMO West 1 | September | 26 | A | TBA - Lon | Marc Alexander | IMGA222028 | BROUGHTON STREET | 510798461 | T1 Policy | 6.1 | Policy | 8 | SI | 241 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4701 | 0 | CMO West 1 | IMGA222028 | BROUGHTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO MCKENDRICK, Alex | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510893130 | CMO | CMO West 1 | September | 26 | A | Trevor Trent | Darren Smith | IMGA222162 | PINNER VIEW | 510893130 | T1 Policy | 2.5 | Policy | 8 | CI | 125 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3125 | 0 | CMO West 1 | IMGA222162 | PINNER VIEW | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | September
510922213 | CMO | CMO West 1 | September | 26 | A | Trevor Trent | Darren Smith | IMGA222167 | UXBRIDGE ROAD | 510922213 | T1 Policy | 0.9 | Policy | 8 | SI | 51 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0459 | 0 | CMO West 1 | IMGA222167 | UXBRIDGE ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510922214 | CMO | CMO West 1 | September | 26 | A | Trevor Trent | Darren Smith | IMGA222167 | UXBRIDGE ROAD | 510922214 | T1 Policy | 0 | Policy | 8 | SI | 83 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222167 | UXBRIDGE ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 ENM CANDIDATE | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510922217 | CMO | CMO West 1 | September | 26 | A | Trevor Trent | Darren Smith | IMGA222167 | UXBRIDGE ROAD | 510922217 | Condition | 0 | Non Policy | 8 | ST | 24 | inch | 8inch | Abandonment 8” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222167 | UXBRIDGE ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 CONNECTED | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Non Policy | Tier 1 | ST | ST LP 8" | September
510922218 | CMO | CMO West 1 | September | 26 | A | Trevor Trent | Darren Smith | IMGA222167 | UXBRIDGE ROAD | 510922218 | T1 Policy | 2.2 | Policy | 8 | SI | 99 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2178 | 0 | CMO West 1 | IMGA222167 | UXBRIDGE ROAD | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO SMITH, Bradley | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510838948 | CMO | CMO West 1 | September | 26 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | CI | 96 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 31.68 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | tRIIO BLAKE, Aaron | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | CI | T2A | September
- | CMO | CMO West 1 | September | 26 | A | Roger Fearn | Lee Blackmore | IMGA222184 | MARLBOROUGH ROAD | - | Condition | 0 | Non Policy | 2 | ST | 20 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222184 | MARLBOROUGH ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO MEAR KLT, Rob | #N/A | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | September
510813649 | CMO | CMO West 1 | September | 27 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 510813649 | T1 Policy | 6.4 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.768 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510847889 | CMO | CMO West 1 | September | 27 | A | Gary Conway | Simon White | IMGA222069 | HEARN RISE | 510847889 | T1 Policy | 9.3 | Policy | 4 | SI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5859 | 0 | CMO West 1 | IMGA222069 | HEARN RISE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510847890 | CMO | CMO West 1 | September | 27 | A | Gary Conway | Simon White | IMGA222069 | HEARN RISE | 510847890 | T1 Policy | 17.1 | Policy | 4 | SI | 62 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0602 | 0 | CMO West 1 | IMGA222069 | HEARN RISE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510822777 | CMO | CMO West 1 | September | 27 | A | Gary Conway | Darren Smith | IMGA222398 | DRAYTON GREEN | 510822777 | T1 Policy | 13 | Policy | 150 | DI | 96 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.248 | 0 | CMO West 1 | IMGA222398 | DRAYTON GREEN | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510909237 | CMO | CMO West 1 | September | 27 | A | Peter Giannini | Mick Bradley | IMGA222214 | SECOND AVENUE | 510909237 | T1 Policy | 20.8 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.04 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510824806 | CMO | CMO West 1 | September | 27 | A | Roger Fearn | Lee Blackmore | IMGA222184 | EASTBOURNE ROAD | 510824806 | T1 Policy | 18.5 | Policy | 6 | CI | 97 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7945 | 0 | CMO West 1 | IMGA222184 | EASTBOURNE ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO MEAR KLT, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510969074 | CMO | CMO West 1 | September | 27 | A | Roger Fearn | Lee Blackmore | IMGA222203 | WEST WAY | 510969074 | T1 Policy | 5.4 | Policy | 4 | CI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.08 | 0 | CMO West 1 | IMGA222203 | WEST WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001617737 | CMO | CMO West 1 | October | 28 | A | Gary Conway | Simon White | IMGA222069 | IRVING AVENUE | 220001617737 | T1 Policy | 1.5 | Policy | 6 | SI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.225 | 0 | CMO West 1 | IMGA222069 | IRVING AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510968698 | CMO | CMO West 1 | October | 28 | A | Gary Conway | Paul Burke | IMGA222084 | ARDEN ROAD | 510968698 | T1 PAST | 301.1 | Policy | 4 | DI | 7.5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2583 | 0 | CMO West 1 | IMGA222084 | ARDEN ROAD | Ealing Council | West 1 | FALSE | PAST | KLT | T1 PAST | CMO LAFLEUR, Ricky | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510930526 | CMO | CMO West 1 | October | 28 | A | Gary Conway | Dominic St. John | IMGA222409 | VICTORIA ROAD | 510930526 | T1 Policy | 6 | Policy | 8 | CI | 85 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO West 1 | IMGA222409 | VICTORIA ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 CBA | tRIIO BOORE, Darren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510824655 | CMO | CMO West 1 | October | 28 | A | Peter Giannini | Mick Bradley | IMGA222210 | EAST SHEEN AVENUE | 510824655 | T1 Policy | 14.3 | Policy | 4 | CI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.5025 | 0 | CMO West 1 | IMGA222210 | EAST SHEEN AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510909237 | CMO | CMO West 1 | October | 28 | A | Peter Giannini | Mick Bradley | IMGA222214 | SECOND AVENUE | 510909237 | T1 Policy | 20.8 | Policy | 4 | CI | 72 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4976 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510831876 | CMO | CMO West 1 | October | 28 | A | Peter Giannini | Marc Alexander | IMGA222221 | FIELDING AVENUE | 510831876 | T1 Policy | 9.6 | Policy | 4 | CI | 94 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9024 | 0 | CMO West 1 | IMGA222221 | FIELDING AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CSE GREEN, Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510942103 | CMO | CMO West 1 | October | 28 | A | Roger Fearn | Lee Blackmore | IMGA222193 | WORTON WAY | 510942103 | T1 Policy | 4 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6 | 0 | CMO West 1 | IMGA222193 | WORTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510969074 | CMO | CMO West 1 | October | 28 | A | Roger Fearn | Lee Blackmore | IMGA222203 | WEST WAY | 510969074 | T1 Policy | 5.4 | Policy | 4 | CI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.08 | 0 | CMO West 1 | IMGA222203 | WEST WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510798461 | CMO | CMO West 1 | October | 28 | A | TBA - Lon | Marc Alexander | IMGA222028 | BROUGHTON STREET | 510798461 | T1 Policy | 6.1 | Policy | 8 | CI | 22 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1342 | 0 | CMO West 1 | IMGA222028 | BROUGHTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO MCKENDRICK, Alex | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510802280 | CMO | CMO West 1 | October | 28 | A | Trevor Trent | Darren Smith | IMGA222173 | CANNON LANE | 510802280 | T1 Policy | 31 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1 | 0 | CMO West 1 | IMGA222173 | CANNON LANE | Harrow Council | West 1 | FALSE |  | KLT | T1 CBA | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510838948 | CMO | CMO West 1 | October | 28 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | DI | 200 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 66 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | tRIIO BLAKE, Aaron | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | October
510813650 | CMO | CMO West 1 | October | 29 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 510813650 | T1 Policy | 14.6 | Policy | 4 | SI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0804 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510828909 | CMO | CMO West 1 | October | 29 | A | Roger Fearn | Ben Noble | IMGA222151 | ETHELDEN ROAD | 510828909 | T1 Policy | 59.2 | Policy | 4 | DI | 96 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.6832 | 0 | CMO West 1 | IMGA222151 | ETHELDEN ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510919686 | CMO | CMO West 1 | October | 29 | A | Roger Fearn | Lee Blackmore | IMGA222203 | SUTTON SQUARE | 510919686 | T1 Policy | 6.4 | Policy | 4 | CI | 178 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1392 | 0 | CMO West 1 | IMGA222203 | SUTTON SQUARE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510942103 | CMO | CMO West 1 | October | 29 | A | Roger Fearn | Lee Blackmore | IMGA222193 | WORTON WAY | 510942103 | T1 Policy | 4 | Policy | 4 | CI | 163 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.652 | 0 | CMO West 1 | IMGA222193 | WORTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510969074 | CMO | CMO West 1 | October | 29 | A | Roger Fearn | Lee Blackmore | IMGA222203 | WEST WAY | 510969074 | T1 Policy | 5.4 | Policy | 4 | CI | 22 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1188 | 0 | CMO West 1 | IMGA222203 | WEST WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510781827 | CMO | CMO West 1 | October | 29 | A | Roger Fearn | Lee Blackmore | IMGA222184 | AMESBURY ROAD | 510781827 | T1 Policy | 7.9 | Policy | 6 | SI | 25 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1975 | 0 | CMO West 1 | IMGA222184 | AMESBURY ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | CMO MEAR KLT, Rob | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510802305 | CMO | CMO West 1 | October | 29 | A | Trevor Trent | Darren Smith | IMGA222173 | CANNON LANE | 510802305 | T1 Policy | 6.6 | Policy | 6 | CI | 200 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.32 | 0 | CMO West 1 | IMGA222173 | CANNON LANE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510831877 | CMO | CMO West 1 | October | 29 | A | Peter Giannini | Marc Alexander | IMGA222221 | FIELDING AVENUE | 510831877 | T1 Policy | 7.8 | Policy | 6 | CI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0234 | 0 | CMO West 1 | IMGA222221 | FIELDING AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO SISSON, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510930161 | CMO | CMO West 1 | October | 29 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE ROAD | 510930161 | T1 Policy | 6.6 | Policy | 6 | CI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0924 | 0 | CMO West 1 | IMGA222210 | VICARAGE ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
220001617737 | CMO | CMO West 1 | October | 29 | A | Gary Conway | Simon White | IMGA222069 | IRVING AVENUE | 220001617737 | T1 Policy | 1.5 | Policy | 6 | SI | 138 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.207 | 0 | CMO West 1 | IMGA222069 | IRVING AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510930161 | CMO | CMO West 1 | October | 29 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE ROAD | 510930161 | T1 Policy | 6.6 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0396 | 0 | CMO West 1 | IMGA222210 | VICARAGE ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510798461 | CMO | CMO West 1 | October | 29 | A | TBA - Lon | Marc Alexander | IMGA222028 | BROUGHTON STREET | 510798461 | T1 Policy | 6.1 | Policy | 8 | CI | 30 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.183 | 0 | CMO West 1 | IMGA222028 | BROUGHTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO MCKENDRICK, Alex | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510893130 | CMO | CMO West 1 | October | 29 | A | Trevor Trent | Darren Smith | IMGA222162 | PINNER VIEW | 510893130 | T1 Policy | 2.5 | Policy | 8 | CI | 85 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2125 | 0 | CMO West 1 | IMGA222162 | PINNER VIEW | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CAULFIELD, Pat | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510930526 | CMO | CMO West 1 | October | 29 | A | Gary Conway | Dominic St. John | IMGA222409 | VICTORIA ROAD | 510930526 | T1 Policy | 6 | Policy | 8 | CI | 65 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.39 | 0 | CMO West 1 | IMGA222409 | VICTORIA ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 CBA | tRIIO BOORE, Darren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
220000478712 | CMO | CMO West 1 | October | 29 | A | Gary Conway | Dominic St. John | IMGA222393 | DOLLIS HILL LANE | 220000478712 | T1 Policy | 50 | Policy | 8 | CI | 245 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 12.25 | 0 | CMO West 1 | IMGA222393 | DOLLIS HILL LANE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO DAWSON, Trevor | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510838948 | CMO | CMO West 1 | October | 29 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | DI | 120 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 39.6 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | tRIIO BLAKE, Aaron | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | October
633235248 | CMO | CMO West 1 | October | 29 | A | Gary Conway | Darren Smith | IMGA222398 | SUTHERLAND ROAD | 633235248 | T1 Policy | 169 | Policy | 100 | DI | 44 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.436 | 0 | CMO West 1 | IMGA222398 | SUTHERLAND ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510856686 | CMO | CMO West 1 | October | 30 | A | Gary Conway | Simon White | IMGA222069 | IRVING AVENUE | 510856686 | T1 Policy | 5.5 | Policy | 4 | SI | 43 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2365 | 0 | CMO West 1 | IMGA222069 | IRVING AVENUE | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510968698 | CMO | CMO West 1 | October | 30 | A | Gary Conway | Paul Burke | IMGA222084 | ARDEN ROAD | 510968698 | T1 PAST | 301.1 | Policy | 4 | DI | 46 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.8506 | 0 | CMO West 1 | IMGA222084 | ARDEN ROAD | Ealing Council | West 1 | FALSE | PAST | KLT | T1 PAST | CMO CARTY KLT, Gavin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510913292 | CMO | CMO West 1 | October | 30 | A | Gary Conway | Dominic St. John | IMGA222394 | SOUTHVIEW AVENUE | 510913292 | T1 Policy | 6 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.42 | 0 | CMO West 1 | IMGA222394 | SOUTHVIEW AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO PARKER, Terry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510930161 | CMO | CMO West 1 | October | 30 | A | Peter Giannini | Mick Bradley | IMGA222210 | VICARAGE ROAD | 510930161 | T1 Policy | 6.6 | Policy | 6 | CI | 56 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3696 | 0 | CMO West 1 | IMGA222210 | VICARAGE ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510831877 | CMO | CMO West 1 | October | 30 | A | Peter Giannini | Marc Alexander | IMGA222221 | FIELDING AVENUE | 510831877 | T1 Policy | 7.8 | Policy | 6 | CI | 57 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4446 | 0 | CMO West 1 | IMGA222221 | FIELDING AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO SISSON, Darren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510783095 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 510783095 | T1 Policy | 0 | Policy | 4 | DI | 24 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
611306104 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Ben Noble | IMGA222151 | ARMINGER ROAD | 611306104 | T1 Policy | 5.6 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0168 | 0 | CMO West 1 | IMGA222151 | ARMINGER ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
220001187020 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Ben Noble | IMGA222151 | INGERSOLL ROAD | 220001187020 | T1 Policy | 27.3 | Policy | 4 | DI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0546 | 0 | CMO West 1 | IMGA222151 | INGERSOLL ROAD | Hammersmith and Fulham London Borough Council | West 1 | FALSE |  | DPF | T1 SECONDARY | CMO HOXHAJ, Samedin | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510781827 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Lee Blackmore | IMGA222184 | AMESBURY ROAD | 510781827 | T1 Policy | 7.9 | Policy | 6 | SI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.395 | 0 | CMO West 1 | IMGA222184 | AMESBURY ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | CMO MEAR KLT, Rob | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510942104 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Lee Blackmore | IMGA222193 | WORTON WAY | 510942104 | T1 Policy | 6.1 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.915 | 0 | CMO West 1 | IMGA222193 | WORTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510919686 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Lee Blackmore | IMGA222203 | SUTTON SQUARE | 510919686 | T1 Policy | 6.4 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.384 | 0 | CMO West 1 | IMGA222203 | SUTTON SQUARE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510919687 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Lee Blackmore | IMGA222203 | SUTTON SQUARE | 510919687 | T1 Policy | 7 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.28 | 0 | CMO West 1 | IMGA222203 | SUTTON SQUARE | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510919733 | CMO | CMO West 1 | October | 30 | A | Roger Fearn | Lee Blackmore | IMGA222203 | SUTTON WAY | 510919733 | T1 Policy | 7.8 | Policy | 4 | CI | 90 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.702 | 0 | CMO West 1 | IMGA222203 | SUTTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510838948 | CMO | CMO West 1 | October | 30 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | DI | 96 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 31.68 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | tRIIO BLAKE, Aaron | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | October
220001740655 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001740655 | Condition | 0 | Non Policy | 1 | ST | 3 | inch | 1inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | <=3” | 1 |  | Non Policy | Tier 1 | ST | ST LP <=3" | October
220001740656 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001740656 | Condition | 0 | Non Policy | 1 | ST | 3 | inch | 1inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | <=3” | 1 |  | Non Policy | Tier 1 | ST | ST LP <=3" | October
220001741015 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001741015 | Condition | 0 | Non Policy | 1 | ST | 3 | inch | 1inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | <=3” | 1 |  | Non Policy | Tier 1 | ST | ST LP <=3" | October
220001741020 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001741020 | Condition | 0 | Non Policy | 1 | ST | 3 | inch | 1inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | <=3” | 1 |  | Non Policy | Tier 1 | ST | ST LP <=3" | October
220001740717 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001740717 | Condition | 0 | Non Policy | 2 | ST | 4 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
220001741027 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001741027 | Condition | 0 | Non Policy | 2 | ST | 2 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
220001748054 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 220001748054 | Condition | 0 | Non Policy | 2 | ST | 3 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 CONNECTED | CMO ANTHONY SNR, Russell | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
510813649 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Simon White | IMGA222069 | COMPTON CRESCENT | 510813649 | T1 Policy | 6.4 | Policy | 4 | SI | 52 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3328 | 0 | CMO West 1 | IMGA222069 | COMPTON CRESCENT | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO ANTHONY SNR, Russell | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510832392 | CMO | CMO West 1 | October | 31 | A | Peter Giannini | Wayne Passingham | IMGA222214 | FIRST AVENUE | 510832392 | T1 Policy | 21.5 | Policy | 4 | CI | 22 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.473 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510832393 | CMO | CMO West 1 | October | 31 | A | Peter Giannini | Wayne Passingham | IMGA222214 | FIRST AVENUE | 510832393 | T1 Policy | 21.6 | Policy | 4 | CI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1296 | 0 | CMO West 1 | IMGA222214 | FIRST AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | tRIIO SEAMAN, Ryan (D MOLE) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510909237 | CMO | CMO West 1 | October | 31 | A | Peter Giannini | Wayne Passingham | IMGA222214 | SECOND AVENUE | 510909237 | T1 Policy | 20.8 | Policy | 4 | CI | 138 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.8704 | 0 | CMO West 1 | IMGA222214 | SECOND AVENUE | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510913292 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Dominic St. John | IMGA222394 | SOUTHVIEW AVENUE | 510913292 | T1 Policy | 6 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.36 | 0 | CMO West 1 | IMGA222394 | SOUTHVIEW AVENUE | Brent Council | West 1 | FALSE |  | SQS | T1 SECONDARY | tRIIO PARKER, Terry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510919733 | CMO | CMO West 1 | October | 31 | A | Roger Fearn | Lee Blackmore | IMGA222203 | SUTTON WAY | 510919733 | T1 Policy | 7.8 | Policy | 4 | CI | 90 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.702 | 0 | CMO West 1 | IMGA222203 | SUTTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510942103 | CMO | CMO West 1 | October | 31 | A | Roger Fearn | Lee Blackmore | IMGA222193 | WORTON WAY | 510942103 | T1 Policy | 4 | Policy | 4 | CI | 22 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.088 | 0 | CMO West 1 | IMGA222193 | WORTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510942104 | CMO | CMO West 1 | October | 31 | A | Roger Fearn | Lee Blackmore | IMGA222193 | WORTON WAY | 510942104 | T1 Policy | 6.1 | Policy | 4 | CI | 140 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.854 | 0 | CMO West 1 | IMGA222193 | WORTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO TAYLOR KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
633235248 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Darren Smith | IMGA222398 | SUTHERLAND ROAD | 633235248 | T1 Policy | 169 | Policy | 4 | DI | 69 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.661 | 0 | CMO West 1 | IMGA222398 | SUTHERLAND ROAD | Ealing Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CLARE, Alfie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510781827 | CMO | CMO West 1 | October | 31 | A | Roger Fearn | Lee Blackmore | IMGA222184 | AMESBURY ROAD | 510781827 | T1 Policy | 7.9 | Policy | 6 | CI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.474 | 0 | CMO West 1 | IMGA222184 | AMESBURY ROAD | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 ENM CONDITION SPECIFIED | CMO MEAR KLT, Rob | LP | ENM P3 | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510802305 | CMO | CMO West 1 | October | 31 | A | Trevor Trent | Darren Smith | IMGA222173 | CANNON LANE | 510802305 | T1 Policy | 6.6 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.792 | 0 | CMO West 1 | IMGA222173 | CANNON LANE | Harrow Council | West 1 | FALSE |  | KLT | T1 SECONDARY | CMO CARTY KLT, Gavin | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510919734 | CMO | CMO West 1 | October | 31 | A | Roger Fearn | Lee Blackmore | IMGA222203 | SUTTON WAY | 510919734 | T1 Policy | 4.7 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.047 | 0 | CMO West 1 | IMGA222203 | SUTTON WAY | Hounslow London Borough Council | West 1 | FALSE |  | KLT | T1 SECONDARY | tRIIO ANTHONY, Russel Jr | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510930161 | CMO | CMO West 1 | October | 31 | A | Peter Giannini | Wayne Passingham | IMGA222210 | VICARAGE ROAD | 510930161 | T1 Policy | 6.6 | Policy | 6 | CI | 44 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2904 | 0 | CMO West 1 | IMGA222210 | VICARAGE ROAD | Richmond upon Thames London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO COX, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510798461 | CMO | CMO West 1 | October | 31 | A | TBA - Lon | Marc Alexander | IMGA222028 | BROUGHTON STREET | 510798461 | T1 Policy | 6.1 | Policy | 8 | CI | 46 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2806 | 0 | CMO West 1 | IMGA222028 | BROUGHTON STREET | Wandsworth London Borough Council | West 1 | FALSE |  | Direct Mole | T1 SECONDARY | CMO HENSLEY, Craig | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510930526 | CMO | CMO West 1 | October | 31 | A | Gary Conway | Dominic St. John | IMGA222409 | VICTORIA ROAD | 510930526 | T1 Policy | 6 | Policy | 8 | CI | 50 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3 | 0 | CMO West 1 | IMGA222409 | VICTORIA ROAD | Brent Council | West 1 | FALSE |  | SQS | T1 CBA | tRIIO BOORE, Darren | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510838948 | CMO | CMO West 1 | October | 31 | A | Trevor Trent | Darren Smith | IMGA222179 | GORDON AVENUE | 510838948 | T2 PAST | 330 | Policy | 10 | DI | 90 | inch | 10inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 29.7 | 0 | CMO West 1 | IMGA222179 | GORDON AVENUE | Harrow Council | West 1 | FALSE | PAST | KLT | T2 PAST | tRIIO BLAKE, Aaron | LP | #N/A | 10-12” | 10 |  | Policy | Tier 2 | DI | T2A | October
510916020 | CMO | CMO West 2 | April | 2 | A | Gary Conway | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916020 | T1 PAST | 0.6 | Policy | 6 | DI | 141 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0846 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510825015 | CMO | CMO West 2 | April | 2 | A | Gary Conway | TBA - Lon | IMGA222362 | EASTERN DENE | 510825015 | T1 PAST | 0.7 | Policy | 4 | DI | 190 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.133 | 0 | CMO West 2 | IMGA222362 | EASTERN DENE | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510812668 | CMO | CMO West 2 | April | 2 | A | Mario Gesner | TBA - Lon | IMGA222229 | COLLEGE AVENUE | 510812668 | T1 Policy | 24.5 | Policy | 4 | SI | 195 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.7775 | 0 | CMO West 2 | IMGA222229 | COLLEGE AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
637912711 | CMO | CMO West 2 | April | 2 | A | Mario Gesner | TBA - Lon | IMGA222229 | MEAD CLOSE | 637912711 | T1 Policy | 41.5 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6225 | 0 | CMO West 2 | IMGA222229 | MEAD CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510789607 | CMO | CMO West 2 | April | 2 | A | Mario Gesner | TBA - Lon | IMGA222242 | BEECHWOOD GARDENS | 510789607 | T1 Policy | 16.3 | Policy | 4 | SI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.26 | 0 | CMO West 2 | IMGA222242 | BEECHWOOD GARDENS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510848565 | CMO | CMO West 2 | April | 2 | A | Mark Prothero | TBA - Lon | IMGA222085 | HENLEY GARDENS | 510848565 | T1 Policy | 23.1 | Policy | 4 | SI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.6565 | 0 | CMO West 2 | IMGA222085 | HENLEY GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510948247 | CMO | CMO West 2 | April | 2 | A | Mark Prothero | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948247 | T1 Policy | 13.4 | Policy | 6 | SI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.804 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510971712 | CMO | CMO West 2 | April | 3 | A | Gary Conway | TBA - Lon | IMGA222129 | CEDAR GROVE | 510971712 | T1 Policy | 0.3 | Policy | 4 | DI | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0432 | 0 | CMO West 2 | IMGA222129 | CEDAR GROVE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510971713 | CMO | CMO West 2 | April | 3 | A | Gary Conway | TBA - Lon | IMGA222129 | CEDAR GROVE | 510971713 | T1 Policy | 0.3 | Policy | 4 | DI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0078 | 0 | CMO West 2 | IMGA222129 | CEDAR GROVE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510856872 | CMO | CMO West 2 | April | 3 | A | Gary Conway | TBA - Lon | IMGA222268 | IVINS ROAD | 510856872 | T1 Policy | 21.8 | Policy | 4 | SI | 126 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7468 | 0 | CMO West 2 | IMGA222268 | IVINS ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510849458 | CMO | CMO West 2 | April | 3 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849458 | T1 Policy | 17.7 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.77 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510937780 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222021 | WHYNSTONES ROAD | 510937780 | T1 Policy | 7.5 | Policy | 4 | DI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6375 | 0 | CMO West 2 | IMGA222021 | WHYNSTONES ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510944320 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944320 | T1 Policy | 33.7 | Policy | 4 | SI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.696 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510789607 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222242 | BEECHWOOD GARDENS | 510789607 | T1 Policy | 16.3 | Policy | 4 | CI | 92 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4996 | 0 | CMO West 2 | IMGA222242 | BEECHWOOD GARDENS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510789608 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222242 | BEECHWOOD GARDENS | 510789608 | T1 Policy | 18.1 | Policy | 4 | CI | 197 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.5657 | 0 | CMO West 2 | IMGA222242 | BEECHWOOD GARDENS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510939618 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222242 | BEECHWOOD GARDENS | 510939618 | T1 Policy | 23.6 | Policy | 4 | CI | 19 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4484 | 0 | CMO West 2 | IMGA222242 | BEECHWOOD GARDENS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510944810 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222287 | ARLINGTON ROAD | 510944810 | T1 Policy | 33 | Policy | 4 | CI | 151 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.983 | 0 | CMO West 2 | IMGA222287 | ARLINGTON ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510944811 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222287 | ARLINGTON ROAD | 510944811 | T1 Policy | 36 | Policy | 4 | CI | 39 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.404 | 0 | CMO West 2 | IMGA222287 | ARLINGTON ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510944489 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222287 | SPRINGFIELD ROAD | 510944489 | T1 Policy | 34.6 | Policy | 4 | CI | 115 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.979 | 0 | CMO West 2 | IMGA222287 | SPRINGFIELD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510796703 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222313 | BRILL CLOSE | 510796703 | T1 Policy | 0.6 | Policy | 4 | SI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.108 | 0 | CMO West 2 | IMGA222313 | BRILL CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510932012 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 510932012 | T1 Policy | 1.4 | Policy | 4 | DI | 165 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.231 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510951242 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222091 | MINET DRIVE | 510951242 | T1 Policy | 29.5 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.425 | 0 | CMO West 2 | IMGA222091 | MINET DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510951246 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222091 | MINET GARDENS | 510951246 | T1 Policy | 35.5 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.84 | 0 | CMO West 2 | IMGA222091 | MINET GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510947862 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222117 | BISHOPS CLOSE | 510947862 | T1 Policy | 21.8 | Policy | 4 | SI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.834 | 0 | CMO West 2 | IMGA222117 | BISHOPS CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
624790321 | CMO | CMO West 2 | April | 3 | A | Shane Compton | TBA - Lon | IMGA222015 | FOREST ROAD | 624790321 | T1 Policy | 64.2 | Policy | 4 | SI | 98 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.2916 | 0 | CMO West 2 | IMGA222015 | FOREST ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
220000326765 | CMO | CMO West 2 | April | 3 | A | Mario Gesner | TBA - Lon | IMGA222287 | CHESTERFIELD ROAD | 220000326765 | T1 Policy | 0 | Policy | 6 | CI | 134 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222287 | CHESTERFIELD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510947383 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222088 | ALMOND CLOSE | 510947383 | T1 Policy | 2.9 | Policy | 6 | DI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.116 | 0 | CMO West 2 | IMGA222088 | ALMOND CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO JACKMAN, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510948362 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222088 | CHESTNUT CLOSE | 510948362 | T1 PAST | 1.1 | Policy | 6 | DI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.11 | 0 | CMO West 2 | IMGA222088 | CHESTNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE | PAST | SQS | T1 PAST | tRIIO JACKMAN, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510948247 | CMO | CMO West 2 | April | 3 | A | Mark Prothero | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948247 | T1 Policy | 13.4 | Policy | 6 | SI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.005 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510838501 | CMO | CMO West 2 | April | 3 | A | Gary Conway | TBA - Lon | IMGA222137 | GOLD HILL WEST | 510838501 | T1 PAST | 1.3 | Policy | 8 | SI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.091 | 0 | CMO West 2 | IMGA222137 | GOLD HILL WEST | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | April
510886180 | CMO | CMO West 2 | April | 3 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886180 | T1 Policy | 0.5 | Policy | 100 | DI | 110 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.055 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510964481 | CMO | CMO West 2 | April | 3 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964481 | T1 Policy | 7.8 | Policy | 100 | DI | 82 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6396 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510964484 | CMO | CMO West 2 | April | 3 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964484 | T1 Policy | 22.2 | Policy | 100 | DI | 68 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5096 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510916020 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916020 | T1 PAST | 0.6 | Policy | 6 | SI | 212 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1272 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510808095 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222136 | CHILTERN HILL | 510808095 | T1 PAST | 10.9 | Policy | 8 | CI | 170 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.853 | 0 | CMO West 2 | IMGA222136 | CHILTERN HILL | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510838501 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222137 | GOLD HILL WEST | 510838501 | T1 PAST | 1.3 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.13 | 0 | CMO West 2 | IMGA222137 | GOLD HILL WEST | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | April
510856872 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222268 | IVINS ROAD | 510856872 | T1 Policy | 21.8 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.616 | 0 | CMO West 2 | IMGA222268 | IVINS ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510825015 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222362 | EASTERN DENE | 510825015 | T1 PAST | 0.7 | Policy | 4 | CI | 235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1645 | 0 | CMO West 2 | IMGA222362 | EASTERN DENE | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510847821 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222362 | HAZLEMERE VIEW | 510847821 | T1 Policy | 36.7 | Policy | 4 | CI | 264 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.6888 | 0 | CMO West 2 | IMGA222362 | HAZLEMERE VIEW | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510875230 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222362 | MAXWELL DRIVE | 510875230 | T1 Policy | 26.9 | Policy | 4 | CI | 146 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.9274 | 0 | CMO West 2 | IMGA222362 | MAXWELL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510875231 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222362 | MAXWELL DRIVE | 510875231 | T1 Policy | 33.4 | Policy | 4 | CI | 149 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.9766 | 0 | CMO West 2 | IMGA222362 | MAXWELL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510874094 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222363 | MARLOW ROAD | 510874094 | T1 PAST | 1.2 | Policy | 4 | DI | 213 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2556 | 0 | CMO West 2 | IMGA222363 | MARLOW ROAD | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510849458 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849458 | T1 Policy | 17.7 | Policy | 4 | SI | 93 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6461 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510849459 | CMO | CMO West 2 | April | 4 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 5.1 | Policy | 8 | SI | 17 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0867 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | April
510937781 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222021 | WHYNSTONES ROAD | 510937781 | T1 Policy | 16.8 | Policy | 4 | SI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.848 | 0 | CMO West 2 | IMGA222021 | WHYNSTONES ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510937782 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222021 | WHYNSTONES ROAD | 510937782 | T1 Policy | 22.2 | Policy | 6 | SI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.998 | 0 | CMO West 2 | IMGA222021 | WHYNSTONES ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510972708 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222229 | MEAD CLOSE | 510972708 | T1 Policy | 0.4 | Policy | 4 | CI | 59 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0236 | 0 | CMO West 2 | IMGA222229 | MEAD CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
637912713 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222229 | MEAD CLOSE | 637912713 | T1 Policy | 1 | Policy | 4 | CI | 159 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.159 | 0 | CMO West 2 | IMGA222229 | MEAD CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510944320 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944320 | T1 Policy | 33.7 | Policy | 4 | SI | 18 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6066 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510944321 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944321 | T1 Policy | 33 | Policy | 4 | SI | 31 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.023 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510782294 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222247 | ANTHONY WAY | 510782294 | T1 Policy | 12.9 | Policy | 6 | CI | 215 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.7735 | 0 | CMO West 2 | IMGA222247 | ANTHONY WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
220000326765 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222287 | CHESTERFIELD ROAD | 220000326765 | T1 Policy | 0 | Policy | 6 | CI | 291 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222287 | CHESTERFIELD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510944945 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222287 | FORD ROAD | 510944945 | T1 Policy | 35.2 | Policy | 4 | CI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7248 | 0 | CMO West 2 | IMGA222287 | FORD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510835618 | CMO | CMO West 2 | April | 4 | A | Mario Gesner | TBA - Lon | IMGA222340 | FURZE ROAD | 510835618 | T1 Policy | 46.9 | Policy | 4 | DI | 99 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.6431 | 0 | CMO West 2 | IMGA222340 | FURZE ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MCQUADE, Sean | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510932012 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 510932012 | T1 Policy | 1.4 | Policy | 4 | DI | 170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.238 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510947383 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222088 | ALMOND CLOSE | 510947383 | T1 Policy | 2.9 | Policy | 6 | DI | 22 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0638 | 0 | CMO West 2 | IMGA222088 | ALMOND CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510947384 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222088 | ALMOND CLOSE | 510947384 | T1 Policy | 1.6 | Policy | 6 | DI | 76 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1216 | 0 | CMO West 2 | IMGA222088 | ALMOND CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510948365 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222088 | CHESTNUT CLOSE | 510948365 | T1 Policy | 2.4 | Policy | 6 | DI | 35 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.084 | 0 | CMO West 2 | IMGA222088 | CHESTNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510951242 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222091 | MINET DRIVE | 510951242 | T1 Policy | 29.5 | Policy | 4 | CI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.9 | 0 | CMO West 2 | IMGA222091 | MINET DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510952603 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222091 | SHOWERS WAY | 510952603 | T1 Policy | 30.2 | Policy | 4 | SI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.755 | 0 | CMO West 2 | IMGA222091 | SHOWERS WAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510948247 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948247 | T1 Policy | 13.4 | Policy | 6 | SI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.804 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510951207 | CMO | CMO West 2 | April | 4 | A | Mark Prothero | TBA - Lon | IMGA222117 | MILLS CLOSE | 510951207 | T1 Policy | 12.2 | Policy | 4 | SI | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.281 | 0 | CMO West 2 | IMGA222117 | MILLS CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510886178 | CMO | CMO West 2 | April | 4 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886178 | T1 Policy | 0.3 | Policy | 100 | DI | 91 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0273 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510886180 | CMO | CMO West 2 | April | 4 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886180 | T1 Policy | 0.5 | Policy | 100 | DI | 39 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0195 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510964481 | CMO | CMO West 2 | April | 4 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964481 | T1 Policy | 7.8 | Policy | 100 | DI | 37 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2886 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510964482 | CMO | CMO West 2 | April | 4 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964482 | T1 Policy | 35.1 | Policy | 100 | DI | 63 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2113 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510928408 | CMO | CMO West 2 | April | 4 | A | Shane Compton | TBA - Lon | IMGA222404 | UFFINGTON DRIVE | 510928408 | T1 Policy | 0 | Policy | 6 | SI | 260 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222404 | UFFINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ |  | tRIIO DOMINY, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510916020 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916020 | T1 PAST | 0.6 | Policy | 6 | SI | 214 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1284 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510916024 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916024 | T1 Policy | 0.2 | Policy | 4 | SI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.016 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510808095 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222136 | CHILTERN HILL | 510808095 | T1 PAST | 10.9 | Policy | 8 | CI | 140 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.526 | 0 | CMO West 2 | IMGA222136 | CHILTERN HILL | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | April
510866588 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222136 | LINCOLN ROAD | 510866588 | T1 PAST | 26.8 | Policy | 6 | CI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.804 | 0 | CMO West 2 | IMGA222136 | LINCOLN ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510930950 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222141 | VILLAGE WAY | 510930950 | T1 PAST | 4.4 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.484 | 0 | CMO West 2 | IMGA222141 | VILLAGE WAY | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510856872 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222268 | IVINS ROAD | 510856872 | T1 Policy | 21.8 | Policy | 4 | SI | 106 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3108 | 0 | CMO West 2 | IMGA222268 | IVINS ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510849460 | CMO | CMO West 2 | April | 5 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849460 | T1 Policy | 15.5 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.55 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510944320 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944320 | T1 Policy | 33.7 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.044 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510782294 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222247 | ANTHONY WAY | 510782294 | T1 Policy | 12.9 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.516 | 0 | CMO West 2 | IMGA222247 | ANTHONY WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510834445 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222247 | FRANCIS WAY | 510834445 | T1 Policy | 31.1 | Policy | 4 | CI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.4425 | 0 | CMO West 2 | IMGA222247 | FRANCIS WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
220000326765 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222287 | CHESTERFIELD ROAD | 220000326765 | T1 Policy | 0 | Policy | 6 | CI | 198 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222287 | CHESTERFIELD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | April
510944509 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222288 | STANLEY ROAD | 510944509 | T1 Policy | 20.9 | Policy | 4 | CI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.836 | 0 | CMO West 2 | IMGA222288 | STANLEY ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510944510 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222288 | STANLEY ROAD | 510944510 | T1 Policy | 40.9 | Policy | 4 | CI | 165 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.7485 | 0 | CMO West 2 | IMGA222288 | STANLEY ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510796703 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222313 | BRILL CLOSE | 510796703 | T1 Policy | 0.6 | Policy | 4 | SI | 68 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0408 | 0 | CMO West 2 | IMGA222313 | BRILL CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510879712 | CMO | CMO West 2 | April | 5 | A | Mario Gesner | TBA - Lon | IMGA222340 | MOSSY VALE | 510879712 | T1 Policy | 34.7 | Policy | 4 | DI | 90 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.123 | 0 | CMO West 2 | IMGA222340 | MOSSY VALE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MCQUADE, Sean | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
220001743992 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001743992 | T1 Policy | 0 | Policy | 6 | DI | 175 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510948365 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222088 | CHESTNUT CLOSE | 510948365 | T1 Policy | 2.4 | Policy | 6 | DI | 137 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3288 | 0 | CMO West 2 | IMGA222088 | CHESTNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | April
510949850 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222091 | HALSWAY | 510949850 | T1 Policy | 0.6 | Policy | 4 | DI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.021 | 0 | CMO West 2 | IMGA222091 | HALSWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510951242 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222091 | MINET DRIVE | 510951242 | T1 Policy | 29.5 | Policy | 4 | CI | 57 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6815 | 0 | CMO West 2 | IMGA222091 | MINET DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510952603 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222091 | SHOWERS WAY | 510952603 | T1 Policy | 30.2 | Policy | 4 | SI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.077 | 0 | CMO West 2 | IMGA222091 | SHOWERS WAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510947463 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222117 | ATTLE CLOSE | 510947463 | T1 Policy | 16.5 | Policy | 4 | CI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0725 | 0 | CMO West 2 | IMGA222117 | ATTLE CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | April
510948247 | CMO | CMO West 2 | April | 5 | A | Mark Prothero | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948247 | T1 Policy | 13.4 | Policy | 6 | SI | 110 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.474 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | April
510964483 | CMO | CMO West 2 | April | 5 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964483 | T1 Policy | 0.5 | Policy | 100 | DI | 79 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0395 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510964485 | CMO | CMO West 2 | April | 5 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964485 | T1 Policy | 0.3 | Policy | 100 | DI | 85 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0255 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | April
510818436 | CMO | CMO West 2 | April | 5 | A | Shane Compton | TBA - Lon | IMGA222404 | CUMNOR WAY | 510818436 | T1 Policy | 60 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.2 | 0 | CMO West 2 | IMGA222404 | CUMNOR WAY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | April
510866588 | CMO | CMO West 2 | May | 6 | A | Gary Conway | TBA - Lon | IMGA222136 | LINCOLN ROAD | 510866588 | T1 PAST | 26.8 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.68 | 0 | CMO West 2 | IMGA222136 | LINCOLN ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510838501 | CMO | CMO West 2 | May | 6 | A | Gary Conway | TBA - Lon | IMGA222137 | GOLD HILL WEST | 510838501 | T1 PAST | 1.3 | Policy | 8 | SI | 85 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1105 | 0 | CMO West 2 | IMGA222137 | GOLD HILL WEST | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | May
510853887 | CMO | CMO West 2 | May | 6 | A | Gary Conway | TBA - Lon | IMGA222268 | HOLTSPUR CLOSE | 510853887 | T1 Policy | 14.9 | Policy | 4 | SI | 128 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9072 | 0 | CMO West 2 | IMGA222268 | HOLTSPUR CLOSE | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510849460 | CMO | CMO West 2 | May | 6 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849460 | T1 Policy | 15.5 | Policy | 4 | SI | 108 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.674 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
637912711 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222229 | MEAD CLOSE | 637912711 | T1 Policy | 41.5 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2905 | 0 | CMO West 2 | IMGA222229 | MEAD CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
637912713 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222229 | MEAD CLOSE | 637912713 | T1 Policy | 1 | Policy | 100 | DI | 36 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.036 | 0 | CMO West 2 | IMGA222229 | MEAD CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
637912715 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222229 | VICARAGE AVENUE | 637912715 | T1 Policy | 36.9 | Policy | 4 | SI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.642 | 0 | CMO West 2 | IMGA222229 | VICARAGE AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510943669 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222238 | CHANDOS ROAD | 510943669 | T1 Policy | 27.8 | Policy | 4 | SI | 73 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0294 | 0 | CMO West 2 | IMGA222238 | CHANDOS ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510834441 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222247 | FRANCIS WAY | 510834441 | T1 Policy | 13.5 | Policy | 6 | SI | 175 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3625 | 0 | CMO West 2 | IMGA222247 | FRANCIS WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510834443 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222247 | FRANCIS WAY | 510834443 | T1 Policy | 10.1 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.707 | 0 | CMO West 2 | IMGA222247 | FRANCIS WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510834445 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222247 | FRANCIS WAY | 510834445 | T1 Policy | 31.1 | Policy | 4 | SI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0215 | 0 | CMO West 2 | IMGA222247 | FRANCIS WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510944509 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222288 | STANLEY ROAD | 510944509 | T1 Policy | 20.9 | Policy | 4 | CI | 276 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.7684 | 0 | CMO West 2 | IMGA222288 | STANLEY ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510879711 | CMO | CMO West 2 | May | 6 | A | Mario Gesner | TBA - Lon | IMGA222340 | MOSSY VALE | 510879711 | T1 Policy | 29.4 | Policy | 4 | DI | 164 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.8216 | 0 | CMO West 2 | IMGA222340 | MOSSY VALE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MCQUADE, Sean | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001743992 | CMO | CMO West 2 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001743992 | T1 Policy | 0 | Policy | 6 | DI | 180 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510948363 | CMO | CMO West 2 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222088 | CHESTNUT CLOSE | 510948363 | T1 Policy | 2 | Policy | 6 | DI | 105 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.21 | 0 | CMO West 2 | IMGA222088 | CHESTNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510948363 | CMO | CMO West 2 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222088 | CHESTNUT CLOSE | 510948363 | T1 Policy | 2 | Policy | 8 | CI | 10 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 2 | IMGA222088 | CHESTNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | May
510953565 | CMO | CMO West 2 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222088 | WALNUT CLOSE | 510953565 | T1 Policy | 0.8 | Policy | 6 | DI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.056 | 0 | CMO West 2 | IMGA222088 | WALNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510953567 | CMO | CMO West 2 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222088 | WALNUT CLOSE | 510953567 | T1 Policy | 16.8 | Policy | 6 | SI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.512 | 0 | CMO West 2 | IMGA222088 | WALNUT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510948246 | CMO | CMO West 2 | May | 6 | A | Mark Prothero | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948246 | T1 Policy | 19.4 | Policy | 4 | CI | 315 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.111 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510971848 | CMO | CMO West 2 | May | 6 | A | Shane Compton | TBA - Lon | IMGA222005 | LONDON ROAD | 510971848 | T1 PAST | 1.1 | Policy | 8 | DI | 210 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.231 | 0 | CMO West 2 | IMGA222005 | LONDON ROAD | Bracknell Forest Borough Council | West 2 | FALSE | PAST | OMJ | T1 PAST | CMO COLLINS (OMJ), Patrick | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | May
612792438 | CMO | CMO West 2 | May | 6 | A | Shane Compton | TBA - Lon | IMGA222005 | LONDON ROAD | 612792438 | T1 Policy | 0.1 | Policy | 4 | DI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0007 | 0 | CMO West 2 | IMGA222005 | LONDON ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510886177 | CMO | CMO West 2 | May | 6 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886177 | T1 Policy | 0.3 | Policy | 100 | DI | 140 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.042 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510886180 | CMO | CMO West 2 | May | 6 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886180 | T1 Policy | 0.5 | Policy | 100 | DI | 60 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.03 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510964481 | CMO | CMO West 2 | May | 6 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964481 | T1 Policy | 7.8 | Policy | 100 | DI | 79 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6162 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510964484 | CMO | CMO West 2 | May | 6 | A | Shane Compton | TBA - Lon | IMGA222012 | SYLVANUS | 510964484 | T1 Policy | 22.2 | Policy | 100 | DI | 7 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1554 | 0 | CMO West 2 | IMGA222012 | SYLVANUS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510796703 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222313 | BRILL CLOSE | 510796703 | T1 Policy | 0.6 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.03 | 0 | CMO West 2 | IMGA222313 | BRILL CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510796704 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222313 | BRILL CLOSE | 510796704 | T1 Policy | 1.5 | Policy | 4 | SI | 226 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.339 | 0 | CMO West 2 | IMGA222313 | BRILL CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510818436 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222404 | CUMNOR WAY | 510818436 | T1 Policy | 60 | Policy | 4 | SI | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.46 | 0 | CMO West 2 | IMGA222404 | CUMNOR WAY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510849460 | CMO | CMO West 2 | May | 7 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849460 | T1 Policy | 15.5 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.55 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510852347 | CMO | CMO West 2 | May | 7 | A | Gary Conway | TBA - Lon | IMGA222139 | HILL RISE | 510852347 | T1 PAST | 15.7 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.256 | 0 | CMO West 2 | IMGA222139 | HILL RISE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510866588 | CMO | CMO West 2 | May | 7 | A | Gary Conway | TBA - Lon | IMGA222136 | LINCOLN ROAD | 510866588 | T1 PAST | 26.8 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.68 | 0 | CMO West 2 | IMGA222136 | LINCOLN ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510873554 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222247 | MARINA WAY | 510873554 | T1 Policy | 0.2 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.008 | 0 | CMO West 2 | IMGA222247 | MARINA WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510886179 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886179 | T1 Policy | 0.3 | Policy | 100 | DI | 68 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0204 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510886180 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886180 | T1 Policy | 0.5 | Policy | 100 | DI | 59 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0295 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510906069 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906069 | T1 Policy | 11.5 | Policy | 6 | CI | 210 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.415 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510916020 | CMO | CMO West 2 | May | 7 | A | Gary Conway | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916020 | T1 PAST | 0.6 | Policy | 6 | CI | 44 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0264 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510923621 | CMO | CMO West 2 | May | 7 | A | Gary Conway | TBA - Lon | IMGA222129 | THE MEADOWS | 510923621 | T1 Policy | 0.2 | Policy | 4 | CI | 220 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.044 | 0 | CMO West 2 | IMGA222129 | THE MEADOWS | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510928048 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222404 | UFFINGTON DRIVE | 510928048 | T1 Policy | 47.4 | Policy | 6 | SI | 110 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.214 | 0 | CMO West 2 | IMGA222404 | UFFINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510931586 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222404 | WALBURY | 510931586 | T1 Policy | 61.3 | Policy | 4 | SI | 56 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.4328 | 0 | CMO West 2 | IMGA222404 | WALBURY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510937781 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222021 | WHYNSTONES ROAD | 510937781 | T1 Policy | 16.8 | Policy | 4 | SI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1344 | 0 | CMO West 2 | IMGA222021 | WHYNSTONES ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510937782 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222021 | WHYNSTONES ROAD | 510937782 | T1 Policy | 22.2 | Policy | 6 | SI | 21 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4662 | 0 | CMO West 2 | IMGA222021 | WHYNSTONES ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510943669 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222238 | CHANDOS ROAD | 510943669 | T1 Policy | 27.8 | Policy | 4 | SI | 173 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.8094 | 0 | CMO West 2 | IMGA222238 | CHANDOS ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510945056 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222288 | FAIRHOLME ROAD | 510945056 | T1 Policy | 22.2 | Policy | 4 | CI | 87 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9314 | 0 | CMO West 2 | IMGA222288 | FAIRHOLME ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510947858 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222090 | BIRCHWAY | 510947858 | T1 Policy | 0.3 | Policy | 6 | DI | 175 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0525 | 0 | CMO West 2 | IMGA222090 | BIRCHWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510951056 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222088 | MANTON CLOSE | 510951056 | T1 Policy | 1 | Policy | 4 | DI | 152 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.152 | 0 | CMO West 2 | IMGA222088 | MANTON CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510972161 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222287 | CHESTERFIELD ROAD | 510972161 | T1 Policy | 20.6 | Policy | 6 | CI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1648 | 0 | CMO West 2 | IMGA222287 | CHESTERFIELD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510972212 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222288 | FAIRHOLME ROAD | 510972212 | T1 Policy | 1.7 | Policy | 4 | DI | 52 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0884 | 0 | CMO West 2 | IMGA222288 | FAIRHOLME ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
612021968 | CMO | CMO West 2 | May | 7 | A | Mario Gesner | TBA - Lon | IMGA222288 | FAIRHOLME ROAD | 612021968 | T1 PAST | 251.2 | Policy | 3 | CI | 8 | inch | 3inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0096 | 0 | CMO West 2 | IMGA222288 | FAIRHOLME ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T1 GD1 ALARP | CMO FYFFE, Ruairi | LP | ALARP | <=3” | 3 |  | Policy | Tier 1 | CI | CI/SI/DI LP <=3" | May
638088408 | CMO | CMO West 2 | May | 7 | A | Gary Conway | TBA - Lon | IMGA222129 | HIGHLAND ROAD | 638088408 | T1 PAST | 0.6 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06 | 0 | CMO West 2 | IMGA222129 | HIGHLAND ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
220001511673 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222403 | SHAFTESBURY CLOSE | 220001511673 | T1 Policy | 0 | Policy | 4 | SI | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222403 | SHAFTESBURY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220001743992 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001743992 | T1 Policy | 0 | Policy | 6 | DI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
220001743994 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001743994 | T1 Policy | 0 | Policy | 6 | DI | 135 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
220001899544 | CMO | CMO West 2 | May | 7 | A | Shane Compton | TBA - Lon | IMGA222404 | UFFINGTON DRIVE | 220001899544 | T1 Policy | 0 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222404 | UFFINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510866588 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222136 | LINCOLN ROAD | 510866588 | T1 PAST | 26.8 | Policy | 6 | CI | 130 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.484 | 0 | CMO West 2 | IMGA222136 | LINCOLN ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510969626 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222139 | HILL RISE CRESCENT | 510969626 | T1 Policy | 16.5 | Policy | 4 | SI | 132 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.178 | 0 | CMO West 2 | IMGA222139 | HILL RISE CRESCENT | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510853905 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222268 | HOLTSPUR WAY | 510853905 | T1 Policy | 20.4 | Policy | 4 | CI | 43 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8772 | 0 | CMO West 2 | IMGA222268 | HOLTSPUR WAY | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510937064 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222360 | WHITEPIT LANE | 510937064 | T1 Policy | 6.2 | Policy | 6 | SI | 136 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8432 | 0 | CMO West 2 | IMGA222360 | WHITEPIT LANE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | May
510849460 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849460 | T1 Policy | 15.5 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.55 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510882549 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882549 | T1 Policy | 24.4 | Policy | 4 | SI | 143 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.4892 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510882556 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882556 | T1 PAST | 1.2 | Policy | 4 | DI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.18 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510882555 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD ROAD | 510882555 | T1 Policy | 20.8 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.08 | 0 | CMO West 2 | IMGA222383 | NEWFIELD ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510882557 | CMO | CMO West 2 | May | 8 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD ROAD | 510882557 | T1 Policy | 20.4 | Policy | 4 | CI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.244 | 0 | CMO West 2 | IMGA222383 | NEWFIELD ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510941332 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941332 | T1 Policy | 0.2 | Policy | 100 | DI | 93 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0186 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510941336 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941336 | T1 Policy | 35.3 | Policy | 4 | SI | 48 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6944 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510791865 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222025 | BIRCH LANE | 510791865 | T1 Policy | 21.4 | Policy | 4 | SI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.819 | 0 | CMO West 2 | IMGA222025 | BIRCH LANE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510972701 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222229 | MANOR LEAZE | 510972701 | T1 Policy | 0.6 | Policy | 100 | DI | 72 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0432 | 0 | CMO West 2 | IMGA222229 | MANOR LEAZE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510972702 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222229 | MANOR LEAZE | 510972702 | T1 Policy | 0.2 | Policy | 100 | DI | 126 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0252 | 0 | CMO West 2 | IMGA222229 | MANOR LEAZE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510972703 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222229 | MANOR LEAZE | 510972703 | T1 Policy | 0.3 | Policy | 2 | DI | 24 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0072 | 0 | CMO West 2 | IMGA222229 | MANOR LEAZE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | DI | CI/SI/DI LP <=3" | May
637912715 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222229 | VICARAGE AVENUE | 637912715 | T1 Policy | 36.9 | Policy | 4 | CI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5535 | 0 | CMO West 2 | IMGA222229 | VICARAGE AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510944321 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944321 | T1 Policy | 33 | Policy | 4 | SI | 66 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.178 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO KIDBY, Steve (AGENT) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510906066 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906066 | Condition | 0 | Non Policy | 2 | ST | 30 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | May
510906069 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906069 | T1 Policy | 11.5 | Policy | 6 | CI | 166 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.909 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510895405 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222284 | Princes Road | 510895405 | T1 Policy | 17.9 | Policy | 6 | CI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.074 | 0 | CMO West 2 | IMGA222284 | Princes Road | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO CUTHBERTSON, Steve | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510945055 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222288 | FAIRHOLME ROAD | 510945055 | T1 Policy | 14.8 | Policy | 6 | CI | 225 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.33 | 0 | CMO West 2 | IMGA222288 | FAIRHOLME ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510972200 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222288 | NELSON ROAD | 510972200 | T1 Policy | 23 | Policy | 4 | CI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.025 | 0 | CMO West 2 | IMGA222288 | NELSON ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510815968 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222313 | COX GREEN ROAD | 510815968 | T1 Policy | 18.2 | Policy | 4 | SI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.729 | 0 | CMO West 2 | IMGA222313 | COX GREEN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220000754721 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222313 | COX GREEN ROAD | 220000754721 | T1 Policy | 0 | Policy | 4 | SI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222313 | COX GREEN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510796597 | CMO | CMO West 2 | May | 8 | A | Mario Gesner | TBA - Lon | IMGA222340 | BRIDLE ROAD | 510796597 | T1 Policy | 11.6 | Policy | 4 | SI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.32 | 0 | CMO West 2 | IMGA222340 | BRIDLE ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO MCQUADE, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510886176 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886176 | T1 Policy | 0.2 | Policy | 100 | DI | 62 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0124 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001743994 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001743994 | T1 Policy | 0 | Policy | 6 | DI | 165 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510947858 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222090 | BIRCHWAY | 510947858 | T1 Policy | 0.3 | Policy | 6 | DI | 233 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0699 | 0 | CMO West 2 | IMGA222090 | BIRCHWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510948245 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948245 | T1 Policy | 36.8 | Policy | 4 | DI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.368 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510948246 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948246 | T1 Policy | 19.4 | Policy | 4 | CI | 59 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1446 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510948369 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222117 | CHETWYND DRIVE | 510948369 | T1 Policy | 0.2 | Policy | 4 | DI | 134 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0268 | 0 | CMO West 2 | IMGA222117 | CHETWYND DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510845938 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845938 | T1 Policy | 25.2 | Policy | 8 | SI | 146 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.6792 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | May
510910077 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222403 | SHAFTESBURY CLOSE | 510910077 | T1 Policy | 33.1 | Policy | 4 | SI | 77 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.5487 | 0 | CMO West 2 | IMGA222403 | SHAFTESBURY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220001511673 | CMO | CMO West 2 | May | 8 | A | Shane Compton | TBA - Lon | IMGA222403 | SHAFTESBURY CLOSE | 220001511673 | T1 Policy | 0 | Policy | 4 | SI | 96 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222403 | SHAFTESBURY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
638088408 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222129 | HIGHLAND ROAD | 638088408 | T1 PAST | 0.6 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.03 | 0 | CMO West 2 | IMGA222129 | HIGHLAND ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510923621 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222129 | THE MEADOWS | 510923621 | T1 Policy | 0.2 | Policy | 4 | CI | 94 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0188 | 0 | CMO West 2 | IMGA222129 | THE MEADOWS | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
220000560479 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222129 | THE MEADOWS | 220000560479 | T1 Policy | 0 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222129 | THE MEADOWS | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510817548 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222132 | RICKMANSWORTH LANE | 510817548 | T1 Policy | 2.9 | Policy | 4 | DI | 9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0261 | 0 | CMO West 2 | IMGA222132 | RICKMANSWORTH LANE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510900913 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222132 | RICKMANSWORTH LANE | 510900913 | T1 PAST | 2.2 | Policy | 4 | CI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.44 | 0 | CMO West 2 | IMGA222132 | RICKMANSWORTH LANE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
220000486776 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222132 | RICKMANSWORTH LANE | 220000486776 | T1 Policy | 0 | Policy | 4 | SI | 9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222132 | RICKMANSWORTH LANE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510941628 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222136 | WOODSIDE HILL | 510941628 | T1 Policy | 12.9 | Policy | 6 | CI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.806 | 0 | CMO West 2 | IMGA222136 | WOODSIDE HILL | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510852347 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222139 | HILL RISE | 510852347 | T1 PAST | 15.7 | Policy | 4 | DI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.355 | 0 | CMO West 2 | IMGA222139 | HILL RISE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510930950 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222141 | VILLAGE WAY | 510930950 | T1 PAST | 4.4 | Policy | 4 | CI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.352 | 0 | CMO West 2 | IMGA222141 | VILLAGE WAY | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510849460 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849460 | T1 Policy | 15.5 | Policy | 4 | CI | 84 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.302 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510882548 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882548 | T1 PAST | 1.3 | Policy | 6 | CI | 200 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.26 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510882554 | CMO | CMO West 2 | May | 9 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD ROAD | 510882554 | T1 Policy | 1.5 | Policy | 6 | CI | 104 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.156 | 0 | CMO West 2 | IMGA222383 | NEWFIELD ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510929801 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 36.2 | Policy | 4 | CI | 139 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.0318 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510944320 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944320 | T1 Policy | 33.7 | Policy | 4 | SI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.8198 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO KIRBY, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510944321 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222238 | CLAREMONT ROAD | 510944321 | T1 Policy | 33 | Policy | 4 | SI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.165 | 0 | CMO West 2 | IMGA222238 | CLAREMONT ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO KIRBY, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510782294 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222247 | ANTHONY WAY | 510782294 | T1 Policy | 12.9 | Policy | 6 | CI | 103 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3287 | 0 | CMO West 2 | IMGA222247 | ANTHONY WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510906064 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906064 | T1 Policy | 29.2 | Policy | 6 | CI | 99 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.8908 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510906065 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906065 | T1 Policy | 86.2 | Policy | 2 | SI | 24 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0688 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | May
510972143 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222284 | CHAUCER ROAD | 510972143 | T1 Policy | 46.6 | Policy | 4 | SI | 204 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.5064 | 0 | CMO West 2 | IMGA222284 | CHAUCER ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
220000327780 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222284 | CHAUCER ROAD | 220000327780 | T1 Policy | 0 | Policy | 4 | CI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222284 | CHAUCER ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510895405 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222284 | Princes Road | 510895405 | T1 Policy | 17.9 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.895 | 0 | CMO West 2 | IMGA222284 | Princes Road | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO CUTHBERTSON, Steve | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | May
510944623 | CMO | CMO West 2 | May | 9 | A | Mario Gesner | TBA - Lon | IMGA222288 | TENNYSON ROAD | 510944623 | T1 Policy | 35.4 | Policy | 4 | CI | 246 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 8.7084 | 0 | CMO West 2 | IMGA222288 | TENNYSON ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510886180 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222006 | OCTAVIA | 510886180 | T1 Policy | 0.5 | Policy | 100 | DI | 10 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.005 | 0 | CMO West 2 | IMGA222006 | OCTAVIA | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510896364 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896364 | T1 Policy | 7.5 | Policy | 100 | DI | 85 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6375 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO COLLINS, Pat | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
220001911722 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001911722 | T1 Policy | 0 | Policy | 4 | CI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510932012 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 510932012 | T1 Policy | 1.4 | Policy | 4 | DI | 58 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0812 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510952954 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222088 | SYCAMORE AVENUE | 510952954 | T1 Policy | 17.8 | Policy | 4 | CI | 145 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.581 | 0 | CMO West 2 | IMGA222088 | SYCAMORE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | May
510947858 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222090 | BIRCHWAY | 510947858 | T1 Policy | 0.3 | Policy | 6 | DI | 202 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0606 | 0 | CMO West 2 | IMGA222090 | BIRCHWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | May
510920465 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222117 | BUCKINGHAM GROVE | 510920465 | T1 Policy | 0.4 | Policy | 4 | DI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.006 | 0 | CMO West 2 | IMGA222117 | BUCKINGHAM GROVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | May
510845933 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845933 | T1 Policy | 15.7 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.099 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510845938 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845938 | T1 Policy | 25.2 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.52 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | May
220001739211 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222403 | WELLINGTON DRIVE | 220001739211 | T1 Policy | 0 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222403 | WELLINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510941828 | CMO | CMO West 2 | May | 9 | A | Shane Compton | TBA - Lon | IMGA222403 | WOOLHAMPTON WAY | 510941828 | T1 Policy | 62 | Policy | 4 | SI | 124 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.688 | 0 | CMO West 2 | IMGA222403 | WOOLHAMPTON WAY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | May
510900913 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222132 | RICKMANSWORTH LANE | 510900913 | T1 PAST | 2.2 | Policy | 4 | SI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0264 | 0 | CMO West 2 | IMGA222132 | RICKMANSWORTH LANE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941628 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222136 | WOODSIDE HILL | 510941628 | T1 Policy | 12.9 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.29 | 0 | CMO West 2 | IMGA222136 | WOODSIDE HILL | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510852347 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222139 | HILL RISE | 510852347 | T1 PAST | 15.7 | Policy | 4 | DI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.57 | 0 | CMO West 2 | IMGA222139 | HILL RISE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510853903 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222268 | HOLTSPUR WAY | 510853903 | T1 Policy | 36.6 | Policy | 4 | CI | 83 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.0378 | 0 | CMO West 2 | IMGA222268 | HOLTSPUR WAY | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510937064 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222360 | WHITEPIT LANE | 510937064 | T1 Policy | 6.2 | Policy | 6 | CI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.496 | 0 | CMO West 2 | IMGA222360 | WHITEPIT LANE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510849459 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 5.1 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510882548 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882548 | T1 PAST | 1.3 | Policy | 6 | CI | 161 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2093 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510882551 | CMO | CMO West 2 | June | 10 | A | Gary Conway | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882551 | T1 Policy | 10.2 | Policy | 6 | CI | 159 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6218 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510941334 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941334 | T1 Policy | 37.8 | Policy | 4 | SI | 118 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.4604 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510929801 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 36.2 | Policy | 4 | CI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.353 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510861869 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222241 | KNOWLE GROVE | 510861869 | T1 Policy | 8.5 | Policy | 4 | CI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO KIRBY, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510906064 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906064 | T1 Policy | 29.2 | Policy | 8 | SI | 5 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.146 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | June
510906067 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906067 | Condition | 0 | Non Policy | 2 | ST | 31 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 ENM CONDITION CANDIDATE | tRIIO PORTER, Stuart | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | June
510972140 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222284 | CHAUCER ROAD | 510972140 | T1 Policy | 38.3 | Policy | 4 | DI | 300 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.49 | 0 | CMO West 2 | IMGA222284 | CHAUCER ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510895405 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222284 | Princes Road | 510895405 | T1 Policy | 17.9 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.895 | 0 | CMO West 2 | IMGA222284 | Princes Road | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO SMITH, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510944789 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222295 | CONDOR ROAD | 510944789 | T1 PAST | 0.6 | Policy | 4 | DI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.096 | 0 | CMO West 2 | IMGA222295 | CONDOR ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T1 PAST | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510872089 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222340 | MALVERN ROAD | 510872089 | T1 Policy | 34.1 | Policy | 4 | SI | 172 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.8652 | 0 | CMO West 2 | IMGA222340 | MALVERN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO MCQUADE, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
220000689719 | CMO | CMO West 2 | June | 10 | A | Mario Gesner | TBA - Lon | IMGA222340 | MALVERN ROAD | 220000689719 | T1 Policy | 0 | Policy | 4 | SI | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222340 | MALVERN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO MCQUADE, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
638088408 | CMO | CMO West 2 | June | 10 | A | Roger Fearn | TBA - Lon | IMGA222129 | HIGHLAND ROAD | 638088408 | T1 PAST | 0.6 | Policy | 4 | CI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO West 2 | IMGA222129 | HIGHLAND ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510896364 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896364 | T1 Policy | 7.5 | Policy | 100 | DI | 86 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.645 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510932009 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 510932009 | T1 Policy | 0.9 | Policy | 4 | DI | 83 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0747 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
220001911722 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001911722 | T1 Policy | 0 | Policy | 4 | CI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510948336 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222090 | Cherry Grove | 510948336 | T1 Policy | 0.8 | Policy | 4 | DI | 93 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0744 | 0 | CMO West 2 | IMGA222090 | Cherry Grove | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510948249 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948249 | T1 Policy | 0 | Policy | 4 | CI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510948247 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222117 | CEDARS DRIVE | 510948247 | T1 Policy | 13.4 | Policy | 6 | SI | 72 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.9648 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
607351713 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222117 | CEDARS DRIVE | 607351713 | T1 Policy | 10.9 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0218 | 0 | CMO West 2 | IMGA222117 | CEDARS DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO FLOODGATE, Ryan | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510806465 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222403 | CHEAM CLOSE | 510806465 | T1 Policy | 25 | Policy | 4 | SI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.25 | 0 | CMO West 2 | IMGA222403 | CHEAM CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510845936 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845936 | T1 Policy | 3.8 | Policy | 8 | SI | 42 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1596 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | June
510845938 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845938 | T1 Policy | 25.2 | Policy | 8 | SI | 56 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4112 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | June
220001511677 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222403 | NIGHTINGALE CRESCENT | 220001511677 | T1 Policy | 0 | Policy | 8 | SI | 2 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222403 | NIGHTINGALE CRESCENT | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | June
510941828 | CMO | CMO West 2 | June | 10 | A | Shane Compton | TBA - Lon | IMGA222403 | WOOLHAMPTON WAY | 510941828 | T1 Policy | 62 | Policy | 4 | SI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.86 | 0 | CMO West 2 | IMGA222403 | WOOLHAMPTON WAY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941331 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941331 | T1 Policy | 13.6 | Policy | 4 | SI | 117 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5912 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510791865 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222025 | BIRCH LANE | 510791865 | T1 Policy | 21.4 | Policy | 4 | SI | 99 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1186 | 0 | CMO West 2 | IMGA222025 | BIRCH LANE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510782294 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222247 | ANTHONY WAY | 510782294 | T1 Policy | 12.9 | Policy | 6 | SI | 81 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0449 | 0 | CMO West 2 | IMGA222247 | ANTHONY WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510873552 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222247 | MARINA WAY | 510873552 | T1 Policy | 10.8 | Policy | 6 | SI | 123 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3284 | 0 | CMO West 2 | IMGA222247 | MARINA WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510934916 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222250 | WESTGATE CRESCENT | 510934916 | T1 Policy | 40.6 | Policy | 4 | SI | 113 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.5878 | 0 | CMO West 2 | IMGA222250 | WESTGATE CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
220001472070 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222250 | WESTGATE CRESCENT | 220001472070 | T1 Policy | 0 | Policy | 4 | SI | 179 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222250 | WESTGATE CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510943458 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222284 | ALBERT ROAD | 510943458 | T1 Policy | 25.6 | Policy | 6 | CI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.768 | 0 | CMO West 2 | IMGA222284 | ALBERT ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO SMITH, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510972140 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222284 | CHAUCER ROAD | 510972140 | T1 Policy | 38.3 | Policy | 4 | SI | 81 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1023 | 0 | CMO West 2 | IMGA222284 | CHAUCER ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510810566 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222284 | CLARENDON ROAD | 510810566 | T1 Policy | 30.8 | Policy | 4 | SI | 117 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.6036 | 0 | CMO West 2 | IMGA222284 | CLARENDON ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510895405 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222284 | Princes Road | 510895405 | T1 Policy | 17.9 | Policy | 6 | CI | 19 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3401 | 0 | CMO West 2 | IMGA222284 | Princes Road | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO SMITH, James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510944639 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222295 | THAMES SIDE | 510944639 | T1 Policy | 17.1 | Policy | 4 | CI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.736 | 0 | CMO West 2 | IMGA222295 | THAMES SIDE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510815968 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222313 | COX GREEN ROAD | 510815968 | T1 Policy | 18.2 | Policy | 4 | SI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.546 | 0 | CMO West 2 | IMGA222313 | COX GREEN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510934709 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222313 | WESSEX WAY | 510934709 | T1 Policy | 21.1 | Policy | 4 | SI | 190 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.009 | 0 | CMO West 2 | IMGA222313 | WESSEX WAY | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510872089 | CMO | CMO West 2 | June | 11 | A | Mario Gesner | TBA - Lon | IMGA222340 | MALVERN ROAD | 510872089 | T1 Policy | 34.1 | Policy | 4 | SI | 62 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1142 | 0 | CMO West 2 | IMGA222340 | MALVERN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO MCQUADE, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
638088408 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222129 | HIGHLAND ROAD | 638088408 | T1 PAST | 0.6 | Policy | 4 | CI | 88 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0528 | 0 | CMO West 2 | IMGA222129 | HIGHLAND ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220000554464 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222129 | HIGHLAND ROAD | 220000554464 | T1 Policy | 0 | Policy | 4 | CI | 14 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222129 | HIGHLAND ROAD | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510916020 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916020 | T1 PAST | 0.6 | Policy | 6 | CI | 94 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0564 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510916024 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 510916024 | T1 Policy | 0.2 | Policy | 6 | CI | 4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0008 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220000554463 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222129 | STANLEY HILL AVENUE | 220000554463 | T1 Policy | 0 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222129 | STANLEY HILL AVENUE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO WARD, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510941628 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222136 | WOODSIDE HILL | 510941628 | T1 Policy | 12.9 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.548 | 0 | CMO West 2 | IMGA222136 | WOODSIDE HILL | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510852347 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222139 | HILL RISE | 510852347 | T1 PAST | 15.7 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.57 | 0 | CMO West 2 | IMGA222139 | HILL RISE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510849459 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 5.1 | Policy | 8 | SI | 60 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.306 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | June
510882548 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882548 | T1 PAST | 1.3 | Policy | 6 | CI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.091 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510882550 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882550 | T1 Policy | 11.3 | Policy | 6 | CI | 77 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8701 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510882551 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882551 | T1 Policy | 10.2 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0612 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510882552 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | 510882552 | T1 PAST | 2.3 | Policy | 6 | CI | 11 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0253 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510882555 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD ROAD | 510882555 | T1 Policy | 20.8 | Policy | 4 | CI | 119 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4752 | 0 | CMO West 2 | IMGA222383 | NEWFIELD ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510882557 | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD ROAD | 510882557 | T1 Policy | 20.4 | Policy | 4 | CI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.612 | 0 | CMO West 2 | IMGA222383 | NEWFIELD ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510887649 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222007 | ORION | 510887649 | T1 Policy | 0.3 | Policy | 100 | DI | 84 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0252 | 0 | CMO West 2 | IMGA222007 | ORION | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510887650 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222007 | ORION | 510887650 | T1 Policy | 0.3 | Policy | 100 | DI | 42 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0126 | 0 | CMO West 2 | IMGA222007 | ORION | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510896364 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896364 | T1 Policy | 7.5 | Policy | 100 | DI | 36 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.27 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510896366 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896366 | T1 Policy | 0.3 | Policy | 100 | DI | 86 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0258 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949849 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222090 | HALSEND | 510949849 | T1 Policy | 0.3 | Policy | 4 | DI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.021 | 0 | CMO West 2 | IMGA222090 | HALSEND | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949851 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222090 | HALSWAY | 510949851 | T1 Policy | 0.3 | Policy | 4 | DI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.012 | 0 | CMO West 2 | IMGA222090 | HALSWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949852 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222091 | HALSWAY | 510949852 | T1 Policy | 0.7 | Policy | 4 | DI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.049 | 0 | CMO West 2 | IMGA222091 | HALSWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949068 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222099 | UXBRIDGE ROAD SERVICE ROAD O/S 156-238 | 510949068 | T1 Policy | 28.8 | Policy | 4 | SI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.32 | 0 | CMO West 2 | IMGA222099 | UXBRIDGE ROAD SERVICE ROAD O/S 156-238 | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510948931 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222125 | DAWLEY AVENUE | 510948931 | T1 Policy | 0.4 | Policy | 4 | DI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510968613 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222125 | LANSDOWNE ROAD | 510968613 | T1 Policy | 1.4 | Policy | 6 | DI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.105 | 0 | CMO West 2 | IMGA222125 | LANSDOWNE ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510806465 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | CHEAM CLOSE | 510806465 | T1 Policy | 25 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.5 | 0 | CMO West 2 | IMGA222403 | CHEAM CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510830840 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | FARINGDON DRIVE | 510830840 | T1 Policy | 14.3 | Policy | 4 | SI | 53 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7579 | 0 | CMO West 2 | IMGA222403 | FARINGDON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510845932 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845932 | T1 Policy | 11.6 | Policy | 4 | SI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.986 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510845934 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845934 | T1 Policy | 8 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510845937 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845937 | T1 Policy | 6 | Policy | 4 | SI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941828 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | WOOLHAMPTON WAY | 510941828 | T1 Policy | 62 | Policy | 4 | SI | 58 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.596 | 0 | CMO West 2 | IMGA222403 | WOOLHAMPTON WAY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941829 | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222403 | WOOLHAMPTON WAY | 510941829 | T1 Policy | 34.3 | Policy | 4 | SI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.029 | 0 | CMO West 2 | IMGA222403 | WOOLHAMPTON WAY | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
- | CMO | CMO West 2 | June | 11 | A | Roger Fearn | TBA - Lon | IMGA222383 | NEWFIELD GARDENS | - | T1 Policy | 0 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222383 | NEWFIELD GARDENS | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222090 | HALSWAY | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222090 | HALSWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222091 | MINET DRIVE | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222091 | MINET DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS |  | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
- | CMO | CMO West 2 | June | 11 | A | Shane Compton | TBA - Lon | IMGA222125 | DAWLEY AVENUE | - | T1 Policy | 0 | Policy | 4 | DI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510778064 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222403 | ABBEY CLOSE | 510778064 | Condition | 0 | Non Policy | 2 | ST | 9 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222403 | ABBEY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 CONNECTED | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | June
602454815 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222403 | ABBEY CLOSE | 602454815 | T1 Policy | 7.8 | Policy | 2 | SI | 13 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1014 | 0 | CMO West 2 | IMGA222403 | ABBEY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | June
510791865 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222025 | BIRCH LANE | 510791865 | T1 Policy | 21.4 | Policy | 4 | SI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1556 | 0 | CMO West 2 | IMGA222025 | BIRCH LANE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510929800 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222234 | VEGAL CRESCENT | 510929800 | T1 Policy | 45.1 | Policy | 4 | CI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.804 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510929801 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 36.2 | Policy | 4 | CI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3168 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510861868 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222241 | KNOWLE GROVE | 510861868 | T1 Policy | 15.2 | Policy | 4 | CI | 218 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.3136 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510944509 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222288 | STANLEY ROAD | 510944509 | T1 Policy | 20.9 | Policy | 4 | CI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1672 | 0 | CMO West 2 | IMGA222288 | STANLEY ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510944639 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222295 | THAMES SIDE | 510944639 | T1 Policy | 17.1 | Policy | 4 | CI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4535 | 0 | CMO West 2 | IMGA222295 | THAMES SIDE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510794685 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222313 | BRACKEN ROAD | 510794685 | T1 Policy | 26.2 | Policy | 4 | SI | 236 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.1832 | 0 | CMO West 2 | IMGA222313 | BRACKEN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510815968 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222313 | COX GREEN ROAD | 510815968 | T1 Policy | 18.2 | Policy | 4 | SI | 9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1638 | 0 | CMO West 2 | IMGA222313 | COX GREEN ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
220000778023 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222086 | MILDRED AVENUE | 220000778023 | T1 Policy | 0 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | MILDRED AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510932012 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 510932012 | T1 Policy | 1.4 | Policy | 4 | DI | 13 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0182 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949068 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222099 | UXBRIDGE ROAD SERVICE ROAD O/S 156-238 | 510949068 | T1 Policy | 28.8 | Policy | 4 | SI | 174 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.0112 | 0 | CMO West 2 | IMGA222099 | UXBRIDGE ROAD SERVICE ROAD O/S 156-238 | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510778065 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222403 | ABBEY CLOSE | 510778065 | T1 Policy | 7.8 | Policy | 4 | SI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.273 | 0 | CMO West 2 | IMGA222403 | ABBEY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510778066 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222403 | ABBEY CLOSE | 510778066 | T1 Policy | 24.1 | Policy | 4 | SI | 48 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1568 | 0 | CMO West 2 | IMGA222403 | ABBEY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510830840 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222403 | FARINGDON DRIVE | 510830840 | T1 Policy | 14.3 | Policy | 4 | SI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7007 | 0 | CMO West 2 | IMGA222403 | FARINGDON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510852347 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222139 | HILL RISE | 510852347 | T1 PAST | 15.7 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.57 | 0 | CMO West 2 | IMGA222139 | HILL RISE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510890619 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222277 | PARSONAGE LANE | 510890619 | T1 Policy | 19.6 | Policy | 4 | SI | 252 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.9392 | 0 | CMO West 2 | IMGA222277 | PARSONAGE LANE | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510943458 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222284 | ALBERT ROAD | 510943458 | T1 Policy | 25.6 | Policy | 6 | CI | 78 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9968 | 0 | CMO West 2 | IMGA222284 | ALBERT ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510943459 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222284 | ALBERT ROAD | 510943459 | T1 Policy | 32 | Policy | 6 | CI | 41 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.312 | 0 | CMO West 2 | IMGA222284 | ALBERT ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220000326765 | CMO | CMO West 2 | June | 12 | A | Mario Gesner | TBA - Lon | IMGA222287 | CHESTERFIELD ROAD | 220000326765 | T1 Policy | 0 | Policy | 6 | CI | 52 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222287 | CHESTERFIELD ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
220001743995 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222086 | MILDRED AVENUE | 220001743995 | T1 Policy | 0 | Policy | 6 | DI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | MILDRED AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
220001743992 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222086 | WALTHAM AVENUE | 220001743992 | T1 Policy | 0 | Policy | 6 | DI | 12 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222086 | WALTHAM AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510845934 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845934 | T1 Policy | 8 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510826903 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222136 | ELLIS AVENUE | 510826903 | T1 Policy | 7 | Policy | 6 | CI | 83 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.581 | 0 | CMO West 2 | IMGA222136 | ELLIS AVENUE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510941628 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222136 | WOODSIDE HILL | 510941628 | T1 Policy | 12.9 | Policy | 6 | CI | 52 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6708 | 0 | CMO West 2 | IMGA222136 | WOODSIDE HILL | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510937064 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222360 | WHITEPIT LANE | 510937064 | T1 Policy | 6.2 | Policy | 6 | SI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.186 | 0 | CMO West 2 | IMGA222360 | WHITEPIT LANE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
220000699706 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222365 | MARLOW HILL | 220000699706 | T1 PAST | 0 | Policy | 6 | CI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222365 | MARLOW HILL | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WALKER, Ross | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510849459 | CMO | CMO West 2 | June | 12 | A | TBA - Lon | TBA - Lon | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 5.1 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510896365 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896365 | T1 Policy | 0.2 | Policy | 100 | DI | 85 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.017 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510896372 | CMO | CMO West 2 | June | 12 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896372 | T1 Policy | 0.2 | Policy | 100 | DI | 101 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0202 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510941331 | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941331 | T1 Policy | 13.6 | Policy | 4 | SI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.544 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510791865 | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222025 | BIRCH LANE | 510791865 | T1 Policy | 21.4 | Policy | 4 | SI | 72 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5408 | 0 | CMO West 2 | IMGA222025 | BIRCH LANE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510929801 | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 36.2 | Policy | 4 | CI | 96 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.4752 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510934915 | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222250 | WESTGATE CRESCENT | 510934915 | T1 Policy | 38 | Policy | 4 | SI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.84 | 0 | CMO West 2 | IMGA222250 | WESTGATE CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510934918 | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222250 | WESTGATE CRESCENT | 510934918 | T1 Policy | 31.3 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.13 | 0 | CMO West 2 | IMGA222250 | WESTGATE CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510966082 | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222337 | CRANBROOK DRIVE | 510966082 | T1 Policy | 0.3 | Policy | 200 | DI | 200 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510887647 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222007 | ORION | 510887647 | T1 Policy | 0.3 | Policy | 100 | DI | 74 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0222 | 0 | CMO West 2 | IMGA222007 | ORION | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510896368 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896368 | T1 Policy | 0.3 | Policy | 150 | DI | 5 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0015 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510896371 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222008 | QUALITAS | 510896371 | T1 Policy | 0.3 | Policy | 100 | DI | 99 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0297 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949852 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222091 | HALSWAY | 510949852 | T1 Policy | 0.7 | Policy | 4 | DI | 140 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.098 | 0 | CMO West 2 | IMGA222091 | HALSWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510950119 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222091 | HERMON GROVE | 510950119 | T1 Policy | 1.8 | Policy | 4 | DI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.072 | 0 | CMO West 2 | IMGA222091 | HERMON GROVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510950120 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222091 | HERMON GROVE | 510950120 | T1 Policy | 41.4 | Policy | 4 | SI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.382 | 0 | CMO West 2 | IMGA222091 | HERMON GROVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510948811 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222099 | CRANBORNE WAYE | 510948811 | T1 Policy | 1.1 | Policy | 6 | SI | 4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0044 | 0 | CMO West 2 | IMGA222099 | CRANBORNE WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510952050 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222099 | QUEBEC ROAD | 510952050 | T1 Policy | 10.7 | Policy | 6 | SI | 168 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7976 | 0 | CMO West 2 | IMGA222099 | QUEBEC ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510949698 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222100 | GLEDWOOD GARDENS | 510949698 | T1 Policy | 17.6 | Policy | 6 | SI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.64 | 0 | CMO West 2 | IMGA222100 | GLEDWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510806465 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222403 | CHEAM CLOSE | 510806465 | T1 Policy | 25 | Policy | 4 | SI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.625 | 0 | CMO West 2 | IMGA222403 | CHEAM CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510806466 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222403 | CHEAM CLOSE | 510806466 | T1 Policy | 23.4 | Policy | 2 | SI | 37 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8658 | 0 | CMO West 2 | IMGA222403 | CHEAM CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | June
510830840 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222403 | FARINGDON DRIVE | 510830840 | T1 Policy | 14.3 | Policy | 4 | SI | 51 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7293 | 0 | CMO West 2 | IMGA222403 | FARINGDON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510845933 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845933 | T1 Policy | 15.7 | Policy | 4 | SI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0471 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510845934 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222403 | HARMANS WATER ROAD | 510845934 | T1 Policy | 8 | Policy | 6 | SI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6 | 0 | CMO West 2 | IMGA222403 | HARMANS WATER ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510964377 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222403 | MERLEWOOD | 510964377 | T1 Policy | 30.5 | Policy | 4 | SI | 62 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.891 | 0 | CMO West 2 | IMGA222403 | MERLEWOOD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510826903 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222136 | ELLIS AVENUE | 510826903 | T1 Policy | 7 | Policy | 6 | CI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14 | 0 | CMO West 2 | IMGA222136 | ELLIS AVENUE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510844018 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222136 | HALFACRE HILL | 510844018 | T1 Policy | 5.3 | Policy | 4 | CI | 215 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1395 | 0 | CMO West 2 | IMGA222136 | HALFACRE HILL | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510844019 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222136 | HALFACRE HILL | 510844019 | T1 Policy | 10.1 | Policy | 4 | CI | 14 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1414 | 0 | CMO West 2 | IMGA222136 | HALFACRE HILL | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510852347 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222139 | HILL RISE | 510852347 | T1 PAST | 15.7 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.099 | 0 | CMO West 2 | IMGA222139 | HILL RISE | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510930950 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222141 | VILLAGE WAY | 510930950 | T1 PAST | 4.4 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.44 | 0 | CMO West 2 | IMGA222141 | VILLAGE WAY | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510890613 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222277 | PARSONAGE LANE | 510890613 | T1 Policy | 1.4 | Policy | 8 | DI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14 | 0 | CMO West 2 | IMGA222277 | PARSONAGE LANE | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | June
510825015 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222362 | EASTERN DENE | 510825015 | T1 PAST | 0.7 | Policy | 4 | CI | 19 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0133 | 0 | CMO West 2 | IMGA222362 | EASTERN DENE | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
220000702797 | CMO | CMO West 2 | June | 13 | A | Tony Ingram 2 | TBA - Lon | IMGA222362 | HILL AVENUE | 220000702797 | T1 Policy | 0 | Policy | 4 | CI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222362 | HILL AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510949099 | CMO | CMO West 2 | June | 13 | A | Shane Compton | TBA - Lon | IMGA222099 | DORCHESTER WAYE | 510949099 | T1 Policy | 17.7 | Policy | 6 | SI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1239 | 0 | CMO West 2 | IMGA222099 | DORCHESTER WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
- | CMO | CMO West 2 | June | 13 | A | Mario Gesner | TBA - Lon | IMGA222337 | CRANBROOK DRIVE | - | T1 Policy | 0 | Policy | 6 | DI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510963972 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 10.3 | Policy | 4 | SI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.309 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941330 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941330 | T1 Policy | 12.4 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.62 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941331 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941331 | T1 Policy | 13.6 | Policy | 4 | SI | 159 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1624 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510941337 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | TBA - Lon | IMGA222021 | WOODLANDS RIDE | 510941337 | T1 Policy | 6.7 | Policy | 4 | SI | 9 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0603 | 0 | CMO West 2 | IMGA222021 | WOODLANDS RIDE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510791866 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Chris Douglas | IMGA222025 | BIRCH LANE | 510791866 | T1 Policy | 10.3 | Policy | 4 | SI | 107 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1021 | 0 | CMO West 2 | IMGA222025 | BIRCH LANE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510861868 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Phil Walden | IMGA222241 | KNOWLE GROVE | 510861868 | T1 Policy | 15.2 | Policy | 4 | CI | 153 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3256 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO KIRBY DHB, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510790622 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Phil Walden | IMGA222248 | BENTLEY ROAD | 510790622 | T1 Policy | 45.8 | Policy | 4 | SI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.664 | 0 | CMO West 2 | IMGA222248 | BENTLEY ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510944639 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Chris Douglas | IMGA222295 | THAMES SIDE | 510944639 | T1 Policy | 17.1 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.171 | 0 | CMO West 2 | IMGA222295 | THAMES SIDE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510943293 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Chris Douglas | IMGA222295 | VICARAGE LANE | 510943293 | T1 Policy | 27.6 | Policy | 4 | CI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3524 | 0 | CMO West 2 | IMGA222295 | VICARAGE LANE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | June
510934709 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | TBA - Lon | IMGA222313 | WESSEX WAY | 510934709 | T1 Policy | 21.1 | Policy | 4 | SI | 104 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.1944 | 0 | CMO West 2 | IMGA222313 | WESSEX WAY | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510896370 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Ryan Smeaton | IMGA222008 | QUALITAS | 510896370 | T1 Policy | 0.2 | Policy | 4 | DI | 84 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0168 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO COLLINS, Pat | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510949850 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Natasha Barrett | IMGA222091 | HALSWAY | 510949850 | T1 Policy | 0.6 | Policy | 4 | DI | 183 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1098 | 0 | CMO West 2 | IMGA222091 | HALSWAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510968613 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Natasha Barrett | IMGA222125 | LANSDOWNE ROAD | 510968613 | T1 Policy | 1.4 | Policy | 4 | DI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.098 | 0 | CMO West 2 | IMGA222125 | LANSDOWNE ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510778066 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Ryan Smeaton | IMGA222403 | ABBEY CLOSE | 510778066 | T1 Policy | 24.1 | Policy | 4 | SI | 71 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.7111 | 0 | CMO West 2 | IMGA222403 | ABBEY CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510918216 | CMO | CMO West 2 | June | 14 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRATHCONA CLOSE | 510918216 | T1 Policy | 21.7 | Policy | 4 | SI | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.1248 | 0 | CMO West 2 | IMGA222360 | STRATHCONA CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
510943504 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Phil Walden | IMGA222237 | BOWES ROAD | 510943504 | T1 Policy | 14.6 | Policy | 6 | SI | 74 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0804 | 0 | CMO West 2 | IMGA222237 | BOWES ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510906068 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | 510906068 | T1 Policy | 26.6 | Policy | 6 | SI | 91 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4206 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510948811 | CMO | CMO West 2 | June | 14 | A | Shane Compton | William Sadler | IMGA222099 | CRANBORNE WAYE | 510948811 | T1 Policy | 1.1 | Policy | 6 | DI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.11 | 0 | CMO West 2 | IMGA222099 | CRANBORNE WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510949698 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Natasha Barrett | IMGA222100 | GLEDWOOD GARDENS | 510949698 | T1 Policy | 17.6 | Policy | 6 | SI | 175 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.08 | 0 | CMO West 2 | IMGA222100 | GLEDWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510948930 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Natasha Barrett | IMGA222125 | DAWLEY AVENUE | 510948930 | T1 Policy | 70.9 | Policy | 6 | SI | 22 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.5598 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | June
510968613 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Natasha Barrett | IMGA222125 | LANSDOWNE ROAD | 510968613 | T1 Policy | 1.4 | Policy | 6 | DI | 35 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.049 | 0 | CMO West 2 | IMGA222125 | LANSDOWNE ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
510826903 | CMO | CMO West 2 | June | 14 | A | Tony Ingram 2 | William Madge | IMGA222136 | ELLIS AVENUE | 510826903 | T1 Policy | 7 | Policy | 6 | CI | 158 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.106 | 0 | CMO West 2 | IMGA222136 | ELLIS AVENUE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | June
510808095 | CMO | CMO West 2 | June | 14 | A | Tony Ingram 2 | William Madge | IMGA222136 | CHILTERN HILL | 510808095 | T1 PAST | 10.9 | Policy | 8 | CI | 30 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.327 | 0 | CMO West 2 | IMGA222136 | CHILTERN HILL | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510890613 | CMO | CMO West 2 | June | 14 | A | Tony Ingram 2 | Kerry Dolan | IMGA222277 | PARSONAGE LANE | 510890613 | T1 Policy | 1.4 | Policy | 8 | CI | 80 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.112 | 0 | CMO West 2 | IMGA222277 | PARSONAGE LANE | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510849459 | CMO | CMO West 2 | June | 14 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 5.1 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.51 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | June
510968783 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Chris Douglas | IMGA222337 | GWENDALE | 510968783 | T1 Policy | 0.3 | Policy | 100 | DI | 10 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.003 | 0 | CMO West 2 | IMGA222337 | GWENDALE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510887648 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Ryan Smeaton | IMGA222007 | ORION | 510887648 | T1 Policy | 0.3 | Policy | 100 | DI | 96 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0288 | 0 | CMO West 2 | IMGA222007 | ORION | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510887650 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Ryan Smeaton | IMGA222007 | ORION | 510887650 | T1 Policy | 0.3 | Policy | 100 | DI | 40 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.012 | 0 | CMO West 2 | IMGA222007 | ORION | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510896368 | CMO | CMO West 2 | June | 14 | A | Shane Compton | Ryan Smeaton | IMGA222008 | QUALITAS | 510896368 | T1 Policy | 0.3 | Policy | 150 | DI | 30 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.009 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO COLLINS, Pat | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
635117331 | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Chris Douglas | IMGA222337 | CRANBROOK DRIVE | 635117331 | T1 Policy | 0.2 | Policy | 200 | DI | 280 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.056 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | June
- | CMO | CMO West 2 | June | 14 | A | Mario Gesner | TBA - Lon | IMGA222247 | ST GEORGES CRESCENT | - | Condition | 0 | Non Policy | 2 | ST | 33 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222247 | ST GEORGES CRESCENT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities |  | tRIIO PORTER, Stuart | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | June
DR4 Requested | CMO | CMO West 2 | June | 14 | A | Shane Compton | Natasha Barrett | IMGA222125 | LANSDOWNE ROAD | DR4 Requested | T1 Policy | 0 | Policy | 4 | SI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222125 | LANSDOWNE ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | June
DR4 Requested | CMO | CMO West 2 | June | 14 | A | Mario Gesner | Chris Douglas | IMGA222337 | CRANBROOK DRIVE | DR4 Requested | T1 Policy | 0 | Policy | 100 | DI | 4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | June
510965869 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Chris Douglas | IMGA222017 | MEADOWBANK ROAD | 510965869 | T1 Policy | 0.3 | Policy | 150 | DI | 207 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0621 | 0 | CMO West 2 | IMGA222017 | MEADOWBANK ROAD | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510963972 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 10.3 | Policy | 4 | CI | 170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.751 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510791866 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Chris Douglas | IMGA222025 | BIRCH LANE | 510791866 | T1 Policy | 10.3 | Policy | 4 | SI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4635 | 0 | CMO West 2 | IMGA222025 | BIRCH LANE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510797006 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Chris Douglas | IMGA222025 | BROAD STREET | 510797006 | T1 Policy | 14.1 | Policy | 4 | SI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6627 | 0 | CMO West 2 | IMGA222025 | BROAD STREET | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
DR4 Requested | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Phil Walden | IMGA222237 | RIVERSIDE DRIVE | DR4 Requested | Condition | 0 | Non Policy | 2 | ST | 42 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222237 | RIVERSIDE DRIVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities |  | CMO HARRIS, Rob | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | July
510944656 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Phil Walden | IMGA222237 | RIVERSIDE DRIVE | 510944656 | T1 Policy | 13.9 | Policy | 4 | CI | 28 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3892 | 0 | CMO West 2 | IMGA222237 | RIVERSIDE DRIVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510944657 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Phil Walden | IMGA222237 | RIVERSIDE DRIVE | 510944657 | T1 Policy | 19.1 | Policy | 4 | SI | 78 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4898 | 0 | CMO West 2 | IMGA222237 | RIVERSIDE DRIVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510790623 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Phil Walden | IMGA222248 | BENTLEY ROAD | 510790623 | T1 Policy | 47.1 | Policy | 4 | SI | 149 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.0179 | 0 | CMO West 2 | IMGA222248 | BENTLEY ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510790624 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Phil Walden | IMGA222248 | BENTLEY ROAD | 510790624 | T1 Policy | 59.2 | Policy | 4 | SI | 88 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.2096 | 0 | CMO West 2 | IMGA222248 | BENTLEY ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510943293 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Chris Douglas | IMGA222295 | VICARAGE LANE | 510943293 | T1 Policy | 27.6 | Policy | 4 | CI | 37 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0212 | 0 | CMO West 2 | IMGA222295 | VICARAGE LANE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510944409 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Leigh Osaer | IMGA222301 | LALEHAM ROAD | 510944409 | T2 PAST | 1 | Policy | 12 | DI | 350 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 0.35 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T2 PAST | tRIIO MCQUADE, Barry | LP | #N/A | 10-12” | 12 |  | Policy | Tier 2 | DI | T2A | July
510886480 | CMO | CMO West 2 | July | 15 | A | Mario Gesner | Leigh Osaer | IMGA222315 | OLD COURT CLOSE | 510886480 | T1 Policy | 19 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.9 | 0 | CMO West 2 | IMGA222315 | OLD COURT CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510964566 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Ryan Smeaton | IMGA222007 | NORTHCOTT | 510964566 | T1 Policy | 11.8 | Policy | 100 | DI | 80 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.944 | 0 | CMO West 2 | IMGA222007 | NORTHCOTT | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510896367 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Ryan Smeaton | IMGA222008 | QUALITAS | 510896367 | T1 Policy | 0.3 | Policy | 100 | DI | 90 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.027 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510896368 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Ryan Smeaton | IMGA222008 | QUALITAS | 510896368 | T1 Policy | 0.3 | Policy | 150 | DI | 30 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.009 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510897484 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897484 | T1 Policy | 0.2 | Policy | 100 | DI | 71 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0142 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510925357 | CMO | CMO West 2 | July | 15 | A | Shane Compton | William Sadler | IMGA222016 | JEALOTTS HILL | 510925357 | T1 PAST | 0.7 | Policy | 4 | DI | 215 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1505 | 0 | CMO West 2 | IMGA222016 | JEALOTTS HILL | Bracknell Forest Borough Council | West 2 | FALSE | PAST | OMJ | T1 PAST | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510948811 | CMO | CMO West 2 | July | 15 | A | Shane Compton | William Sadler | IMGA222099 | CRANBORNE WAYE | 510948811 | T1 Policy | 1.1 | Policy | 6 | DI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.088 | 0 | CMO West 2 | IMGA222099 | CRANBORNE WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510949699 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Natasha Barrett | IMGA222100 | GLEDWOOD GARDENS | 510949699 | T1 Policy | 13.6 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.36 | 0 | CMO West 2 | IMGA222100 | GLEDWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
220001276022 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Natasha Barrett | IMGA222100 | GLEDWOOD GARDENS | 220001276022 | T1 Policy | 0 | Policy | 6 | SI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222100 | GLEDWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
DR4 Requested | CMO | CMO West 2 | July | 15 | A | Shane Compton | Natasha Barrett | IMGA222125 | CHESTER CLOSE | DR4 Requested | T1 Policy | 0 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222125 | CHESTER CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS |  | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510948351 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Natasha Barrett | IMGA222125 | CHESTER CLOSE | 510948351 | T1 Policy | 81 | Policy | 4 | SI | 52 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.212 | 0 | CMO West 2 | IMGA222125 | CHESTER CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510948930 | CMO | CMO West 2 | July | 15 | A | Shane Compton | Natasha Barrett | IMGA222125 | DAWLEY AVENUE | 510948930 | T1 Policy | 70.9 | Policy | 6 | SI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.963 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510808095 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | William Madge | IMGA222136 | CHILTERN HILL | 510808095 | T1 PAST | 10.9 | Policy | 8 | DI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.09 | 0 | CMO West 2 | IMGA222136 | CHILTERN HILL | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | July
510930950 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Kerry Dolan | IMGA222141 | VILLAGE WAY | 510930950 | T1 PAST | 4.4 | Policy | 4 | DI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.44 | 0 | CMO West 2 | IMGA222141 | VILLAGE WAY | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510890613 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Kerry Dolan | IMGA222277 | PARSONAGE LANE | 510890613 | T1 Policy | 1.4 | Policy | 8 | CI | 119 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1666 | 0 | CMO West 2 | IMGA222277 | PARSONAGE LANE | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510890616 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Kerry Dolan | IMGA222277 | PARSONAGE LANE | 510890616 | T1 Policy | 8.9 | Policy | 4 | CI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0712 | 0 | CMO West 2 | IMGA222277 | PARSONAGE LANE | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510815547 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | COURT CLOSE | 510815547 | T1 Policy | 16.8 | Policy | 4 | SI | 180 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.024 | 0 | CMO West 2 | IMGA222371 | COURT CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
- | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | LYNDHURST CLOSE | - | T1 Policy | 0 | Policy | 4 | DI | 18 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222371 | LYNDHURST CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT |  | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510870886 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | LYNDHURST CLOSE | 510870886 | T1 Policy | 1 | Policy | 6 | CI | 242 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.242 | 0 | CMO West 2 | IMGA222371 | LYNDHURST CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT |  | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510870886 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | LYNDHURST CLOSE | 510870886 | T1 PAST | 1 | Policy | 4 | DI | 116 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.116 | 0 | CMO West 2 | IMGA222371 | LYNDHURST CLOSE | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510936126 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | WESTOVER COURT | 510936126 | T1 Policy | 0.3 | Policy | 4 | DI | 39 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0117 | 0 | CMO West 2 | IMGA222371 | WESTOVER COURT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510849459 | CMO | CMO West 2 | July | 15 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 5.1 | Policy | 8 | SI | 80 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.408 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | July
510834445 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | TBA - Lon | IMGA222247 | FRANCIS WAY | 510834445 | T1 Policy | 31.1 | Policy | 4 | CI | -175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | -5.4425 | 0 | CMO West 2 | IMGA222247 | FRANCIS WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510834444 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | TBA - Lon | IMGA222247 | FRANCIS WAY | 510834444 | T1 Policy | 13.3 | Policy | 4 | CI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3275 | 0 | CMO West 2 | IMGA222247 | FRANCIS WAY | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510928408 | CMO | CMO West 2 | July | 16 | A | Shane Compton | TBA - Lon | IMGA222404 | UFFINGTON DRIVE | 510928408 | T1 Policy | 0 | Policy | 6 | SI | -260 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222404 | UFFINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ |  | tRIIO DOMINY, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510928048 | CMO | CMO West 2 | July | 16 | A | Shane Compton | TBA - Lon | IMGA222404 | UFFINGTON DRIVE | 510928048 | T1 Policy | 47.4 | Policy | 6 | SI | 260 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 12.324 | 0 | CMO West 2 | IMGA222404 | UFFINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO DOMINY, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510949099 | CMO | CMO West 2 | July | 16 | A | Shane Compton | TBA - Lon | IMGA222099 | DORCHESTER WAYE | 510949099 | T1 Policy | 17.7 | Policy | 6 | SI | -7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | -0.1239 | 0 | CMO West 2 | IMGA222099 | DORCHESTER WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510949096 | CMO | CMO West 2 | July | 16 | A | Shane Compton | TBA - Lon | IMGA222099 | DORCHESTER WAYE | 510949096 | T1 Policy | 0.5 | Policy | 6 | DI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0035 | 0 | CMO West 2 | IMGA222099 | DORCHESTER WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510870886 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | LYNDHURST CLOSE | 510870886 | T1 Policy | 1 | Policy | 6 | CI | -242 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | -0.242 | 0 | CMO West 2 | IMGA222371 | LYNDHURST CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT |  | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510870886 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | Adam Madge | IMGA222371 | LYNDHURST CLOSE | 510870886 | T1 PAST | 227.2 | Policy | 6 | CI | 242 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 54.9824 | 0 | CMO West 2 | IMGA222371 | LYNDHURST CLOSE | Wycombe District Council | West 2 | FALSE | PAST | KLT |  | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510843143 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222017 | RIVERSIDE AVENUE | 510843143 | T1 Policy | 2.2 | Policy | 200 | DI | 65 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.143 | 0 | CMO West 2 | IMGA222017 | RIVERSIDE AVENUE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510965890 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222017 | RIVERSIDE AVENUE | 510965890 | T1 Policy | 3.2 | Policy | 200 | DI | 162 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5184 | 0 | CMO West 2 | IMGA222017 | RIVERSIDE AVENUE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510965892 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222017 | RIVERSIDE AVENUE | 510965892 | T1 Policy | 1.7 | Policy | 200 | DI | 57 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0969 | 0 | CMO West 2 | IMGA222017 | RIVERSIDE AVENUE | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510963973 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963973 | T1 Policy | 11.2 | Policy | 4 | SI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.68 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510797006 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222025 | BROAD STREET | 510797006 | T1 Policy | 2.1 | Policy | 4 | DI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.063 | 0 | CMO West 2 | IMGA222025 | BROAD STREET | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510797007 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222025 | BROAD STREET | 510797007 | T1 Policy | 2.2 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.033 | 0 | CMO West 2 | IMGA222025 | BROAD STREET | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
- | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Phil Walden | IMGA222237 | RIVERSIDE DRIVE | - | T1 Policy | 0 | Policy | 4 | DI | 52 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222237 | RIVERSIDE DRIVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510944656 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Phil Walden | IMGA222237 | RIVERSIDE DRIVE | 510944656 | T1 Policy | 6.5 | Policy | 4 | CI | 128 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.832 | 0 | CMO West 2 | IMGA222237 | RIVERSIDE DRIVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510873971 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Phil Walden | IMGA222319 | MARLBOROUGH ROAD | 510873971 | T1 Policy | 14 | Policy | 4 | DI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.45 | 0 | CMO West 2 | IMGA222319 | MARLBOROUGH ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
- | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222337 | CRANBROOK DRIVE | - | T1 Policy | 0 | Policy | 100 | DI | 4 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO SMITH, James | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
- | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222337 | CRANBROOK DRIVE | - | T1 Policy | 0 | Policy | 150 | DI | 10 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO SMITH, James | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
635117331 | CMO | CMO West 2 | July | 16 | A | Mario Gesner | Chris Douglas | IMGA222337 | CRANBROOK DRIVE | 635117331 | T1 Policy | 2.4 | Policy | 200 | DI | 70 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.168 | 0 | CMO West 2 | IMGA222337 | CRANBROOK DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO SMITH, James | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510964566 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222007 | NORTHCOTT | 510964566 | T1 Policy | 3.5 | Policy | 100 | DI | 75 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2625 | 0 | CMO West 2 | IMGA222007 | NORTHCOTT | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510964573 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222007 | NORTHCOTT | 510964573 | T1 Policy | 1.1 | Policy | 100 | DI | 2 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0022 | 0 | CMO West 2 | IMGA222007 | NORTHCOTT | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510896368 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222008 | QUALITAS | 510896368 | T1 Policy | 3.6 | Policy | 150 | DI | 70 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.252 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510896369 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222008 | QUALITAS | 510896369 | T1 Policy | 3.8 | Policy | 100 | DI | 75 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.285 | 0 | CMO West 2 | IMGA222008 | QUALITAS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510897485 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897485 | T1 Policy | 3.1 | Policy | 100 | DI | 155 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4805 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
606701818 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 606701818 | T1 Policy | 2.6 | Policy | 100 | DI | 5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.013 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510897488 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897488 | T1 Policy | 2.9 | Policy | 100 | DI | 100 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.29 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510925357 | CMO | CMO West 2 | July | 16 | A | Shane Compton | William Sadler | IMGA222016 | JEALOTTS HILL | 510925357 | T1 PAST | 179.4 | Policy | 4 | CI | 285 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 51.129 | 0 | CMO West 2 | IMGA222016 | JEALOTTS HILL | Bracknell Forest Borough Council | West 2 | FALSE | PAST | OMJ | T1 PAST | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
612114338 | CMO | CMO West 2 | July | 16 | A | Shane Compton | William Sadler | IMGA222016 | JEALOTTS HILL | 612114338 | T1 Policy | 2.9 | Policy | 3 | CI | 6 | inch | 3inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0174 | 0 | CMO West 2 | IMGA222016 | JEALOTTS HILL | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | <=3” | 3 |  | Policy | Tier 1 | CI | CI/SI/DI LP <=3" | July
613779490 | CMO | CMO West 2 | July | 16 | A | Shane Compton | William Sadler | IMGA222016 | JEALOTTS HILL | 613779490 | T1 Policy | 9.6 | Policy | 4 | DI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0576 | 0 | CMO West 2 | IMGA222016 | JEALOTTS HILL | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510947809 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Natasha Barrett | IMGA222097 | BELMORE AVENUE | 510947809 | T1 Policy | 93 | Policy | 6 | DI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.95 | 0 | CMO West 2 | IMGA222097 | BELMORE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510948811 | CMO | CMO West 2 | July | 16 | A | Shane Compton | William Sadler | IMGA222099 | CRANBORNE WAYE | 510948811 | T1 Policy | 114 | Policy | 6 | CI | 117 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.338 | 0 | CMO West 2 | IMGA222099 | CRANBORNE WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510949699 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Natasha Barrett | IMGA222100 | GLEDWOOD GARDENS | 510949699 | T1 Policy | 2.8 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.28 | 0 | CMO West 2 | IMGA222100 | GLEDWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510948930 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Natasha Barrett | IMGA222125 | DAWLEY AVENUE | 510948930 | T1 Policy | 7.9 | Policy | 6 | SI | 75 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5925 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510949858 | CMO | CMO West 2 | July | 16 | A | Shane Compton | Natasha Barrett | IMGA222125 | HARDINGE CLOSE | 510949858 | T1 Policy | 9.2 | Policy | 4 | DI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.598 | 0 | CMO West 2 | IMGA222125 | HARDINGE CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510895843 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | Kerry Dolan | IMGA222134 | PRIORY ROAD | 510895843 | T1 PAST | 206 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 30.9 | 0 | CMO West 2 | IMGA222134 | PRIORY ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510875738 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | William Madge | IMGA222135 | MEADOWCROFT | 510875738 | T1 Policy | 4.6 | Policy | 6 | CI | 95 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.437 | 0 | CMO West 2 | IMGA222135 | MEADOWCROFT | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | July
510875739 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | William Madge | IMGA222135 | MEADOWCROFT | 510875739 | T1 Policy | 7.4 | Policy | 4 | CI | 187 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3838 | 0 | CMO West 2 | IMGA222135 | MEADOWCROFT | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510808095 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | William Madge | IMGA222136 | CHILTERN HILL | 510808095 | T1 PAST | 231.9 | Policy | 8 | CI | 70 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 16.233 | 0 | CMO West 2 | IMGA222136 | CHILTERN HILL | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510969469 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRATHCONA WAY | 510969469 | T1 Policy | 6.9 | Policy | 4 | CI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5658 | 0 | CMO West 2 | IMGA222360 | STRATHCONA WAY | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510849459 | CMO | CMO West 2 | July | 16 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 1.2 | Policy | 8 | CI | 130 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.156 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | July
510806993 | CMO | CMO West 2 | July | 17 | A | Tony Ingram 2 | William Madge | IMGA222135 | Cherry Tree Lane | 510806993 | Condition | 0 | Non Policy | 2 | ST | 52 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222135 | Cherry Tree Lane | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 CONNECTED | tRIIO BROWN, Warren | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | July
510797007 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Chris Douglas | IMGA222025 | BROAD STREET | 510797007 | T1 Policy | 2.2 | Policy | 4 | SI | 54 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1188 | 0 | CMO West 2 | IMGA222025 | BROAD STREET | Surrey Heath Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PAVIOUR, William | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510806990 | CMO | CMO West 2 | July | 17 | A | Tony Ingram 2 | William Madge | IMGA222135 | Cherry Tree Lane | 510806990 | T1 PAST | 194.2 | Policy | 4 | CI | 192 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 37.2864 | 0 | CMO West 2 | IMGA222135 | Cherry Tree Lane | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510806991 | CMO | CMO West 2 | July | 17 | A | Tony Ingram 2 | William Madge | IMGA222135 | Cherry Tree Lane | 510806991 | T1 Policy | 12.3 | Policy | 4 | CI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.738 | 0 | CMO West 2 | IMGA222135 | Cherry Tree Lane | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510811826 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Chris Douglas | IMGA222228 | CLOCKHOUSE LANE EAST | 510811826 | T1 Policy | 5.3 | Policy | 4 | CI | 261 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3833 | 0 | CMO West 2 | IMGA222228 | CLOCKHOUSE LANE EAST | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO CUTHBERTSON, Steve | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510895843 | CMO | CMO West 2 | July | 17 | A | Tony Ingram 2 | Kerry Dolan | IMGA222134 | PRIORY ROAD | 510895843 | T1 PAST | 206 | Policy | 4 | CI | 77 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 15.862 | 0 | CMO West 2 | IMGA222134 | PRIORY ROAD | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510914678 | CMO | CMO West 2 | July | 17 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914678 | T1 Policy | 6 | Policy | 4 | SI | 108 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.648 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510918216 | CMO | CMO West 2 | July | 17 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRATHCONA CLOSE | 510918216 | T1 Policy | 10.7 | Policy | 4 | SI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6955 | 0 | CMO West 2 | IMGA222360 | STRATHCONA CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510930950 | CMO | CMO West 2 | July | 17 | A | Tony Ingram 2 | Kerry Dolan | IMGA222141 | VILLAGE WAY | 510930950 | T1 PAST | 107.2 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 10.72 | 0 | CMO West 2 | IMGA222141 | VILLAGE WAY | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO WHEELER, Liam | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510939057 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Leigh Osaer | IMGA222315 | WINCHESTER DRIVE | 510939057 | T1 Policy | 4.8 | Policy | 4 | SI | 145 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.696 | 0 | CMO West 2 | IMGA222315 | WINCHESTER DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510943293 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Chris Douglas | IMGA222295 | VICARAGE LANE | 510943293 | T1 Policy | 14 | Policy | 4 | CI | 53 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.742 | 0 | CMO West 2 | IMGA222295 | VICARAGE LANE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510943503 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Phil Walden | IMGA222237 | BOWES ROAD | 510943503 | T1 Policy | 7.9 | Policy | 4 | SI | 113 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8927 | 0 | CMO West 2 | IMGA222237 | BOWES ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510950933 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Natasha Barrett | IMGA222125 | LONSDALE CLOSE | 510950933 | T1 Policy | 130.4 | Policy | 4 | DI | 104 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.5616 | 0 | CMO West 2 | IMGA222125 | LONSDALE CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510963973 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963973 | T1 Policy | 11.2 | Policy | 4 | SI | 110 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.232 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
DR4 Requested | CMO | CMO West 2 | July | 17 | A | Shane Compton | Natasha Barrett | IMGA222125 | LONSDALE CLOSE | DR4 Requested | T1 Policy | 0 | Policy | 4 | DI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222125 | LONSDALE CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510885608 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 510885608 | T1 Policy | 2 | Policy | 6 | SI | 26 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.052 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510885609 | CMO | CMO West 2 | July | 17 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 510885609 | T1 Policy | 2.1 | Policy | 6 | SI | 194 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4074 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510914680 | CMO | CMO West 2 | July | 17 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914680 | T1 Policy | 5 | Policy | 6 | SI | 13 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.065 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510947809 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Natasha Barrett | IMGA222097 | BELMORE AVENUE | 510947809 | T1 Policy | 93 | Policy | 6 | DI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 13.95 | 0 | CMO West 2 | IMGA222097 | BELMORE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510948930 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Natasha Barrett | IMGA222125 | DAWLEY AVENUE | 510948930 | T1 Policy | 7.9 | Policy | 6 | SI | 60 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.474 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510949699 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Natasha Barrett | IMGA222100 | GLEDWOOD GARDENS | 510949699 | T1 Policy | 2.8 | Policy | 6 | SI | 103 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2884 | 0 | CMO West 2 | IMGA222100 | GLEDWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510897485 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897485 | T1 Policy | 3.1 | Policy | 100 | DI | 110 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.341 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510897488 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897488 | T1 Policy | 2.9 | Policy | 100 | DI | 96 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2784 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510964573 | CMO | CMO West 2 | July | 17 | A | Shane Compton | Ryan Smeaton | IMGA222007 | NORTHCOTT | 510964573 | T1 Policy | 1.1 | Policy | 100 | DI | 7 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0077 | 0 | CMO West 2 | IMGA222007 | NORTHCOTT | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510963972 | CMO | CMO West 2 | July | 18 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 4.4 | Policy | 4 | CI | 85 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.374 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510943504 | CMO | CMO West 2 | July | 18 | A | Mario Gesner | Phil Walden | IMGA222237 | BOWES ROAD | 510943504 | T1 Policy | 5.9 | Policy | 6 | SI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.295 | 0 | CMO West 2 | IMGA222237 | BOWES ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510943293 | CMO | CMO West 2 | July | 18 | A | Mario Gesner | Chris Douglas | IMGA222295 | VICARAGE LANE | 510943293 | T1 Policy | 14 | Policy | 4 | CI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.49 | 0 | CMO West 2 | IMGA222295 | VICARAGE LANE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | July
510939056 | CMO | CMO West 2 | July | 18 | A | Mario Gesner | Leigh Osaer | IMGA222315 | WINCHESTER DRIVE | 510939056 | T1 Policy | 3 | Policy | 4 | SI | 197 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.591 | 0 | CMO West 2 | IMGA222315 | WINCHESTER DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510873970 | CMO | CMO West 2 | July | 18 | A | Mario Gesner | Phil Walden | IMGA222319 | MARLBOROUGH ROAD | 510873970 | T1 Policy | 4.9 | Policy | 8 | SI | 130 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.637 | 0 | CMO West 2 | IMGA222319 | MARLBOROUGH ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | July
510885608 | CMO | CMO West 2 | July | 18 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 510885608 | T1 Policy | 2 | Policy | 8 | SI | 200 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | July
510964567 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Ryan Smeaton | IMGA222007 | NORTHCOTT | 510964567 | T1 Policy | 2.7 | Policy | 100 | DI | 123 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3321 | 0 | CMO West 2 | IMGA222007 | NORTHCOTT | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510897485 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897485 | T1 Policy | 3.1 | Policy | 100 | DI | 100 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.31 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510897486 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897486 | T1 Policy | 2.9 | Policy | 150 | DI | 51 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1479 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510908541 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908541 | T1 Policy | 5.2 | Policy | 4 | DI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.338 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510908542 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908542 | T1 Policy | 3.4 | Policy | 6 | SI | 55 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.187 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510908544 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908544 | T1 Policy | 4.9 | Policy | 4 | SI | 55 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2695 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510951056 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Natasha Barrett | IMGA222088 | MANTON CLOSE | 510951056 | T1 Policy | 21.5 | Policy | 4 | DI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5375 | 0 | CMO West 2 | IMGA222088 | MANTON CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510953575 | CMO | CMO West 2 | July | 18 | A | Shane Compton | Natasha Barrett | IMGA222097 | WARLEY AVENUE | 510953575 | T1 Policy | 16.2 | Policy | 6 | DI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.43 | 0 | CMO West 2 | IMGA222097 | WARLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510948812 | CMO | CMO West 2 | July | 18 | A | Shane Compton | William Sadler | IMGA222099 | CRANBORNE WAYE | 510948812 | T1 Policy | 4.9 | Policy | 6 | DI | 64 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3136 | 0 | CMO West 2 | IMGA222099 | CRANBORNE WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
510914679 | CMO | CMO West 2 | July | 18 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914679 | T1 Policy | 5 | Policy | 6 | SI | 196 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.98 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510914682 | CMO | CMO West 2 | July | 18 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914682 | T1 Policy | 4 | Policy | 100 | DI | 40 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.16 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
- | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | William Madge | IMGA222135 | Cherry Tree Lane | - | Condition | 0 | Non Policy | 1.5 | ST | 53 | inch | 1.5inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222135 | Cherry Tree Lane | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 CONNECTED | tRIIO BROWN, Warren | LP | #N/A | <=3” | 1.5 |  | Non Policy | Tier 1 | ST | ST LP <=3" | July
510971335 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | BURROUGHS CRESCENT | 510971335 | T1 Policy | 4.6 | Policy | 4 | DI | 49 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2254 | 0 | CMO West 2 | IMGA222357 | BURROUGHS CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | July
510971336 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | BURROUGHS CRESCENT | 510971336 | T1 Policy | 7.5 | Policy | 4 | SI | 8 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.06 | 0 | CMO West 2 | IMGA222357 | BURROUGHS CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
510971336 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | BURROUGHS CRESCENT | 510971336 | T1 Policy | 7.5 | Policy | 6 | DI | 33 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2475 | 0 | CMO West 2 | IMGA222357 | BURROUGHS CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | July
220000675532 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | BURROUGHS CRESCENT | 220000675532 | T1 Policy | 3.1 | Policy | 4 | SI | 5 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0155 | 0 | CMO West 2 | IMGA222357 | BURROUGHS CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
220000675533 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | BURROUGHS CRESCENT | 220000675533 | T1 Policy | 5.6 | Policy | 4 | SI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0112 | 0 | CMO West 2 | IMGA222357 | BURROUGHS CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | July
- | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | WENDOVER ROAD | - | Condition | 0 | Non Policy | 3 | ST | 35 | inch | 3inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222357 | WENDOVER ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 CONNECTED | CMO ASHDOWN, Tom | LP | #N/A | <=3” | 3 |  | Non Policy | Tier 1 | ST | ST LP <=3" | July
510934538 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | WENDOVER ROAD | 510934538 | T1 Policy | 1.8 | Policy | 6 | SI | 393 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7074 | 0 | CMO West 2 | IMGA222357 | WENDOVER ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
220000686929 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Adam Madge | IMGA222357 | WENDOVER ROAD | 220000686929 | T1 Policy | 1.7 | Policy | 6 | SI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0102 | 0 | CMO West 2 | IMGA222357 | WENDOVER ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510937064 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | WHITEPIT LANE | 510937064 | T1 Policy | 2.9 | Policy | 6 | SI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.116 | 0 | CMO West 2 | IMGA222360 | WHITEPIT LANE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510781691 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | William Madge | IMGA222373 | AMERSHAM HILL DRIVE | 510781691 | T1 Policy | 2.7 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.27 | 0 | CMO West 2 | IMGA222373 | AMERSHAM HILL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | July
510849459 | CMO | CMO West 2 | July | 18 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 1.2 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT |  | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | July
510929606 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Ryan Smeaton | IMGA222407 | VANDYKE | 510929606 | Condition | 0 | Non Policy | 2 | ST | 41 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222407 | VANDYKE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 CBA | CMO CLARK (OMJ), James | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | August
510867449 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | 510867449 | T1 Policy | 10.1 | Policy | 4 | SI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.616 | 0 | CMO West 2 | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510908543 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908543 | T1 Policy | 5.5 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.275 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510909933 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Phil Walden | IMGA222245 | SHACKLETON ROAD | 510909933 | T1 Policy | 150.5 | Policy | 4 | DI | 215 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 32.3575 | 0 | CMO West 2 | IMGA222245 | SHACKLETON ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510937065 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | WHITEPIT LANE | 510937065 | T1 Policy | 9.7 | Policy | 4 | SI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.388 | 0 | CMO West 2 | IMGA222360 | WHITEPIT LANE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510944769 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Phil Walden | IMGA222237 | BOWES ROAD | 510944769 | T1 Policy | 0 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222237 | BOWES ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities |  | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220001219438 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Chris Douglas | IMGA222324 | ACCESS FROM OAKEN GROVE TO FURZE PLATT INFANT AND FURZE PLATT JUNIOR SCHOOL | 220001219438 | T1 Policy | 2.1 | Policy | 4 | CI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.063 | 0 | CMO West 2 | IMGA222324 | ACCESS FROM OAKEN GROVE TO FURZE PLATT INFANT AND FURZE PLATT JUNIOR SCHOOL | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510778942 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | William Madge | IMGA222373 | TUCKER CLOSE | 510778942 | T1 Policy | 3.5 | Policy | 6 | CI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.245 | 0 | CMO West 2 | IMGA222373 | TUCKER CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT |  | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510781691 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | William Madge | IMGA222373 | AMERSHAM HILL DRIVE | 510781691 | T1 Policy | 2.7 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.27 | 0 | CMO West 2 | IMGA222373 | AMERSHAM HILL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510867590 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | Adam Madge | IMGA222359 | LITTLEWORTH ROAD | 510867590 | T1 PAST | 390.7 | Policy | 6 | CI | 250 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 97.675 | 0 | CMO West 2 | IMGA222359 | LITTLEWORTH ROAD | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510908542 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908542 | T1 Policy | 3.4 | Policy | 6 | SI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.306 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510914679 | CMO | CMO West 2 | August | 19 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914679 | T1 Policy | 5 | Policy | 6 | SI | 29 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.145 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510943504 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Phil Walden | IMGA222237 | BOWES ROAD | 510943504 | T1 Policy | 5.9 | Policy | 6 | SI | 85 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5015 | 0 | CMO West 2 | IMGA222237 | BOWES ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510953575 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Natasha Barrett | IMGA222097 | WARLEY AVENUE | 510953575 | T1 Policy | 16.2 | Policy | 6 | DI | 142 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3004 | 0 | CMO West 2 | IMGA222097 | WARLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
220000706284 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 220000706284 | T1 Policy | 7.9 | Policy | 6 | SI | 16 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1264 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
220001689190 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | Adam Madge | IMGA222359 | HITHERCROFT ROAD | 220001689190 | T1 Policy | 0 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222359 | HITHERCROFT ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
Side Street | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Leigh Osaer | IMGA222301 | LALEHAM ROAD | Side Street | T1 Policy | 0 | Policy | 6 | CI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO MCQUADE, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510849459 | CMO | CMO West 2 | August | 19 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 1.2 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510885608 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 510885608 | T1 Policy | 2 | Policy | 8 | SI | 177 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.354 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510953987 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 510953987 | T1 Policy | 4.1 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.41 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510944409 | CMO | CMO West 2 | August | 19 | A | Mario Gesner | Leigh Osaer | IMGA222301 | LALEHAM ROAD | 510944409 | T2 PAST | 233.5 | Policy | 12 | DI | 193 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 45.0655 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T2 PAST | tRIIO MCQUADE, Barry | LP | #N/A | 10-12” | 12 |  | Policy | Tier 2 | DI | T2A | August
510897489 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897489 | T1 Policy | 3.5 | Policy | 100 | DI | 80 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.28 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510914681 | CMO | CMO West 2 | August | 19 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914681 | T1 Policy | 4 | Policy | 100 | DI | 45 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.18 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510914682 | CMO | CMO West 2 | August | 19 | A | Shane Compton | William Sadler | IMGA222402 | SPRING MEADOW | 510914682 | T1 Policy | 4 | Policy | 100 | DI | 74 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.296 | 0 | CMO West 2 | IMGA222402 | SPRING MEADOW | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510897486 | CMO | CMO West 2 | August | 19 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897486 | T1 Policy | 2.9 | Policy | 150 | DI | 50 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.145 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
- | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Phil Walden | IMGA222237 | RIVERSIDE DRIVE | - | Condition | 0 | Non Policy | 2 | ST | 42 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222237 | RIVERSIDE DRIVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities |  | CMO HARRIS, Rob | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | August
510861869 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Chris Douglas | IMGA222241 | KNOWLE GROVE | 510861869 | T1 Policy | 4.3 | Policy | 4 | CI | 12 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0516 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510909931 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Phil Walden | IMGA222245 | SHACKLETON ROAD | 510909931 | T1 Policy | 12.9 | Policy | 4 | SI | 95 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2255 | 0 | CMO West 2 | IMGA222245 | SHACKLETON ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510909933 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Phil Walden | IMGA222245 | SHACKLETON ROAD | 510909933 | T1 Policy | 150.5 | Policy | 4 | SI | 105 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 15.8025 | 0 | CMO West 2 | IMGA222245 | SHACKLETON ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510886480 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Leigh Osaer | IMGA222315 | OLD COURT CLOSE | 510886480 | T1 Policy | 7.8 | Policy | 6 | SI | 8 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0624 | 0 | CMO West 2 | IMGA222315 | OLD COURT CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510932828 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Leigh Osaer | IMGA222315 | WARWICK CLOSE | 510932828 | T1 Policy | 9.7 | Policy | 4 | SI | 67 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6499 | 0 | CMO West 2 | IMGA222315 | WARWICK CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510932830 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Leigh Osaer | IMGA222315 | WARWICK CLOSE | 510932830 | T1 Policy | 3.2 | Policy | 4 | SI | 82 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2624 | 0 | CMO West 2 | IMGA222315 | WARWICK CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510939057 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Leigh Osaer | IMGA222315 | WINCHESTER DRIVE | 510939057 | T1 Policy | 4.8 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.072 | 0 | CMO West 2 | IMGA222315 | WINCHESTER DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220000706282 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Chris Douglas | IMGA222324 | CLAREFIELD ROAD | 220000706282 | T1 Policy | 5.2 | Policy | 4 | CI | 33 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1716 | 0 | CMO West 2 | IMGA222324 | CLAREFIELD ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220001219438 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 220001219438 | T1 Policy | 2.1 | Policy | 4 | CI | 160 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.336 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities |  | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
220000706284 | CMO | CMO West 2 | August | 20 | A | Mario Gesner | Chris Douglas | IMGA222324 | OAKEN GROVE | 220000706284 | T1 Policy | 7.9 | Policy | 6 | SI | 207 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6353 | 0 | CMO West 2 | IMGA222324 | OAKEN GROVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510908542 | CMO | CMO West 2 | August | 20 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908542 | T1 Policy | 3.4 | Policy | 6 | SI | 7 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0238 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510908543 | CMO | CMO West 2 | August | 20 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908543 | T1 Policy | 5.5 | Policy | 4 | SI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1485 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510908544 | CMO | CMO West 2 | August | 20 | A | Shane Compton | Ryan Smeaton | IMGA222010 | SARUM | 510908544 | T1 Policy | 4.9 | Policy | 4 | SI | 91 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4459 | 0 | CMO West 2 | IMGA222010 | SARUM | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510949096 | CMO | CMO West 2 | August | 20 | A | Shane Compton | William Sadler | IMGA222099 | DORCHESTER WAYE | 510949096 | T1 Policy | 9.6 | Policy | 6 | DI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.96 | 0 | CMO West 2 | IMGA222099 | DORCHESTER WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510948908 | CMO | CMO West 2 | August | 20 | A | Shane Compton | Natasha Barrett | IMGA222105 | DALE DRIVE | 510948908 | T1 Policy | 8.3 | Policy | 6 | DI | 155 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.2865 | 0 | CMO West 2 | IMGA222105 | DALE DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510953987 | CMO | CMO West 2 | August | 20 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 510953987 | T1 Policy | 4.1 | Policy | 8 | SI | 130 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.533 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510935399 | CMO | CMO West 2 | August | 20 | A | Shane Compton | William Sadler | IMGA222402 | WESTBROOK GARDENS | 510935399 | T1 Policy | 5 | Policy | 4 | SI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.65 | 0 | CMO West 2 | IMGA222402 | WESTBROOK GARDENS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220001689190 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | Adam Madge | IMGA222359 | HITHERCROFT ROAD | 220001689190 | T1 Policy | 0 | Policy | 6 | CI | 2 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222359 | HITHERCROFT ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510867590 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | Adam Madge | IMGA222359 | LITTLEWORTH ROAD | 510867590 | T1 PAST | 390.7 | Policy | 6 | CI | 93 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 36.3351 | 0 | CMO West 2 | IMGA222359 | LITTLEWORTH ROAD | Wycombe District Council | West 2 | FALSE | PAST | KLT | T1 PAST | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510867589 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | Adam Madge | IMGA222359 | OLD FARM ROAD | 510867589 | T1 Policy | 7.7 | Policy | 4 | DI | 93 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7161 | 0 | CMO West 2 | IMGA222359 | OLD FARM ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510886504 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | Adam Madge | IMGA222359 | OLD FARM ROAD | 510886504 | T1 Policy | 17.9 | Policy | 4 | CI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4165 | 0 | CMO West 2 | IMGA222359 | OLD FARM ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510781691 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | William Madge | IMGA222373 | AMERSHAM HILL DRIVE | 510781691 | T1 Policy | 2.7 | Policy | 6 | SI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.216 | 0 | CMO West 2 | IMGA222373 | AMERSHAM HILL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510781778 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | William Madge | IMGA222373 | Amersham Road | 510781778 | T1 Policy | 0 | Policy | 8 | CI | 40 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222373 | Amersham Road | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510867443 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | 510867443 | T1 Policy | 0 | Policy | 4 | SI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510867449 | CMO | CMO West 2 | August | 20 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | 510867449 | T1 Policy | 10.1 | Policy | 4 | SI | 140 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.414 | 0 | CMO West 2 | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510941285 | CMO | CMO West 2 | August | 21 | A | Mario Gesner | Leigh Osaer | IMGA222020 | WOODLANDS CLOSE | 510941285 | T1 Policy | 6.4 | Policy | 4 | SI | 106 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6784 | 0 | CMO West 2 | IMGA222020 | WOODLANDS CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510864087 | CMO | CMO West 2 | August | 21 | A | Mario Gesner | Phil Walden | IMGA222234 | LAUREL AVENUE | 510864087 | T1 Policy | 4.8 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.48 | 0 | CMO West 2 | IMGA222234 | LAUREL AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
- | CMO | CMO West 2 | August | 21 | A | Mario Gesner | Phil Walden | IMGA222245 | BELGRAVE ROAD | - | T1 Policy | 0 | Policy | 6 | SI | 250 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222245 | BELGRAVE ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510841791 | CMO | CMO West 2 | August | 21 | A | Mario Gesner | Chris Douglas | IMGA222322 | GREENWAYS DRIVE | 510841791 | T1 Policy | 5.2 | Policy | 4 | SI | 173 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8996 | 0 | CMO West 2 | IMGA222322 | GREENWAYS DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220001315404 | CMO | CMO West 2 | August | 21 | A | Mario Gesner | Chris Douglas | IMGA222322 | PINKNEYS ROAD | 220001315404 | T1 Policy | 3.2 | Policy | 6 | SI | 180 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.576 | 0 | CMO West 2 | IMGA222322 | PINKNEYS ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510897486 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897486 | T1 Policy | 2.9 | Policy | 150 | DI | 52 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1508 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510897487 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Ryan Smeaton | IMGA222009 | QUINTILIS | 510897487 | T1 Policy | 4.1 | Policy | 100 | DI | 73 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2993 | 0 | CMO West 2 | IMGA222009 | QUINTILIS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510952561 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 510952561 | T1 Policy | 6.3 | Policy | 6 | DI | 114 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7182 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510952572 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 510952572 | T1 Policy | 6.7 | Policy | 6 | DI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.67 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
220001258122 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 220001258122 | T1 Policy | 3.7 | Policy | 6 | DI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0111 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
220001258127 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 220001258127 | T1 Policy | 3.7 | Policy | 6 | DI | 4 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0148 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510949096 | CMO | CMO West 2 | August | 21 | A | Shane Compton | William Sadler | IMGA222099 | DORCHESTER WAYE | 510949096 | T1 Policy | 9.6 | Policy | 6 | DI | 80 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.768 | 0 | CMO West 2 | IMGA222099 | DORCHESTER WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510948154 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Natasha Barrett | IMGA222105 | BYRON WAY | 510948154 | T1 Policy | 6.2 | Policy | 6 | DI | 143 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8866 | 0 | CMO West 2 | IMGA222105 | BYRON WAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510948908 | CMO | CMO West 2 | August | 21 | A | Shane Compton | Natasha Barrett | IMGA222105 | DALE DRIVE | 510948908 | T1 Policy | 8.3 | Policy | 6 | DI | 137 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.1371 | 0 | CMO West 2 | IMGA222105 | DALE DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510935398 | CMO | CMO West 2 | August | 21 | A | Shane Compton | William Sadler | IMGA222402 | WESTBROOK GARDENS | 510935398 | T1 Policy | 9 | Policy | 4 | SI | 152 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.368 | 0 | CMO West 2 | IMGA222402 | WESTBROOK GARDENS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510935399 | CMO | CMO West 2 | August | 21 | A | Shane Compton | William Sadler | IMGA222402 | WESTBROOK GARDENS | 510935399 | T1 Policy | 5 | Policy | 4 | SI | 17 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.085 | 0 | CMO West 2 | IMGA222402 | WESTBROOK GARDENS | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510838501 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | Adam Madge | IMGA222137 | GOLD HILL WEST | 510838501 | T1 PAST | 251.9 | Policy | 8 | CI | 37 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.3203 | 0 | CMO West 2 | IMGA222137 | GOLD HILL WEST | Chiltern District Council (Lower) | West 2 | FALSE | PAST | KLT | T1 PAST | CMO SMITH KLT, Russell | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510888691 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | Adam Madge | IMGA222278 | PACKHORSE ROAD | 510888691 | T1 Policy | 1.6 | Policy | 6 | SI | 130 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.208 | 0 | CMO West 2 | IMGA222278 | PACKHORSE ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510781778 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | William Madge | IMGA222373 | Amersham Road | 510781778 | T1 Policy | 27 | Policy | 8 | CI | 85 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.295 | 0 | CMO West 2 | IMGA222373 | Amersham Road | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510849459 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 1.2 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510858476 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | KENNEDY CLOSE | 510858476 | T1 Policy | 13.8 | Policy | 4 | SI | 79 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0902 | 0 | CMO West 2 | IMGA222380 | KENNEDY CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510942440 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942440 | T1 Policy | 10 | Policy | 4 | SI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.64 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510942440 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942440 | T1 Policy | 10 | Policy | 6 | SI | 186 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.86 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510826651 | CMO | CMO West 2 | August | 21 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | ELIZABETH ROAD | 510826651 | T1 Policy | 7.5 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.125 | 0 | CMO West 2 | IMGA222382 | ELIZABETH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510963972 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 4.4 | Policy | 4 | SI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.77 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510941285 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Leigh Osaer | IMGA222020 | WOODLANDS CLOSE | 510941285 | T1 Policy | 6.4 | Policy | 4 | SI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.384 | 0 | CMO West 2 | IMGA222020 | WOODLANDS CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510864087 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Phil Walden | IMGA222234 | LAUREL AVENUE | 510864087 | T1 Policy | 4.8 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.24 | 0 | CMO West 2 | IMGA222234 | LAUREL AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220000796795 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Phil Walden | IMGA222245 | BELGRAVE ROAD | 220000796795 | T1 Policy | 8.2 | Policy | 4 | DI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.205 | 0 | CMO West 2 | IMGA222245 | BELGRAVE ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510909933 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Phil Walden | IMGA222245 | SHACKLETON ROAD | 510909933 | T1 Policy | 150.5 | Policy | 4 | SI | 140 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 21.07 | 0 | CMO West 2 | IMGA222245 | SHACKLETON ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
220001323184 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Phil Walden | IMGA222245 | SHACKLETON ROAD | 220001323184 | T1 Policy | 0 | Policy | 4 | DI | 40 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222245 | SHACKLETON ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510944409 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Leigh Osaer | IMGA222301 | LALEHAM ROAD | 510944409 | T2 PAST | 233.5 | Policy | 12 | DI | 98 | inch | 12inch | Abandonment 10-12” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 22.883 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T2 PAST | tRIIO MCQUADE, Barry | LP | #N/A | 10-12” | 12 |  | Policy | Tier 2 | DI | T2A | August
510873970 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Leigh Osaer | IMGA222319 | MARLBOROUGH ROAD | 510873970 | T1 Policy | 4.9 | Policy | 8 | SI | 160 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.784 | 0 | CMO West 2 | IMGA222319 | MARLBOROUGH ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510873971 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Leigh Osaer | IMGA222319 | MARLBOROUGH ROAD | 510873971 | T1 Policy | 14 | Policy | 4 | SI | 13 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.182 | 0 | CMO West 2 | IMGA222319 | MARLBOROUGH ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510966103 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Chris Douglas | IMGA222322 | HALIFAX WAY | 510966103 | T1 Policy | 4.7 | Policy | 4 | DI | 63 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2961 | 0 | CMO West 2 | IMGA222322 | HALIFAX WAY | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
220001315404 | CMO | CMO West 2 | August | 22 | A | Mario Gesner | Chris Douglas | IMGA222322 | PINKNEYS ROAD | 220001315404 | T1 Policy | 3.2 | Policy | 6 | SI | 69 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2208 | 0 | CMO West 2 | IMGA222322 | PINKNEYS ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | August
510964489 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Ryan Smeaton | IMGA222011 | TAWFIELD | 510964489 | T1 Policy | 1.8 | Policy | 4 | DI | 34 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0612 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510964490 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Ryan Smeaton | IMGA222011 | TAWFIELD | 510964490 | T1 Policy | 2.7 | Policy | 4 | DI | 305 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8235 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510926852 | CMO | CMO West 2 | August | 22 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926852 | T1 Policy | 4.1 | Policy | 4 | DI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2624 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | August
510951214 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222097 | MILTON CLOSE | 510951214 | T1 Policy | 5.6 | Policy | 4 | SI | 140 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.784 | 0 | CMO West 2 | IMGA222097 | MILTON CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510952561 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 510952561 | T1 Policy | 6.3 | Policy | 6 | DI | 84 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5292 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
220001246142 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 220001246142 | T1 Policy | 4 | Policy | 6 | DI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
220001255004 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222097 | SHAKESPEARE AVENUE | 220001255004 | T1 Policy | 6.7 | Policy | 6 | DI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0335 | 0 | CMO West 2 | IMGA222097 | SHAKESPEARE AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510948909 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222105 | DALE DRIVE | 510948909 | T1 Policy | 10 | Policy | 6 | DI | 145 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.45 | 0 | CMO West 2 | IMGA222105 | DALE DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | August
510951114 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222126 | MAYGOODS GREEN | 510951114 | T1 Policy | 7.9 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.395 | 0 | CMO West 2 | IMGA222126 | MAYGOODS GREEN | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510953987 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 510953987 | T1 Policy | 4.1 | Policy | 8 | SI | 66 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2706 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | August
510953988 | CMO | CMO West 2 | August | 22 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 510953988 | T1 Policy | 10.9 | Policy | 4 | SI | 93 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0137 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | August
510888691 | CMO | CMO West 2 | August | 22 | A | Tony Ingram 2 | Adam Madge | IMGA222278 | PACKHORSE ROAD | 510888691 | T1 Policy | 1.6 | Policy | 6 | CI | 130 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.208 | 0 | CMO West 2 | IMGA222278 | PACKHORSE ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510849459 | CMO | CMO West 2 | August | 22 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 1.2 | Policy | 8 | CI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.12 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | August
510878036 | CMO | CMO West 2 | August | 22 | A | Tony Ingram 2 | William Madge | IMGA222378 | MISBOURNE AVENUE | 510878036 | T1 Policy | 5.7 | Policy | 4 | CI | 47 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2679 | 0 | CMO West 2 | IMGA222378 | MISBOURNE AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510942442 | CMO | CMO West 2 | August | 22 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942442 | T1 Policy | 3.2 | Policy | 6 | CI | 300 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.96 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | August
510825884 | CMO | CMO West 2 | August | 22 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | EDINBURGH ROAD | 510825884 | T1 Policy | 24.6 | Policy | 4 | CI | 155 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.813 | 0 | CMO West 2 | IMGA222382 | EDINBURGH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
DR4 Requested | CMO | CMO West 2 | August | 22 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | ELIZABETH ROAD | DR4 Requested | T1 Policy | 0 | Policy | 4 | CI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222382 | ELIZABETH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT |  | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | August
510867723 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR CLOSE | 510867723 | T1 Policy | 6 | Policy | 4 | SI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.36 | 0 | CMO West 2 | IMGA222020 | LLANVAIR CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510864087 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Phil Walden | IMGA222234 | LAUREL AVENUE | 510864087 | T1 Policy | 4.8 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.24 | 0 | CMO West 2 | IMGA222234 | LAUREL AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510861868 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Chris Douglas | IMGA222241 | KNOWLE GROVE | 510861868 | T1 Policy | 4.3 | Policy | 4 | CI | 130 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.559 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220000796795 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Phil Walden | IMGA222245 | BELGRAVE ROAD | 220000796795 | T1 Policy | 8.2 | Policy | 4 | SI | 166 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3612 | 0 | CMO West 2 | IMGA222245 | BELGRAVE ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
220000787114 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Chris Douglas | IMGA222322 | CAMLEY GARDENS | 220000787114 | T1 Policy | 1.9 | Policy | 6 | SI | 114 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2166 | 0 | CMO West 2 | IMGA222322 | CAMLEY GARDENS | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220000836500 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Chris Douglas | IMGA222322 | CAMLEY GARDENS | 220000836500 | T1 Policy | 2.3 | Policy | 6 | SI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0138 | 0 | CMO West 2 | IMGA222322 | CAMLEY GARDENS | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001315404 | CMO | CMO West 2 | September | 23 | A | Mario Gesner | Chris Douglas | IMGA222322 | PINKNEYS ROAD | 220001315404 | T1 Policy | 3.2 | Policy | 6 | SI | 148 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4736 | 0 | CMO West 2 | IMGA222322 | PINKNEYS ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510964488 | CMO | CMO West 2 | September | 23 | A | Shane Compton | Ryan Smeaton | IMGA222011 | TAWFIELD | 510964488 | T1 Policy | 3.1 | Policy | 100 | DI | 167 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5177 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926852 | CMO | CMO West 2 | September | 23 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926852 | T1 Policy | 4.1 | Policy | 4 | DI | 98 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4018 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510949163 | CMO | CMO West 2 | September | 23 | A | Shane Compton | Natasha Barrett | IMGA222097 | DUNBAR CLOSE | 510949163 | T1 Policy | 23.9 | Policy | 4 | DI | 173 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.1347 | 0 | CMO West 2 | IMGA222097 | DUNBAR CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510948155 | CMO | CMO West 2 | September | 23 | A | Shane Compton | Natasha Barrett | IMGA222105 | BYRON WAY | 510948155 | T1 Policy | 10.9 | Policy | 6 | DI | 152 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6568 | 0 | CMO West 2 | IMGA222105 | BYRON WAY | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510953988 | CMO | CMO West 2 | September | 23 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 510953988 | T1 Policy | 10.9 | Policy | 4 | SI | 129 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.4061 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
606497147 | CMO | CMO West 2 | September | 23 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 606497147 | T1 Policy | 3.4 | Policy | 4 | CI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0238 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510963901 | CMO | CMO West 2 | September | 23 | A | Shane Compton | Ryan Smeaton | IMGA222436 | GAINSBOROUGH DRIVE | 510963901 | T1 Policy | 6 | Policy | 100 | DI | 55 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.33 | 0 | CMO West 2 | IMGA222436 | GAINSBOROUGH DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510913112 | CMO | CMO West 2 | September | 23 | A | TBA - Lon | Kerry Dolan | IMGA222279 | SOUTH PARK CRESCENT | 510913112 | T1 Policy | 3.4 | Policy | 4 | CI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.34 | 0 | CMO West 2 | IMGA222279 | SOUTH PARK CRESCENT | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | SQS JONES, Ashton | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510954230 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222271 | THE FAIRWAY | 510954230 | T1 Policy | 5.8 | Policy | 4 | SI | 270 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.566 | 0 | CMO West 2 | IMGA222271 | THE FAIRWAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510888691 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Adam Madge | IMGA222278 | PACKHORSE ROAD | 510888691 | T1 Policy | 1.6 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.192 | 0 | CMO West 2 | IMGA222278 | PACKHORSE ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220001696693 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 220001696693 | T1 Policy | 0 | Policy | 4 | CI | 116 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510942441 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942441 | T1 Policy | 9.6 | Policy | 4 | CI | 239 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.2944 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510942444 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942444 | T1 Policy | 4 | Policy | 4 | SI | 61 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.244 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510825884 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | EDINBURGH ROAD | 510825884 | T1 Policy | 24.6 | Policy | 4 | CI | 53 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3038 | 0 | CMO West 2 | IMGA222382 | EDINBURGH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
- | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | ELIZABETH ROAD | - | T1 Policy | 0 | Policy | 4 | CI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222382 | ELIZABETH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510826651 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | ELIZABETH ROAD | 510826651 | T1 Policy | 7.5 | Policy | 4 | SI | 23 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1725 | 0 | CMO West 2 | IMGA222382 | ELIZABETH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510826653 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | ELIZABETH ROAD | 510826653 | T1 Policy | 11.2 | Policy | 4 | CI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.512 | 0 | CMO West 2 | IMGA222382 | ELIZABETH ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510867443 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | 510867443 | T1 Policy | 0 | Policy | 4 | CI | 2 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510867449 | CMO | CMO West 2 | September | 23 | A | Tony Ingram 2 | Kerry Dolan | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | 510867449 | T1 Policy | 10.1 | Policy | 4 | CI | 19 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1919 | 0 | CMO West 2 | IMGA222382 | LITTLE MARLOW ROAD SERVICE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510867723 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR CLOSE | 510867723 | T1 Policy | 6 | Policy | 4 | CI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.18 | 0 | CMO West 2 | IMGA222020 | LLANVAIR CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510963973 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963973 | T1 Policy | 11.2 | Policy | 4 | CI | 170 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.904 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510869480 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Phil Walden | IMGA222228 | LONGSIDE CLOSE | 510869480 | T1 Policy | 4.7 | Policy | 4 | SI | 74 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3478 | 0 | CMO West 2 | IMGA222228 | LONGSIDE CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PUGSLEY, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510861868 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Chris Douglas | IMGA222241 | KNOWLE GROVE | 510861868 | T1 Policy | 4.3 | Policy | 4 | CI | 131 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5633 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510944404 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Leigh Osaer | IMGA222301 | LALEHAM ROAD | 510944404 | T2 PAST | 507.6 | Policy | 15 | SI | 158 | inch | 15inch | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 80.2008 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T2 PAST | tRIIO MCQUADE, Barry | LP | #N/A | >12-17” | 15 |  | Policy | Tier 2 | SI | T2A | September
510851763 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Leigh Osaer | IMGA222319 | HIGHWAY AVENUE | 510851763 | T1 Policy | 5.3 | Policy | 6 | SI | 113 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5989 | 0 | CMO West 2 | IMGA222319 | HIGHWAY AVENUE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001558486 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Leigh Osaer | IMGA222319 | HIGHWAY AVENUE | 220001558486 | T1 Policy | 6 | Policy | 4 | SI | 21 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.126 | 0 | CMO West 2 | IMGA222319 | HIGHWAY AVENUE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510801821 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Chris Douglas | IMGA222322 | CAMLEY GARDENS | 510801821 | T1 Policy | 3.7 | Policy | 4 | SI | 26 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0962 | 0 | CMO West 2 | IMGA222322 | CAMLEY GARDENS | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
220000836500 | CMO | CMO West 2 | September | 24 | A | Mario Gesner | Chris Douglas | IMGA222322 | CAMLEY GARDENS | 220000836500 | T1 Policy | 2.3 | Policy | 6 | SI | 190 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.437 | 0 | CMO West 2 | IMGA222322 | CAMLEY GARDENS | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510964486 | CMO | CMO West 2 | September | 24 | A | Shane Compton | William Sadler | IMGA222011 | TAWFIELD | 510964486 | T1 Policy | 3.2 | Policy | 100 | DI | 28 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0896 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ |  | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510964487 | CMO | CMO West 2 | September | 24 | A | Shane Compton | William Sadler | IMGA222011 | TAWFIELD | 510964487 | T1 Policy | 3.3 | Policy | 100 | DI | 100 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.33 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510949097 | CMO | CMO West 2 | September | 24 | A | Shane Compton | William Sadler | IMGA222099 | BROOKSIDE ROAD | 510949097 | T1 Policy | 2.2 | Policy | 6 | SI | 15 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.033 | 0 | CMO West 2 | IMGA222099 | BROOKSIDE ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510949096 | CMO | CMO West 2 | September | 24 | A | Shane Compton | William Sadler | IMGA222099 | DORCHESTER WAYE | 510949096 | T1 Policy | 9.6 | Policy | 6 | SI | 82 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7872 | 0 | CMO West 2 | IMGA222099 | DORCHESTER WAYE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001337503 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Natasha Barrett | IMGA222101 | BALMORAL DRIVE | 220001337503 | T1 Policy | 2.5 | Policy | 6 | CI | 83 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2075 | 0 | CMO West 2 | IMGA222101 | BALMORAL DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510953995 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Natasha Barrett | IMGA222101 | WYATT CLOSE | 510953995 | T1 Policy | 5.5 | Policy | 4 | SI | 152 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.836 | 0 | CMO West 2 | IMGA222101 | WYATT CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510947979 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Natasha Barrett | IMGA222104 | BRADENHAM ROAD | 510947979 | T1 Policy | 62 | Policy | 6 | DI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.3 | 0 | CMO West 2 | IMGA222104 | BRADENHAM ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510951114 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Natasha Barrett | IMGA222126 | MAYGOODS GREEN | 510951114 | T1 Policy | 7.9 | Policy | 4 | SI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.185 | 0 | CMO West 2 | IMGA222126 | MAYGOODS GREEN | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510953989 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 510953989 | T1 Policy | 18.7 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.309 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510964512 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Ryan Smeaton | IMGA222406 | FOREST ROAD | 510964512 | T1 Policy | 6 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6 | 0 | CMO West 2 | IMGA222406 | FOREST ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 CBA | tRIIO GOODBODY, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510963902 | CMO | CMO West 2 | September | 24 | A | Shane Compton | Ryan Smeaton | IMGA222436 | GAINSBOROUGH DRIVE | 510963902 | T1 Policy | 5 | Policy | 100 | DI | 50 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.25 | 0 | CMO West 2 | IMGA222436 | GAINSBOROUGH DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510954223 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | Kerry Dolan | IMGA222271 | THE FAIRWAY | 510954223 | T1 Policy | 7.4 | Policy | 4 | SI | 190 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.406 | 0 | CMO West 2 | IMGA222271 | THE FAIRWAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510886631 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | Kerry Dolan | IMGA222275 | OLD MILL ROAD | 510886631 | T1 Policy | 2.5 | Policy | 4 | SI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5 | 0 | CMO West 2 | IMGA222275 | OLD MILL ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO SCOTT, David | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510888691 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | Adam Madge | IMGA222278 | PACKHORSE ROAD | 510888691 | T1 Policy | 1.6 | Policy | 6 | CI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.08 | 0 | CMO West 2 | IMGA222278 | PACKHORSE ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510922874 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRAIGHT BIT | 510922874 | T1 Policy | 6.8 | Policy | 6 | SI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.204 | 0 | CMO West 2 | IMGA222360 | STRAIGHT BIT | Wycombe District Council | West 2 | FALSE |  | KLT |  | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001244906 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRAIGHT BIT | 220001244906 | T1 Policy | 2.1 | Policy | 6 | SI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.189 | 0 | CMO West 2 | IMGA222360 | STRAIGHT BIT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510781691 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | William Madge | IMGA222373 | AMERSHAM HILL DRIVE | 510781691 | T1 Policy | 2.7 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.27 | 0 | CMO West 2 | IMGA222373 | AMERSHAM HILL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510849459 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849459 | T1 Policy | 1.2 | Policy | 6 | CI | 27 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0324 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510849462 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510849462 | T1 Policy | 9.5 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.095 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510968846 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | William Madge | IMGA222378 | HICKS FARM RISE | 510968846 | T1 Policy | 1.8 | Policy | 6 | CI | 25 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.045 | 0 | CMO West 2 | IMGA222378 | HICKS FARM RISE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO GOODMAN KLT, Michael Paul | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510942444 | CMO | CMO West 2 | September | 24 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942444 | T1 Policy | 4 | Policy | 4 | SI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510954231 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Kerry Dolan | IMGA222271 | THE FAIRWAY | 510954231 | T1 Policy | 10.8 | Policy | 2 | SI | 61 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6588 | 0 | CMO West 2 | IMGA222271 | THE FAIRWAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | September
510867722 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR CLOSE | 510867722 | T1 Policy | 4.1 | Policy | 4 | CI | 83 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3403 | 0 | CMO West 2 | IMGA222020 | LLANVAIR CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510867723 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR CLOSE | 510867723 | T1 Policy | 6 | Policy | 4 | CI | 161 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.966 | 0 | CMO West 2 | IMGA222020 | LLANVAIR CLOSE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510963973 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963973 | T1 Policy | 11.2 | Policy | 4 | CI | 73 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8176 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510864087 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Phil Walden | IMGA222234 | LAUREL AVENUE | 510864087 | T1 Policy | 4.8 | Policy | 4 | SI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.168 | 0 | CMO West 2 | IMGA222234 | LAUREL AVENUE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510929801 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Phil Walden | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 5.7 | Policy | 4 | SI | 15 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0855 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510861869 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Chris Douglas | IMGA222241 | KNOWLE GROVE | 510861869 | T1 Policy | 4.3 | Policy | 4 | CI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1935 | 0 | CMO West 2 | IMGA222241 | KNOWLE GROVE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510909933 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Phil Walden | IMGA222245 | SHACKLETON ROAD | 510909933 | T1 Policy | 150.5 | Policy | 4 | DI | 6 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.903 | 0 | CMO West 2 | IMGA222245 | SHACKLETON ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO LARMOUR, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510790117 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Phil Walden | IMGA222254 | BELMONT | 510790117 | T1 Policy | 5.2 | Policy | 4 | DI | 235 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.222 | 0 | CMO West 2 | IMGA222254 | BELMONT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510966869 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Phil Walden | IMGA222254 | GREENSIDE | 510966869 | T1 Policy | 5.9 | Policy | 4 | DI | 220 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.298 | 0 | CMO West 2 | IMGA222254 | GREENSIDE | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510964486 | CMO | CMO West 2 | September | 25 | A | Shane Compton | William Sadler | IMGA222011 | TAWFIELD | 510964486 | T1 Policy | 3.2 | Policy | 4 | DI | 83 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2656 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510964491 | CMO | CMO West 2 | September | 25 | A | Shane Compton | William Sadler | IMGA222011 | TAWFIELD | 510964491 | T1 Policy | 3.4 | Policy | 4 | DI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.34 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926854 | CMO | CMO West 2 | September | 25 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926854 | T1 Policy | 0 | Policy | 4 | DI | 124 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926852 | CMO | CMO West 2 | September | 25 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926852 | T1 Policy | 4.1 | Policy | 4 | SI | 145 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5945 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510950579 | CMO | CMO West 2 | September | 25 | A | Shane Compton | Natasha Barrett | IMGA222101 | JONSON CLOSE | 510950579 | T1 Policy | 5.3 | Policy | 4 | SI | 152 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8056 | 0 | CMO West 2 | IMGA222101 | JONSON CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510907235 | CMO | CMO West 2 | September | 25 | A | TBA - Lon | Kerry Dolan | IMGA222140 | ST NICHOLAS CLOSE | 510907235 | T1 Policy | 7.7 | Policy | 4 | SI | 55 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4235 | 0 | CMO West 2 | IMGA222140 | ST NICHOLAS CLOSE | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510954223 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Kerry Dolan | IMGA222271 | THE FAIRWAY | 510954223 | T1 Policy | 7.4 | Policy | 4 | SI | 229 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.6946 | 0 | CMO West 2 | IMGA222271 | THE FAIRWAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510781694 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | William Madge | IMGA222373 | AMERSHAM HILL DRIVE | 510781694 | T1 Policy | 2.3 | Policy | 4 | SI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0621 | 0 | CMO West 2 | IMGA222373 | AMERSHAM HILL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510942444 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942444 | T1 Policy | 4 | Policy | 4 | SI | 35 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.14 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510942450 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942450 | T1 Policy | 3.7 | Policy | 4 | SI | 64 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2368 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
638667060 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Phil Walden | IMGA222254 | BELMONT | 638667060 | T1 Policy | 3.9 | Policy | 6 | SI | 6 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0234 | 0 | CMO West 2 | IMGA222254 | BELMONT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001315404 | CMO | CMO West 2 | September | 25 | A | Mario Gesner | Chris Douglas | IMGA222322 | PINKNEYS ROAD | 220001315404 | T1 Policy | 3.2 | Policy | 6 | SI | 245 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.784 | 0 | CMO West 2 | IMGA222322 | PINKNEYS ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001337503 | CMO | CMO West 2 | September | 25 | A | Shane Compton | Natasha Barrett | IMGA222101 | BALMORAL DRIVE | 220001337503 | T1 Policy | 2.5 | Policy | 6 | SI | 70 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.175 | 0 | CMO West 2 | IMGA222101 | BALMORAL DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510947979 | CMO | CMO West 2 | September | 25 | A | Shane Compton | Natasha Barrett | IMGA222104 | BRADENHAM ROAD | 510947979 | T1 Policy | 62 | Policy | 6 | DI | 84 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.208 | 0 | CMO West 2 | IMGA222104 | BRADENHAM ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510886632 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Kerry Dolan | IMGA222275 | OLD MILL ROAD | 510886632 | T1 Policy | 1.4 | Policy | 6 | SI | 190 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.266 | 0 | CMO West 2 | IMGA222275 | OLD MILL ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO SCOTT, David | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510888691 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Adam Madge | IMGA222278 | PACKHORSE ROAD | 510888691 | T1 Policy | 1.6 | Policy | 6 | CI | 120 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.192 | 0 | CMO West 2 | IMGA222278 | PACKHORSE ROAD | South Bucks District Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510781691 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | William Madge | IMGA222373 | AMERSHAM HILL DRIVE | 510781691 | T1 Policy | 2.7 | Policy | 6 | SI | 18 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0486 | 0 | CMO West 2 | IMGA222373 | AMERSHAM HILL DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510903780 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Adam Madge | IMGA222375 | ROWAN AVENUE | 510903780 | T1 Policy | 29.2 | Policy | 6 | SI | 190 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.548 | 0 | CMO West 2 | IMGA222375 | ROWAN AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510942442 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942442 | T1 Policy | 3.2 | Policy | 6 | SI | 11 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0352 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510964512 | CMO | CMO West 2 | September | 25 | A | Shane Compton | Ryan Smeaton | IMGA222406 | FOREST ROAD | 510964512 | T1 Policy | 6 | Policy | 8 | SI | 100 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6 | 0 | CMO West 2 | IMGA222406 | FOREST ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 CBA | tRIIO GOODBODY, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510963901 | CMO | CMO West 2 | September | 25 | A | Shane Compton | Ryan Smeaton | IMGA222436 | GAINSBOROUGH DRIVE | 510963901 | T1 Policy | 6 | Policy | 100 | DI | 3 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.018 | 0 | CMO West 2 | IMGA222436 | GAINSBOROUGH DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510942449 | CMO | CMO West 2 | September | 25 | A | Tony Ingram 2 | Adam Madge | IMGA222380 | WYCOMBE ROAD | 510942449 | T1 Policy | 2.5 | Policy | 150 | DI | 27 | mm | 150mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0675 | 0 | CMO West 2 | IMGA222380 | WYCOMBE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 150 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
510963972 | CMO | CMO West 2 | September | 26 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 4.4 | Policy | 4 | SI | 90 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.396 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510966869 | CMO | CMO West 2 | September | 26 | A | Mario Gesner | Phil Walden | IMGA222254 | GREENSIDE | 510966869 | T1 Policy | 5.9 | Policy | 4 | CI | 72 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4248 | 0 | CMO West 2 | IMGA222254 | GREENSIDE | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510924813 | CMO | CMO West 2 | September | 26 | A | Mario Gesner | Phil Walden | IMGA222254 | THORNDIKE | 510924813 | T1 Policy | 6.5 | Policy | 4 | CI | 163 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.0595 | 0 | CMO West 2 | IMGA222254 | THORNDIKE | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510798623 | CMO | CMO West 2 | September | 26 | A | Mario Gesner | Chris Douglas | IMGA222419 | BROX ROAD | 510798623 | T1 Policy | 11 | Policy | 5 | SI | 195 | inch | 5inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.145 | 0 | CMO West 2 | IMGA222419 | BROX ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 5 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510798622 | CMO | CMO West 2 | September | 26 | A | Mario Gesner | Chris Douglas | IMGA222419 | TIMBER HILL CLOSE | 510798622 | T1 Policy | 16 | Policy | 100 | DI | 74 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.184 | 0 | CMO West 2 | IMGA222419 | TIMBER HILL CLOSE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510891870 | CMO | CMO West 2 | September | 26 | A | Mario Gesner | Leigh Osaer | IMGA222429 | PENYSTON ROAD | 510891870 | T1 Policy | 8 | Policy | 7 | SI | 100 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222429 | PENYSTON ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510964490 | CMO | CMO West 2 | September | 26 | A | Shane Compton | William Sadler | IMGA222011 | TAWFIELD | 510964490 | T1 Policy | 2.7 | Policy | 100 | DI | 13 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0351 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510964491 | CMO | CMO West 2 | September | 26 | A | Shane Compton | William Sadler | IMGA222011 | TAWFIELD | 510964491 | T1 Policy | 3.4 | Policy | 100 | DI | 99 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3366 | 0 | CMO West 2 | IMGA222011 | TAWFIELD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO BARRACLOUGH (OMJ), Kirt | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
| CMO | CMO West 2 | September | 26 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN |  | T1 Policy | 0 | Policy | 100 | DI | 5 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926848 | CMO | CMO West 2 | September | 26 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926848 | T1 Policy | 0 | Policy | 4 | CI | 175 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510948930 | CMO | CMO West 2 | September | 26 | A | Shane Compton | Natasha Barrett | IMGA222125 | DAWLEY AVENUE | 510948930 | T1 Policy | 7.9 | Policy | 6 | SI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0395 | 0 | CMO West 2 | IMGA222125 | DAWLEY AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510968613 | CMO | CMO West 2 | September | 26 | A | Shane Compton | Natasha Barrett | IMGA222125 | LANSDOWNE ROAD | 510968613 | T1 Policy | 114.6 | Policy | 6 | CI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.146 | 0 | CMO West 2 | IMGA222125 | LANSDOWNE ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510964512 | CMO | CMO West 2 | September | 26 | A | Shane Compton | Ryan Smeaton | IMGA222406 | FOREST ROAD | 510964512 | T1 Policy | 6 | Policy | 8 | SI | 9 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.054 | 0 | CMO West 2 | IMGA222406 | FOREST ROAD | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 CBA | tRIIO GOODBODY, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510964512 | CMO | CMO West 2 | September | 26 | A | Shane Compton | Ryan Smeaton | IMGA222406 | WARFIELD STREET | 510964512 | T1 Policy | 6 | Policy | 8 | SI | 239 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.434 | 0 | CMO West 2 | IMGA222406 | WARFIELD STREET | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 CBA | tRIIO GOODBODY, Mark | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510963899 | CMO | CMO West 2 | September | 26 | A | Shane Compton | Ryan Smeaton | IMGA222436 | GAINSBOROUGH DRIVE | 510963899 | T1 Policy | 5 | Policy | 100 | DI | 61 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.305 | 0 | CMO West 2 | IMGA222436 | GAINSBOROUGH DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510948259 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Natasha Barrett | IMGA222098 | CERNE CLOSE | 510948259 | T1 Policy | 62.4 | Policy | 4 | DI | 183 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.4192 | 0 | CMO West 2 | IMGA222098 | CERNE CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510948260 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Natasha Barrett | IMGA222098 | CERNE CLOSE | 510948260 | T1 Policy | 5.5 | Policy | 4 | SI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0385 | 0 | CMO West 2 | IMGA222098 | CERNE CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
220001337503 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Natasha Barrett | IMGA222101 | BALMORAL DRIVE | 220001337503 | T1 Policy | 2.5 | Policy | 6 | SI | 105 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2625 | 0 | CMO West 2 | IMGA222101 | BALMORAL DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
220001337503 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Natasha Barrett | IMGA222101 | BALMORAL DRIVE | 220001337503 | T1 Policy | 2.5 | Policy | 8 | SI | 10 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.025 | 0 | CMO West 2 | IMGA222101 | BALMORAL DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510995038 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Natasha Barrett | IMGA222104 | BRADENHAM ROAD | 510995038 | T1 Policy | 26.2 | Policy | 6 | DI | 55 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.441 | 0 | CMO West 2 | IMGA222104 | BRADENHAM ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | September
220001422661 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Natasha Barrett | IMGA222126 | WORCESTER ROAD | 220001422661 | T1 Policy | 7.1 | Policy | 8 | SI | 115 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8165 | 0 | CMO West 2 | IMGA222126 | WORCESTER ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | SI | CI/SI/DI LP 8" | September
510868995 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Kerry Dolan | IMGA222271 | LONG DRIVE | 510868995 | T1 Policy | 61.1 | Policy | 4 | SI | 293 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 17.9023 | 0 | CMO West 2 | IMGA222271 | LONG DRIVE | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510868996 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Kerry Dolan | IMGA222271 | LONG DRIVE | 510868996 | T1 Policy | 12.7 | Policy | 4 | SI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0889 | 0 | CMO West 2 | IMGA222271 | LONG DRIVE | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510820593 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Kerry Dolan | IMGA222275 | DENHAM WAY | 510820593 | T1 Policy | 5 | Policy | 4 | CI | 83 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.415 | 0 | CMO West 2 | IMGA222275 | DENHAM WAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO SCOTT, David | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510820594 | CMO | CMO West 2 | September | 26 | A | TBA - Lon | Kerry Dolan | IMGA222275 | DENHAM WAY | 510820594 | T1 Policy | 4.8 | Policy | 4 | CI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.576 | 0 | CMO West 2 | IMGA222275 | DENHAM WAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO SCOTT, David | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510971129 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | William Madge | IMGA222354 | LOCKBRIDGE ROAD | 510971129 | T1 Policy | 2.6 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.39 | 0 | CMO West 2 | IMGA222354 | LOCKBRIDGE ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
220001244906 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRAIGHT BIT | 220001244906 | T1 Policy | 2.1 | Policy | 6 | CI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.21 | 0 | CMO West 2 | IMGA222360 | STRAIGHT BIT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510778940 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | William Madge | IMGA222373 | ADAM CLOSE | 510778940 | T1 Policy | 123.1 | Policy | 6 | CI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 17.234 | 0 | CMO West 2 | IMGA222373 | ADAM CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510794351 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | Adam Madge | IMGA222375 | BOWERDEAN ROAD | 510794351 | T1 Policy | 29 | Policy | 6 | CI | 119 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 3.451 | 0 | CMO West 2 | IMGA222375 | BOWERDEAN ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510903780 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | Adam Madge | IMGA222375 | ROWAN AVENUE | 510903780 | T1 Policy | 29.2 | Policy | 6 | CI | 187 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.4604 | 0 | CMO West 2 | IMGA222375 | ROWAN AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
220000464649 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | Adam Madge | IMGA222375 | ROWAN AVENUE | 220000464649 | T1 Policy | 2.5 | Policy | 6 | CI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.035 | 0 | CMO West 2 | IMGA222375 | ROWAN AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | September
510786741 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | William Madge | IMGA222377 | BARING ROAD | 510786741 | T1 Policy | 3 | Policy | 4 | SI | 154 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.462 | 0 | CMO West 2 | IMGA222377 | BARING ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510786741 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | William Madge | IMGA222377 | BARING ROAD | 510786741 | T1 Policy | 3 | Policy | 6 | SI | 97 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.291 | 0 | CMO West 2 | IMGA222377 | BARING ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510836320 | CMO | CMO West 2 | September | 26 | A | Tony Ingram 2 | William Madge | IMGA222377 | GAYHURST ROAD | 510836320 | T1 Policy | 3.2 | Policy | 6 | SI | 9 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0288 | 0 | CMO West 2 | IMGA222377 | GAYHURST ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510963972 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 4.4 | Policy | 4 | SI | 120 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.528 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510929801 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Phil Walden | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 5.7 | Policy | 4 | CI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.285 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | September
510790116 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Phil Walden | IMGA222254 | BELMONT | 510790116 | T1 Policy | 5 | Policy | 4 | SI | 243 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.215 | 0 | CMO West 2 | IMGA222254 | BELMONT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
638667060 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Phil Walden | IMGA222254 | BELMONT | 638667060 | T1 Policy | 3.9 | Policy | 6 | SI | 13 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0507 | 0 | CMO West 2 | IMGA222254 | BELMONT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510938444 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Phil Walden | IMGA222254 | WILLONERS | 510938444 | T1 Policy | 6.6 | Policy | 4 | SI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.396 | 0 | CMO West 2 | IMGA222254 | WILLONERS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
220001315404 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Chris Douglas | IMGA222322 | PINKNEYS ROAD | 220001315404 | T1 Policy | 3.2 | Policy | 6 | SI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.032 | 0 | CMO West 2 | IMGA222322 | PINKNEYS ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510798623 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Chris Douglas | IMGA222419 | BROX ROAD | 510798623 | T1 Policy | 11 | Policy | 5 | SI | 230 | inch | 5inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.53 | 0 | CMO West 2 | IMGA222419 | BROX ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 5 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510891870 | CMO | CMO West 2 | September | 27 | A | Mario Gesner | Leigh Osaer | IMGA222429 | PENYSTON ROAD | 510891870 | T1 Policy | 8 | Policy | 7 | SI | 40 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.32 | 0 | CMO West 2 | IMGA222429 | PENYSTON ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510949855 | CMO | CMO West 2 | September | 27 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | HAMILTON ROAD | 510949855 | T1 Policy | 12.3 | Policy | 6 | SI | 210 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.583 | 0 | CMO West 2 | IMGA222092 | HAMILTON ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510951429 | CMO | CMO West 2 | September | 27 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | Newman Road | 510951429 | T1 Policy | 3.4 | Policy | 6 | SI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.068 | 0 | CMO West 2 | IMGA222092 | Newman Road | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510954011 | CMO | CMO West 2 | September | 27 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | YEADING GARDENS | 510954011 | T1 Policy | 3.8 | Policy | 6 | SI | 182 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6916 | 0 | CMO West 2 | IMGA222102 | YEADING GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510951846 | CMO | CMO West 2 | September | 27 | A | Sanjeev Pathak | Natasha Barrett | IMGA222104 | PERCY GARDENS | 510951846 | T1 Policy | 5 | Policy | 4 | SI | 80 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4 | 0 | CMO West 2 | IMGA222104 | PERCY GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510868995 | CMO | CMO West 2 | September | 27 | A | Sanjeev Pathak | Kerry Dolan | IMGA222271 | LONG DRIVE | 510868995 | T1 Policy | 61.1 | Policy | 4 | SI | 162 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 9.8982 | 0 | CMO West 2 | IMGA222271 | LONG DRIVE | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510815404 | CMO | CMO West 2 | September | 27 | A | Sanjeev Pathak | Kerry Dolan | IMGA222280 | COTTAGE PARK ROAD | 510815404 | T1 Policy | 4.6 | Policy | 6 | SI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.69 | 0 | CMO West 2 | IMGA222280 | COTTAGE PARK ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO TURNBULL, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510888828 | CMO | CMO West 2 | September | 27 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510888828 | T1 Policy | 0 | Policy | 100 | DI | 3 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | #N/A | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926849 | CMO | CMO West 2 | September | 27 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926849 | T1 Policy | 0 | Policy | 4 | DI | 125 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926850 | CMO | CMO West 2 | September | 27 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926850 | T1 Policy | 0 | Policy | 4 | DI | 30 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
510926851 | CMO | CMO West 2 | September | 27 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926851 | T1 Policy | 0 | Policy | 4 | DI | 106 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | September
220001244906 | CMO | CMO West 2 | September | 27 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRAIGHT BIT | 220001244906 | T1 Policy | 2.1 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.21 | 0 | CMO West 2 | IMGA222360 | STRAIGHT BIT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510778940 | CMO | CMO West 2 | September | 27 | A | Tony Ingram 2 | William Madge | IMGA222373 | ADAM CLOSE | 510778940 | T1 Policy | 123.1 | Policy | 6 | SI | 93 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 11.4483 | 0 | CMO West 2 | IMGA222373 | ADAM CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510778942 | CMO | CMO West 2 | September | 27 | A | Tony Ingram 2 | William Madge | IMGA222373 | ADAM CLOSE | 510778942 | T1 Policy | 3.5 | Policy | 6 | SI | 131 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4585 | 0 | CMO West 2 | IMGA222373 | ADAM CLOSE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDINER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510794351 | CMO | CMO West 2 | September | 27 | A | Tony Ingram 2 | Adam Madge | IMGA222375 | BOWERDEAN ROAD | 510794351 | T1 Policy | 29 | Policy | 6 | SI | 180 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 5.22 | 0 | CMO West 2 | IMGA222375 | BOWERDEAN ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510786740 | CMO | CMO West 2 | September | 27 | A | Tony Ingram 2 | William Madge | IMGA222377 | BARING ROAD | 510786740 | T1 Policy | 2.9 | Policy | 4 | SI | 121 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3509 | 0 | CMO West 2 | IMGA222377 | BARING ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | September
510836320 | CMO | CMO West 2 | September | 27 | A | Tony Ingram 2 | William Madge | IMGA222377 | GAYHURST ROAD | 510836320 | T1 Policy | 3.2 | Policy | 6 | SI | 69 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2208 | 0 | CMO West 2 | IMGA222377 | GAYHURST ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | September
510963972 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963972 | T1 Policy | 4.4 | Policy | 4 | CI | 164 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7216 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510963974 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Leigh Osaer | IMGA222020 | LLANVAIR DRIVE | 510963974 | T1 Policy | 2 | Policy | 4 | CI | 10 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 2 | IMGA222020 | LLANVAIR DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510929801 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Phil Walden | IMGA222234 | VEGAL CRESCENT | 510929801 | T1 Policy | 5.7 | Policy | 4 | CI | 23 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1311 | 0 | CMO West 2 | IMGA222234 | VEGAL CRESCENT | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510938789 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Phil Walden | IMGA222234 | WILLSON ROAD | 510938789 | T1 Policy | 5.7 | Policy | 4 | DI | 27 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1539 | 0 | CMO West 2 | IMGA222234 | WILLSON ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510790116 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Phil Walden | IMGA222254 | BELMONT | 510790116 | T1 Policy | 5 | Policy | 4 | DI | 7 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.035 | 0 | CMO West 2 | IMGA222254 | BELMONT | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510924814 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Phil Walden | IMGA222254 | THORNDIKE | 510924814 | T1 Policy | 8 | Policy | 4 | DI | 317 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.536 | 0 | CMO West 2 | IMGA222254 | THORNDIKE | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510944404 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Leigh Osaer | IMGA222301 | LALEHAM ROAD | 510944404 | T2 PAST | 507.6 | Policy | 15 | DI | 253 | inch | 15inch | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 128.4228 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T2 PAST | tRIIO MCQUADE, Barry | LP | #N/A | >12-17” | 15 |  | Policy | Tier 2 | DI | T2A | October
510798623 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Chris Douglas | IMGA222419 | BROX ROAD | 510798623 | T1 Policy | 11 | Policy | 5 | SI | 150 | inch | 5inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.65 | 0 | CMO West 2 | IMGA222419 | BROX ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 5 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510891870 | CMO | CMO West 2 | October | 28 | A | Mario Gesner | Leigh Osaer | IMGA222429 | PENYSTON ROAD | 510891870 | T1 Policy | 8 | Policy | 7 | SI | 100 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222429 | PENYSTON ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510949855 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | HAMILTON ROAD | 510949855 | T1 Policy | 12.3 | Policy | 6 | SI | 10 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.123 | 0 | CMO West 2 | IMGA222092 | HAMILTON ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510951429 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | Newman Road | 510951429 | T1 Policy | 3.4 | Policy | 6 | SI | 64 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2176 | 0 | CMO West 2 | IMGA222092 | Newman Road | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510952853 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | STIRLING ROAD | 510952853 | T1 Policy | 3.3 | Policy | 6 | SI | 76 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2508 | 0 | CMO West 2 | IMGA222092 | STIRLING ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
220001633753 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | HOLLYWOOD GARDENS | 220001633753 | T1 Policy | 0 | Policy | 6 | SI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222102 | HOLLYWOOD GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510954009 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | YEADING GARDENS | 510954009 | T1 Policy | 5.8 | Policy | 4 | DI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.145 | 0 | CMO West 2 | IMGA222102 | YEADING GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
220001551099 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | YEADING GARDENS | 220001551099 | T1 Policy | 3.9 | Policy | 6 | SI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.39 | 0 | CMO West 2 | IMGA222102 | YEADING GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510947978 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Natasha Barrett | IMGA222104 | BRADENHAM ROAD | 510947978 | T1 Policy | 61.8 | Policy | 6 | DI | 105 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.489 | 0 | CMO West 2 | IMGA222104 | BRADENHAM ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
DR4 Requested | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | MIDDLE WALK | DR4 Requested | Condition | 0 | Non Policy | 2 | ST | 25 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222270 | MIDDLE WALK | South Bucks District Council | West 2 | FALSE |  | SQS | T1 CONNECTED | tRIIO ARNOLD, Liam (SQS) | #N/A | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
510967126 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | MIDDLE WALK | 510967126 | T1 Policy | 3.7 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.259 | 0 | CMO West 2 | IMGA222270 | MIDDLE WALK | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510967403 | CMO | CMO West 2 | October | 28 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | SUMMERS ROAD | 510967403 | T1 Policy | 4.5 | Policy | 4 | SI | 135 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6075 | 0 | CMO West 2 | IMGA222270 | SUMMERS ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510926853 | CMO | CMO West 2 | October | 28 | A | Shane Compton | William Sadler | IMGA222011 | TREVELYAN | 510926853 | T1 Policy | 0 | Policy | 6 | DI | 168 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222011 | TREVELYAN | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510963898 | CMO | CMO West 2 | October | 28 | A | Shane Compton | Ryan Smeaton | IMGA222436 | GAINSBOROUGH DRIVE | 510963898 | T1 Policy | 6 | Policy | 200 | DI | 100 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6 | 0 | CMO West 2 | IMGA222436 | GAINSBOROUGH DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO COLLINS, Pat | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510954635 | CMO | CMO West 2 | October | 28 | A | Shane Compton | Ryan Smeaton | IMGA222442 | WAVERLEY DRIVE | 510954635 | T1 Policy | 4 | Policy | 4 | DI | 122 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.488 | 0 | CMO West 2 | IMGA222442 | WAVERLEY DRIVE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510954637 | CMO | CMO West 2 | October | 28 | A | Shane Compton | Ryan Smeaton | IMGA222442 | WAVERLEY DRIVE | 510954637 | T1 Policy | 7 | Policy | 6 | DI | 3 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.021 | 0 | CMO West 2 | IMGA222442 | WAVERLEY DRIVE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510886632 | CMO | CMO West 2 | October | 28 | A | TBA - Lon | Kerry Dolan | IMGA222275 | OLD MILL ROAD | 510886632 | T1 Policy | 1.4 | Policy | 6 | SI | 40 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.056 | 0 | CMO West 2 | IMGA222275 | OLD MILL ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO SCOTT, David | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510971268 | CMO | CMO West 2 | October | 28 | A | Tony Ingram 2 | William Madge | IMGA222354 | THE AVENUE | 510971268 | T1 Policy | 1.9 | Policy | 4 | SI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.285 | 0 | CMO West 2 | IMGA222354 | THE AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510794351 | CMO | CMO West 2 | October | 28 | A | Tony Ingram 2 | Adam Madge | IMGA222375 | BOWERDEAN ROAD | 510794351 | T1 Policy | 29 | Policy | 6 | SI | 210 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.09 | 0 | CMO West 2 | IMGA222375 | BOWERDEAN ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510778243 | CMO | CMO West 2 | October | 29 | A | Tony Ingram 2 | William Madge | IMGA222354 | SAILING CLUB ROAD | 510778243 | T1 Policy | 4.1 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.41 | 0 | CMO West 2 | IMGA222354 | SAILING CLUB ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510778244 | CMO | CMO West 2 | October | 29 | A | Tony Ingram 2 | William Madge | IMGA222354 | SAILING CLUB ROAD | 510778244 | T1 Policy | 6.9 | Policy | 4 | SI | 48 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3312 | 0 | CMO West 2 | IMGA222354 | SAILING CLUB ROAD | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510815403 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Kerry Dolan | IMGA222280 | COTTAGE PARK ROAD | 510815403 | T1 Policy | 4.9 | Policy | 4 | SI | 113 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5537 | 0 | CMO West 2 | IMGA222280 | COTTAGE PARK ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO TURNBULL, Dean | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510924813 | CMO | CMO West 2 | October | 29 | A | Mario Gesner | Phil Walden | IMGA222254 | THORNDIKE | 510924813 | T1 Policy | 6.5 | Policy | 4 | DI | 200 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.3 | 0 | CMO West 2 | IMGA222254 | THORNDIKE | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510931167 | CMO | CMO West 2 | October | 29 | A | Tony Ingram 2 | Adam Madge | IMGA222358 | VINEYARD DRIVE | 510931167 | T1 Policy | 3 | Policy | 4 | DI | 144 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.432 | 0 | CMO West 2 | IMGA222358 | VINEYARD DRIVE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510931821 | CMO | CMO West 2 | October | 29 | A | Shane Compton | William Sadler | IMGA222440 | WALLINGFORD CLOSE | 510931821 | T1 Policy | 3 | Policy | 4 | SI | 67 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.201 | 0 | CMO West 2 | IMGA222440 | WALLINGFORD CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO JANES, Alun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510931822 | CMO | CMO West 2 | October | 29 | A | Shane Compton | William Sadler | IMGA222440 | WALLINGFORD CLOSE | 510931822 | T1 Policy | 3 | Policy | 4 | SI | 51 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.153 | 0 | CMO West 2 | IMGA222440 | WALLINGFORD CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO JANES, Alun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510933677 | CMO | CMO West 2 | October | 29 | A | Shane Compton | William Sadler | IMGA222440 | WAYLAND CLOSE | 510933677 | T1 Policy | 4 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4 | 0 | CMO West 2 | IMGA222440 | WAYLAND CLOSE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO CLARK, James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510938445 | CMO | CMO West 2 | October | 29 | A | Mario Gesner | Phil Walden | IMGA222254 | WILLONERS | 510938445 | T1 Policy | 4.7 | Policy | 4 | SI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.282 | 0 | CMO West 2 | IMGA222254 | WILLONERS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510938446 | CMO | CMO West 2 | October | 29 | A | Mario Gesner | Phil Walden | IMGA222254 | WILLONERS | 510938446 | T1 Policy | 5.6 | Policy | 4 | SI | 59 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3304 | 0 | CMO West 2 | IMGA222254 | WILLONERS | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510938789 | CMO | CMO West 2 | October | 29 | A | Mario Gesner | Phil Walden | IMGA222234 | WILLSON ROAD | 510938789 | T1 Policy | 5.7 | Policy | 4 | DI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.285 | 0 | CMO West 2 | IMGA222234 | WILLSON ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510947422 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Natasha Barrett | IMGA222114 | ARLINGTON DRIVE | 510947422 | T1 Policy | 10.8 | Policy | 4 | SI | 220 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.376 | 0 | CMO West 2 | IMGA222114 | ARLINGTON DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510967404 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | SUMMERS ROAD | 510967404 | T1 Policy | 2.3 | Policy | 4 | SI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.115 | 0 | CMO West 2 | IMGA222270 | SUMMERS ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510967545 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | WILMOT ROAD | 510967545 | T1 Policy | 4.2 | Policy | 4 | DI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.294 | 0 | CMO West 2 | IMGA222270 | WILMOT ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
220001382256 | CMO | CMO West 2 | October | 29 | A | Tony Ingram 2 | William Madge | IMGA222373 | MAYHEW CRESCENT | 220001382256 | T1 Policy | 7.7 | Policy | 4 | DI | 236 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.8172 | 0 | CMO West 2 | IMGA222373 | MAYHEW CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDNER, Barry | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
220001648089 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | BEDFORD AVENUE | 220001648089 | T1 Policy | 2.9 | Policy | 4 | DI | 13 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0377 | 0 | CMO West 2 | IMGA222102 | BEDFORD AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510857602 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Kerry Dolan | IMGA222280 | JONES WAY | 510857602 | T1 Policy | 4.5 | Policy | 6 | SI | 30 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.135 | 0 | CMO West 2 | IMGA222280 | JONES WAY | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO TURNBULL, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510947978 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Natasha Barrett | IMGA222104 | BRADENHAM ROAD | 510947978 | T1 Policy | 61.8 | Policy | 6 | DI | 127 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 7.8486 | 0 | CMO West 2 | IMGA222104 | BRADENHAM ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510952853 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | STIRLING ROAD | 510952853 | T1 Policy | 3.3 | Policy | 6 | SI | 150 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.495 | 0 | CMO West 2 | IMGA222092 | STIRLING ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510954637 | CMO | CMO West 2 | October | 29 | A | Shane Compton | Ryan Smeaton | IMGA222442 | WAVERLEY DRIVE | 510954637 | T1 Policy | 7 | Policy | 6 | DI | 68 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.476 | 0 | CMO West 2 | IMGA222442 | WAVERLEY DRIVE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
220001244906 | CMO | CMO West 2 | October | 29 | A | Tony Ingram 2 | Kerry Dolan | IMGA222360 | STRAIGHT BIT | 220001244906 | T1 Policy | 2.1 | Policy | 6 | CI | 85 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1785 | 0 | CMO West 2 | IMGA222360 | STRAIGHT BIT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
220001551099 | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | YEADING GARDENS | 220001551099 | T1 Policy | 3.9 | Policy | 6 | SI | 90 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.351 | 0 | CMO West 2 | IMGA222102 | YEADING GARDENS | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
220001624303 | CMO | CMO West 2 | October | 29 | A | Shane Compton | Ryan Smeaton | IMGA222439 | BARKER ROAD | 220001624303 | T1 Policy | 4 | Policy | 6 | CI | 5 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.02 | 0 | CMO West 2 | IMGA222439 | BARKER ROAD | Runnymede Borough Council | West 2 | FALSE |  | I & G | T1 SECONDARY | CMO Norris, Terry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
220001786991 | CMO | CMO West 2 | October | 29 | A | Tony Ingram 2 | William Madge | IMGA222373 | MAYHEW CRESCENT | 220001786991 | T1 Policy | 0 | Policy | 6 | DI | 50 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222373 | MAYHEW CRESCENT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO GARDNER, Barry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
DR4 Requested | CMO | CMO West 2 | October | 29 | A | Sanjeev Pathak | Natasha Barrett | IMGA222102 | BEDFORD AVENUE | DR4 Requested | T1 Policy | 0 | Policy | 6 | SI | 20 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222102 | BEDFORD AVENUE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | #N/A | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510891870 | CMO | CMO West 2 | October | 29 | A | Mario Gesner | Leigh Osaer | IMGA222429 | PENYSTON ROAD | 510891870 | T1 Policy | 8 | Policy | 7 | SI | 40 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.32 | 0 | CMO West 2 | IMGA222429 | PENYSTON ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510954636 | CMO | CMO West 2 | October | 29 | A | Shane Compton | Ryan Smeaton | IMGA222442 | WAVERLEY DRIVE | 510954636 | T1 Policy | 4 | Policy | 8 | DI | 197 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.788 | 0 | CMO West 2 | IMGA222442 | WAVERLEY DRIVE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | DI | CI/SI/DI LP 8" | October
220001610925 | CMO | CMO West 2 | October | 29 | A | Shane Compton | Ryan Smeaton | IMGA222436 | SUTHERLAND CHASE | 220001610925 | T1 Policy | 4 | Policy | 100 | DI | 36 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.144 | 0 | CMO West 2 | IMGA222436 | SUTHERLAND CHASE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510963898 | CMO | CMO West 2 | October | 29 | A | Shane Compton | Ryan Smeaton | IMGA222436 | GAINSBOROUGH DRIVE | 510963898 | T1 Policy | 6 | Policy | 200 | DI | 34 | mm | 200mm | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.204 | 0 | CMO West 2 | IMGA222436 | GAINSBOROUGH DRIVE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 6-7” | 200 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510972463 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222228 | TEN ACRE LANE | 510972463 | T1 Policy | 2.4 | Policy | 4 | DI | 24 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0576 | 0 | CMO West 2 | IMGA222228 | TEN ACRE LANE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510921398 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222228 | TEN ACRE LANE | 510921398 | T1 Policy | 0.9 | Policy | 8 | CI | 89 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0801 | 0 | CMO West 2 | IMGA222228 | TEN ACRE LANE | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO CLIFFORD, Mathew | LP | #N/A | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510925044 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222228 | THORPE LEA ROAD | 510925044 | T1 Policy | 4.3 | Policy | 8 | CI | 562 | inch | 8inch | Abandonment 8” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.4166 | 0 | CMO West 2 | IMGA222228 | THORPE LEA ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 ENM CONDITION SPECIFIED | CMO CLIFFORD, Mathew | LP | ENM P2 | 8” | 8 |  | Policy | Tier 1 | CI | CI/SI/DI LP 8" | October
510808172 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Phil Walden | IMGA222260 | CHILWICK ROAD | 510808172 | T1 Policy | 10.6 | Policy | 4 | SI | 193 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.0458 | 0 | CMO West 2 | IMGA222260 | CHILWICK ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510838859 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Phil Walden | IMGA222260 | GOODWIN ROAD | 510838859 | T1 Policy | 30.3 | Policy | 4 | SI | 77 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 2.3331 | 0 | CMO West 2 | IMGA222260 | GOODWIN ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510910151 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222293 | SHAFTESBURY CRESCENT | 510910151 | T1 Policy | 3.3 | Policy | 4 | DI | 65 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2145 | 0 | CMO West 2 | IMGA222293 | SHAFTESBURY CRESCENT | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510910152 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222293 | SHAFTESBURY CRESCENT | 510910152 | T1 Policy | 3.3 | Policy | 4 | DI | 50 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.165 | 0 | CMO West 2 | IMGA222293 | SHAFTESBURY CRESCENT | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510910153 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222293 | SHAFTESBURY CRESCENT | 510910153 | T1 Policy | 3.6 | Policy | 4 | SI | 39 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1404 | 0 | CMO West 2 | IMGA222293 | SHAFTESBURY CRESCENT | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510972262 | CMO | CMO West 2 | October | 30 | A | Mario Gesner | Chris Douglas | IMGA222293 | Tavistock Close | 510972262 | T1 Policy | 4.5 | Policy | 4 | SI | 60 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.27 | 0 | CMO West 2 | IMGA222293 | Tavistock Close | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510950359 | CMO | CMO West 2 | October | 30 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | HITHERBROOM ROAD | 510950359 | T1 Policy | 7.9 | Policy | 6 | SI | 95 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.7505 | 0 | CMO West 2 | IMGA222092 | HITHERBROOM ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510950586 | CMO | CMO West 2 | October | 30 | A | Sanjeev Pathak | Natasha Barrett | IMGA222101 | KEATS CLOSE | 510950586 | T1 Policy | 2.7 | Policy | 4 | SI | 77 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2079 | 0 | CMO West 2 | IMGA222101 | KEATS CLOSE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510951972 | CMO | CMO West 2 | October | 30 | A | Sanjeev Pathak | Natasha Barrett | IMGA222104 | PORTLAND ROAD | 510951972 | T1 Policy | 46.8 | Policy | 4 | DI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 4.68 | 0 | CMO West 2 | IMGA222104 | PORTLAND ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO JACKMAN KLT, Billy | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510967132 | CMO | CMO West 2 | October | 30 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | MINNIECROFT ROAD | 510967132 | T1 Policy | 4.5 | Policy | 100 | DI | 42 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.189 | 0 | CMO West 2 | IMGA222270 | MINNIECROFT ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510967544 | CMO | CMO West 2 | October | 30 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | WILMOT ROAD | 510967544 | T1 Policy | 9.2 | Policy | 100 | DI | 61 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.5612 | 0 | CMO West 2 | IMGA222270 | WILMOT ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510815404 | CMO | CMO West 2 | October | 30 | A | Sanjeev Pathak | Kerry Dolan | IMGA222280 | COTTAGE PARK ROAD | 510815404 | T1 Policy | 4.6 | Policy | 6 | SI | 14 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0644 | 0 | CMO West 2 | IMGA222280 | COTTAGE PARK ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO TURNBULL, Dean | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510852066 | CMO | CMO West 2 | October | 30 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852066 | T1 Policy | 3 | Policy | 4 | SI | 25 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.075 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510852066 | CMO | CMO West 2 | October | 30 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852066 | T1 Policy | 3 | Policy | 4 | SI | 111 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.333 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510852071 | CMO | CMO West 2 | October | 30 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852071 | T1 Policy | 4 | Policy | 1.5 | ST | 8 | inch | 1.5inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelPolicy | FALSE | FALSE | #N/A | 0.032 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 CONNECTED | CMO DOMINY (OMJ), Scott | LP | #N/A | <=3” | 1.5 |  | Policy | Tier 1 | ST | ST LP <=3" | October
510909389 | CMO | CMO West 2 | October | 30 | A | Shane Compton | William Sadler | IMGA222440 | SEGSBURY GROVE | 510909389 | T1 Policy | 8 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222440 | SEGSBURY GROVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO CLARK (OMJ), James | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510867497 | CMO | CMO West 2 | October | 30 | A | Shane Compton | William Sadler | IMGA222440 | UFFINGTON DRIVE | 510867497 | T1 Policy | 9 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.63 | 0 | CMO West 2 | IMGA222440 | UFFINGTON DRIVE | Bracknell Forest Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | tRIIO JANES, Alun | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510831463 | CMO | CMO West 2 | October | 30 | A | Shane Compton | Ryan Smeaton | IMGA222442 | FERNDALE AVENUE | 510831463 | T1 Policy | 7 | Policy | 4 | SI | 4 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.028 | 0 | CMO West 2 | IMGA222442 | FERNDALE AVENUE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510954637 | CMO | CMO West 2 | October | 30 | A | Shane Compton | Ryan Smeaton | IMGA222442 | WAVERLEY DRIVE | 510954637 | T1 Policy | 7 | Policy | 6 | DI | 132 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.924 | 0 | CMO West 2 | IMGA222442 | WAVERLEY DRIVE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510918578 | CMO | CMO West 2 | October | 30 | A | Tony Ingram 2 | Adam Madge | IMGA222444 | STYLECROFT ROAD | 510918578 | T1 Policy | 6 | Policy | 4 | SI | 280 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.68 | 0 | CMO West 2 | IMGA222444 | STYLECROFT ROAD | Chiltern District Council (Lower) | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO ASHDOWN, Tom | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
- | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | - | Condition | 0 | Non Policy | 1.5 | ST | 13 | inch | 1.5inch | Abandonment <=3” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 CONNECTED | CMO DOMINY (OMJ), Scott | #N/A | #N/A | <=3” | 1.5 |  | Non Policy | Tier 1 | ST | ST LP <=3" | October
510852067 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852067 | Condition | 0 | Non Policy | 2 | ST | 39 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 CONNECTED | CMO DOMINY (OMJ), Scott | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
510852070 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852070 | T1 Policy | 3 | Policy | 2 | SI | 9 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.027 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | October
510852071 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852071 | T1 Policy | 4 | Policy | 2 | SI | 14 | inch | 2inch | Abandonment <=3” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.056 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | <=3” | 2 |  | Policy | Tier 1 | SI | CI/SI/DI LP <=3" | October
608065028 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 608065028 | Condition | 0 | Non Policy | 2 | ST | 43 | inch | 2inch | Abandonment 2” | Tier 1 | Steel | Tier 1SteelNon Policy | FALSE | FALSE | #N/A | 0 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 CONNECTED | CMO DOMINY (OMJ), Scott | LP | #N/A | 2” | 2 |  | Non Policy | Tier 1 | ST | 2" ST | October
510808173 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Leigh Osaer | IMGA222260 | CHILWICK ROAD | 510808173 | T1 Policy | 7.5 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.525 | 0 | CMO West 2 | IMGA222260 | CHILWICK ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510827031 | CMO | CMO West 2 | October | 31 | A | Tony Ingram 2 | Andrew Wilding | IMGA222358 | ELM LANE | 510827031 | T1 Policy | 4 | Policy | 4 | SI | 100 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4 | 0 | CMO West 2 | IMGA222358 | ELM LANE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | tRIIO BROWN, Warren | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510831463 | CMO | CMO West 2 | October | 31 | A | Shane Compton | Ryan Smeaton | IMGA222442 | FERNDALE AVENUE | 510831463 | T1 Policy | 7 | Policy | 4 | SI | 205 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.435 | 0 | CMO West 2 | IMGA222442 | FERNDALE AVENUE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510838859 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Leigh Osaer | IMGA222260 | GOODWIN ROAD | 510838859 | T1 Policy | 30.3 | Policy | 4 | SI | 230 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 6.969 | 0 | CMO West 2 | IMGA222260 | GOODWIN ROAD | Slough Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | tRIIO PORTER, Stuart | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510852065 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852065 | T1 Policy | 3 | Policy | 4 | SI | 156 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.468 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510852066 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852066 | T1 Policy | 3 | Policy | 4 | SI | 3 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.009 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510852068 | CMO | CMO West 2 | October | 31 | A | Shane Compton | William Sadler | IMGA222438 | Hilltop Close | 510852068 | T1 Policy | 7 | Policy | 4 | SI | 31 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.217 | 0 | CMO West 2 | IMGA222438 | Hilltop Close | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO DOMINY (OMJ), Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510938789 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Chris Douglas | IMGA222234 | WILLSON ROAD | 510938789 | T1 Policy | 5.7 | Policy | 4 | DI | 45 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2565 | 0 | CMO West 2 | IMGA222234 | WILLSON ROAD | Runnymede Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO HARRIS, Rob | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510944110 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Chris Douglas | IMGA222292 | CHARLES ROAD | 510944110 | T1 Policy | 3.2 | Policy | 4 | CI | 96 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3072 | 0 | CMO West 2 | IMGA222292 | CHARLES ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510945221 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Chris Douglas | IMGA222292 | BOOTH DRIVE | 510945221 | T1 Policy | 4.3 | Policy | 4 | CI | 59 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2537 | 0 | CMO West 2 | IMGA222292 | BOOTH DRIVE | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510947422 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Natasha Barrett | IMGA222114 | ARLINGTON DRIVE | 510947422 | T1 Policy | 10.8 | Policy | 4 | SI | 70 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.756 | 0 | CMO West 2 | IMGA222114 | ARLINGTON DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510947423 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Natasha Barrett | IMGA222114 | ARLINGTON DRIVE | 510947423 | T1 Policy | 12.4 | Policy | 4 | SI | 147 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.8228 | 0 | CMO West 2 | IMGA222114 | ARLINGTON DRIVE | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO BARNES KLT, Scott | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
510954637 | CMO | CMO West 2 | October | 31 | A | Shane Compton | Ryan Smeaton | IMGA222442 | WAVERLEY DRIVE | 510954637 | T1 Policy | 7 | Policy | 4 | CI | 150 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 1.05 | 0 | CMO West 2 | IMGA222442 | WAVERLEY DRIVE | Runnymede Borough Council | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO HARRISON (OMJ), Thomas | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | CI | CI/SI/DI LP 4"-5" | October
510971266 | CMO | CMO West 2 | October | 31 | A | Tony Ingram 2 | William Madge | IMGA222354 | THE AVENUE | 510971266 | T1 Policy | 1.8 | Policy | 4 | SI | 167 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.3006 | 0 | CMO West 2 | IMGA222354 | THE AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | SI | CI/SI/DI LP 4"-5" | October
220001610925 | CMO | CMO West 2 | October | 31 | A | Shane Compton | Ryan Smeaton | IMGA222436 | SUTHERLAND CHASE | 220001610925 | T1 Policy | 4 | Policy | 4 | DI | 140 | inch | 4inch | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.56 | 0 | CMO West 2 | IMGA222436 | SUTHERLAND CHASE | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | OMJ | T1 SECONDARY | CMO COLLINS (OMJ), Patrick | LP | #N/A | 4-5” | 4 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510944111 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Chris Douglas | IMGA222292 | CHARLES ROAD | 510944111 | T1 Policy | 1.3 | Policy | 6 | CI | 73 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0949 | 0 | CMO West 2 | IMGA222292 | CHARLES ROAD | Spelthorne Borough Council | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO FYFFE, Ruairi | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510947601 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Natasha Barrett | IMGA222107 | BARNHILL ROAD | 510947601 | T1 Policy | 5.8 | Policy | 6 | DI | 140 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.812 | 0 | CMO West 2 | IMGA222107 | BARNHILL ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | CMO STEVENSON KLT, Jamie | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510949856 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Natasha Barrett | IMGA222092 | HAMILTON ROAD | 510949856 | T1 Policy | 3 | Policy | 6 | SI | 200 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.6 | 0 | CMO West 2 | IMGA222092 | HAMILTON ROAD | Hillingdon London Borough Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO NELMES, Michael | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510966796 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Phil Walden | IMGA222349 | DUNCANNON CRESCENT | 510966796 | T1 Policy | 4.8 | Policy | 6 | DI | 100 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.48 | 0 | CMO West 2 | IMGA222349 | DUNCANNON CRESCENT | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 SECONDARY | CMO MADLEY, Philip | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | DI | CI/SIDI LP 6"-7" | October
510971265 | CMO | CMO West 2 | October | 31 | A | Tony Ingram 2 | William Madge | IMGA222354 | THE AVENUE | 510971265 | T1 Policy | 0.6 | Policy | 6 | SI | 28 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.0168 | 0 | CMO West 2 | IMGA222354 | THE AVENUE | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO VALE KLT, Aaron | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
220001244906 | CMO | CMO West 2 | October | 31 | A | Tony Ingram 2 | William Madge | IMGA222360 | STRAIGHT BIT | 220001244906 | T1 Policy | 2.1 | Policy | 6 | SI | 58 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.1218 | 0 | CMO West 2 | IMGA222360 | STRAIGHT BIT | Wycombe District Council | West 2 | FALSE |  | KLT | T1 SECONDARY | CMO MCPADDEN KLT, Mick | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
220001624303 | CMO | CMO West 2 | October | 31 | A | Shane Compton | Ryan Smeaton | IMGA222439 | BARKER ROAD | 220001624303 | T1 Policy | 4 | Policy | 6 | CI | 45 | inch | 6inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.18 | 0 | CMO West 2 | IMGA222439 | BARKER ROAD | Runnymede Borough Council | West 2 | FALSE |  | I & G | T1 SECONDARY | CMO Norris, Terry | LP | #N/A | 6-7” | 6 |  | Policy | Tier 1 | CI | CI/SI/DI LP 6"-7" | October
510891870 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Leigh Osaer | IMGA222429 | PENYSTON ROAD | 510891870 | T1 Policy | 8 | Policy | 7 | SI | 100 | inch | 7inch | Abandonment 6-7” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.8 | 0 | CMO West 2 | IMGA222429 | PENYSTON ROAD | Windsor & Maidenhead Royal Borough | West 2 | FALSE |  | DHB Utilities | T1 CBA | CMO LARMOUR, Rob | LP | #N/A | 6-7” | 7 |  | Policy | Tier 1 | SI | CI/SI/DI LP 6"-7" | October
510944404 | CMO | CMO West 2 | October | 31 | A | Mario Gesner | Phil Walden | IMGA222301 | LALEHAM ROAD | 510944404 | T2 PAST | 507.6 | Policy | 15 | CI | 230 | inch | 15inch | Abandonment >12-17” | Tier 2 | Iron | Tier 2IronPolicy | FALSE | FALSE | #N/A | 116.748 | 0 | CMO West 2 | IMGA222301 | LALEHAM ROAD | Spelthorne Borough Council | West 2 | FALSE | PAST | DHB Utilities | T2 PAST | tRIIO MCQUADE, Barry | LP | #N/A | >12-17” | 15 |  | Policy | Tier 2 | CI | T2A | October
510967130 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | MINNIECROFT ROAD | 510967130 | T1 Policy | 6.4 | Policy | 100 | DI | 66 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.4224 | 0 | CMO West 2 | IMGA222270 | MINNIECROFT ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510967131 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | MINNIECROFT ROAD | 510967131 | T1 Policy | 4.4 | Policy | 100 | DI | 51 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.2244 | 0 | CMO West 2 | IMGA222270 | MINNIECROFT ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October
510967132 | CMO | CMO West 2 | October | 31 | A | Sanjeev Pathak | Kerry Dolan | IMGA222270 | MINNIECROFT ROAD | 510967132 | T1 Policy | 4.5 | Policy | 100 | DI | 122 | mm | 100mm | Abandonment 4-5” | Tier 1 | Iron | Tier 1IronPolicy | FALSE | FALSE | #N/A | 0.549 | 0 | CMO West 2 | IMGA222270 | MINNIECROFT ROAD | South Bucks District Council | West 2 | FALSE |  | SQS | T1 SECONDARY | tRIIO ARNOLD, Liam (SQS) | LP | #N/A | 4-5” | 100 |  | Policy | Tier 1 | DI | CI/SI/DI LP 4"-5" | October

## Reference Table
Material | Banding | CODE1 | CODE2 | Tier | Policy /Non Policy | Category
CI | <=3” | CI<=3” | CITier 1 | Tier 1 |  | CI/SI/DI LP <=3"
CI | 4-5ˮ | CI4-5ˮ | CITier 1 | Tier 1 |  | CI/SI/DI LP 4"-5"
CI | 6-7” | CI6-7” | CITier 1 | Tier 1 |  | CI/SI/DI LP 6"-7"
CI | 8” | CI8” | CITier 1 | Tier 1 |  | CI/SI/DI LP 8"
CI | 8” | CI8” | CITier 1 | Tier 1 |  | CI/SI/DI MP 8"
CI | <=3” | CI<=3” | CITier 1 | Tier 1 |  | CI/SI/DI LP <=3"
CI | 4-5” | CI4-5” | CITier 1 | Tier 1 |  | CI/SI/DI LP 4"-5"
CI | 6-7” | CI6-7” | CITier 1 | Tier 1 |  | CI/SI/DI LP 6"-7"
CI | 8” | CI8” | CITier 1 | Tier 1 |  | CI/SI/DI LP 8"
CI | 8” | CI8” | CITier 1 | Tier 1 |  | CI/SI/DI MP 8"
SI | <=3” | SI<=3” | SITier 1 | Tier 1 |  | CI/SI/DI LP <=3"
SI | 4-5” | SI4-5” | SITier 1 | Tier 1 |  | CI/SI/DI LP 4"-5"
SI | 6-7” | SI6-7” | SITier 1 | Tier 1 |  | CI/SI/DI LP 6"-7"
SI | 8” | SI8” | SITier 1 | Tier 1 |  | CI/SI/DI LP 8"
SI | 8” | SI8” | SITier 1 | Tier 1 |  | CI/SI/DI MP 8"
SI | <=3” | SI<=3” | SITier 1 | Tier 1 |  | CI/SI/DI LP <=3"
SI | 4-5” | SI4-5” | SITier 1 | Tier 1 |  | CI/SI/DI LP 4"-5"
SI | 6-7” | SI6-7” | SITier 1 | Tier 1 |  | CI/SIDI LP 6"-7"
SI | 8” | SI8” | SITier 1 | Tier 1 |  | CI/SI/DI LP 8"
SI | 8” | SI8” | SITier 1 | Tier 1 |  | CI/SI/DI MP 8"
ST | 2” | ST2” | STTier 1 | Tier 1 |  | 2" ST
ST | <=3” | ST<=3” | STTier 1 | Tier 1 |  | ST LP <=3"
ST | 4-5” | ST4-5” | STTier 1 | Tier 1 |  | ST LP 4"-5"
ST | 6-7” | ST6-7” | STTier 1 | Tier 1 |  | ST LP 6"-7"
ST | 8” | ST8” | STTier 1 | Tier 1 |  | ST LP 8"
ST | 8” | ST8” | STTier 1 | Tier 1 |  | ST MP 8"
ST | 2” | ST2” | STTier 1 | Tier 1 |  | 2" ST
ST | <=3” | ST<=3” | STTier 1 | Tier 1 |  | ST LP <=3"
ST | 4-5” | ST4-5” | STTier 1 | Tier 1 |  | ST LP 4"-5"
ST | 6-7” | ST6-7” | STTier 1 | Tier 1 |  | ST LP 6"-7"
ST | 8” | ST8” | STTier 1 | Tier 1 |  | ST LP 8"
ST | 8” | ST8” | STTier 1 | Tier 1 |  | ST MP 8"
DI | <=3” | DI<=3” | DITier 1 | Tier 1 |  | CI/SI/DI LP <=3"
DI | 4-5” | DI4-5” | DITier 1 | Tier 1 |  | CI/SI/DI LP 4"-5"
DI | 6-7” | DI6-7” | DITier 1 | Tier 1 |  | CI/SIDI LP 6"-7"
DI | 8” | DI8” | DITier 1 | Tier 1 |  | CI/SI/DI LP 8"
DI | <=3” | DI<=3” | DITier 1 | Tier 1 |  | DI LP <=3"
DI | 4-5” | DI4-5” | DITier 1 | Tier 1 |  | DI LP 4"-5"
DI | 6-7” | DI6-7” | DITier 1 | Tier 1 |  | DI LP 6"-7"
DI | 8” | DI8” | DITier 1 | Tier 1 |  | DI LP 8"
|  |  | Tier 2 | Tier 2 | Policy | T2A
|  |  | Tier 2 | Tier 2 | Non Policy | T2B
|  |  | Tier 3 | Tier 3 |  | T3

## Lookups
Material | Banding | Code | Code2 | Tier | Category
CI | <=3'' | CI <=3'' | CITier 1 | Tier 1 | CI/SI LP <=3"
CI | 4-5” | CI4-5” | CITier 1 | Tier 1 | CI/SI LP 4"-5"
CI | 6-7” | CI6-7” | CITier 1 | Tier 1 | CI/SI LP 6"-7"
CI | 8” | CI8” | CITier 1 | Tier 1 | CI/SI LP 8"
CI | 8” | CI8” | CITier 1 | Tier 1 | CI/SI MP 8"
SI | <=3'' | SI <=3'' | SITier 1 | Tier 1 | CI/SI LP <=3"
SI | 4-5” | SI4-5” | SITier 1 | Tier 1 | CI/SI LP 4"-5"
SI | 6-7” | SI6-7” | SITier 1 | Tier 1 | CI/SI LP 6"-7"
SI | 8” | SI8” | SITier 1 | Tier 1 | CI/SI LP 8"
SI | 8” | SI8” | SITier 1 | Tier 1 | CI/SI MP 8"
ST | <=3'' | ST <=3'' | STTier 1 | Tier 1 | ST LP <=3"
ST | 4-5” | ST4-5” | STTier 1 | Tier 1 | ST LP 4"-5"
ST | 6-7” | ST6-7” | STTier 1 | Tier 1 | ST LP 6"-7"
ST | 8” | ST8” | STTier 1 | Tier 1 | ST LP 8"
ST | 8” | ST8” | STTier 1 | Tier 1 | ST MP 8"
DI | <=3'' | DI <=3'' | DITier 1 | Tier 1 | DI LP <=3"
DI | 4-5” | DI4-5” | DITier 1 | Tier 1 | DI LP 4"-5"
DI | 6-7” | DI6-7” | DITier 1 | Tier 1 | DI LP 6"-7"
DI | 8” | DI8” | DITier 1 | Tier 1 | DI LP 8"
ST | 2” | ST2” | STTier 1 | Tier 1 | 2" ST
|  |  | Tier 2 | Tier 2 | T2/3
|  |  | Tier 3 | Tier 3 | T2/3
Connected ST

## Master
[5 empty] | CI/SI/DI LP <=3" | CI/SI LP/DI 4"-5" | CI/SI LP 6"-7" | CI/SI LP 8" | T2A | T2B | T3
[5 empty] | Tier 1 |  |  |  | Tier 2 |  | Tier 3 | LMPS |  | Steel |  |  |  | Services |  | MOBS |  | Material |  |  |  | Pressure
Week No | Month | Area | LDP | BFA | <=3" | 4"-5" | 6-7" | 8" | HSE | CBA | Tier 3 | LMPS | 2" | <=3" | 4"-5" | 6-7" | 8" | Transfer | Relay | HRB | MRB | CI | SI | DI | ST | LP | MP
1 | 2021-04-01 | CMO West 1 | Terra Firma | Budget
1 | 2021-04-01 | CMO West 1 | Terra Firma | Forecast | 0
1 | 2021-04-01 | CMO West 1 | Terra Firma | Actual | 0
1 | 2021-04-01 | CMO West 1 | KLT | Budget
1 | 2021-04-01 | CMO West 1 | KLT | Forecast | 0
1 | 2021-04-01 | CMO West 1 | KLT | Actual | 0
1 | 2021-04-01 | CMO West 1 | Forefront | Budget
1 | 2021-04-01 | CMO West 1 | Forefront | Forecast | 0
1 | 2021-04-01 | CMO West 1 | Forefront | Actual | 0
1 | 2021-04-01 | CMO West 1 | DPF | Budget
1 | 2021-04-01 | CMO West 1 | DPF | Forecast | 0
1 | 2021-04-01 | CMO West 1 | DPF | Actual | 0
1 | 2021-04-01 | CMO West 1 | OMJ | Budget
1 | 2021-04-01 | CMO West 1 | OMJ | Forecast | 0
1 | 2021-04-01 | CMO West 1 | OMJ | Actual | 0
1 | 2021-04-01 | CMO West 1 | DHB Utilities | Budget
1 | 2021-04-01 | CMO West 1 | DHB Utilities | Forecast | 0
1 | 2021-04-01 | CMO West 1 | DHB Utilities | Actual | 0
1 | 2021-04-01 | CMO West 1 | JDT | Budget
1 | 2021-04-01 | CMO West 1 | JDT | Forecast | 0
1 | 2021-04-01 | CMO West 1 | JDT | Actual | 0
1 | 2021-04-01 | CMO West 1 | MURRAY | Budget
1 | 2021-04-01 | CMO West 1 | MURRAY | Forecast | 0
1 | 2021-04-01 | CMO West 1 | MURRAY | Actual | 0
1 | 2021-04-01 | CMO West 2 | Terra Firma | Budget
1 | 2021-04-01 | CMO West 2 | Terra Firma | Forecast | 0
1 | 2021-04-01 | CMO West 2 | Terra Firma | Actual | 0
1 | 2021-04-01 | CMO West 2 | KLT | Budget
1 | 2021-04-01 | CMO West 2 | KLT | Forecast | 0
1 | 2021-04-01 | CMO West 2 | KLT | Actual | 0
1 | 2021-04-01 | CMO West 2 | Forefront | Budget
1 | 2021-04-01 | CMO West 2 | Forefront | Forecast | 0
1 | 2021-04-01 | CMO West 2 | Forefront | Actual | 0
1 | 2021-04-01 | CMO West 2 | DPF | Budget
1 | 2021-04-01 | CMO West 2 | DPF | Forecast | 0
1 | 2021-04-01 | CMO West 2 | DPF | Actual | 0
1 | 2021-04-01 | CMO West 2 | OMJ | Budget
1 | 2021-04-01 | CMO West 2 | OMJ | Forecast | 0
1 | 2021-04-01 | CMO West 2 | OMJ | Actual | 0
1 | 2021-04-01 | CMO West 2 | DHB Utilities | Budget
1 | 2021-04-01 | CMO West 2 | DHB Utilities | Forecast | 0
1 | 2021-04-01 | CMO West 2 | DHB Utilities | Actual | 0
1 | 2021-04-01 | CMO West 2 | JDT | Budget
1 | 2021-04-01 | CMO West 2 | JDT | Forecast | 0
1 | 2021-04-01 | CMO West 2 | JDT | Actual | 0
1 | 2021-04-01 | CMO West 2 | MURRAY | Budget
1 | 2021-04-01 | CMO West 2 | MURRAY | Forecast | 0
1 | 2021-04-01 | CMO West 2 | MURRAY | Actual | 0
1 | 2021-04-01 | CMO East 1 | Terra Firma | Budget
1 | 2021-04-01 | CMO East 1 | Terra Firma | Forecast | 0
1 | 2021-04-01 | CMO East 1 | Terra Firma | Actual | 0
1 | 2021-04-01 | CMO East 1 | KLT | Budget
1 | 2021-04-01 | CMO East 1 | KLT | Forecast | 0
1 | 2021-04-01 | CMO East 1 | KLT | Actual | 0
1 | 2021-04-01 | CMO East 1 | Forefront | Budget
1 | 2021-04-01 | CMO East 1 | Forefront | Forecast | 0
1 | 2021-04-01 | CMO East 1 | Forefront | Actual | 0
1 | 2021-04-01 | CMO East 1 | DPF | Budget
1 | 2021-04-01 | CMO East 1 | DPF | Forecast | 0
1 | 2021-04-01 | CMO East 1 | DPF | Actual | 0
1 | 2021-04-01 | CMO East 1 | OMJ | Budget
1 | 2021-04-01 | CMO East 1 | OMJ | Forecast | 0
1 | 2021-04-01 | CMO East 1 | OMJ | Actual | 0
1 | 2021-04-01 | CMO East 1 | DHB Utilities | Budget
1 | 2021-04-01 | CMO East 1 | DHB Utilities | Forecast | 0
1 | 2021-04-01 | CMO East 1 | DHB Utilities | Actual | 0
1 | 2021-04-01 | CMO East 1 | JDT | Budget
1 | 2021-04-01 | CMO East 1 | JDT | Forecast | 0
1 | 2021-04-01 | CMO East 1 | JDT | Actual | 0
1 | 2021-04-01 | CMO East 1 | MURRAY | Budget
1 | 2021-04-01 | CMO East 1 | MURRAY | Forecast | 0
1 | 2021-04-01 | CMO East 1 | MURRAY | Actual | 0
1 | 2021-04-01 | CMO East 2 | Terra Firma | Budget
1 | 2021-04-01 | CMO East 2 | Terra Firma | Forecast | 0
1 | 2021-04-01 | CMO East 2 | Terra Firma | Actual | 0
1 | 2021-04-01 | CMO East 2 | KLT | Budget
1 | 2021-04-01 | CMO East 2 | KLT | Forecast | 0
1 | 2021-04-01 | CMO East 2 | KLT | Actual | 0
1 | 2021-04-01 | CMO East 2 | Forefront | Budget
1 | 2021-04-01 | CMO East 2 | Forefront | Forecast | 0
1 | 2021-04-01 | CMO East 2 | Forefront | Actual | 0
1 | 2021-04-01 | CMO East 2 | DPF | Budget
1 | 2021-04-01 | CMO East 2 | DPF | Forecast | 0
1 | 2021-04-01 | CMO East 2 | DPF | Actual | 0
1 | 2021-04-01 | CMO East 2 | OMJ | Budget
1 | 2021-04-01 | CMO East 2 | OMJ | Forecast | 0
1 | 2021-04-01 | CMO East 2 | OMJ | Actual | 0
1 | 2021-04-01 | CMO East 2 | DHB Utilities | Budget
1 | 2021-04-01 | CMO East 2 | DHB Utilities | Forecast | 0
1 | 2021-04-01 | CMO East 2 | DHB Utilities | Actual | 0
1 | 2021-04-01 | CMO East 2 | JDT | Budget
1 | 2021-04-01 | CMO East 2 | JDT | Forecast | 0
1 | 2021-04-01 | CMO East 2 | JDT | Actual | 0
1 | 2021-04-01 | CMO East 2 | MURRAY | Budget
1 | 2021-04-01 | CMO East 2 | MURRAY | Forecast | 0
1 | 2021-04-01 | CMO East 2 | MURRAY | Actual | 0
1 | 2021-04-01 | West | Terra Firma | Budget
1 | 2021-04-01 | West | Terra Firma | Forecast | 0
1 | 2021-04-01 | West | Terra Firma | Actual | 0
1 | 2021-04-01 | West | KLT | Budget
1 | 2021-04-01 | West | KLT | Forecast | 0
1 | 2021-04-01 | West | KLT | Actual | 0
1 | 2021-04-01 | West | Forefront | Budget
1 | 2021-04-01 | West | Forefront | Forecast | 0
1 | 2021-04-01 | West | Forefront | Actual | 0
1 | 2021-04-01 | West | DPF | Budget
1 | 2021-04-01 | West | DPF | Forecast | 0
1 | 2021-04-01 | West | DPF | Actual | 0
1 | 2021-04-01 | West | OMJ | Budget
1 | 2021-04-01 | West | OMJ | Forecast | 0
1 | 2021-04-01 | West | OMJ | Actual | 0
1 | 2021-04-01 | West | DHB Utilities | Budget
1 | 2021-04-01 | West | DHB Utilities | Forecast | 0
1 | 2021-04-01 | West | DHB Utilities | Actual | 0
1 | 2021-04-01 | West | JDT | Budget
1 | 2021-04-01 | West | JDT | Forecast | 0
1 | 2021-04-01 | West | JDT | Actual | 0
1 | 2021-04-01 | West | MURRAY | Budget
1 | 2021-04-01 | West | MURRAY | Forecast | 0
1 | 2021-04-01 | West | MURRAY | Actual | 0
1 | 2021-04-01 | East | Terra Firma | Budget
1 | 2021-04-01 | East | Terra Firma | Forecast | 0
1 | 2021-04-01 | East | Terra Firma | Actual | 0
1 | 2021-04-01 | East | KLT | Budget
1 | 2021-04-01 | East | KLT | Forecast | 0
1 | 2021-04-01 | East | KLT | Actual | 0
1 | 2021-04-01 | East | Forefront | Budget
1 | 2021-04-01 | East | Forefront | Forecast | 0
1 | 2021-04-01 | East | Forefront | Actual | 0
1 | 2021-04-01 | East | DPF | Budget
1 | 2021-04-01 | East | DPF | Forecast | 0
1 | 2021-04-01 | East | DPF | Actual | 0
1 | 2021-04-01 | East | OMJ | Budget
1 | 2021-04-01 | East | OMJ | Forecast | 0
1 | 2021-04-01 | East | OMJ | Actual | 0
1 | 2021-04-01 | East | DHB Utilities | Budget
1 | 2021-04-01 | East | DHB Utilities | Forecast | 0
1 | 2021-04-01 | East | DHB Utilities | Actual | 0
1 | 2021-04-01 | East | JDT | Budget
1 | 2021-04-01 | East | JDT | Forecast | 0
1 | 2021-04-01 | East | JDT | Actual | 0
1 | 2021-04-01 | East | MURRAY | Budget
1 | 2021-04-01 | East | MURRAY | Forecast | 0
1 | 2021-04-01 | East | MURRAY | Actual | 0
1 | 2021-04-01 | Central | Terra Firma | Budget
1 | 2021-04-01 | Central | Terra Firma | Forecast | 0
1 | 2021-04-01 | Central | Terra Firma | Actual | 0
1 | 2021-04-01 | Central | KLT | Budget
1 | 2021-04-01 | Central | KLT | Forecast | 0
1 | 2021-04-01 | Central | KLT | Actual | 0
1 | 2021-04-01 | Central | Forefront | Budget
1 | 2021-04-01 | Central | Forefront | Forecast | 0
1 | 2021-04-01 | Central | Forefront | Actual | 0
1 | 2021-04-01 | Central | DPF | Budget
1 | 2021-04-01 | Central | DPF | Forecast | 0
1 | 2021-04-01 | Central | DPF | Actual | 0
1 | 2021-04-01 | Central | OMJ | Budget
1 | 2021-04-01 | Central | OMJ | Forecast | 0
1 | 2021-04-01 | Central | OMJ | Actual | 0
1 | 2021-04-01 | Central | DHB Utilities | Budget
1 | 2021-04-01 | Central | DHB Utilities | Forecast | 0
1 | 2021-04-01 | Central | DHB Utilities | Actual | 0
1 | 2021-04-01 | Central | JDT | Budget
1 | 2021-04-01 | Central | JDT | Forecast | 0
1 | 2021-04-01 | Central | JDT | Actual | 0
1 | 2021-04-01 | Central | MURRAY | Budget
1 | 2021-04-01 | Central | MURRAY | Forecast | 0
1 | 2021-04-01 | Central | MURRAY | Actual | 0
1 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Budget
1 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Budget
1 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Budget
1 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Budget
1 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | West | DIRECT MOLE | Budget
1 | 2021-04-01 | West | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | West | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | East | DIRECT MOLE | Budget
1 | 2021-04-01 | East | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | East | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | Central | DIRECT MOLE | Budget
1 | 2021-04-01 | Central | DIRECT MOLE | Forecast | 0
1 | 2021-04-01 | Central | DIRECT MOLE | Actual | 0
1 | 2021-04-01 | CMO West 1 | SQS | Budget
1 | 2021-04-01 | CMO West 1 | SQS | Forecast | 0
1 | 2021-04-01 | CMO West 1 | SQS | Actual | 0
1 | 2021-04-01 | CMO West 2 | SQS | Budget
1 | 2021-04-01 | CMO West 2 | SQS | Forecast | 0
1 | 2021-04-01 | CMO West 2 | SQS | Actual | 0
1 | 2021-04-01 | CMO East 1 | SQS | Budget
1 | 2021-04-01 | CMO East 1 | SQS | Forecast | 0
1 | 2021-04-01 | CMO East 1 | SQS | Actual | 0
1 | 2021-04-01 | CMO East 2 | SQS | Budget
1 | 2021-04-01 | CMO East 2 | SQS | Forecast | 0
1 | 2021-04-01 | CMO East 2 | SQS | Actual | 0
1 | 2021-04-01 | West | SQS | Budget
1 | 2021-04-01 | West | SQS | Forecast | 0
1 | 2021-04-01 | West | SQS | Actual | 0
1 | 2021-04-01 | East | SQS | Budget
1 | 2021-04-01 | East | SQS | Forecast | 0
1 | 2021-04-01 | East | SQS | Actual | 0
2 | 2021-04-01 | Central | SQS | Budget
2 | 2021-04-01 | Central | SQS | Forecast | 0
2 | 2021-04-01 | Central | SQS | Actual | 0
2 | 2021-04-01 | CMO West 1 | Terra Firma | Budget
2 | 2021-04-01 | CMO West 1 | Terra Firma | Forecast | 0
2 | 2021-04-01 | CMO West 1 | Terra Firma | Actual | 0
2 | 2021-04-01 | CMO West 1 | KLT | Budget
2 | 2021-04-01 | CMO West 1 | KLT | Forecast | 0
2 | 2021-04-01 | CMO West 1 | KLT | Actual | 0
2 | 2021-04-01 | CMO West 1 | Forefront | Budget
2 | 2021-04-01 | CMO West 1 | Forefront | Forecast | 0
2 | 2021-04-01 | CMO West 1 | Forefront | Actual | 0
2 | 2021-04-01 | CMO West 1 | DPF | Budget
2 | 2021-04-01 | CMO West 1 | DPF | Forecast | 0
2 | 2021-04-01 | CMO West 1 | DPF | Actual | 0
2 | 2021-04-01 | CMO West 1 | OMJ | Budget
2 | 2021-04-01 | CMO West 1 | OMJ | Forecast | 0
2 | 2021-04-01 | CMO West 1 | OMJ | Actual | 0
2 | 2021-04-01 | CMO West 1 | DHB Utilities | Budget
2 | 2021-04-01 | CMO West 1 | DHB Utilities | Forecast | 0
2 | 2021-04-01 | CMO West 1 | DHB Utilities | Actual | 0
2 | 2021-04-01 | CMO West 1 | JDT | Budget
2 | 2021-04-01 | CMO West 1 | JDT | Forecast | 0
2 | 2021-04-01 | CMO West 1 | JDT | Actual | 0
2 | 2021-04-01 | CMO West 1 | MURRAY | Budget
2 | 2021-04-01 | CMO West 1 | MURRAY | Forecast | 0
2 | 2021-04-01 | CMO West 1 | MURRAY | Actual | 0
2 | 2021-04-01 | CMO West 2 | Terra Firma | Budget
2 | 2021-04-01 | CMO West 2 | Terra Firma | Forecast | 0
2 | 2021-04-01 | CMO West 2 | Terra Firma | Actual | 0
2 | 2021-04-01 | CMO West 2 | KLT | Budget
2 | 2021-04-01 | CMO West 2 | KLT | Forecast | 0
2 | 2021-04-01 | CMO West 2 | KLT | Actual | 0
2 | 2021-04-01 | CMO West 2 | Forefront | Budget
2 | 2021-04-01 | CMO West 2 | Forefront | Forecast | 0
2 | 2021-04-01 | CMO West 2 | Forefront | Actual | 0
2 | 2021-04-01 | CMO West 2 | DPF | Budget
2 | 2021-04-01 | CMO West 2 | DPF | Forecast | 0
2 | 2021-04-01 | CMO West 2 | DPF | Actual | 0
2 | 2021-04-01 | CMO West 2 | OMJ | Budget
2 | 2021-04-01 | CMO West 2 | OMJ | Forecast | 0
2 | 2021-04-01 | CMO West 2 | OMJ | Actual | 0
2 | 2021-04-01 | CMO West 2 | DHB Utilities | Budget
2 | 2021-04-01 | CMO West 2 | DHB Utilities | Forecast | 0
2 | 2021-04-01 | CMO West 2 | DHB Utilities | Actual | 0
2 | 2021-04-01 | CMO West 2 | JDT | Budget
2 | 2021-04-01 | CMO West 2 | JDT | Forecast | 0
2 | 2021-04-01 | CMO West 2 | JDT | Actual | 0
2 | 2021-04-01 | CMO West 2 | MURRAY | Budget
2 | 2021-04-01 | CMO West 2 | MURRAY | Forecast | 0
2 | 2021-04-01 | CMO West 2 | MURRAY | Actual | 0
2 | 2021-04-01 | CMO East 1 | Terra Firma | Budget
2 | 2021-04-01 | CMO East 1 | Terra Firma | Forecast | 0
2 | 2021-04-01 | CMO East 1 | Terra Firma | Actual | 0
2 | 2021-04-01 | CMO East 1 | KLT | Budget
2 | 2021-04-01 | CMO East 1 | KLT | Forecast | 0
2 | 2021-04-01 | CMO East 1 | KLT | Actual | 0
2 | 2021-04-01 | CMO East 1 | Forefront | Budget
2 | 2021-04-01 | CMO East 1 | Forefront | Forecast | 0
2 | 2021-04-01 | CMO East 1 | Forefront | Actual | 0
2 | 2021-04-01 | CMO East 1 | DPF | Budget
2 | 2021-04-01 | CMO East 1 | DPF | Forecast | 0
2 | 2021-04-01 | CMO East 1 | DPF | Actual | 0
2 | 2021-04-01 | CMO East 1 | OMJ | Budget
2 | 2021-04-01 | CMO East 1 | OMJ | Forecast | 0
2 | 2021-04-01 | CMO East 1 | OMJ | Actual | 0
2 | 2021-04-01 | CMO East 1 | DHB Utilities | Budget
2 | 2021-04-01 | CMO East 1 | DHB Utilities | Forecast | 0
2 | 2021-04-01 | CMO East 1 | DHB Utilities | Actual | 0
2 | 2021-04-01 | CMO East 1 | JDT | Budget
2 | 2021-04-01 | CMO East 1 | JDT | Forecast | 0
2 | 2021-04-01 | CMO East 1 | JDT | Actual | 0
2 | 2021-04-01 | CMO East 1 | MURRAY | Budget
2 | 2021-04-01 | CMO East 1 | MURRAY | Forecast | 0
2 | 2021-04-01 | CMO East 1 | MURRAY | Actual | 0
2 | 2021-04-01 | CMO East 2 | Terra Firma | Budget
2 | 2021-04-01 | CMO East 2 | Terra Firma | Forecast | 0
2 | 2021-04-01 | CMO East 2 | Terra Firma | Actual | 0
2 | 2021-04-01 | CMO East 2 | KLT | Budget
2 | 2021-04-01 | CMO East 2 | KLT | Forecast | 0
2 | 2021-04-01 | CMO East 2 | KLT | Actual | 0
2 | 2021-04-01 | CMO East 2 | Forefront | Budget
2 | 2021-04-01 | CMO East 2 | Forefront | Forecast | 0
2 | 2021-04-01 | CMO East 2 | Forefront | Actual | 0
2 | 2021-04-01 | CMO East 2 | DPF | Budget
2 | 2021-04-01 | CMO East 2 | DPF | Forecast | 0
2 | 2021-04-01 | CMO East 2 | DPF | Actual | 0
2 | 2021-04-01 | CMO East 2 | OMJ | Budget
2 | 2021-04-01 | CMO East 2 | OMJ | Forecast | 0
2 | 2021-04-01 | CMO East 2 | OMJ | Actual | 0
2 | 2021-04-01 | CMO East 2 | DHB Utilities | Budget
2 | 2021-04-01 | CMO East 2 | DHB Utilities | Forecast | 0
2 | 2021-04-01 | CMO East 2 | DHB Utilities | Actual | 0
2 | 2021-04-01 | CMO East 2 | JDT | Budget
2 | 2021-04-01 | CMO East 2 | JDT | Forecast | 0
2 | 2021-04-01 | CMO East 2 | JDT | Actual | 0
2 | 2021-04-01 | CMO East 2 | MURRAY | Budget
2 | 2021-04-01 | CMO East 2 | MURRAY | Forecast | 0
2 | 2021-04-01 | CMO East 2 | MURRAY | Actual | 0
2 | 2021-04-01 | West | Terra Firma | Budget
2 | 2021-04-01 | West | Terra Firma | Forecast | 0
2 | 2021-04-01 | West | Terra Firma | Actual | 0
2 | 2021-04-01 | West | KLT | Budget
2 | 2021-04-01 | West | KLT | Forecast | 0
2 | 2021-04-01 | West | KLT | Actual | 0
2 | 2021-04-01 | West | Forefront | Budget
2 | 2021-04-01 | West | Forefront | Forecast | 0
2 | 2021-04-01 | West | Forefront | Actual | 0
2 | 2021-04-01 | West | DPF | Budget
2 | 2021-04-01 | West | DPF | Forecast | 0
2 | 2021-04-01 | West | DPF | Actual | 0
2 | 2021-04-01 | West | OMJ | Budget
2 | 2021-04-01 | West | OMJ | Forecast | 0
2 | 2021-04-01 | West | OMJ | Actual | 0
2 | 2021-04-01 | West | DHB Utilities | Budget
2 | 2021-04-01 | West | DHB Utilities | Forecast | 0
2 | 2021-04-01 | West | DHB Utilities | Actual | 0
2 | 2021-04-01 | West | JDT | Budget
2 | 2021-04-01 | West | JDT | Forecast | 0
2 | 2021-04-01 | West | JDT | Actual | 0
2 | 2021-04-01 | West | MURRAY | Budget
2 | 2021-04-01 | West | MURRAY | Forecast | 0
2 | 2021-04-01 | West | MURRAY | Actual | 0
2 | 2021-04-01 | East | Terra Firma | Budget
2 | 2021-04-01 | East | Terra Firma | Forecast | 0
2 | 2021-04-01 | East | Terra Firma | Actual | 0
2 | 2021-04-01 | East | KLT | Budget
2 | 2021-04-01 | East | KLT | Forecast | 0
2 | 2021-04-01 | East | KLT | Actual | 0
2 | 2021-04-01 | East | Forefront | Budget
2 | 2021-04-01 | East | Forefront | Forecast | 0
2 | 2021-04-01 | East | Forefront | Actual | 0
2 | 2021-04-01 | East | DPF | Budget
2 | 2021-04-01 | East | DPF | Forecast | 0
2 | 2021-04-01 | East | DPF | Actual | 0
2 | 2021-04-01 | East | OMJ | Budget
2 | 2021-04-01 | East | OMJ | Forecast | 0
2 | 2021-04-01 | East | OMJ | Actual | 0
2 | 2021-04-01 | East | DHB Utilities | Budget
2 | 2021-04-01 | East | DHB Utilities | Forecast | 0
2 | 2021-04-01 | East | DHB Utilities | Actual | 0
2 | 2021-04-01 | East | JDT | Budget
2 | 2021-04-01 | East | JDT | Forecast | 0
2 | 2021-04-01 | East | JDT | Actual | 0
2 | 2021-04-01 | East | MURRAY | Budget
2 | 2021-04-01 | East | MURRAY | Forecast | 0
2 | 2021-04-01 | East | MURRAY | Actual | 0
2 | 2021-04-01 | Central | Terra Firma | Budget
2 | 2021-04-01 | Central | Terra Firma | Forecast | 0
2 | 2021-04-01 | Central | Terra Firma | Actual | 0
2 | 2021-04-01 | Central | KLT | Budget
2 | 2021-04-01 | Central | KLT | Forecast | 0
2 | 2021-04-01 | Central | KLT | Actual | 0
2 | 2021-04-01 | Central | Forefront | Budget
2 | 2021-04-01 | Central | Forefront | Forecast | 0
2 | 2021-04-01 | Central | Forefront | Actual | 0
2 | 2021-04-01 | Central | DPF | Budget
2 | 2021-04-01 | Central | DPF | Forecast | 0
2 | 2021-04-01 | Central | DPF | Actual | 0
2 | 2021-04-01 | Central | OMJ | Budget
2 | 2021-04-01 | Central | OMJ | Forecast | 0
2 | 2021-04-01 | Central | OMJ | Actual | 0
2 | 2021-04-01 | Central | DHB Utilities | Budget
2 | 2021-04-01 | Central | DHB Utilities | Forecast | 0
2 | 2021-04-01 | Central | DHB Utilities | Actual | 0
2 | 2021-04-01 | Central | JDT | Budget
2 | 2021-04-01 | Central | JDT | Forecast | 0
2 | 2021-04-01 | Central | JDT | Actual | 0
2 | 2021-04-01 | Central | MURRAY | Budget
2 | 2021-04-01 | Central | MURRAY | Forecast | 0
2 | 2021-04-01 | Central | MURRAY | Actual | 0
2 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Budget
2 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Budget
2 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Budget
2 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Budget
2 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | West | DIRECT MOLE | Budget
2 | 2021-04-01 | West | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | West | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | East | DIRECT MOLE | Budget
2 | 2021-04-01 | East | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | East | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | Central | DIRECT MOLE | Budget
2 | 2021-04-01 | Central | DIRECT MOLE | Forecast | 0
2 | 2021-04-01 | Central | DIRECT MOLE | Actual | 0
2 | 2021-04-01 | CMO West 1 | SQS | Budget
2 | 2021-04-01 | CMO West 1 | SQS | Forecast | 0
2 | 2021-04-01 | CMO West 1 | SQS | Actual | 0
2 | 2021-04-01 | CMO West 2 | SQS | Budget
2 | 2021-04-01 | CMO West 2 | SQS | Forecast | 0
2 | 2021-04-01 | CMO West 2 | SQS | Actual | 0
2 | 2021-04-01 | CMO East 1 | SQS | Budget
2 | 2021-04-01 | CMO East 1 | SQS | Forecast | 0
2 | 2021-04-01 | CMO East 1 | SQS | Actual | 0
2 | 2021-04-01 | CMO East 2 | SQS | Budget
2 | 2021-04-01 | CMO East 2 | SQS | Forecast | 0
2 | 2021-04-01 | CMO East 2 | SQS | Actual | 0
2 | 2021-04-01 | West | SQS | Budget
2 | 2021-04-01 | West | SQS | Forecast | 0
2 | 2021-04-01 | West | SQS | Actual | 0
2 | 2021-04-01 | East | SQS | Budget
2 | 2021-04-01 | East | SQS | Forecast | 0
3 | 2021-04-01 | East | SQS | Actual | 0
3 | 2021-04-01 | Central | SQS | Budget
3 | 2021-04-01 | Central | SQS | Forecast | 0
2 | 2021-04-01 | Central | SQS | Actual | 0
3 | 2021-04-01 | CMO West 1 | Terra Firma | Budget
3 | 2021-04-01 | CMO West 1 | Terra Firma | Forecast | 0
3 | 2021-04-01 | CMO West 1 | Terra Firma | Actual | 0
3 | 2021-04-01 | CMO West 1 | KLT | Budget
3 | 2021-04-01 | CMO West 1 | KLT | Forecast | 0
3 | 2021-04-01 | CMO West 1 | KLT | Actual | 0
3 | 2021-04-01 | CMO West 1 | Forefront | Budget
3 | 2021-04-01 | CMO West 1 | Forefront | Forecast | 0
3 | 2021-04-01 | CMO West 1 | Forefront | Actual | 0
3 | 2021-04-01 | CMO West 1 | DPF | Budget
3 | 2021-04-01 | CMO West 1 | DPF | Forecast | 0
3 | 2021-04-01 | CMO West 1 | DPF | Actual | 0
3 | 2021-04-01 | CMO West 1 | OMJ | Budget
3 | 2021-04-01 | CMO West 1 | OMJ | Forecast | 0
3 | 2021-04-01 | CMO West 1 | OMJ | Actual | 0
3 | 2021-04-01 | CMO West 1 | DHB Utilities | Budget
3 | 2021-04-01 | CMO West 1 | DHB Utilities | Forecast | 0
3 | 2021-04-01 | CMO West 1 | DHB Utilities | Actual | 0
3 | 2021-04-01 | CMO West 1 | JDT | Budget
3 | 2021-04-01 | CMO West 1 | JDT | Forecast | 0
3 | 2021-04-01 | CMO West 1 | JDT | Actual | 0
3 | 2021-04-01 | CMO West 1 | MURRAY | Budget
3 | 2021-04-01 | CMO West 1 | MURRAY | Forecast | 0
3 | 2021-04-01 | CMO West 1 | MURRAY | Actual | 0
3 | 2021-04-01 | CMO West 2 | Terra Firma | Budget
3 | 2021-04-01 | CMO West 2 | Terra Firma | Forecast | 0
3 | 2021-04-01 | CMO West 2 | Terra Firma | Actual | 0
3 | 2021-04-01 | CMO West 2 | KLT | Budget
3 | 2021-04-01 | CMO West 2 | KLT | Forecast | 0
3 | 2021-04-01 | CMO West 2 | KLT | Actual | 0
3 | 2021-04-01 | CMO West 2 | Forefront | Budget
3 | 2021-04-01 | CMO West 2 | Forefront | Forecast | 0
3 | 2021-04-01 | CMO West 2 | Forefront | Actual | 0
3 | 2021-04-01 | CMO West 2 | DPF | Budget
3 | 2021-04-01 | CMO West 2 | DPF | Forecast | 0
3 | 2021-04-01 | CMO West 2 | DPF | Actual | 0
3 | 2021-04-01 | CMO West 2 | OMJ | Budget
3 | 2021-04-01 | CMO West 2 | OMJ | Forecast | 0
3 | 2021-04-01 | CMO West 2 | OMJ | Actual | 0
3 | 2021-04-01 | CMO West 2 | DHB Utilities | Budget
3 | 2021-04-01 | CMO West 2 | DHB Utilities | Forecast | 0
3 | 2021-04-01 | CMO West 2 | DHB Utilities | Actual | 0
3 | 2021-04-01 | CMO West 2 | JDT | Budget
3 | 2021-04-01 | CMO West 2 | JDT | Forecast | 0
3 | 2021-04-01 | CMO West 2 | JDT | Actual | 0
3 | 2021-04-01 | CMO West 2 | MURRAY | Budget
3 | 2021-04-01 | CMO West 2 | MURRAY | Forecast | 0
3 | 2021-04-01 | CMO West 2 | MURRAY | Actual | 0
3 | 2021-04-01 | CMO East 1 | Terra Firma | Budget
3 | 2021-04-01 | CMO East 1 | Terra Firma | Forecast | 0
3 | 2021-04-01 | CMO East 1 | Terra Firma | Actual | 0
3 | 2021-04-01 | CMO East 1 | KLT | Budget
3 | 2021-04-01 | CMO East 1 | KLT | Forecast | 0
3 | 2021-04-01 | CMO East 1 | KLT | Actual | 0
3 | 2021-04-01 | CMO East 1 | Forefront | Budget
3 | 2021-04-01 | CMO East 1 | Forefront | Forecast | 0
3 | 2021-04-01 | CMO East 1 | Forefront | Actual | 0
3 | 2021-04-01 | CMO East 1 | DPF | Budget
3 | 2021-04-01 | CMO East 1 | DPF | Forecast | 0
3 | 2021-04-01 | CMO East 1 | DPF | Actual | 0
3 | 2021-04-01 | CMO East 1 | OMJ | Budget
3 | 2021-04-01 | CMO East 1 | OMJ | Forecast | 0
3 | 2021-04-01 | CMO East 1 | OMJ | Actual | 0
3 | 2021-04-01 | CMO East 1 | DHB Utilities | Budget
3 | 2021-04-01 | CMO East 1 | DHB Utilities | Forecast | 0
3 | 2021-04-01 | CMO East 1 | DHB Utilities | Actual | 0
3 | 2021-04-01 | CMO East 1 | JDT | Budget
3 | 2021-04-01 | CMO East 1 | JDT | Forecast | 0
3 | 2021-04-01 | CMO East 1 | JDT | Actual | 0
3 | 2021-04-01 | CMO East 1 | MURRAY | Budget
3 | 2021-04-01 | CMO East 1 | MURRAY | Forecast | 0
3 | 2021-04-01 | CMO East 1 | MURRAY | Actual | 0
3 | 2021-04-01 | CMO East 2 | Terra Firma | Budget
3 | 2021-04-01 | CMO East 2 | Terra Firma | Forecast | 0
3 | 2021-04-01 | CMO East 2 | Terra Firma | Actual | 0
3 | 2021-04-01 | CMO East 2 | KLT | Budget
3 | 2021-04-01 | CMO East 2 | KLT | Forecast | 0
3 | 2021-04-01 | CMO East 2 | KLT | Actual | 0
3 | 2021-04-01 | CMO East 2 | Forefront | Budget
3 | 2021-04-01 | CMO East 2 | Forefront | Forecast | 0
3 | 2021-04-01 | CMO East 2 | Forefront | Actual | 0
3 | 2021-04-01 | CMO East 2 | DPF | Budget
3 | 2021-04-01 | CMO East 2 | DPF | Forecast | 0
3 | 2021-04-01 | CMO East 2 | DPF | Actual | 0
3 | 2021-04-01 | CMO East 2 | OMJ | Budget
3 | 2021-04-01 | CMO East 2 | OMJ | Forecast | 0
3 | 2021-04-01 | CMO East 2 | OMJ | Actual | 0
3 | 2021-04-01 | CMO East 2 | DHB Utilities | Budget
3 | 2021-04-01 | CMO East 2 | DHB Utilities | Forecast | 0
3 | 2021-04-01 | CMO East 2 | DHB Utilities | Actual | 0
3 | 2021-04-01 | CMO East 2 | JDT | Budget
3 | 2021-04-01 | CMO East 2 | JDT | Forecast | 0
3 | 2021-04-01 | CMO East 2 | JDT | Actual | 0
3 | 2021-04-01 | CMO East 2 | MURRAY | Budget
3 | 2021-04-01 | CMO East 2 | MURRAY | Forecast | 0
3 | 2021-04-01 | CMO East 2 | MURRAY | Actual | 0
3 | 2021-04-01 | West | Terra Firma | Budget
3 | 2021-04-01 | West | Terra Firma | Forecast | 0
3 | 2021-04-01 | West | Terra Firma | Actual | 0
3 | 2021-04-01 | West | KLT | Budget
3 | 2021-04-01 | West | KLT | Forecast | 0
3 | 2021-04-01 | West | KLT | Actual | 0
3 | 2021-04-01 | West | Forefront | Budget
3 | 2021-04-01 | West | Forefront | Forecast | 0
3 | 2021-04-01 | West | Forefront | Actual | 0
3 | 2021-04-01 | West | DPF | Budget
3 | 2021-04-01 | West | DPF | Forecast | 0
3 | 2021-04-01 | West | DPF | Actual | 0
3 | 2021-04-01 | West | OMJ | Budget
3 | 2021-04-01 | West | OMJ | Forecast | 0
3 | 2021-04-01 | West | OMJ | Actual | 0
3 | 2021-04-01 | West | DHB Utilities | Budget
3 | 2021-04-01 | West | DHB Utilities | Forecast | 0
3 | 2021-04-01 | West | DHB Utilities | Actual | 0
3 | 2021-04-01 | West | JDT | Budget
3 | 2021-04-01 | West | JDT | Forecast | 0
3 | 2021-04-01 | West | JDT | Actual | 0
3 | 2021-04-01 | West | MURRAY | Budget
3 | 2021-04-01 | West | MURRAY | Forecast | 0
3 | 2021-04-01 | West | MURRAY | Actual | 0
3 | 2021-04-01 | East | Terra Firma | Budget
3 | 2021-04-01 | East | Terra Firma | Forecast | 0
3 | 2021-04-01 | East | Terra Firma | Actual | 0
3 | 2021-04-01 | East | KLT | Budget
3 | 2021-04-01 | East | KLT | Forecast | 0
3 | 2021-04-01 | East | KLT | Actual | 0
3 | 2021-04-01 | East | Forefront | Budget
3 | 2021-04-01 | East | Forefront | Forecast | 0
3 | 2021-04-01 | East | Forefront | Actual | 0
3 | 2021-04-01 | East | DPF | Budget
3 | 2021-04-01 | East | DPF | Forecast | 0
3 | 2021-04-01 | East | DPF | Actual | 0
3 | 2021-04-01 | East | OMJ | Budget
3 | 2021-04-01 | East | OMJ | Forecast | 0
3 | 2021-04-01 | East | OMJ | Actual | 0
3 | 2021-04-01 | East | DHB Utilities | Budget
3 | 2021-04-01 | East | DHB Utilities | Forecast | 0
3 | 2021-04-01 | East | DHB Utilities | Actual | 0
3 | 2021-04-01 | East | JDT | Budget
3 | 2021-04-01 | East | JDT | Forecast | 0
3 | 2021-04-01 | East | JDT | Actual | 0
3 | 2021-04-01 | East | MURRAY | Budget
3 | 2021-04-01 | East | MURRAY | Forecast | 0
3 | 2021-04-01 | East | MURRAY | Actual | 0
3 | 2021-04-01 | Central | Terra Firma | Budget
3 | 2021-04-01 | Central | Terra Firma | Forecast | 0
3 | 2021-04-01 | Central | Terra Firma | Actual | 0
3 | 2021-04-01 | Central | KLT | Budget
3 | 2021-04-01 | Central | KLT | Forecast | 0
3 | 2021-04-01 | Central | KLT | Actual | 0
3 | 2021-04-01 | Central | Forefront | Budget
3 | 2021-04-01 | Central | Forefront | Forecast | 0
3 | 2021-04-01 | Central | Forefront | Actual | 0
3 | 2021-04-01 | Central | DPF | Budget
3 | 2021-04-01 | Central | DPF | Forecast | 0
3 | 2021-04-01 | Central | DPF | Actual | 0
3 | 2021-04-01 | Central | OMJ | Budget
3 | 2021-04-01 | Central | OMJ | Forecast | 0
3 | 2021-04-01 | Central | OMJ | Actual | 0
3 | 2021-04-01 | Central | DHB Utilities | Budget
3 | 2021-04-01 | Central | DHB Utilities | Forecast | 0
3 | 2021-04-01 | Central | DHB Utilities | Actual | 0
3 | 2021-04-01 | Central | JDT | Budget
3 | 2021-04-01 | Central | JDT | Forecast | 0
3 | 2021-04-01 | Central | JDT | Actual | 0
3 | 2021-04-01 | Central | MURRAY | Budget
3 | 2021-04-01 | Central | MURRAY | Forecast | 0
3 | 2021-04-01 | Central | MURRAY | Actual | 0
3 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Budget
3 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Budget
3 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Budget
3 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Budget
3 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | West | DIRECT MOLE | Budget
3 | 2021-04-01 | West | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | West | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | East | DIRECT MOLE | Budget
3 | 2021-04-01 | East | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | East | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | Central | DIRECT MOLE | Budget
3 | 2021-04-01 | Central | DIRECT MOLE | Forecast | 0
3 | 2021-04-01 | Central | DIRECT MOLE | Actual | 0
3 | 2021-04-01 | CMO West 1 | SQS | Budget
3 | 2021-04-01 | CMO West 1 | SQS | Forecast | 0
3 | 2021-04-01 | CMO West 1 | SQS | Actual | 0
3 | 2021-04-01 | CMO West 2 | SQS | Budget
3 | 2021-04-01 | CMO West 2 | SQS | Forecast | 0
3 | 2021-04-01 | CMO West 2 | SQS | Actual | 0
3 | 2021-04-01 | CMO East 1 | SQS | Budget
3 | 2021-04-01 | CMO East 1 | SQS | Forecast | 0
3 | 2021-04-01 | CMO East 1 | SQS | Actual | 0
3 | 2021-04-01 | CMO East 2 | SQS | Budget
3 | 2021-04-01 | CMO East 2 | SQS | Forecast | 0
3 | 2021-04-01 | CMO East 2 | SQS | Actual | 0
3 | 2021-04-01 | West | SQS | Budget
3 | 2021-04-01 | West | SQS | Forecast | 0
3 | 2021-04-01 | West | SQS | Actual | 0
3 | 2021-04-01 | East | SQS | Budget
3 | 2021-04-01 | East | SQS | Forecast | 0
4 | 2021-04-01 | East | SQS | Actual | 0
4 | 2021-04-01 | Central | SQS | Budget
4 | 2021-04-01 | Central | SQS | Forecast | 0
3 | 2021-04-01 | Central | SQS | Actual | 0
4 | 2021-04-01 | CMO West 1 | Terra Firma | Budget
4 | 2021-04-01 | CMO West 1 | Terra Firma | Forecast | 0
4 | 2021-04-01 | CMO West 1 | Terra Firma | Actual | 0
4 | 2021-04-01 | CMO West 1 | KLT | Budget
4 | 2021-04-01 | CMO West 1 | KLT | Forecast | 0
4 | 2021-04-01 | CMO West 1 | KLT | Actual | 0
4 | 2021-04-01 | CMO West 1 | Forefront | Budget
4 | 2021-04-01 | CMO West 1 | Forefront | Forecast | 0
4 | 2021-04-01 | CMO West 1 | Forefront | Actual | 0
4 | 2021-04-01 | CMO West 1 | DPF | Budget
4 | 2021-04-01 | CMO West 1 | DPF | Forecast | 0
4 | 2021-04-01 | CMO West 1 | DPF | Actual | 0
4 | 2021-04-01 | CMO West 1 | OMJ | Budget
4 | 2021-04-01 | CMO West 1 | OMJ | Forecast | 0
4 | 2021-04-01 | CMO West 1 | OMJ | Actual | 0
4 | 2021-04-01 | CMO West 1 | DHB Utilities | Budget
4 | 2021-04-01 | CMO West 1 | DHB Utilities | Forecast | 0
4 | 2021-04-01 | CMO West 1 | DHB Utilities | Actual | 0
4 | 2021-04-01 | CMO West 1 | JDT | Budget
4 | 2021-04-01 | CMO West 1 | JDT | Forecast | 0
4 | 2021-04-01 | CMO West 1 | JDT | Actual | 0
4 | 2021-04-01 | CMO West 1 | MURRAY | Budget
4 | 2021-04-01 | CMO West 1 | MURRAY | Forecast | 0
4 | 2021-04-01 | CMO West 1 | MURRAY | Actual | 0
4 | 2021-04-01 | CMO West 2 | Terra Firma | Budget
4 | 2021-04-01 | CMO West 2 | Terra Firma | Forecast | 0
4 | 2021-04-01 | CMO West 2 | Terra Firma | Actual | 0
4 | 2021-04-01 | CMO West 2 | KLT | Budget
4 | 2021-04-01 | CMO West 2 | KLT | Forecast | 0
4 | 2021-04-01 | CMO West 2 | KLT | Actual | 0
4 | 2021-04-01 | CMO West 2 | Forefront | Budget
4 | 2021-04-01 | CMO West 2 | Forefront | Forecast | 0
4 | 2021-04-01 | CMO West 2 | Forefront | Actual | 0
4 | 2021-04-01 | CMO West 2 | DPF | Budget
4 | 2021-04-01 | CMO West 2 | DPF | Forecast | 0
4 | 2021-04-01 | CMO West 2 | DPF | Actual | 0
4 | 2021-04-01 | CMO West 2 | OMJ | Budget
4 | 2021-04-01 | CMO West 2 | OMJ | Forecast | 0
4 | 2021-04-01 | CMO West 2 | OMJ | Actual | 0
4 | 2021-04-01 | CMO West 2 | DHB Utilities | Budget
4 | 2021-04-01 | CMO West 2 | DHB Utilities | Forecast | 0
4 | 2021-04-01 | CMO West 2 | DHB Utilities | Actual | 0
4 | 2021-04-01 | CMO West 2 | JDT | Budget
4 | 2021-04-01 | CMO West 2 | JDT | Forecast | 0
4 | 2021-04-01 | CMO West 2 | JDT | Actual | 0
4 | 2021-04-01 | CMO West 2 | MURRAY | Budget
4 | 2021-04-01 | CMO West 2 | MURRAY | Forecast | 0
4 | 2021-04-01 | CMO West 2 | MURRAY | Actual | 0
4 | 2021-04-01 | CMO East 1 | Terra Firma | Budget
4 | 2021-04-01 | CMO East 1 | Terra Firma | Forecast | 0
4 | 2021-04-01 | CMO East 1 | Terra Firma | Actual | 0
4 | 2021-04-01 | CMO East 1 | KLT | Budget
4 | 2021-04-01 | CMO East 1 | KLT | Forecast | 0
4 | 2021-04-01 | CMO East 1 | KLT | Actual | 0
4 | 2021-04-01 | CMO East 1 | Forefront | Budget
4 | 2021-04-01 | CMO East 1 | Forefront | Forecast | 0
4 | 2021-04-01 | CMO East 1 | Forefront | Actual | 0
4 | 2021-04-01 | CMO East 1 | DPF | Budget
4 | 2021-04-01 | CMO East 1 | DPF | Forecast | 0
4 | 2021-04-01 | CMO East 1 | DPF | Actual | 0
4 | 2021-04-01 | CMO East 1 | OMJ | Budget
4 | 2021-04-01 | CMO East 1 | OMJ | Forecast | 0
4 | 2021-04-01 | CMO East 1 | OMJ | Actual | 0
4 | 2021-04-01 | CMO East 1 | DHB Utilities | Budget
4 | 2021-04-01 | CMO East 1 | DHB Utilities | Forecast | 0
4 | 2021-04-01 | CMO East 1 | DHB Utilities | Actual | 0
4 | 2021-04-01 | CMO East 1 | JDT | Budget
4 | 2021-04-01 | CMO East 1 | JDT | Forecast | 0
4 | 2021-04-01 | CMO East 1 | JDT | Actual | 0
4 | 2021-04-01 | CMO East 1 | MURRAY | Budget
4 | 2021-04-01 | CMO East 1 | MURRAY | Forecast | 0
4 | 2021-04-01 | CMO East 1 | MURRAY | Actual | 0
4 | 2021-04-01 | CMO East 2 | Terra Firma | Budget
4 | 2021-04-01 | CMO East 2 | Terra Firma | Forecast | 0
4 | 2021-04-01 | CMO East 2 | Terra Firma | Actual | 0
4 | 2021-04-01 | CMO East 2 | KLT | Budget
4 | 2021-04-01 | CMO East 2 | KLT | Forecast | 0
4 | 2021-04-01 | CMO East 2 | KLT | Actual | 0
4 | 2021-04-01 | CMO East 2 | Forefront | Budget
4 | 2021-04-01 | CMO East 2 | Forefront | Forecast | 0
4 | 2021-04-01 | CMO East 2 | Forefront | Actual | 0
4 | 2021-04-01 | CMO East 2 | DPF | Budget
4 | 2021-04-01 | CMO East 2 | DPF | Forecast | 0
4 | 2021-04-01 | CMO East 2 | DPF | Actual | 0
4 | 2021-04-01 | CMO East 2 | OMJ | Budget
4 | 2021-04-01 | CMO East 2 | OMJ | Forecast | 0
4 | 2021-04-01 | CMO East 2 | OMJ | Actual | 0
4 | 2021-04-01 | CMO East 2 | DHB Utilities | Budget
4 | 2021-04-01 | CMO East 2 | DHB Utilities | Forecast | 0
4 | 2021-04-01 | CMO East 2 | DHB Utilities | Actual | 0
4 | 2021-04-01 | CMO East 2 | JDT | Budget
4 | 2021-04-01 | CMO East 2 | JDT | Forecast | 0
4 | 2021-04-01 | CMO East 2 | JDT | Actual | 0
4 | 2021-04-01 | CMO East 2 | MURRAY | Budget
4 | 2021-04-01 | CMO East 2 | MURRAY | Forecast | 0
4 | 2021-04-01 | CMO East 2 | MURRAY | Actual | 0
4 | 2021-04-01 | West | Terra Firma | Budget
4 | 2021-04-01 | West | Terra Firma | Forecast | 0
4 | 2021-04-01 | West | Terra Firma | Actual | 0
4 | 2021-04-01 | West | KLT | Budget
4 | 2021-04-01 | West | KLT | Forecast | 0
4 | 2021-04-01 | West | KLT | Actual | 0
4 | 2021-04-01 | West | Forefront | Budget
4 | 2021-04-01 | West | Forefront | Forecast | 0
4 | 2021-04-01 | West | Forefront | Actual | 0
4 | 2021-04-01 | West | DPF | Budget
4 | 2021-04-01 | West | DPF | Forecast | 0
4 | 2021-04-01 | West | DPF | Actual | 0
4 | 2021-04-01 | West | OMJ | Budget
4 | 2021-04-01 | West | OMJ | Forecast | 0
4 | 2021-04-01 | West | OMJ | Actual | 0
4 | 2021-04-01 | West | DHB Utilities | Budget
4 | 2021-04-01 | West | DHB Utilities | Forecast | 0
4 | 2021-04-01 | West | DHB Utilities | Actual | 0
4 | 2021-04-01 | West | JDT | Budget
4 | 2021-04-01 | West | JDT | Forecast | 0
4 | 2021-04-01 | West | JDT | Actual | 0
4 | 2021-04-01 | West | MURRAY | Budget
4 | 2021-04-01 | West | MURRAY | Forecast | 0
4 | 2021-04-01 | West | MURRAY | Actual | 0
4 | 2021-04-01 | East | Terra Firma | Budget
4 | 2021-04-01 | East | Terra Firma | Forecast | 0
4 | 2021-04-01 | East | Terra Firma | Actual | 0
4 | 2021-04-01 | East | KLT | Budget
4 | 2021-04-01 | East | KLT | Forecast | 0
4 | 2021-04-01 | East | KLT | Actual | 0
4 | 2021-04-01 | East | Forefront | Budget
4 | 2021-04-01 | East | Forefront | Forecast | 0
4 | 2021-04-01 | East | Forefront | Actual | 0
4 | 2021-04-01 | East | DPF | Budget
4 | 2021-04-01 | East | DPF | Forecast | 0
4 | 2021-04-01 | East | DPF | Actual | 0
4 | 2021-04-01 | East | OMJ | Budget
4 | 2021-04-01 | East | OMJ | Forecast | 0
4 | 2021-04-01 | East | OMJ | Actual | 0
4 | 2021-04-01 | East | DHB Utilities | Budget
4 | 2021-04-01 | East | DHB Utilities | Forecast | 0
4 | 2021-04-01 | East | DHB Utilities | Actual | 0
4 | 2021-04-01 | East | JDT | Budget
4 | 2021-04-01 | East | JDT | Forecast | 0
4 | 2021-04-01 | East | JDT | Actual | 0
4 | 2021-04-01 | East | MURRAY | Budget
4 | 2021-04-01 | East | MURRAY | Forecast | 0
4 | 2021-04-01 | East | MURRAY | Actual | 0
4 | 2021-04-01 | Central | Terra Firma | Budget
4 | 2021-04-01 | Central | Terra Firma | Forecast | 0
4 | 2021-04-01 | Central | Terra Firma | Actual | 0
4 | 2021-04-01 | Central | KLT | Budget
4 | 2021-04-01 | Central | KLT | Forecast | 0
4 | 2021-04-01 | Central | KLT | Actual | 0
4 | 2021-04-01 | Central | Forefront | Budget
4 | 2021-04-01 | Central | Forefront | Forecast | 0
4 | 2021-04-01 | Central | Forefront | Actual | 0
4 | 2021-04-01 | Central | DPF | Budget
4 | 2021-04-01 | Central | DPF | Forecast | 0
4 | 2021-04-01 | Central | DPF | Actual | 0
4 | 2021-04-01 | Central | OMJ | Budget
4 | 2021-04-01 | Central | OMJ | Forecast | 0
4 | 2021-04-01 | Central | OMJ | Actual | 0
4 | 2021-04-01 | Central | DHB Utilities | Budget
4 | 2021-04-01 | Central | DHB Utilities | Forecast | 0
4 | 2021-04-01 | Central | DHB Utilities | Actual | 0
4 | 2021-04-01 | Central | JDT | Budget
4 | 2021-04-01 | Central | JDT | Forecast | 0
4 | 2021-04-01 | Central | JDT | Actual | 0
4 | 2021-04-01 | Central | MURRAY | Budget
4 | 2021-04-01 | Central | MURRAY | Forecast | 0
4 | 2021-04-01 | Central | MURRAY | Actual | 0
4 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Budget
4 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Budget
4 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Budget
4 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Budget
4 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | West | DIRECT MOLE | Budget
4 | 2021-04-01 | West | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | West | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | East | DIRECT MOLE | Budget
4 | 2021-04-01 | East | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | East | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | Central | DIRECT MOLE | Budget
4 | 2021-04-01 | Central | DIRECT MOLE | Forecast | 0
4 | 2021-04-01 | Central | DIRECT MOLE | Actual | 0
4 | 2021-04-01 | CMO West 1 | SQS | Budget
4 | 2021-04-01 | CMO West 1 | SQS | Forecast | 0
4 | 2021-04-01 | CMO West 1 | SQS | Actual | 0
4 | 2021-04-01 | CMO West 2 | SQS | Budget
4 | 2021-04-01 | CMO West 2 | SQS | Forecast | 0
4 | 2021-04-01 | CMO West 2 | SQS | Actual | 0
4 | 2021-04-01 | CMO East 1 | SQS | Budget
4 | 2021-04-01 | CMO East 1 | SQS | Forecast | 0
4 | 2021-04-01 | CMO East 1 | SQS | Actual | 0
4 | 2021-04-01 | CMO East 2 | SQS | Budget
4 | 2021-04-01 | CMO East 2 | SQS | Forecast | 0
4 | 2021-04-01 | CMO East 2 | SQS | Actual | 0
4 | 2021-04-01 | West | SQS | Budget
4 | 2021-04-01 | West | SQS | Forecast | 0
4 | 2021-04-01 | West | SQS | Actual | 0
4 | 2021-04-01 | East | SQS | Budget
4 | 2021-04-01 | East | SQS | Forecast | 0
5 | 2021-04-01 | East | SQS | Actual | 0
5 | 2021-04-01 | Central | SQS | Budget
5 | 2021-04-01 | Central | SQS | Forecast | 0
4 | 2021-04-01 | Central | SQS | Actual | 0
5 | 2021-04-01 | CMO West 1 | Terra Firma | Budget
5 | 2021-04-01 | CMO West 1 | Terra Firma | Forecast | 0
5 | 2021-04-01 | CMO West 1 | Terra Firma | Actual | 0
5 | 2021-04-01 | CMO West 1 | KLT | Budget
5 | 2021-04-01 | CMO West 1 | KLT | Forecast | 0
5 | 2021-04-01 | CMO West 1 | KLT | Actual | 0
5 | 2021-04-01 | CMO West 1 | Forefront | Budget
5 | 2021-04-01 | CMO West 1 | Forefront | Forecast | 0
5 | 2021-04-01 | CMO West 1 | Forefront | Actual | 0
5 | 2021-04-01 | CMO West 1 | DPF | Budget
5 | 2021-04-01 | CMO West 1 | DPF | Forecast | 0
5 | 2021-04-01 | CMO West 1 | DPF | Actual | 0
5 | 2021-04-01 | CMO West 1 | OMJ | Budget
5 | 2021-04-01 | CMO West 1 | OMJ | Forecast | 0
5 | 2021-04-01 | CMO West 1 | OMJ | Actual | 0
5 | 2021-04-01 | CMO West 1 | DHB Utilities | Budget
5 | 2021-04-01 | CMO West 1 | DHB Utilities | Forecast | 0
5 | 2021-04-01 | CMO West 1 | DHB Utilities | Actual | 0
5 | 2021-04-01 | CMO West 1 | JDT | Budget
5 | 2021-04-01 | CMO West 1 | JDT | Forecast | 0
5 | 2021-04-01 | CMO West 1 | JDT | Actual | 0
5 | 2021-04-01 | CMO West 1 | MURRAY | Budget
5 | 2021-04-01 | CMO West 1 | MURRAY | Forecast | 0
5 | 2021-04-01 | CMO West 1 | MURRAY | Actual | 0
5 | 2021-04-01 | CMO West 2 | Terra Firma | Budget
5 | 2021-04-01 | CMO West 2 | Terra Firma | Forecast | 0
5 | 2021-04-01 | CMO West 2 | Terra Firma | Actual | 0
5 | 2021-04-01 | CMO West 2 | KLT | Budget
5 | 2021-04-01 | CMO West 2 | KLT | Forecast | 0
5 | 2021-04-01 | CMO West 2 | KLT | Actual | 0
5 | 2021-04-01 | CMO West 2 | Forefront | Budget
5 | 2021-04-01 | CMO West 2 | Forefront | Forecast | 0
5 | 2021-04-01 | CMO West 2 | Forefront | Actual | 0
5 | 2021-04-01 | CMO West 2 | DPF | Budget
5 | 2021-04-01 | CMO West 2 | DPF | Forecast | 0
5 | 2021-04-01 | CMO West 2 | DPF | Actual | 0
5 | 2021-04-01 | CMO West 2 | OMJ | Budget
5 | 2021-04-01 | CMO West 2 | OMJ | Forecast | 0
5 | 2021-04-01 | CMO West 2 | OMJ | Actual | 0
5 | 2021-04-01 | CMO West 2 | DHB Utilities | Budget
5 | 2021-04-01 | CMO West 2 | DHB Utilities | Forecast | 0
5 | 2021-04-01 | CMO West 2 | DHB Utilities | Actual | 0
5 | 2021-04-01 | CMO West 2 | JDT | Budget
5 | 2021-04-01 | CMO West 2 | JDT | Forecast | 0
5 | 2021-04-01 | CMO West 2 | JDT | Actual | 0
5 | 2021-04-01 | CMO West 2 | MURRAY | Budget
5 | 2021-04-01 | CMO West 2 | MURRAY | Forecast | 0
5 | 2021-04-01 | CMO West 2 | MURRAY | Actual | 0
5 | 2021-04-01 | CMO East 1 | Terra Firma | Budget
5 | 2021-04-01 | CMO East 1 | Terra Firma | Forecast | 0
5 | 2021-04-01 | CMO East 1 | Terra Firma | Actual | 0
5 | 2021-04-01 | CMO East 1 | KLT | Budget
5 | 2021-04-01 | CMO East 1 | KLT | Forecast | 0
5 | 2021-04-01 | CMO East 1 | KLT | Actual | 0
5 | 2021-04-01 | CMO East 1 | Forefront | Budget
5 | 2021-04-01 | CMO East 1 | Forefront | Forecast | 0
5 | 2021-04-01 | CMO East 1 | Forefront | Actual | 0
5 | 2021-04-01 | CMO East 1 | DPF | Budget
5 | 2021-04-01 | CMO East 1 | DPF | Forecast | 0
5 | 2021-04-01 | CMO East 1 | DPF | Actual | 0
5 | 2021-04-01 | CMO East 1 | OMJ | Budget
5 | 2021-04-01 | CMO East 1 | OMJ | Forecast | 0
5 | 2021-04-01 | CMO East 1 | OMJ | Actual | 0
5 | 2021-04-01 | CMO East 1 | DHB Utilities | Budget
5 | 2021-04-01 | CMO East 1 | DHB Utilities | Forecast | 0
5 | 2021-04-01 | CMO East 1 | DHB Utilities | Actual | 0
5 | 2021-04-01 | CMO East 1 | JDT | Budget
5 | 2021-04-01 | CMO East 1 | JDT | Forecast | 0
5 | 2021-04-01 | CMO East 1 | JDT | Actual | 0
5 | 2021-04-01 | CMO East 1 | MURRAY | Budget
5 | 2021-04-01 | CMO East 1 | MURRAY | Forecast | 0
5 | 2021-04-01 | CMO East 1 | MURRAY | Actual | 0
5 | 2021-04-01 | CMO East 2 | Terra Firma | Budget
5 | 2021-04-01 | CMO East 2 | Terra Firma | Forecast | 0
5 | 2021-04-01 | CMO East 2 | Terra Firma | Actual | 0
5 | 2021-04-01 | CMO East 2 | KLT | Budget
5 | 2021-04-01 | CMO East 2 | KLT | Forecast | 0
5 | 2021-04-01 | CMO East 2 | KLT | Actual | 0
5 | 2021-04-01 | CMO East 2 | Forefront | Budget
5 | 2021-04-01 | CMO East 2 | Forefront | Forecast | 0
5 | 2021-04-01 | CMO East 2 | Forefront | Actual | 0
5 | 2021-04-01 | CMO East 2 | DPF | Budget
5 | 2021-04-01 | CMO East 2 | DPF | Forecast | 0
5 | 2021-04-01 | CMO East 2 | DPF | Actual | 0
5 | 2021-04-01 | CMO East 2 | OMJ | Budget
5 | 2021-04-01 | CMO East 2 | OMJ | Forecast | 0
5 | 2021-04-01 | CMO East 2 | OMJ | Actual | 0
5 | 2021-04-01 | CMO East 2 | DHB Utilities | Budget
5 | 2021-04-01 | CMO East 2 | DHB Utilities | Forecast | 0
5 | 2021-04-01 | CMO East 2 | DHB Utilities | Actual | 0
5 | 2021-04-01 | CMO East 2 | JDT | Budget
5 | 2021-04-01 | CMO East 2 | JDT | Forecast | 0
5 | 2021-04-01 | CMO East 2 | JDT | Actual | 0
5 | 2021-04-01 | CMO East 2 | MURRAY | Budget
5 | 2021-04-01 | CMO East 2 | MURRAY | Forecast | 0
5 | 2021-04-01 | CMO East 2 | MURRAY | Actual | 0
5 | 2021-04-01 | West | Terra Firma | Budget
5 | 2021-04-01 | West | Terra Firma | Forecast | 0
5 | 2021-04-01 | West | Terra Firma | Actual | 0
5 | 2021-04-01 | West | KLT | Budget
5 | 2021-04-01 | West | KLT | Forecast | 0
5 | 2021-04-01 | West | KLT | Actual | 0
5 | 2021-04-01 | West | Forefront | Budget
5 | 2021-04-01 | West | Forefront | Forecast | 0
5 | 2021-04-01 | West | Forefront | Actual | 0
5 | 2021-04-01 | West | DPF | Budget
5 | 2021-04-01 | West | DPF | Forecast | 0
5 | 2021-04-01 | West | DPF | Actual | 0
5 | 2021-04-01 | West | OMJ | Budget
5 | 2021-04-01 | West | OMJ | Forecast | 0
5 | 2021-04-01 | West | OMJ | Actual | 0
5 | 2021-04-01 | West | DHB Utilities | Budget
5 | 2021-04-01 | West | DHB Utilities | Forecast | 0
5 | 2021-04-01 | West | DHB Utilities | Actual | 0
5 | 2021-04-01 | West | JDT | Budget
5 | 2021-04-01 | West | JDT | Forecast | 0
5 | 2021-04-01 | West | JDT | Actual | 0
5 | 2021-04-01 | West | MURRAY | Budget
5 | 2021-04-01 | West | MURRAY | Forecast | 0
5 | 2021-04-01 | West | MURRAY | Actual | 0
5 | 2021-04-01 | East | Terra Firma | Budget
5 | 2021-04-01 | East | Terra Firma | Forecast | 0
5 | 2021-04-01 | East | Terra Firma | Actual | 0
5 | 2021-04-01 | East | KLT | Budget
5 | 2021-04-01 | East | KLT | Forecast | 0
5 | 2021-04-01 | East | KLT | Actual | 0
5 | 2021-04-01 | East | Forefront | Budget
5 | 2021-04-01 | East | Forefront | Forecast | 0
5 | 2021-04-01 | East | Forefront | Actual | 0
5 | 2021-04-01 | East | DPF | Budget
5 | 2021-04-01 | East | DPF | Forecast | 0
5 | 2021-04-01 | East | DPF | Actual | 0
5 | 2021-04-01 | East | OMJ | Budget
5 | 2021-04-01 | East | OMJ | Forecast | 0
5 | 2021-04-01 | East | OMJ | Actual | 0
5 | 2021-04-01 | East | DHB Utilities | Budget
5 | 2021-04-01 | East | DHB Utilities | Forecast | 0
5 | 2021-04-01 | East | DHB Utilities | Actual | 0
5 | 2021-04-01 | East | JDT | Budget
5 | 2021-04-01 | East | JDT | Forecast | 0
5 | 2021-04-01 | East | JDT | Actual | 0
5 | 2021-04-01 | East | MURRAY | Budget
5 | 2021-04-01 | East | MURRAY | Forecast | 0
5 | 2021-04-01 | East | MURRAY | Actual | 0
5 | 2021-04-01 | Central | Terra Firma | Budget
5 | 2021-04-01 | Central | Terra Firma | Forecast | 0
5 | 2021-04-01 | Central | Terra Firma | Actual | 0
5 | 2021-04-01 | Central | KLT | Budget
5 | 2021-04-01 | Central | KLT | Forecast | 0
5 | 2021-04-01 | Central | KLT | Actual | 0
5 | 2021-04-01 | Central | Forefront | Budget
5 | 2021-04-01 | Central | Forefront | Forecast | 0
5 | 2021-04-01 | Central | Forefront | Actual | 0
5 | 2021-04-01 | Central | DPF | Budget
5 | 2021-04-01 | Central | DPF | Forecast | 0
5 | 2021-04-01 | Central | DPF | Actual | 0
5 | 2021-04-01 | Central | OMJ | Budget
5 | 2021-04-01 | Central | OMJ | Forecast | 0
5 | 2021-04-01 | Central | OMJ | Actual | 0
5 | 2021-04-01 | Central | DHB Utilities | Budget
5 | 2021-04-01 | Central | DHB Utilities | Forecast | 0
5 | 2021-04-01 | Central | DHB Utilities | Actual | 0
5 | 2021-04-01 | Central | JDT | Budget
5 | 2021-04-01 | Central | JDT | Forecast | 0
5 | 2021-04-01 | Central | JDT | Actual | 0
5 | 2021-04-01 | Central | MURRAY | Budget
5 | 2021-04-01 | Central | MURRAY | Forecast | 0
5 | 2021-04-01 | Central | MURRAY | Actual | 0
5 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Budget
5 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | CMO West 1 | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Budget
5 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | CMO West 2 | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Budget
5 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | CMO East 1 | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Budget
5 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | CMO East 2 | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | West | DIRECT MOLE | Budget
5 | 2021-04-01 | West | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | West | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | East | DIRECT MOLE | Budget
5 | 2021-04-01 | East | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | East | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | Central | DIRECT MOLE | Budget
5 | 2021-04-01 | Central | DIRECT MOLE | Forecast | 0
5 | 2021-04-01 | Central | DIRECT MOLE | Actual | 0
5 | 2021-04-01 | CMO West 1 | SQS | Budget
5 | 2021-04-01 | CMO West 1 | SQS | Forecast | 0
5 | 2021-04-01 | CMO West 1 | SQS | Actual | 0
5 | 2021-04-01 | CMO West 2 | SQS | Budget
5 | 2021-04-01 | CMO West 2 | SQS | Forecast | 0
5 | 2021-04-01 | CMO West 2 | SQS | Actual | 0
5 | 2021-04-01 | CMO East 1 | SQS | Budget
5 | 2021-04-01 | CMO East 1 | SQS | Forecast | 0
5 | 2021-04-01 | CMO East 1 | SQS | Actual | 0
5 | 2021-04-01 | CMO East 2 | SQS | Budget
5 | 2021-04-01 | CMO East 2 | SQS | Forecast | 0
5 | 2021-04-01 | CMO East 2 | SQS | Actual | 0
5 | 2021-04-01 | West | SQS | Budget
5 | 2021-04-01 | West | SQS | Forecast | 0
5 | 2021-04-01 | West | SQS | Actual | 0
5 | 2021-04-01 | East | SQS | Budget
5 | 2021-04-01 | East | SQS | Forecast | 0
6 | 2021-04-01 | East | SQS | Actual | 0
6 | 2021-04-01 | Central | SQS | Budget
6 | 2021-04-01 | Central | SQS | Forecast | 0
5 | 2021-04-01 | Central | SQS | Actual | 0
6 | 2021-05-01 | CMO West 1 | Terra Firma | Budget
6 | 2021-05-01 | CMO West 1 | Terra Firma | Forecast | 0
6 | 2021-05-01 | CMO West 1 | Terra Firma | Actual | 0
6 | 2021-05-01 | CMO West 1 | KLT | Budget
6 | 2021-05-01 | CMO West 1 | KLT | Forecast | 0
6 | 2021-05-01 | CMO West 1 | KLT | Actual | 0
6 | 2021-05-01 | CMO West 1 | Forefront | Budget
6 | 2021-05-01 | CMO West 1 | Forefront | Forecast | 0
6 | 2021-05-01 | CMO West 1 | Forefront | Actual | 0
6 | 2021-05-01 | CMO West 1 | DPF | Budget
6 | 2021-05-01 | CMO West 1 | DPF | Forecast | 0
6 | 2021-05-01 | CMO West 1 | DPF | Actual | 0
6 | 2021-05-01 | CMO West 1 | OMJ | Budget
6 | 2021-05-01 | CMO West 1 | OMJ | Forecast | 0
6 | 2021-05-01 | CMO West 1 | OMJ | Actual | 0
6 | 2021-05-01 | CMO West 1 | DHB Utilities | Budget
6 | 2021-05-01 | CMO West 1 | DHB Utilities | Forecast | 0
6 | 2021-05-01 | CMO West 1 | DHB Utilities | Actual | 0
6 | 2021-05-01 | CMO West 1 | JDT | Budget
6 | 2021-05-01 | CMO West 1 | JDT | Forecast | 0
6 | 2021-05-01 | CMO West 1 | JDT | Actual | 0
6 | 2021-05-01 | CMO West 1 | MURRAY | Budget
6 | 2021-05-01 | CMO West 1 | MURRAY | Forecast | 0
6 | 2021-05-01 | CMO West 1 | MURRAY | Actual | 0
6 | 2021-05-01 | CMO West 2 | Terra Firma | Budget
6 | 2021-05-01 | CMO West 2 | Terra Firma | Forecast | 0
6 | 2021-05-01 | CMO West 2 | Terra Firma | Actual | 0
6 | 2021-05-01 | CMO West 2 | KLT | Budget
6 | 2021-05-01 | CMO West 2 | KLT | Forecast | 0
6 | 2021-05-01 | CMO West 2 | KLT | Actual | 0
6 | 2021-05-01 | CMO West 2 | Forefront | Budget
6 | 2021-05-01 | CMO West 2 | Forefront | Forecast | 0
6 | 2021-05-01 | CMO West 2 | Forefront | Actual | 0
6 | 2021-05-01 | CMO West 2 | DPF | Budget
6 | 2021-05-01 | CMO West 2 | DPF | Forecast | 0
6 | 2021-05-01 | CMO West 2 | DPF | Actual | 0
6 | 2021-05-01 | CMO West 2 | OMJ | Budget
6 | 2021-05-01 | CMO West 2 | OMJ | Forecast | 0
6 | 2021-05-01 | CMO West 2 | OMJ | Actual | 0
6 | 2021-05-01 | CMO West 2 | DHB Utilities | Budget
6 | 2021-05-01 | CMO West 2 | DHB Utilities | Forecast | 0
6 | 2021-05-01 | CMO West 2 | DHB Utilities | Actual | 0
6 | 2021-05-01 | CMO West 2 | JDT | Budget
6 | 2021-05-01 | CMO West 2 | JDT | Forecast | 0
6 | 2021-05-01 | CMO West 2 | JDT | Actual | 0
6 | 2021-05-01 | CMO West 2 | MURRAY | Budget
6 | 2021-05-01 | CMO West 2 | MURRAY | Forecast | 0
6 | 2021-05-01 | CMO West 2 | MURRAY | Actual | 0
6 | 2021-05-01 | CMO East 1 | Terra Firma | Budget
6 | 2021-05-01 | CMO East 1 | Terra Firma | Forecast | 0
6 | 2021-05-01 | CMO East 1 | Terra Firma | Actual | 0
6 | 2021-05-01 | CMO East 1 | KLT | Budget
6 | 2021-05-01 | CMO East 1 | KLT | Forecast | 0
6 | 2021-05-01 | CMO East 1 | KLT | Actual | 0
6 | 2021-05-01 | CMO East 1 | Forefront | Budget
6 | 2021-05-01 | CMO East 1 | Forefront | Forecast | 0
6 | 2021-05-01 | CMO East 1 | Forefront | Actual | 0
6 | 2021-05-01 | CMO East 1 | DPF | Budget
6 | 2021-05-01 | CMO East 1 | DPF | Forecast | 0
6 | 2021-05-01 | CMO East 1 | DPF | Actual | 0
6 | 2021-05-01 | CMO East 1 | OMJ | Budget
6 | 2021-05-01 | CMO East 1 | OMJ | Forecast | 0
6 | 2021-05-01 | CMO East 1 | OMJ | Actual | 0
6 | 2021-05-01 | CMO East 1 | DHB Utilities | Budget
6 | 2021-05-01 | CMO East 1 | DHB Utilities | Forecast | 0
6 | 2021-05-01 | CMO East 1 | DHB Utilities | Actual | 0
6 | 2021-05-01 | CMO East 1 | JDT | Budget
6 | 2021-05-01 | CMO East 1 | JDT | Forecast | 0
6 | 2021-05-01 | CMO East 1 | JDT | Actual | 0
6 | 2021-05-01 | CMO East 1 | MURRAY | Budget
6 | 2021-05-01 | CMO East 1 | MURRAY | Forecast | 0
6 | 2021-05-01 | CMO East 1 | MURRAY | Actual | 0
6 | 2021-05-01 | CMO East 2 | Terra Firma | Budget
6 | 2021-05-01 | CMO East 2 | Terra Firma | Forecast | 0
6 | 2021-05-01 | CMO East 2 | Terra Firma | Actual | 0
6 | 2021-05-01 | CMO East 2 | KLT | Budget
6 | 2021-05-01 | CMO East 2 | KLT | Forecast | 0
6 | 2021-05-01 | CMO East 2 | KLT | Actual | 0
6 | 2021-05-01 | CMO East 2 | Forefront | Budget
6 | 2021-05-01 | CMO East 2 | Forefront | Forecast | 0
6 | 2021-05-01 | CMO East 2 | Forefront | Actual | 0
6 | 2021-05-01 | CMO East 2 | DPF | Budget
6 | 2021-05-01 | CMO East 2 | DPF | Forecast | 0
6 | 2021-05-01 | CMO East 2 | DPF | Actual | 0
6 | 2021-05-01 | CMO East 2 | OMJ | Budget
6 | 2021-05-01 | CMO East 2 | OMJ | Forecast | 0
6 | 2021-05-01 | CMO East 2 | OMJ | Actual | 0
6 | 2021-05-01 | CMO East 2 | DHB Utilities | Budget
6 | 2021-05-01 | CMO East 2 | DHB Utilities | Forecast | 0
6 | 2021-05-01 | CMO East 2 | DHB Utilities | Actual | 0
6 | 2021-05-01 | CMO East 2 | JDT | Budget
6 | 2021-05-01 | CMO East 2 | JDT | Forecast | 0
6 | 2021-05-01 | CMO East 2 | JDT | Actual | 0
6 | 2021-05-01 | CMO East 2 | MURRAY | Budget
6 | 2021-05-01 | CMO East 2 | MURRAY | Forecast | 0
6 | 2021-05-01 | CMO East 2 | MURRAY | Actual | 0
6 | 2021-05-01 | West | Terra Firma | Budget
6 | 2021-05-01 | West | Terra Firma | Forecast | 0
6 | 2021-05-01 | West | Terra Firma | Actual | 0
6 | 2021-05-01 | West | KLT | Budget
6 | 2021-05-01 | West | KLT | Forecast | 0
6 | 2021-05-01 | West | KLT | Actual | 0
6 | 2021-05-01 | West | Forefront | Budget
6 | 2021-05-01 | West | Forefront | Forecast | 0
6 | 2021-05-01 | West | Forefront | Actual | 0
6 | 2021-05-01 | West | DPF | Budget
6 | 2021-05-01 | West | DPF | Forecast | 0
6 | 2021-05-01 | West | DPF | Actual | 0
6 | 2021-05-01 | West | OMJ | Budget
6 | 2021-05-01 | West | OMJ | Forecast | 0
6 | 2021-05-01 | West | OMJ | Actual | 0
6 | 2021-05-01 | West | DHB Utilities | Budget
6 | 2021-05-01 | West | DHB Utilities | Forecast | 0
6 | 2021-05-01 | West | DHB Utilities | Actual | 0
6 | 2021-05-01 | West | JDT | Budget
6 | 2021-05-01 | West | JDT | Forecast | 0
6 | 2021-05-01 | West | JDT | Actual | 0
6 | 2021-05-01 | West | MURRAY | Budget
6 | 2021-05-01 | West | MURRAY | Forecast | 0
6 | 2021-05-01 | West | MURRAY | Actual | 0
6 | 2021-05-01 | East | Terra Firma | Budget
6 | 2021-05-01 | East | Terra Firma | Forecast | 0
6 | 2021-05-01 | East | Terra Firma | Actual | 0
6 | 2021-05-01 | East | KLT | Budget
6 | 2021-05-01 | East | KLT | Forecast | 0
6 | 2021-05-01 | East | KLT | Actual | 0
6 | 2021-05-01 | East | Forefront | Budget
6 | 2021-05-01 | East | Forefront | Forecast | 0
6 | 2021-05-01 | East | Forefront | Actual | 0
6 | 2021-05-01 | East | DPF | Budget
6 | 2021-05-01 | East | DPF | Forecast | 0
6 | 2021-05-01 | East | DPF | Actual | 0
6 | 2021-05-01 | East | OMJ | Budget
6 | 2021-05-01 | East | OMJ | Forecast | 0
6 | 2021-05-01 | East | OMJ | Actual | 0
6 | 2021-05-01 | East | DHB Utilities | Budget
6 | 2021-05-01 | East | DHB Utilities | Forecast | 0
6 | 2021-05-01 | East | DHB Utilities | Actual | 0
6 | 2021-05-01 | East | JDT | Budget
6 | 2021-05-01 | East | JDT | Forecast | 0
6 | 2021-05-01 | East | JDT | Actual | 0
6 | 2021-05-01 | East | MURRAY | Budget
6 | 2021-05-01 | East | MURRAY | Forecast | 0
6 | 2021-05-01 | East | MURRAY | Actual | 0
6 | 2021-05-01 | Central | Terra Firma | Budget
6 | 2021-05-01 | Central | Terra Firma | Forecast | 0
6 | 2021-05-01 | Central | Terra Firma | Actual | 0
6 | 2021-05-01 | Central | KLT | Budget
6 | 2021-05-01 | Central | KLT | Forecast | 0
6 | 2021-05-01 | Central | KLT | Actual | 0
6 | 2021-05-01 | Central | Forefront | Budget
6 | 2021-05-01 | Central | Forefront | Forecast | 0
6 | 2021-05-01 | Central | Forefront | Actual | 0
6 | 2021-05-01 | Central | DPF | Budget
6 | 2021-05-01 | Central | DPF | Forecast | 0
6 | 2021-05-01 | Central | DPF | Actual | 0
6 | 2021-05-01 | Central | OMJ | Budget
6 | 2021-05-01 | Central | OMJ | Forecast | 0
6 | 2021-05-01 | Central | OMJ | Actual | 0
6 | 2021-05-01 | Central | DHB Utilities | Budget
6 | 2021-05-01 | Central | DHB Utilities | Forecast | 0
6 | 2021-05-01 | Central | DHB Utilities | Actual | 0
6 | 2021-05-01 | Central | JDT | Budget
6 | 2021-05-01 | Central | JDT | Forecast | 0
6 | 2021-05-01 | Central | JDT | Actual | 0
6 | 2021-05-01 | Central | MURRAY | Budget
6 | 2021-05-01 | Central | MURRAY | Forecast | 0
6 | 2021-05-01 | Central | MURRAY | Actual | 0
6 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Budget
6 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Budget
6 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Budget
6 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Budget
6 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | West | DIRECT MOLE | Budget
6 | 2021-05-01 | West | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | West | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | East | DIRECT MOLE | Budget
6 | 2021-05-01 | East | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | East | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | Central | DIRECT MOLE | Budget
6 | 2021-05-01 | Central | DIRECT MOLE | Forecast | 0
6 | 2021-05-01 | Central | DIRECT MOLE | Actual | 0
6 | 2021-05-01 | CMO West 1 | SQS | Budget
6 | 2021-05-01 | CMO West 1 | SQS | Forecast | 0
6 | 2021-05-01 | CMO West 1 | SQS | Actual | 0
6 | 2021-05-01 | CMO West 2 | SQS | Budget
6 | 2021-05-01 | CMO West 2 | SQS | Forecast | 0
6 | 2021-05-01 | CMO West 2 | SQS | Actual | 0
6 | 2021-05-01 | CMO East 1 | SQS | Budget
6 | 2021-05-01 | CMO East 1 | SQS | Forecast | 0
6 | 2021-05-01 | CMO East 1 | SQS | Actual | 0
6 | 2021-05-01 | CMO East 2 | SQS | Budget
6 | 2021-05-01 | CMO East 2 | SQS | Forecast | 0
6 | 2021-05-01 | CMO East 2 | SQS | Actual | 0
6 | 2021-05-01 | West | SQS | Budget
6 | 2021-05-01 | West | SQS | Forecast | 0
6 | 2021-05-01 | West | SQS | Actual | 0
6 | 2021-05-01 | East | SQS | Budget
6 | 2021-05-01 | East | SQS | Forecast | 0
7 | 2021-05-01 | East | SQS | Actual | 0
7 | 2021-05-01 | Central | SQS | Budget
7 | 2021-05-01 | Central | SQS | Forecast | 0
6 | 2021-05-01 | Central | SQS | Actual | 0
7 | 2021-05-01 | CMO West 1 | Terra Firma | Budget
7 | 2021-05-01 | CMO West 1 | Terra Firma | Forecast | 0
7 | 2021-05-01 | CMO West 1 | Terra Firma | Actual | 0
7 | 2021-05-01 | CMO West 1 | KLT | Budget
7 | 2021-05-01 | CMO West 1 | KLT | Forecast | 0
7 | 2021-05-01 | CMO West 1 | KLT | Actual | 0
7 | 2021-05-01 | CMO West 1 | Forefront | Budget
7 | 2021-05-01 | CMO West 1 | Forefront | Forecast | 0
7 | 2021-05-01 | CMO West 1 | Forefront | Actual | 0
7 | 2021-05-01 | CMO West 1 | DPF | Budget
7 | 2021-05-01 | CMO West 1 | DPF | Forecast | 0
7 | 2021-05-01 | CMO West 1 | DPF | Actual | 0
7 | 2021-05-01 | CMO West 1 | OMJ | Budget
7 | 2021-05-01 | CMO West 1 | OMJ | Forecast | 0
7 | 2021-05-01 | CMO West 1 | OMJ | Actual | 0
7 | 2021-05-01 | CMO West 1 | DHB Utilities | Budget
7 | 2021-05-01 | CMO West 1 | DHB Utilities | Forecast | 0
7 | 2021-05-01 | CMO West 1 | DHB Utilities | Actual | 0
7 | 2021-05-01 | CMO West 1 | JDT | Budget
7 | 2021-05-01 | CMO West 1 | JDT | Forecast | 0
7 | 2021-05-01 | CMO West 1 | JDT | Actual | 0
7 | 2021-05-01 | CMO West 1 | MURRAY | Budget
7 | 2021-05-01 | CMO West 1 | MURRAY | Forecast | 0
7 | 2021-05-01 | CMO West 1 | MURRAY | Actual | 0
7 | 2021-05-01 | CMO West 2 | Terra Firma | Budget
7 | 2021-05-01 | CMO West 2 | Terra Firma | Forecast | 0
7 | 2021-05-01 | CMO West 2 | Terra Firma | Actual | 0
7 | 2021-05-01 | CMO West 2 | KLT | Budget
7 | 2021-05-01 | CMO West 2 | KLT | Forecast | 0
7 | 2021-05-01 | CMO West 2 | KLT | Actual | 0
7 | 2021-05-01 | CMO West 2 | Forefront | Budget
7 | 2021-05-01 | CMO West 2 | Forefront | Forecast | 0
7 | 2021-05-01 | CMO West 2 | Forefront | Actual | 0
7 | 2021-05-01 | CMO West 2 | DPF | Budget
7 | 2021-05-01 | CMO West 2 | DPF | Forecast | 0
7 | 2021-05-01 | CMO West 2 | DPF | Actual | 0
7 | 2021-05-01 | CMO West 2 | OMJ | Budget
7 | 2021-05-01 | CMO West 2 | OMJ | Forecast | 0
7 | 2021-05-01 | CMO West 2 | OMJ | Actual | 0
7 | 2021-05-01 | CMO West 2 | DHB Utilities | Budget
7 | 2021-05-01 | CMO West 2 | DHB Utilities | Forecast | 0
7 | 2021-05-01 | CMO West 2 | DHB Utilities | Actual | 0
7 | 2021-05-01 | CMO West 2 | JDT | Budget
7 | 2021-05-01 | CMO West 2 | JDT | Forecast | 0
7 | 2021-05-01 | CMO West 2 | JDT | Actual | 0
7 | 2021-05-01 | CMO West 2 | MURRAY | Budget
7 | 2021-05-01 | CMO West 2 | MURRAY | Forecast | 0
7 | 2021-05-01 | CMO West 2 | MURRAY | Actual | 0
7 | 2021-05-01 | CMO East 1 | Terra Firma | Budget
7 | 2021-05-01 | CMO East 1 | Terra Firma | Forecast | 0
7 | 2021-05-01 | CMO East 1 | Terra Firma | Actual | 0
7 | 2021-05-01 | CMO East 1 | KLT | Budget
7 | 2021-05-01 | CMO East 1 | KLT | Forecast | 0
7 | 2021-05-01 | CMO East 1 | KLT | Actual | 0
7 | 2021-05-01 | CMO East 1 | Forefront | Budget
7 | 2021-05-01 | CMO East 1 | Forefront | Forecast | 0
7 | 2021-05-01 | CMO East 1 | Forefront | Actual | 0
7 | 2021-05-01 | CMO East 1 | DPF | Budget
7 | 2021-05-01 | CMO East 1 | DPF | Forecast | 0
7 | 2021-05-01 | CMO East 1 | DPF | Actual | 0
7 | 2021-05-01 | CMO East 1 | OMJ | Budget
7 | 2021-05-01 | CMO East 1 | OMJ | Forecast | 0
7 | 2021-05-01 | CMO East 1 | OMJ | Actual | 0
7 | 2021-05-01 | CMO East 1 | DHB Utilities | Budget
7 | 2021-05-01 | CMO East 1 | DHB Utilities | Forecast | 0
7 | 2021-05-01 | CMO East 1 | DHB Utilities | Actual | 0
7 | 2021-05-01 | CMO East 1 | JDT | Budget
7 | 2021-05-01 | CMO East 1 | JDT | Forecast | 0
7 | 2021-05-01 | CMO East 1 | JDT | Actual | 0
7 | 2021-05-01 | CMO East 1 | MURRAY | Budget
7 | 2021-05-01 | CMO East 1 | MURRAY | Forecast | 0
7 | 2021-05-01 | CMO East 1 | MURRAY | Actual | 0
7 | 2021-05-01 | CMO East 2 | Terra Firma | Budget
7 | 2021-05-01 | CMO East 2 | Terra Firma | Forecast | 0
7 | 2021-05-01 | CMO East 2 | Terra Firma | Actual | 0
7 | 2021-05-01 | CMO East 2 | KLT | Budget
7 | 2021-05-01 | CMO East 2 | KLT | Forecast | 0
7 | 2021-05-01 | CMO East 2 | KLT | Actual | 0
7 | 2021-05-01 | CMO East 2 | Forefront | Budget
7 | 2021-05-01 | CMO East 2 | Forefront | Forecast | 0
7 | 2021-05-01 | CMO East 2 | Forefront | Actual | 0
7 | 2021-05-01 | CMO East 2 | DPF | Budget
7 | 2021-05-01 | CMO East 2 | DPF | Forecast | 0
7 | 2021-05-01 | CMO East 2 | DPF | Actual | 0
7 | 2021-05-01 | CMO East 2 | OMJ | Budget
7 | 2021-05-01 | CMO East 2 | OMJ | Forecast | 0
7 | 2021-05-01 | CMO East 2 | OMJ | Actual | 0
7 | 2021-05-01 | CMO East 2 | DHB Utilities | Budget
7 | 2021-05-01 | CMO East 2 | DHB Utilities | Forecast | 0
7 | 2021-05-01 | CMO East 2 | DHB Utilities | Actual | 0
7 | 2021-05-01 | CMO East 2 | JDT | Budget
7 | 2021-05-01 | CMO East 2 | JDT | Forecast | 0
7 | 2021-05-01 | CMO East 2 | JDT | Actual | 0
7 | 2021-05-01 | CMO East 2 | MURRAY | Budget
7 | 2021-05-01 | CMO East 2 | MURRAY | Forecast | 0
7 | 2021-05-01 | CMO East 2 | MURRAY | Actual | 0
7 | 2021-05-01 | West | Terra Firma | Budget
7 | 2021-05-01 | West | Terra Firma | Forecast | 0
7 | 2021-05-01 | West | Terra Firma | Actual | 0
7 | 2021-05-01 | West | KLT | Budget
7 | 2021-05-01 | West | KLT | Forecast | 0
7 | 2021-05-01 | West | KLT | Actual | 0
7 | 2021-05-01 | West | Forefront | Budget
7 | 2021-05-01 | West | Forefront | Forecast | 0
7 | 2021-05-01 | West | Forefront | Actual | 0
7 | 2021-05-01 | West | DPF | Budget
7 | 2021-05-01 | West | DPF | Forecast | 0
7 | 2021-05-01 | West | DPF | Actual | 0
7 | 2021-05-01 | West | OMJ | Budget
7 | 2021-05-01 | West | OMJ | Forecast | 0
7 | 2021-05-01 | West | OMJ | Actual | 0
7 | 2021-05-01 | West | DHB Utilities | Budget
7 | 2021-05-01 | West | DHB Utilities | Forecast | 0
7 | 2021-05-01 | West | DHB Utilities | Actual | 0
7 | 2021-05-01 | West | JDT | Budget
7 | 2021-05-01 | West | JDT | Forecast | 0
7 | 2021-05-01 | West | JDT | Actual | 0
7 | 2021-05-01 | West | MURRAY | Budget
7 | 2021-05-01 | West | MURRAY | Forecast | 0
7 | 2021-05-01 | West | MURRAY | Actual | 0
7 | 2021-05-01 | East | Terra Firma | Budget
7 | 2021-05-01 | East | Terra Firma | Forecast | 0
7 | 2021-05-01 | East | Terra Firma | Actual | 0
7 | 2021-05-01 | East | KLT | Budget
7 | 2021-05-01 | East | KLT | Forecast | 0
7 | 2021-05-01 | East | KLT | Actual | 0
7 | 2021-05-01 | East | Forefront | Budget
7 | 2021-05-01 | East | Forefront | Forecast | 0
7 | 2021-05-01 | East | Forefront | Actual | 0
7 | 2021-05-01 | East | DPF | Budget
7 | 2021-05-01 | East | DPF | Forecast | 0
7 | 2021-05-01 | East | DPF | Actual | 0
7 | 2021-05-01 | East | OMJ | Budget
7 | 2021-05-01 | East | OMJ | Forecast | 0
7 | 2021-05-01 | East | OMJ | Actual | 0
7 | 2021-05-01 | East | DHB Utilities | Budget
7 | 2021-05-01 | East | DHB Utilities | Forecast | 0
7 | 2021-05-01 | East | DHB Utilities | Actual | 0
7 | 2021-05-01 | East | JDT | Budget
7 | 2021-05-01 | East | JDT | Forecast | 0
7 | 2021-05-01 | East | JDT | Actual | 0
7 | 2021-05-01 | East | MURRAY | Budget
7 | 2021-05-01 | East | MURRAY | Forecast | 0
7 | 2021-05-01 | East | MURRAY | Actual | 0
7 | 2021-05-01 | Central | Terra Firma | Budget
7 | 2021-05-01 | Central | Terra Firma | Forecast | 0
7 | 2021-05-01 | Central | Terra Firma | Actual | 0
7 | 2021-05-01 | Central | KLT | Budget
7 | 2021-05-01 | Central | KLT | Forecast | 0
7 | 2021-05-01 | Central | KLT | Actual | 0
7 | 2021-05-01 | Central | Forefront | Budget
7 | 2021-05-01 | Central | Forefront | Forecast | 0
7 | 2021-05-01 | Central | Forefront | Actual | 0
7 | 2021-05-01 | Central | DPF | Budget
7 | 2021-05-01 | Central | DPF | Forecast | 0
7 | 2021-05-01 | Central | DPF | Actual | 0
7 | 2021-05-01 | Central | OMJ | Budget
7 | 2021-05-01 | Central | OMJ | Forecast | 0
7 | 2021-05-01 | Central | OMJ | Actual | 0
7 | 2021-05-01 | Central | DHB Utilities | Budget
7 | 2021-05-01 | Central | DHB Utilities | Forecast | 0
7 | 2021-05-01 | Central | DHB Utilities | Actual | 0
7 | 2021-05-01 | Central | JDT | Budget
7 | 2021-05-01 | Central | JDT | Forecast | 0
7 | 2021-05-01 | Central | JDT | Actual | 0
7 | 2021-05-01 | Central | MURRAY | Budget
7 | 2021-05-01 | Central | MURRAY | Forecast | 0
7 | 2021-05-01 | Central | MURRAY | Actual | 0
7 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Budget
7 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Budget
7 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Budget
7 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Budget
7 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | West | DIRECT MOLE | Budget
7 | 2021-05-01 | West | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | West | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | East | DIRECT MOLE | Budget
7 | 2021-05-01 | East | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | East | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | Central | DIRECT MOLE | Budget
7 | 2021-05-01 | Central | DIRECT MOLE | Forecast | 0
7 | 2021-05-01 | Central | DIRECT MOLE | Actual | 0
7 | 2021-05-01 | CMO West 1 | SQS | Budget
7 | 2021-05-01 | CMO West 1 | SQS | Forecast | 0
7 | 2021-05-01 | CMO West 1 | SQS | Actual | 0
7 | 2021-05-01 | CMO West 2 | SQS | Budget
7 | 2021-05-01 | CMO West 2 | SQS | Forecast | 0
7 | 2021-05-01 | CMO West 2 | SQS | Actual | 0
7 | 2021-05-01 | CMO East 1 | SQS | Budget
7 | 2021-05-01 | CMO East 1 | SQS | Forecast | 0
7 | 2021-05-01 | CMO East 1 | SQS | Actual | 0
7 | 2021-05-01 | CMO East 2 | SQS | Budget
7 | 2021-05-01 | CMO East 2 | SQS | Forecast | 0
7 | 2021-05-01 | CMO East 2 | SQS | Actual | 0
7 | 2021-05-01 | West | SQS | Budget
7 | 2021-05-01 | West | SQS | Forecast | 0
7 | 2021-05-01 | West | SQS | Actual | 0
7 | 2021-05-01 | East | SQS | Budget
7 | 2021-05-01 | East | SQS | Forecast | 0
8 | 2021-05-01 | East | SQS | Actual | 0
8 | 2021-05-01 | Central | SQS | Budget
8 | 2021-05-01 | Central | SQS | Forecast | 0
7 | 2021-05-01 | Central | SQS | Actual | 0
8 | 2021-05-01 | CMO West 1 | Terra Firma | Budget
8 | 2021-05-01 | CMO West 1 | Terra Firma | Forecast | 0
8 | 2021-05-01 | CMO West 1 | Terra Firma | Actual | 0
8 | 2021-05-01 | CMO West 1 | KLT | Budget
8 | 2021-05-01 | CMO West 1 | KLT | Forecast | 0
8 | 2021-05-01 | CMO West 1 | KLT | Actual | 0
8 | 2021-05-01 | CMO West 1 | Forefront | Budget
8 | 2021-05-01 | CMO West 1 | Forefront | Forecast | 0
8 | 2021-05-01 | CMO West 1 | Forefront | Actual | 0
8 | 2021-05-01 | CMO West 1 | DPF | Budget
8 | 2021-05-01 | CMO West 1 | DPF | Forecast | 0
8 | 2021-05-01 | CMO West 1 | DPF | Actual | 0
8 | 2021-05-01 | CMO West 1 | OMJ | Budget
8 | 2021-05-01 | CMO West 1 | OMJ | Forecast | 0
8 | 2021-05-01 | CMO West 1 | OMJ | Actual | 0
8 | 2021-05-01 | CMO West 1 | DHB Utilities | Budget
8 | 2021-05-01 | CMO West 1 | DHB Utilities | Forecast | 0
8 | 2021-05-01 | CMO West 1 | DHB Utilities | Actual | 0
8 | 2021-05-01 | CMO West 1 | JDT | Budget
8 | 2021-05-01 | CMO West 1 | JDT | Forecast | 0
8 | 2021-05-01 | CMO West 1 | JDT | Actual | 0
8 | 2021-05-01 | CMO West 1 | MURRAY | Budget
8 | 2021-05-01 | CMO West 1 | MURRAY | Forecast | 0
8 | 2021-05-01 | CMO West 1 | MURRAY | Actual | 0
8 | 2021-05-01 | CMO West 2 | Terra Firma | Budget
8 | 2021-05-01 | CMO West 2 | Terra Firma | Forecast | 0
8 | 2021-05-01 | CMO West 2 | Terra Firma | Actual | 0
8 | 2021-05-01 | CMO West 2 | KLT | Budget
8 | 2021-05-01 | CMO West 2 | KLT | Forecast | 0
8 | 2021-05-01 | CMO West 2 | KLT | Actual | 0
8 | 2021-05-01 | CMO West 2 | Forefront | Budget
8 | 2021-05-01 | CMO West 2 | Forefront | Forecast | 0
8 | 2021-05-01 | CMO West 2 | Forefront | Actual | 0
8 | 2021-05-01 | CMO West 2 | DPF | Budget
8 | 2021-05-01 | CMO West 2 | DPF | Forecast | 0
8 | 2021-05-01 | CMO West 2 | DPF | Actual | 0
8 | 2021-05-01 | CMO West 2 | OMJ | Budget
8 | 2021-05-01 | CMO West 2 | OMJ | Forecast | 0
8 | 2021-05-01 | CMO West 2 | OMJ | Actual | 0
8 | 2021-05-01 | CMO West 2 | DHB Utilities | Budget
8 | 2021-05-01 | CMO West 2 | DHB Utilities | Forecast | 0
8 | 2021-05-01 | CMO West 2 | DHB Utilities | Actual | 0
8 | 2021-05-01 | CMO West 2 | JDT | Budget
8 | 2021-05-01 | CMO West 2 | JDT | Forecast | 0
8 | 2021-05-01 | CMO West 2 | JDT | Actual | 0
8 | 2021-05-01 | CMO West 2 | MURRAY | Budget
8 | 2021-05-01 | CMO West 2 | MURRAY | Forecast | 0
8 | 2021-05-01 | CMO West 2 | MURRAY | Actual | 0
8 | 2021-05-01 | CMO East 1 | Terra Firma | Budget
8 | 2021-05-01 | CMO East 1 | Terra Firma | Forecast | 0
8 | 2021-05-01 | CMO East 1 | Terra Firma | Actual | 0
8 | 2021-05-01 | CMO East 1 | KLT | Budget
8 | 2021-05-01 | CMO East 1 | KLT | Forecast | 0
8 | 2021-05-01 | CMO East 1 | KLT | Actual | 0
8 | 2021-05-01 | CMO East 1 | Forefront | Budget
8 | 2021-05-01 | CMO East 1 | Forefront | Forecast | 0
8 | 2021-05-01 | CMO East 1 | Forefront | Actual | 0
8 | 2021-05-01 | CMO East 1 | DPF | Budget
8 | 2021-05-01 | CMO East 1 | DPF | Forecast | 0
8 | 2021-05-01 | CMO East 1 | DPF | Actual | 0
8 | 2021-05-01 | CMO East 1 | OMJ | Budget
8 | 2021-05-01 | CMO East 1 | OMJ | Forecast | 0
8 | 2021-05-01 | CMO East 1 | OMJ | Actual | 0
8 | 2021-05-01 | CMO East 1 | DHB Utilities | Budget
8 | 2021-05-01 | CMO East 1 | DHB Utilities | Forecast | 0
8 | 2021-05-01 | CMO East 1 | DHB Utilities | Actual | 0
8 | 2021-05-01 | CMO East 1 | JDT | Budget
8 | 2021-05-01 | CMO East 1 | JDT | Forecast | 0
8 | 2021-05-01 | CMO East 1 | JDT | Actual | 0
8 | 2021-05-01 | CMO East 1 | MURRAY | Budget
8 | 2021-05-01 | CMO East 1 | MURRAY | Forecast | 0
8 | 2021-05-01 | CMO East 1 | MURRAY | Actual | 0
8 | 2021-05-01 | CMO East 2 | Terra Firma | Budget
8 | 2021-05-01 | CMO East 2 | Terra Firma | Forecast | 0
8 | 2021-05-01 | CMO East 2 | Terra Firma | Actual | 0
8 | 2021-05-01 | CMO East 2 | KLT | Budget
8 | 2021-05-01 | CMO East 2 | KLT | Forecast | 0
8 | 2021-05-01 | CMO East 2 | KLT | Actual | 0
8 | 2021-05-01 | CMO East 2 | Forefront | Budget
8 | 2021-05-01 | CMO East 2 | Forefront | Forecast | 0
8 | 2021-05-01 | CMO East 2 | Forefront | Actual | 0
8 | 2021-05-01 | CMO East 2 | DPF | Budget
8 | 2021-05-01 | CMO East 2 | DPF | Forecast | 0
8 | 2021-05-01 | CMO East 2 | DPF | Actual | 0
8 | 2021-05-01 | CMO East 2 | OMJ | Budget
8 | 2021-05-01 | CMO East 2 | OMJ | Forecast | 0
8 | 2021-05-01 | CMO East 2 | OMJ | Actual | 0
8 | 2021-05-01 | CMO East 2 | DHB Utilities | Budget
8 | 2021-05-01 | CMO East 2 | DHB Utilities | Forecast | 0
8 | 2021-05-01 | CMO East 2 | DHB Utilities | Actual | 0
8 | 2021-05-01 | CMO East 2 | JDT | Budget
8 | 2021-05-01 | CMO East 2 | JDT | Forecast | 0
8 | 2021-05-01 | CMO East 2 | JDT | Actual | 0
8 | 2021-05-01 | CMO East 2 | MURRAY | Budget
8 | 2021-05-01 | CMO East 2 | MURRAY | Forecast | 0
8 | 2021-05-01 | CMO East 2 | MURRAY | Actual | 0
8 | 2021-05-01 | West | Terra Firma | Budget
8 | 2021-05-01 | West | Terra Firma | Forecast | 0
8 | 2021-05-01 | West | Terra Firma | Actual | 0
8 | 2021-05-01 | West | KLT | Budget
8 | 2021-05-01 | West | KLT | Forecast | 0
8 | 2021-05-01 | West | KLT | Actual | 0
8 | 2021-05-01 | West | Forefront | Budget
8 | 2021-05-01 | West | Forefront | Forecast | 0
8 | 2021-05-01 | West | Forefront | Actual | 0
8 | 2021-05-01 | West | DPF | Budget
8 | 2021-05-01 | West | DPF | Forecast | 0
8 | 2021-05-01 | West | DPF | Actual | 0
8 | 2021-05-01 | West | OMJ | Budget
8 | 2021-05-01 | West | OMJ | Forecast | 0
8 | 2021-05-01 | West | OMJ | Actual | 0
8 | 2021-05-01 | West | DHB Utilities | Budget
8 | 2021-05-01 | West | DHB Utilities | Forecast | 0
8 | 2021-05-01 | West | DHB Utilities | Actual | 0
8 | 2021-05-01 | West | JDT | Budget
8 | 2021-05-01 | West | JDT | Forecast | 0
8 | 2021-05-01 | West | JDT | Actual | 0
8 | 2021-05-01 | West | MURRAY | Budget
8 | 2021-05-01 | West | MURRAY | Forecast | 0
8 | 2021-05-01 | West | MURRAY | Actual | 0
8 | 2021-05-01 | East | Terra Firma | Budget
8 | 2021-05-01 | East | Terra Firma | Forecast | 0
8 | 2021-05-01 | East | Terra Firma | Actual | 0
8 | 2021-05-01 | East | KLT | Budget
8 | 2021-05-01 | East | KLT | Forecast | 0
8 | 2021-05-01 | East | KLT | Actual | 0
8 | 2021-05-01 | East | Forefront | Budget
8 | 2021-05-01 | East | Forefront | Forecast | 0
8 | 2021-05-01 | East | Forefront | Actual | 0
8 | 2021-05-01 | East | DPF | Budget
8 | 2021-05-01 | East | DPF | Forecast | 0
8 | 2021-05-01 | East | DPF | Actual | 0
8 | 2021-05-01 | East | OMJ | Budget
8 | 2021-05-01 | East | OMJ | Forecast | 0
8 | 2021-05-01 | East | OMJ | Actual | 0
8 | 2021-05-01 | East | DHB Utilities | Budget
8 | 2021-05-01 | East | DHB Utilities | Forecast | 0
8 | 2021-05-01 | East | DHB Utilities | Actual | 0
8 | 2021-05-01 | East | JDT | Budget
8 | 2021-05-01 | East | JDT | Forecast | 0
8 | 2021-05-01 | East | JDT | Actual | 0
8 | 2021-05-01 | East | MURRAY | Budget
8 | 2021-05-01 | East | MURRAY | Forecast | 0
8 | 2021-05-01 | East | MURRAY | Actual | 0
8 | 2021-05-01 | Central | Terra Firma | Budget
8 | 2021-05-01 | Central | Terra Firma | Forecast | 0
8 | 2021-05-01 | Central | Terra Firma | Actual | 0
8 | 2021-05-01 | Central | KLT | Budget
8 | 2021-05-01 | Central | KLT | Forecast | 0
8 | 2021-05-01 | Central | KLT | Actual | 0
8 | 2021-05-01 | Central | Forefront | Budget
8 | 2021-05-01 | Central | Forefront | Forecast | 0
8 | 2021-05-01 | Central | Forefront | Actual | 0
8 | 2021-05-01 | Central | DPF | Budget
8 | 2021-05-01 | Central | DPF | Forecast | 0
8 | 2021-05-01 | Central | DPF | Actual | 0
8 | 2021-05-01 | Central | OMJ | Budget
8 | 2021-05-01 | Central | OMJ | Forecast | 0
8 | 2021-05-01 | Central | OMJ | Actual | 0
8 | 2021-05-01 | Central | DHB Utilities | Budget
8 | 2021-05-01 | Central | DHB Utilities | Forecast | 0
8 | 2021-05-01 | Central | DHB Utilities | Actual | 0
8 | 2021-05-01 | Central | JDT | Budget
8 | 2021-05-01 | Central | JDT | Forecast | 0
8 | 2021-05-01 | Central | JDT | Actual | 0
8 | 2021-05-01 | Central | MURRAY | Budget
8 | 2021-05-01 | Central | MURRAY | Forecast | 0
8 | 2021-05-01 | Central | MURRAY | Actual | 0
8 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Budget
8 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Budget
8 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Budget
8 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Budget
8 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | West | DIRECT MOLE | Budget
8 | 2021-05-01 | West | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | West | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | East | DIRECT MOLE | Budget
8 | 2021-05-01 | East | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | East | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | Central | DIRECT MOLE | Budget
8 | 2021-05-01 | Central | DIRECT MOLE | Forecast | 0
8 | 2021-05-01 | Central | DIRECT MOLE | Actual | 0
8 | 2021-05-01 | CMO West 1 | SQS | Budget
8 | 2021-05-01 | CMO West 1 | SQS | Forecast | 0
8 | 2021-05-01 | CMO West 1 | SQS | Actual | 0
8 | 2021-05-01 | CMO West 2 | SQS | Budget
8 | 2021-05-01 | CMO West 2 | SQS | Forecast | 0
8 | 2021-05-01 | CMO West 2 | SQS | Actual | 0
8 | 2021-05-01 | CMO East 1 | SQS | Budget
8 | 2021-05-01 | CMO East 1 | SQS | Forecast | 0
8 | 2021-05-01 | CMO East 1 | SQS | Actual | 0
8 | 2021-05-01 | CMO East 2 | SQS | Budget
8 | 2021-05-01 | CMO East 2 | SQS | Forecast | 0
8 | 2021-05-01 | CMO East 2 | SQS | Actual | 0
8 | 2021-05-01 | West | SQS | Budget
8 | 2021-05-01 | West | SQS | Forecast | 0
8 | 2021-05-01 | West | SQS | Actual | 0
8 | 2021-05-01 | East | SQS | Budget
8 | 2021-05-01 | East | SQS | Forecast | 0
9 | 2021-05-01 | East | SQS | Actual | 0
9 | 2021-05-01 | Central | SQS | Budget
9 | 2021-05-01 | Central | SQS | Forecast | 0
8 | 2021-05-01 | Central | SQS | Actual | 0
9 | 2021-05-01 | CMO West 1 | Terra Firma | Budget
9 | 2021-05-01 | CMO West 1 | Terra Firma | Forecast | 0
9 | 2021-05-01 | CMO West 1 | Terra Firma | Actual | 0
9 | 2021-05-01 | CMO West 1 | KLT | Budget
9 | 2021-05-01 | CMO West 1 | KLT | Forecast | 0
9 | 2021-05-01 | CMO West 1 | KLT | Actual | 0
9 | 2021-05-01 | CMO West 1 | Forefront | Budget
9 | 2021-05-01 | CMO West 1 | Forefront | Forecast | 0
9 | 2021-05-01 | CMO West 1 | Forefront | Actual | 0
9 | 2021-05-01 | CMO West 1 | DPF | Budget
9 | 2021-05-01 | CMO West 1 | DPF | Forecast | 0
9 | 2021-05-01 | CMO West 1 | DPF | Actual | 0
9 | 2021-05-01 | CMO West 1 | OMJ | Budget
9 | 2021-05-01 | CMO West 1 | OMJ | Forecast | 0
9 | 2021-05-01 | CMO West 1 | OMJ | Actual | 0
9 | 2021-05-01 | CMO West 1 | DHB Utilities | Budget
9 | 2021-05-01 | CMO West 1 | DHB Utilities | Forecast | 0
9 | 2021-05-01 | CMO West 1 | DHB Utilities | Actual | 0
9 | 2021-05-01 | CMO West 1 | JDT | Budget
9 | 2021-05-01 | CMO West 1 | JDT | Forecast | 0
9 | 2021-05-01 | CMO West 1 | JDT | Actual | 0
9 | 2021-05-01 | CMO West 1 | MURRAY | Budget
9 | 2021-05-01 | CMO West 1 | MURRAY | Forecast | 0
9 | 2021-05-01 | CMO West 1 | MURRAY | Actual | 0
9 | 2021-05-01 | CMO West 2 | Terra Firma | Budget
9 | 2021-05-01 | CMO West 2 | Terra Firma | Forecast | 0
9 | 2021-05-01 | CMO West 2 | Terra Firma | Actual | 0
9 | 2021-05-01 | CMO West 2 | KLT | Budget
9 | 2021-05-01 | CMO West 2 | KLT | Forecast | 0
9 | 2021-05-01 | CMO West 2 | KLT | Actual | 0
9 | 2021-05-01 | CMO West 2 | Forefront | Budget
9 | 2021-05-01 | CMO West 2 | Forefront | Forecast | 0
9 | 2021-05-01 | CMO West 2 | Forefront | Actual | 0
9 | 2021-05-01 | CMO West 2 | DPF | Budget
9 | 2021-05-01 | CMO West 2 | DPF | Forecast | 0
9 | 2021-05-01 | CMO West 2 | DPF | Actual | 0
9 | 2021-05-01 | CMO West 2 | OMJ | Budget
9 | 2021-05-01 | CMO West 2 | OMJ | Forecast | 0
9 | 2021-05-01 | CMO West 2 | OMJ | Actual | 0
9 | 2021-05-01 | CMO West 2 | DHB Utilities | Budget
9 | 2021-05-01 | CMO West 2 | DHB Utilities | Forecast | 0
9 | 2021-05-01 | CMO West 2 | DHB Utilities | Actual | 0
9 | 2021-05-01 | CMO West 2 | JDT | Budget
9 | 2021-05-01 | CMO West 2 | JDT | Forecast | 0
9 | 2021-05-01 | CMO West 2 | JDT | Actual | 0
9 | 2021-05-01 | CMO West 2 | MURRAY | Budget
9 | 2021-05-01 | CMO West 2 | MURRAY | Forecast | 0
9 | 2021-05-01 | CMO West 2 | MURRAY | Actual | 0
9 | 2021-05-01 | CMO East 1 | Terra Firma | Budget
9 | 2021-05-01 | CMO East 1 | Terra Firma | Forecast | 0
9 | 2021-05-01 | CMO East 1 | Terra Firma | Actual | 0
9 | 2021-05-01 | CMO East 1 | KLT | Budget
9 | 2021-05-01 | CMO East 1 | KLT | Forecast | 0
9 | 2021-05-01 | CMO East 1 | KLT | Actual | 0
9 | 2021-05-01 | CMO East 1 | Forefront | Budget
9 | 2021-05-01 | CMO East 1 | Forefront | Forecast | 0
9 | 2021-05-01 | CMO East 1 | Forefront | Actual | 0
9 | 2021-05-01 | CMO East 1 | DPF | Budget
9 | 2021-05-01 | CMO East 1 | DPF | Forecast | 0
9 | 2021-05-01 | CMO East 1 | DPF | Actual | 0
9 | 2021-05-01 | CMO East 1 | OMJ | Budget
9 | 2021-05-01 | CMO East 1 | OMJ | Forecast | 0
9 | 2021-05-01 | CMO East 1 | OMJ | Actual | 0
9 | 2021-05-01 | CMO East 1 | DHB Utilities | Budget
9 | 2021-05-01 | CMO East 1 | DHB Utilities | Forecast | 0
9 | 2021-05-01 | CMO East 1 | DHB Utilities | Actual | 0
9 | 2021-05-01 | CMO East 1 | JDT | Budget
9 | 2021-05-01 | CMO East 1 | JDT | Forecast | 0
9 | 2021-05-01 | CMO East 1 | JDT | Actual | 0
9 | 2021-05-01 | CMO East 1 | MURRAY | Budget
9 | 2021-05-01 | CMO East 1 | MURRAY | Forecast | 0
9 | 2021-05-01 | CMO East 1 | MURRAY | Actual | 0
9 | 2021-05-01 | CMO East 2 | Terra Firma | Budget
9 | 2021-05-01 | CMO East 2 | Terra Firma | Forecast | 0
9 | 2021-05-01 | CMO East 2 | Terra Firma | Actual | 0
9 | 2021-05-01 | CMO East 2 | KLT | Budget
9 | 2021-05-01 | CMO East 2 | KLT | Forecast | 0
9 | 2021-05-01 | CMO East 2 | KLT | Actual | 0
9 | 2021-05-01 | CMO East 2 | Forefront | Budget
9 | 2021-05-01 | CMO East 2 | Forefront | Forecast | 0
9 | 2021-05-01 | CMO East 2 | Forefront | Actual | 0
9 | 2021-05-01 | CMO East 2 | DPF | Budget
9 | 2021-05-01 | CMO East 2 | DPF | Forecast | 0
9 | 2021-05-01 | CMO East 2 | DPF | Actual | 0
9 | 2021-05-01 | CMO East 2 | OMJ | Budget
9 | 2021-05-01 | CMO East 2 | OMJ | Forecast | 0
9 | 2021-05-01 | CMO East 2 | OMJ | Actual | 0
9 | 2021-05-01 | CMO East 2 | DHB Utilities | Budget
9 | 2021-05-01 | CMO East 2 | DHB Utilities | Forecast | 0
9 | 2021-05-01 | CMO East 2 | DHB Utilities | Actual | 0
9 | 2021-05-01 | CMO East 2 | JDT | Budget
9 | 2021-05-01 | CMO East 2 | JDT | Forecast | 0
9 | 2021-05-01 | CMO East 2 | JDT | Actual | 0
9 | 2021-05-01 | CMO East 2 | MURRAY | Budget
9 | 2021-05-01 | CMO East 2 | MURRAY | Forecast | 0
9 | 2021-05-01 | CMO East 2 | MURRAY | Actual | 0
9 | 2021-05-01 | West | Terra Firma | Budget
9 | 2021-05-01 | West | Terra Firma | Forecast | 0
9 | 2021-05-01 | West | Terra Firma | Actual | 0
9 | 2021-05-01 | West | KLT | Budget
9 | 2021-05-01 | West | KLT | Forecast | 0
9 | 2021-05-01 | West | KLT | Actual | 0
9 | 2021-05-01 | West | Forefront | Budget
9 | 2021-05-01 | West | Forefront | Forecast | 0
9 | 2021-05-01 | West | Forefront | Actual | 0
9 | 2021-05-01 | West | DPF | Budget
9 | 2021-05-01 | West | DPF | Forecast | 0
9 | 2021-05-01 | West | DPF | Actual | 0
9 | 2021-05-01 | West | OMJ | Budget
9 | 2021-05-01 | West | OMJ | Forecast | 0
9 | 2021-05-01 | West | OMJ | Actual | 0
9 | 2021-05-01 | West | DHB Utilities | Budget
9 | 2021-05-01 | West | DHB Utilities | Forecast | 0
9 | 2021-05-01 | West | DHB Utilities | Actual | 0
9 | 2021-05-01 | West | JDT | Budget
9 | 2021-05-01 | West | JDT | Forecast | 0
9 | 2021-05-01 | West | JDT | Actual | 0
9 | 2021-05-01 | West | MURRAY | Budget
9 | 2021-05-01 | West | MURRAY | Forecast | 0
9 | 2021-05-01 | West | MURRAY | Actual | 0
9 | 2021-05-01 | East | Terra Firma | Budget
9 | 2021-05-01 | East | Terra Firma | Forecast | 0
9 | 2021-05-01 | East | Terra Firma | Actual | 0
9 | 2021-05-01 | East | KLT | Budget
9 | 2021-05-01 | East | KLT | Forecast | 0
9 | 2021-05-01 | East | KLT | Actual | 0
9 | 2021-05-01 | East | Forefront | Budget
9 | 2021-05-01 | East | Forefront | Forecast | 0
9 | 2021-05-01 | East | Forefront | Actual | 0
9 | 2021-05-01 | East | DPF | Budget
9 | 2021-05-01 | East | DPF | Forecast | 0
9 | 2021-05-01 | East | DPF | Actual | 0
9 | 2021-05-01 | East | OMJ | Budget
9 | 2021-05-01 | East | OMJ | Forecast | 0
9 | 2021-05-01 | East | OMJ | Actual | 0
9 | 2021-05-01 | East | DHB Utilities | Budget
9 | 2021-05-01 | East | DHB Utilities | Forecast | 0
9 | 2021-05-01 | East | DHB Utilities | Actual | 0
9 | 2021-05-01 | East | JDT | Budget
9 | 2021-05-01 | East | JDT | Forecast | 0
9 | 2021-05-01 | East | JDT | Actual | 0
9 | 2021-05-01 | East | MURRAY | Budget
9 | 2021-05-01 | East | MURRAY | Forecast | 0
9 | 2021-05-01 | East | MURRAY | Actual | 0
9 | 2021-05-01 | Central | Terra Firma | Budget
9 | 2021-05-01 | Central | Terra Firma | Forecast | 0
9 | 2021-05-01 | Central | Terra Firma | Actual | 0
9 | 2021-05-01 | Central | KLT | Budget
9 | 2021-05-01 | Central | KLT | Forecast | 0
9 | 2021-05-01 | Central | KLT | Actual | 0
9 | 2021-05-01 | Central | Forefront | Budget
9 | 2021-05-01 | Central | Forefront | Forecast | 0
9 | 2021-05-01 | Central | Forefront | Actual | 0
9 | 2021-05-01 | Central | DPF | Budget
9 | 2021-05-01 | Central | DPF | Forecast | 0
9 | 2021-05-01 | Central | DPF | Actual | 0
9 | 2021-05-01 | Central | OMJ | Budget
9 | 2021-05-01 | Central | OMJ | Forecast | 0
9 | 2021-05-01 | Central | OMJ | Actual | 0
9 | 2021-05-01 | Central | DHB Utilities | Budget
9 | 2021-05-01 | Central | DHB Utilities | Forecast | 0
9 | 2021-05-01 | Central | DHB Utilities | Actual | 0
9 | 2021-05-01 | Central | JDT | Budget
9 | 2021-05-01 | Central | JDT | Forecast | 0
9 | 2021-05-01 | Central | JDT | Actual | 0
9 | 2021-05-01 | Central | MURRAY | Budget
9 | 2021-05-01 | Central | MURRAY | Forecast | 0
9 | 2021-05-01 | Central | MURRAY | Actual | 0
9 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Budget
9 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | CMO West 1 | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Budget
9 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | CMO West 2 | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Budget
9 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | CMO East 1 | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Budget
9 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | CMO East 2 | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | West | DIRECT MOLE | Budget
9 | 2021-05-01 | West | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | West | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | East | DIRECT MOLE | Budget
9 | 2021-05-01 | East | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | East | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | Central | DIRECT MOLE | Budget
9 | 2021-05-01 | Central | DIRECT MOLE | Forecast | 0
9 | 2021-05-01 | Central | DIRECT MOLE | Actual | 0
9 | 2021-05-01 | CMO West 1 | SQS | Budget
9 | 2021-05-01 | CMO West 1 | SQS | Forecast | 0
9 | 2021-05-01 | CMO West 1 | SQS | Actual | 0
9 | 2021-05-01 | CMO West 2 | SQS | Budget
9 | 2021-05-01 | CMO West 2 | SQS | Forecast | 0
9 | 2021-05-01 | CMO West 2 | SQS | Actual | 0
9 | 2021-05-01 | CMO East 1 | SQS | Budget
9 | 2021-05-01 | CMO East 1 | SQS | Forecast | 0
9 | 2021-05-01 | CMO East 1 | SQS | Actual | 0
9 | 2021-05-01 | CMO East 2 | SQS | Budget
9 | 2021-05-01 | CMO East 2 | SQS | Forecast | 0
9 | 2021-05-01 | CMO East 2 | SQS | Actual | 0
9 | 2021-05-01 | West | SQS | Budget
9 | 2021-05-01 | West | SQS | Forecast | 0
9 | 2021-05-01 | West | SQS | Actual | 0
9 | 2021-05-01 | East | SQS | Budget
9 | 2021-05-01 | East | SQS | Forecast | 0
10 | 2021-05-01 | East | SQS | Actual | 0
10 | 2021-05-01 | Central | SQS | Budget
10 | 2021-05-01 | Central | SQS | Forecast | 0
9 | 2021-05-01 | Central | SQS | Actual | 0
10 | 2021-06-01 | CMO West 1 | Terra Firma | Budget
10 | 2021-06-01 | CMO West 1 | Terra Firma | Forecast | 0
10 | 2021-06-01 | CMO West 1 | Terra Firma | Actual | 0
10 | 2021-06-01 | CMO West 1 | KLT | Budget
10 | 2021-06-01 | CMO West 1 | KLT | Forecast | 0
10 | 2021-06-01 | CMO West 1 | KLT | Actual | 0
10 | 2021-06-01 | CMO West 1 | Forefront | Budget
10 | 2021-06-01 | CMO West 1 | Forefront | Forecast | 0
10 | 2021-06-01 | CMO West 1 | Forefront | Actual | 0
10 | 2021-06-01 | CMO West 1 | DPF | Budget
10 | 2021-06-01 | CMO West 1 | DPF | Forecast | 0
10 | 2021-06-01 | CMO West 1 | DPF | Actual | 0
10 | 2021-06-01 | CMO West 1 | OMJ | Budget
10 | 2021-06-01 | CMO West 1 | OMJ | Forecast | 0
10 | 2021-06-01 | CMO West 1 | OMJ | Actual | 0
10 | 2021-06-01 | CMO West 1 | DHB Utilities | Budget
10 | 2021-06-01 | CMO West 1 | DHB Utilities | Forecast | 0
10 | 2021-06-01 | CMO West 1 | DHB Utilities | Actual | 0
10 | 2021-06-01 | CMO West 1 | JDT | Budget
10 | 2021-06-01 | CMO West 1 | JDT | Forecast | 0
10 | 2021-06-01 | CMO West 1 | JDT | Actual | 0
10 | 2021-06-01 | CMO West 1 | MURRAY | Budget
10 | 2021-06-01 | CMO West 1 | MURRAY | Forecast | 0
10 | 2021-06-01 | CMO West 1 | MURRAY | Actual | 0
10 | 2021-06-01 | CMO West 2 | Terra Firma | Budget
10 | 2021-06-01 | CMO West 2 | Terra Firma | Forecast | 0
10 | 2021-06-01 | CMO West 2 | Terra Firma | Actual | 0
10 | 2021-06-01 | CMO West 2 | KLT | Budget
10 | 2021-06-01 | CMO West 2 | KLT | Forecast | 0
10 | 2021-06-01 | CMO West 2 | KLT | Actual | 0
10 | 2021-06-01 | CMO West 2 | Forefront | Budget
10 | 2021-06-01 | CMO West 2 | Forefront | Forecast | 0
10 | 2021-06-01 | CMO West 2 | Forefront | Actual | 0
10 | 2021-06-01 | CMO West 2 | DPF | Budget
10 | 2021-06-01 | CMO West 2 | DPF | Forecast | 0
10 | 2021-06-01 | CMO West 2 | DPF | Actual | 0
10 | 2021-06-01 | CMO West 2 | OMJ | Budget
10 | 2021-06-01 | CMO West 2 | OMJ | Forecast | 0
10 | 2021-06-01 | CMO West 2 | OMJ | Actual | 0
10 | 2021-06-01 | CMO West 2 | DHB Utilities | Budget
10 | 2021-06-01 | CMO West 2 | DHB Utilities | Forecast | 0
10 | 2021-06-01 | CMO West 2 | DHB Utilities | Actual | 0
10 | 2021-06-01 | CMO West 2 | JDT | Budget
10 | 2021-06-01 | CMO West 2 | JDT | Forecast | 0
10 | 2021-06-01 | CMO West 2 | JDT | Actual | 0
10 | 2021-06-01 | CMO West 2 | MURRAY | Budget
10 | 2021-06-01 | CMO West 2 | MURRAY | Forecast | 0
10 | 2021-06-01 | CMO West 2 | MURRAY | Actual | 0
10 | 2021-06-01 | CMO East 1 | Terra Firma | Budget
10 | 2021-06-01 | CMO East 1 | Terra Firma | Forecast | 0
10 | 2021-06-01 | CMO East 1 | Terra Firma | Actual | 0
10 | 2021-06-01 | CMO East 1 | KLT | Budget
10 | 2021-06-01 | CMO East 1 | KLT | Forecast | 0
10 | 2021-06-01 | CMO East 1 | KLT | Actual | 0
10 | 2021-06-01 | CMO East 1 | Forefront | Budget
10 | 2021-06-01 | CMO East 1 | Forefront | Forecast | 0
10 | 2021-06-01 | CMO East 1 | Forefront | Actual | 0
10 | 2021-06-01 | CMO East 1 | DPF | Budget
10 | 2021-06-01 | CMO East 1 | DPF | Forecast | 0
10 | 2021-06-01 | CMO East 1 | DPF | Actual | 0
10 | 2021-06-01 | CMO East 1 | OMJ | Budget
10 | 2021-06-01 | CMO East 1 | OMJ | Forecast | 0
10 | 2021-06-01 | CMO East 1 | OMJ | Actual | 0
10 | 2021-06-01 | CMO East 1 | DHB Utilities | Budget
10 | 2021-06-01 | CMO East 1 | DHB Utilities | Forecast | 0
10 | 2021-06-01 | CMO East 1 | DHB Utilities | Actual | 0
10 | 2021-06-01 | CMO East 1 | JDT | Budget
10 | 2021-06-01 | CMO East 1 | JDT | Forecast | 0
10 | 2021-06-01 | CMO East 1 | JDT | Actual | 0
10 | 2021-06-01 | CMO East 1 | MURRAY | Budget
10 | 2021-06-01 | CMO East 1 | MURRAY | Forecast | 0
10 | 2021-06-01 | CMO East 1 | MURRAY | Actual | 0
10 | 2021-06-01 | CMO East 2 | Terra Firma | Budget
10 | 2021-06-01 | CMO East 2 | Terra Firma | Forecast | 0
10 | 2021-06-01 | CMO East 2 | Terra Firma | Actual | 0
10 | 2021-06-01 | CMO East 2 | KLT | Budget
10 | 2021-06-01 | CMO East 2 | KLT | Forecast | 0
10 | 2021-06-01 | CMO East 2 | KLT | Actual | 0
10 | 2021-06-01 | CMO East 2 | Forefront | Budget
10 | 2021-06-01 | CMO East 2 | Forefront | Forecast | 0
10 | 2021-06-01 | CMO East 2 | Forefront | Actual | 0
10 | 2021-06-01 | CMO East 2 | DPF | Budget
10 | 2021-06-01 | CMO East 2 | DPF | Forecast | 0
10 | 2021-06-01 | CMO East 2 | DPF | Actual | 0
10 | 2021-06-01 | CMO East 2 | OMJ | Budget
10 | 2021-06-01 | CMO East 2 | OMJ | Forecast | 0
10 | 2021-06-01 | CMO East 2 | OMJ | Actual | 0
10 | 2021-06-01 | CMO East 2 | DHB Utilities | Budget
10 | 2021-06-01 | CMO East 2 | DHB Utilities | Forecast | 0
10 | 2021-06-01 | CMO East 2 | DHB Utilities | Actual | 0
10 | 2021-06-01 | CMO East 2 | JDT | Budget
10 | 2021-06-01 | CMO East 2 | JDT | Forecast | 0
10 | 2021-06-01 | CMO East 2 | JDT | Actual | 0
10 | 2021-06-01 | CMO East 2 | MURRAY | Budget
10 | 2021-06-01 | CMO East 2 | MURRAY | Forecast | 0
10 | 2021-06-01 | CMO East 2 | MURRAY | Actual | 0
10 | 2021-06-01 | West | Terra Firma | Budget
10 | 2021-06-01 | West | Terra Firma | Forecast | 0
10 | 2021-06-01 | West | Terra Firma | Actual | 0
10 | 2021-06-01 | West | KLT | Budget
10 | 2021-06-01 | West | KLT | Forecast | 0
10 | 2021-06-01 | West | KLT | Actual | 0
10 | 2021-06-01 | West | Forefront | Budget
10 | 2021-06-01 | West | Forefront | Forecast | 0
10 | 2021-06-01 | West | Forefront | Actual | 0
10 | 2021-06-01 | West | DPF | Budget
10 | 2021-06-01 | West | DPF | Forecast | 0
10 | 2021-06-01 | West | DPF | Actual | 0
10 | 2021-06-01 | West | OMJ | Budget
10 | 2021-06-01 | West | OMJ | Forecast | 0
10 | 2021-06-01 | West | OMJ | Actual | 0
10 | 2021-06-01 | West | DHB Utilities | Budget
10 | 2021-06-01 | West | DHB Utilities | Forecast | 0
10 | 2021-06-01 | West | DHB Utilities | Actual | 0
10 | 2021-06-01 | West | JDT | Budget
10 | 2021-06-01 | West | JDT | Forecast | 0
10 | 2021-06-01 | West | JDT | Actual | 0
10 | 2021-06-01 | West | MURRAY | Budget
10 | 2021-06-01 | West | MURRAY | Forecast | 0
10 | 2021-06-01 | West | MURRAY | Actual | 0
10 | 2021-06-01 | East | Terra Firma | Budget
10 | 2021-06-01 | East | Terra Firma | Forecast | 0
10 | 2021-06-01 | East | Terra Firma | Actual | 0
10 | 2021-06-01 | East | KLT | Budget
10 | 2021-06-01 | East | KLT | Forecast | 0
10 | 2021-06-01 | East | KLT | Actual | 0
10 | 2021-06-01 | East | Forefront | Budget
10 | 2021-06-01 | East | Forefront | Forecast | 0
10 | 2021-06-01 | East | Forefront | Actual | 0
10 | 2021-06-01 | East | DPF | Budget
10 | 2021-06-01 | East | DPF | Forecast | 0
10 | 2021-06-01 | East | DPF | Actual | 0
10 | 2021-06-01 | East | OMJ | Budget
10 | 2021-06-01 | East | OMJ | Forecast | 0
10 | 2021-06-01 | East | OMJ | Actual | 0
10 | 2021-06-01 | East | DHB Utilities | Budget
10 | 2021-06-01 | East | DHB Utilities | Forecast | 0
10 | 2021-06-01 | East | DHB Utilities | Actual | 0
10 | 2021-06-01 | East | JDT | Budget
10 | 2021-06-01 | East | JDT | Forecast | 0
10 | 2021-06-01 | East | JDT | Actual | 0
10 | 2021-06-01 | East | MURRAY | Budget
10 | 2021-06-01 | East | MURRAY | Forecast | 0
10 | 2021-06-01 | East | MURRAY | Actual | 0
10 | 2021-06-01 | Central | Terra Firma | Budget
10 | 2021-06-01 | Central | Terra Firma | Forecast | 0
10 | 2021-06-01 | Central | Terra Firma | Actual | 0
10 | 2021-06-01 | Central | KLT | Budget
10 | 2021-06-01 | Central | KLT | Forecast | 0
10 | 2021-06-01 | Central | KLT | Actual | 0
10 | 2021-06-01 | Central | Forefront | Budget
10 | 2021-06-01 | Central | Forefront | Forecast | 0
10 | 2021-06-01 | Central | Forefront | Actual | 0
10 | 2021-06-01 | Central | DPF | Budget
10 | 2021-06-01 | Central | DPF | Forecast | 0
10 | 2021-06-01 | Central | DPF | Actual | 0
10 | 2021-06-01 | Central | OMJ | Budget
10 | 2021-06-01 | Central | OMJ | Forecast | 0
10 | 2021-06-01 | Central | OMJ | Actual | 0
10 | 2021-06-01 | Central | DHB Utilities | Budget
10 | 2021-06-01 | Central | DHB Utilities | Forecast | 0
10 | 2021-06-01 | Central | DHB Utilities | Actual | 0
10 | 2021-06-01 | Central | JDT | Budget
10 | 2021-06-01 | Central | JDT | Forecast | 0
10 | 2021-06-01 | Central | JDT | Actual | 0
10 | 2021-06-01 | Central | MURRAY | Budget
10 | 2021-06-01 | Central | MURRAY | Forecast | 0
10 | 2021-06-01 | Central | MURRAY | Actual | 0
10 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Budget
10 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Budget
10 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Budget
10 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Budget
10 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | West | DIRECT MOLE | Budget
10 | 2021-06-01 | West | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | West | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | East | DIRECT MOLE | Budget
10 | 2021-06-01 | East | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | East | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | Central | DIRECT MOLE | Budget
10 | 2021-06-01 | Central | DIRECT MOLE | Forecast | 0
10 | 2021-06-01 | Central | DIRECT MOLE | Actual | 0
10 | 2021-06-01 | CMO West 1 | SQS | Budget
10 | 2021-06-01 | CMO West 1 | SQS | Forecast | 0
10 | 2021-06-01 | CMO West 1 | SQS | Actual | 0
10 | 2021-06-01 | CMO West 2 | SQS | Budget
10 | 2021-06-01 | CMO West 2 | SQS | Forecast | 0
10 | 2021-06-01 | CMO West 2 | SQS | Actual | 0
10 | 2021-06-01 | CMO East 1 | SQS | Budget
10 | 2021-06-01 | CMO East 1 | SQS | Forecast | 0
10 | 2021-06-01 | CMO East 1 | SQS | Actual | 0
10 | 2021-06-01 | CMO East 2 | SQS | Budget
10 | 2021-06-01 | CMO East 2 | SQS | Forecast | 0
10 | 2021-06-01 | CMO East 2 | SQS | Actual | 0
10 | 2021-06-01 | West | SQS | Budget
10 | 2021-06-01 | West | SQS | Forecast | 0
10 | 2021-06-01 | West | SQS | Actual | 0
10 | 2021-06-01 | East | SQS | Budget
10 | 2021-06-01 | East | SQS | Forecast | 0
11 | 2021-06-01 | East | SQS | Actual | 0
11 | 2021-06-01 | Central | SQS | Budget
11 | 2021-06-01 | Central | SQS | Forecast | 0
10 | 2021-06-01 | Central | SQS | Actual | 0
11 | 2021-06-01 | CMO West 1 | Terra Firma | Budget
11 | 2021-06-01 | CMO West 1 | Terra Firma | Forecast | 0
11 | 2021-06-01 | CMO West 1 | Terra Firma | Actual | 0
11 | 2021-06-01 | CMO West 1 | KLT | Budget
11 | 2021-06-01 | CMO West 1 | KLT | Forecast | 0
11 | 2021-06-01 | CMO West 1 | KLT | Actual | 0
11 | 2021-06-01 | CMO West 1 | Forefront | Budget
11 | 2021-06-01 | CMO West 1 | Forefront | Forecast | 0
11 | 2021-06-01 | CMO West 1 | Forefront | Actual | 0
11 | 2021-06-01 | CMO West 1 | DPF | Budget
11 | 2021-06-01 | CMO West 1 | DPF | Forecast | 0
11 | 2021-06-01 | CMO West 1 | DPF | Actual | 0
11 | 2021-06-01 | CMO West 1 | OMJ | Budget
11 | 2021-06-01 | CMO West 1 | OMJ | Forecast | 0
11 | 2021-06-01 | CMO West 1 | OMJ | Actual | 0
11 | 2021-06-01 | CMO West 1 | DHB Utilities | Budget
11 | 2021-06-01 | CMO West 1 | DHB Utilities | Forecast | 0
11 | 2021-06-01 | CMO West 1 | DHB Utilities | Actual | 0
11 | 2021-06-01 | CMO West 1 | JDT | Budget
11 | 2021-06-01 | CMO West 1 | JDT | Forecast | 0
11 | 2021-06-01 | CMO West 1 | JDT | Actual | 0
11 | 2021-06-01 | CMO West 1 | MURRAY | Budget
11 | 2021-06-01 | CMO West 1 | MURRAY | Forecast | 0
11 | 2021-06-01 | CMO West 1 | MURRAY | Actual | 0
11 | 2021-06-01 | CMO West 2 | Terra Firma | Budget
11 | 2021-06-01 | CMO West 2 | Terra Firma | Forecast | 0
11 | 2021-06-01 | CMO West 2 | Terra Firma | Actual | 0
11 | 2021-06-01 | CMO West 2 | KLT | Budget
11 | 2021-06-01 | CMO West 2 | KLT | Forecast | 0
11 | 2021-06-01 | CMO West 2 | KLT | Actual | 0
11 | 2021-06-01 | CMO West 2 | Forefront | Budget
11 | 2021-06-01 | CMO West 2 | Forefront | Forecast | 0
11 | 2021-06-01 | CMO West 2 | Forefront | Actual | 0
11 | 2021-06-01 | CMO West 2 | DPF | Budget
11 | 2021-06-01 | CMO West 2 | DPF | Forecast | 0
11 | 2021-06-01 | CMO West 2 | DPF | Actual | 0
11 | 2021-06-01 | CMO West 2 | OMJ | Budget
11 | 2021-06-01 | CMO West 2 | OMJ | Forecast | 0
11 | 2021-06-01 | CMO West 2 | OMJ | Actual | 0
11 | 2021-06-01 | CMO West 2 | DHB Utilities | Budget
11 | 2021-06-01 | CMO West 2 | DHB Utilities | Forecast | 0
11 | 2021-06-01 | CMO West 2 | DHB Utilities | Actual | 0
11 | 2021-06-01 | CMO West 2 | JDT | Budget
11 | 2021-06-01 | CMO West 2 | JDT | Forecast | 0
11 | 2021-06-01 | CMO West 2 | JDT | Actual | 0
11 | 2021-06-01 | CMO West 2 | MURRAY | Budget
11 | 2021-06-01 | CMO West 2 | MURRAY | Forecast | 0
11 | 2021-06-01 | CMO West 2 | MURRAY | Actual | 0
11 | 2021-06-01 | CMO East 1 | Terra Firma | Budget
11 | 2021-06-01 | CMO East 1 | Terra Firma | Forecast | 0
11 | 2021-06-01 | CMO East 1 | Terra Firma | Actual | 0
11 | 2021-06-01 | CMO East 1 | KLT | Budget
11 | 2021-06-01 | CMO East 1 | KLT | Forecast | 0
11 | 2021-06-01 | CMO East 1 | KLT | Actual | 0
11 | 2021-06-01 | CMO East 1 | Forefront | Budget
11 | 2021-06-01 | CMO East 1 | Forefront | Forecast | 0
11 | 2021-06-01 | CMO East 1 | Forefront | Actual | 0
11 | 2021-06-01 | CMO East 1 | DPF | Budget
11 | 2021-06-01 | CMO East 1 | DPF | Forecast | 0
11 | 2021-06-01 | CMO East 1 | DPF | Actual | 0
11 | 2021-06-01 | CMO East 1 | OMJ | Budget
11 | 2021-06-01 | CMO East 1 | OMJ | Forecast | 0
11 | 2021-06-01 | CMO East 1 | OMJ | Actual | 0
11 | 2021-06-01 | CMO East 1 | DHB Utilities | Budget
11 | 2021-06-01 | CMO East 1 | DHB Utilities | Forecast | 0
11 | 2021-06-01 | CMO East 1 | DHB Utilities | Actual | 0
11 | 2021-06-01 | CMO East 1 | JDT | Budget
11 | 2021-06-01 | CMO East 1 | JDT | Forecast | 0
11 | 2021-06-01 | CMO East 1 | JDT | Actual | 0
11 | 2021-06-01 | CMO East 1 | MURRAY | Budget
11 | 2021-06-01 | CMO East 1 | MURRAY | Forecast | 0
11 | 2021-06-01 | CMO East 1 | MURRAY | Actual | 0
11 | 2021-06-01 | CMO East 2 | Terra Firma | Budget
11 | 2021-06-01 | CMO East 2 | Terra Firma | Forecast | 0
11 | 2021-06-01 | CMO East 2 | Terra Firma | Actual | 0
11 | 2021-06-01 | CMO East 2 | KLT | Budget
11 | 2021-06-01 | CMO East 2 | KLT | Forecast | 0
11 | 2021-06-01 | CMO East 2 | KLT | Actual | 0
11 | 2021-06-01 | CMO East 2 | Forefront | Budget
11 | 2021-06-01 | CMO East 2 | Forefront | Forecast | 0
11 | 2021-06-01 | CMO East 2 | Forefront | Actual | 0
11 | 2021-06-01 | CMO East 2 | DPF | Budget
11 | 2021-06-01 | CMO East 2 | DPF | Forecast | 0
11 | 2021-06-01 | CMO East 2 | DPF | Actual | 0
11 | 2021-06-01 | CMO East 2 | OMJ | Budget
11 | 2021-06-01 | CMO East 2 | OMJ | Forecast | 0
11 | 2021-06-01 | CMO East 2 | OMJ | Actual | 0
11 | 2021-06-01 | CMO East 2 | DHB Utilities | Budget
11 | 2021-06-01 | CMO East 2 | DHB Utilities | Forecast | 0
11 | 2021-06-01 | CMO East 2 | DHB Utilities | Actual | 0
11 | 2021-06-01 | CMO East 2 | JDT | Budget
11 | 2021-06-01 | CMO East 2 | JDT | Forecast | 0
11 | 2021-06-01 | CMO East 2 | JDT | Actual | 0
11 | 2021-06-01 | CMO East 2 | MURRAY | Budget
11 | 2021-06-01 | CMO East 2 | MURRAY | Forecast | 0
11 | 2021-06-01 | CMO East 2 | MURRAY | Actual | 0
11 | 2021-06-01 | West | Terra Firma | Budget
11 | 2021-06-01 | West | Terra Firma | Forecast | 0
11 | 2021-06-01 | West | Terra Firma | Actual | 0
11 | 2021-06-01 | West | KLT | Budget
11 | 2021-06-01 | West | KLT | Forecast | 0
11 | 2021-06-01 | West | KLT | Actual | 0
11 | 2021-06-01 | West | Forefront | Budget
11 | 2021-06-01 | West | Forefront | Forecast | 0
11 | 2021-06-01 | West | Forefront | Actual | 0
11 | 2021-06-01 | West | DPF | Budget
11 | 2021-06-01 | West | DPF | Forecast | 0
11 | 2021-06-01 | West | DPF | Actual | 0
11 | 2021-06-01 | West | OMJ | Budget
11 | 2021-06-01 | West | OMJ | Forecast | 0
11 | 2021-06-01 | West | OMJ | Actual | 0
11 | 2021-06-01 | West | DHB Utilities | Budget
11 | 2021-06-01 | West | DHB Utilities | Forecast | 0
11 | 2021-06-01 | West | DHB Utilities | Actual | 0
11 | 2021-06-01 | West | JDT | Budget
11 | 2021-06-01 | West | JDT | Forecast | 0
11 | 2021-06-01 | West | JDT | Actual | 0
11 | 2021-06-01 | West | MURRAY | Budget
11 | 2021-06-01 | West | MURRAY | Forecast | 0
11 | 2021-06-01 | West | MURRAY | Actual | 0
11 | 2021-06-01 | East | Terra Firma | Budget
11 | 2021-06-01 | East | Terra Firma | Forecast | 0
11 | 2021-06-01 | East | Terra Firma | Actual | 0
11 | 2021-06-01 | East | KLT | Budget
11 | 2021-06-01 | East | KLT | Forecast | 0
11 | 2021-06-01 | East | KLT | Actual | 0
11 | 2021-06-01 | East | Forefront | Budget
11 | 2021-06-01 | East | Forefront | Forecast | 0
11 | 2021-06-01 | East | Forefront | Actual | 0
11 | 2021-06-01 | East | DPF | Budget
11 | 2021-06-01 | East | DPF | Forecast | 0
11 | 2021-06-01 | East | DPF | Actual | 0
11 | 2021-06-01 | East | OMJ | Budget
11 | 2021-06-01 | East | OMJ | Forecast | 0
11 | 2021-06-01 | East | OMJ | Actual | 0
11 | 2021-06-01 | East | DHB Utilities | Budget
11 | 2021-06-01 | East | DHB Utilities | Forecast | 0
11 | 2021-06-01 | East | DHB Utilities | Actual | 0
11 | 2021-06-01 | East | JDT | Budget
11 | 2021-06-01 | East | JDT | Forecast | 0
11 | 2021-06-01 | East | JDT | Actual | 0
11 | 2021-06-01 | East | MURRAY | Budget
11 | 2021-06-01 | East | MURRAY | Forecast | 0
11 | 2021-06-01 | East | MURRAY | Actual | 0
11 | 2021-06-01 | Central | Terra Firma | Budget
11 | 2021-06-01 | Central | Terra Firma | Forecast | 0
11 | 2021-06-01 | Central | Terra Firma | Actual | 0
11 | 2021-06-01 | Central | KLT | Budget
11 | 2021-06-01 | Central | KLT | Forecast | 0
11 | 2021-06-01 | Central | KLT | Actual | 0
11 | 2021-06-01 | Central | Forefront | Budget
11 | 2021-06-01 | Central | Forefront | Forecast | 0
11 | 2021-06-01 | Central | Forefront | Actual | 0
11 | 2021-06-01 | Central | DPF | Budget
11 | 2021-06-01 | Central | DPF | Forecast | 0
11 | 2021-06-01 | Central | DPF | Actual | 0
11 | 2021-06-01 | Central | OMJ | Budget
11 | 2021-06-01 | Central | OMJ | Forecast | 0
11 | 2021-06-01 | Central | OMJ | Actual | 0
11 | 2021-06-01 | Central | DHB Utilities | Budget
11 | 2021-06-01 | Central | DHB Utilities | Forecast | 0
11 | 2021-06-01 | Central | DHB Utilities | Actual | 0
11 | 2021-06-01 | Central | JDT | Budget
11 | 2021-06-01 | Central | JDT | Forecast | 0
11 | 2021-06-01 | Central | JDT | Actual | 0
11 | 2021-06-01 | Central | MURRAY | Budget
11 | 2021-06-01 | Central | MURRAY | Forecast | 0
11 | 2021-06-01 | Central | MURRAY | Actual | 0
11 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Budget
11 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Budget
11 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Budget
11 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Budget
11 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | West | DIRECT MOLE | Budget
11 | 2021-06-01 | West | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | West | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | East | DIRECT MOLE | Budget
11 | 2021-06-01 | East | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | East | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | Central | DIRECT MOLE | Budget
11 | 2021-06-01 | Central | DIRECT MOLE | Forecast | 0
11 | 2021-06-01 | Central | DIRECT MOLE | Actual | 0
11 | 2021-06-01 | CMO West 1 | SQS | Budget
11 | 2021-06-01 | CMO West 1 | SQS | Forecast | 0
11 | 2021-06-01 | CMO West 1 | SQS | Actual | 0
11 | 2021-06-01 | CMO West 2 | SQS | Budget
11 | 2021-06-01 | CMO West 2 | SQS | Forecast | 0
11 | 2021-06-01 | CMO West 2 | SQS | Actual | 0
11 | 2021-06-01 | CMO East 1 | SQS | Budget
11 | 2021-06-01 | CMO East 1 | SQS | Forecast | 0
11 | 2021-06-01 | CMO East 1 | SQS | Actual | 0
11 | 2021-06-01 | CMO East 2 | SQS | Budget
11 | 2021-06-01 | CMO East 2 | SQS | Forecast | 0
11 | 2021-06-01 | CMO East 2 | SQS | Actual | 0
11 | 2021-06-01 | West | SQS | Budget
11 | 2021-06-01 | West | SQS | Forecast | 0
11 | 2021-06-01 | West | SQS | Actual | 0
11 | 2021-06-01 | East | SQS | Budget
11 | 2021-06-01 | East | SQS | Forecast | 0
12 | 2021-06-01 | East | SQS | Actual | 0
12 | 2021-06-01 | Central | SQS | Budget
12 | 2021-06-01 | Central | SQS | Forecast | 0
11 | 2021-06-01 | Central | SQS | Actual | 0
12 | 2021-06-01 | CMO West 1 | Terra Firma | Budget
12 | 2021-06-01 | CMO West 1 | Terra Firma | Forecast | 0
12 | 2021-06-01 | CMO West 1 | Terra Firma | Actual | 0
12 | 2021-06-01 | CMO West 1 | KLT | Budget
12 | 2021-06-01 | CMO West 1 | KLT | Forecast | 0
12 | 2021-06-01 | CMO West 1 | KLT | Actual | 0
12 | 2021-06-01 | CMO West 1 | Forefront | Budget
12 | 2021-06-01 | CMO West 1 | Forefront | Forecast | 0
12 | 2021-06-01 | CMO West 1 | Forefront | Actual | 0
12 | 2021-06-01 | CMO West 1 | DPF | Budget
12 | 2021-06-01 | CMO West 1 | DPF | Forecast | 0
12 | 2021-06-01 | CMO West 1 | DPF | Actual | 0
12 | 2021-06-01 | CMO West 1 | OMJ | Budget
12 | 2021-06-01 | CMO West 1 | OMJ | Forecast | 0
12 | 2021-06-01 | CMO West 1 | OMJ | Actual | 0
12 | 2021-06-01 | CMO West 1 | DHB Utilities | Budget
12 | 2021-06-01 | CMO West 1 | DHB Utilities | Forecast | 0
12 | 2021-06-01 | CMO West 1 | DHB Utilities | Actual | 0
12 | 2021-06-01 | CMO West 1 | JDT | Budget
12 | 2021-06-01 | CMO West 1 | JDT | Forecast | 0
12 | 2021-06-01 | CMO West 1 | JDT | Actual | 0
12 | 2021-06-01 | CMO West 1 | MURRAY | Budget
12 | 2021-06-01 | CMO West 1 | MURRAY | Forecast | 0
12 | 2021-06-01 | CMO West 1 | MURRAY | Actual | 0
12 | 2021-06-01 | CMO West 2 | Terra Firma | Budget
12 | 2021-06-01 | CMO West 2 | Terra Firma | Forecast | 0
12 | 2021-06-01 | CMO West 2 | Terra Firma | Actual | 0
12 | 2021-06-01 | CMO West 2 | KLT | Budget
12 | 2021-06-01 | CMO West 2 | KLT | Forecast | 0
12 | 2021-06-01 | CMO West 2 | KLT | Actual | 0
12 | 2021-06-01 | CMO West 2 | Forefront | Budget
12 | 2021-06-01 | CMO West 2 | Forefront | Forecast | 0
12 | 2021-06-01 | CMO West 2 | Forefront | Actual | 0
12 | 2021-06-01 | CMO West 2 | DPF | Budget
12 | 2021-06-01 | CMO West 2 | DPF | Forecast | 0
12 | 2021-06-01 | CMO West 2 | DPF | Actual | 0
12 | 2021-06-01 | CMO West 2 | OMJ | Budget
12 | 2021-06-01 | CMO West 2 | OMJ | Forecast | 0
12 | 2021-06-01 | CMO West 2 | OMJ | Actual | 0
12 | 2021-06-01 | CMO West 2 | DHB Utilities | Budget
12 | 2021-06-01 | CMO West 2 | DHB Utilities | Forecast | 0
12 | 2021-06-01 | CMO West 2 | DHB Utilities | Actual | 0
12 | 2021-06-01 | CMO West 2 | JDT | Budget
12 | 2021-06-01 | CMO West 2 | JDT | Forecast | 0
12 | 2021-06-01 | CMO West 2 | JDT | Actual | 0
12 | 2021-06-01 | CMO West 2 | MURRAY | Budget
12 | 2021-06-01 | CMO West 2 | MURRAY | Forecast | 0
12 | 2021-06-01 | CMO West 2 | MURRAY | Actual | 0
12 | 2021-06-01 | CMO East 1 | Terra Firma | Budget
12 | 2021-06-01 | CMO East 1 | Terra Firma | Forecast | 0
12 | 2021-06-01 | CMO East 1 | Terra Firma | Actual | 0
12 | 2021-06-01 | CMO East 1 | KLT | Budget
12 | 2021-06-01 | CMO East 1 | KLT | Forecast | 0
12 | 2021-06-01 | CMO East 1 | KLT | Actual | 0
12 | 2021-06-01 | CMO East 1 | Forefront | Budget
12 | 2021-06-01 | CMO East 1 | Forefront | Forecast | 0
12 | 2021-06-01 | CMO East 1 | Forefront | Actual | 0
12 | 2021-06-01 | CMO East 1 | DPF | Budget
12 | 2021-06-01 | CMO East 1 | DPF | Forecast | 0
12 | 2021-06-01 | CMO East 1 | DPF | Actual | 0
12 | 2021-06-01 | CMO East 1 | OMJ | Budget
12 | 2021-06-01 | CMO East 1 | OMJ | Forecast | 0
12 | 2021-06-01 | CMO East 1 | OMJ | Actual | 0
12 | 2021-06-01 | CMO East 1 | DHB Utilities | Budget
12 | 2021-06-01 | CMO East 1 | DHB Utilities | Forecast | 0
12 | 2021-06-01 | CMO East 1 | DHB Utilities | Actual | 0
12 | 2021-06-01 | CMO East 1 | JDT | Budget
12 | 2021-06-01 | CMO East 1 | JDT | Forecast | 0
12 | 2021-06-01 | CMO East 1 | JDT | Actual | 0
12 | 2021-06-01 | CMO East 1 | MURRAY | Budget
12 | 2021-06-01 | CMO East 1 | MURRAY | Forecast | 0
12 | 2021-06-01 | CMO East 1 | MURRAY | Actual | 0
12 | 2021-06-01 | CMO East 2 | Terra Firma | Budget
12 | 2021-06-01 | CMO East 2 | Terra Firma | Forecast | 0
12 | 2021-06-01 | CMO East 2 | Terra Firma | Actual | 0
12 | 2021-06-01 | CMO East 2 | KLT | Budget
12 | 2021-06-01 | CMO East 2 | KLT | Forecast | 0
12 | 2021-06-01 | CMO East 2 | KLT | Actual | 0
12 | 2021-06-01 | CMO East 2 | Forefront | Budget
12 | 2021-06-01 | CMO East 2 | Forefront | Forecast | 0
12 | 2021-06-01 | CMO East 2 | Forefront | Actual | 0
12 | 2021-06-01 | CMO East 2 | DPF | Budget
12 | 2021-06-01 | CMO East 2 | DPF | Forecast | 0
12 | 2021-06-01 | CMO East 2 | DPF | Actual | 0
12 | 2021-06-01 | CMO East 2 | OMJ | Budget
12 | 2021-06-01 | CMO East 2 | OMJ | Forecast | 0
12 | 2021-06-01 | CMO East 2 | OMJ | Actual | 0
12 | 2021-06-01 | CMO East 2 | DHB Utilities | Budget
12 | 2021-06-01 | CMO East 2 | DHB Utilities | Forecast | 0
12 | 2021-06-01 | CMO East 2 | DHB Utilities | Actual | 0
12 | 2021-06-01 | CMO East 2 | JDT | Budget
12 | 2021-06-01 | CMO East 2 | JDT | Forecast | 0
12 | 2021-06-01 | CMO East 2 | JDT | Actual | 0
12 | 2021-06-01 | CMO East 2 | MURRAY | Budget
12 | 2021-06-01 | CMO East 2 | MURRAY | Forecast | 0
12 | 2021-06-01 | CMO East 2 | MURRAY | Actual | 0
12 | 2021-06-01 | West | Terra Firma | Budget
12 | 2021-06-01 | West | Terra Firma | Forecast | 0
12 | 2021-06-01 | West | Terra Firma | Actual | 0
12 | 2021-06-01 | West | KLT | Budget
12 | 2021-06-01 | West | KLT | Forecast | 0
12 | 2021-06-01 | West | KLT | Actual | 0
12 | 2021-06-01 | West | Forefront | Budget
12 | 2021-06-01 | West | Forefront | Forecast | 0
12 | 2021-06-01 | West | Forefront | Actual | 0
12 | 2021-06-01 | West | DPF | Budget
12 | 2021-06-01 | West | DPF | Forecast | 0
12 | 2021-06-01 | West | DPF | Actual | 0
12 | 2021-06-01 | West | OMJ | Budget
12 | 2021-06-01 | West | OMJ | Forecast | 0
12 | 2021-06-01 | West | OMJ | Actual | 0
12 | 2021-06-01 | West | DHB Utilities | Budget
12 | 2021-06-01 | West | DHB Utilities | Forecast | 0
12 | 2021-06-01 | West | DHB Utilities | Actual | 0
12 | 2021-06-01 | West | JDT | Budget
12 | 2021-06-01 | West | JDT | Forecast | 0
12 | 2021-06-01 | West | JDT | Actual | 0
12 | 2021-06-01 | West | MURRAY | Budget
12 | 2021-06-01 | West | MURRAY | Forecast | 0
12 | 2021-06-01 | West | MURRAY | Actual | 0
12 | 2021-06-01 | East | Terra Firma | Budget
12 | 2021-06-01 | East | Terra Firma | Forecast | 0
12 | 2021-06-01 | East | Terra Firma | Actual | 0
12 | 2021-06-01 | East | KLT | Budget
12 | 2021-06-01 | East | KLT | Forecast | 0
12 | 2021-06-01 | East | KLT | Actual | 0
12 | 2021-06-01 | East | Forefront | Budget
12 | 2021-06-01 | East | Forefront | Forecast | 0
12 | 2021-06-01 | East | Forefront | Actual | 0
12 | 2021-06-01 | East | DPF | Budget
12 | 2021-06-01 | East | DPF | Forecast | 0
12 | 2021-06-01 | East | DPF | Actual | 0
12 | 2021-06-01 | East | OMJ | Budget
12 | 2021-06-01 | East | OMJ | Forecast | 0
12 | 2021-06-01 | East | OMJ | Actual | 0
12 | 2021-06-01 | East | DHB Utilities | Budget
12 | 2021-06-01 | East | DHB Utilities | Forecast | 0
12 | 2021-06-01 | East | DHB Utilities | Actual | 0
12 | 2021-06-01 | East | JDT | Budget
12 | 2021-06-01 | East | JDT | Forecast | 0
12 | 2021-06-01 | East | JDT | Actual | 0
12 | 2021-06-01 | East | MURRAY | Budget
12 | 2021-06-01 | East | MURRAY | Forecast | 0
12 | 2021-06-01 | East | MURRAY | Actual | 0
12 | 2021-06-01 | Central | Terra Firma | Budget
12 | 2021-06-01 | Central | Terra Firma | Forecast | 0
12 | 2021-06-01 | Central | Terra Firma | Actual | 0
12 | 2021-06-01 | Central | KLT | Budget
12 | 2021-06-01 | Central | KLT | Forecast | 0
12 | 2021-06-01 | Central | KLT | Actual | 0
12 | 2021-06-01 | Central | Forefront | Budget
12 | 2021-06-01 | Central | Forefront | Forecast | 0
12 | 2021-06-01 | Central | Forefront | Actual | 0
12 | 2021-06-01 | Central | DPF | Budget
12 | 2021-06-01 | Central | DPF | Forecast | 0
12 | 2021-06-01 | Central | DPF | Actual | 0
12 | 2021-06-01 | Central | OMJ | Budget
12 | 2021-06-01 | Central | OMJ | Forecast | 0
12 | 2021-06-01 | Central | OMJ | Actual | 0
12 | 2021-06-01 | Central | DHB Utilities | Budget
12 | 2021-06-01 | Central | DHB Utilities | Forecast | 0
12 | 2021-06-01 | Central | DHB Utilities | Actual | 0
12 | 2021-06-01 | Central | JDT | Budget
12 | 2021-06-01 | Central | JDT | Forecast | 0
12 | 2021-06-01 | Central | JDT | Actual | 0
12 | 2021-06-01 | Central | MURRAY | Budget
12 | 2021-06-01 | Central | MURRAY | Forecast | 0
12 | 2021-06-01 | Central | MURRAY | Actual | 0
12 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Budget
12 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Budget
12 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Budget
12 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Budget
12 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | West | DIRECT MOLE | Budget
12 | 2021-06-01 | West | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | West | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | East | DIRECT MOLE | Budget
12 | 2021-06-01 | East | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | East | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | Central | DIRECT MOLE | Budget
12 | 2021-06-01 | Central | DIRECT MOLE | Forecast | 0
12 | 2021-06-01 | Central | DIRECT MOLE | Actual | 0
12 | 2021-06-01 | CMO West 1 | SQS | Budget
12 | 2021-06-01 | CMO West 1 | SQS | Forecast | 0
12 | 2021-06-01 | CMO West 1 | SQS | Actual | 0
12 | 2021-06-01 | CMO West 2 | SQS | Budget
12 | 2021-06-01 | CMO West 2 | SQS | Forecast | 0
12 | 2021-06-01 | CMO West 2 | SQS | Actual | 0
12 | 2021-06-01 | CMO East 1 | SQS | Budget
12 | 2021-06-01 | CMO East 1 | SQS | Forecast | 0
12 | 2021-06-01 | CMO East 1 | SQS | Actual | 0
12 | 2021-06-01 | CMO East 2 | SQS | Budget
12 | 2021-06-01 | CMO East 2 | SQS | Forecast | 0
12 | 2021-06-01 | CMO East 2 | SQS | Actual | 0
12 | 2021-06-01 | West | SQS | Budget
12 | 2021-06-01 | West | SQS | Forecast | 0
12 | 2021-06-01 | West | SQS | Actual | 0
12 | 2021-06-01 | East | SQS | Budget
12 | 2021-06-01 | East | SQS | Forecast | 0
13 | 2021-06-01 | East | SQS | Actual | 0
13 | 2021-06-01 | Central | SQS | Budget
13 | 2021-06-01 | Central | SQS | Forecast | 0
12 | 2021-06-01 | Central | SQS | Actual | 0
13 | 2021-06-01 | CMO West 1 | Terra Firma | Budget
13 | 2021-06-01 | CMO West 1 | Terra Firma | Forecast | 0
13 | 2021-06-01 | CMO West 1 | Terra Firma | Actual | 0
13 | 2021-06-01 | CMO West 1 | KLT | Budget
13 | 2021-06-01 | CMO West 1 | KLT | Forecast | 0
13 | 2021-06-01 | CMO West 1 | KLT | Actual | 0
13 | 2021-06-01 | CMO West 1 | Forefront | Budget
13 | 2021-06-01 | CMO West 1 | Forefront | Forecast | 0
13 | 2021-06-01 | CMO West 1 | Forefront | Actual | 0
13 | 2021-06-01 | CMO West 1 | DPF | Budget
13 | 2021-06-01 | CMO West 1 | DPF | Forecast | 0
13 | 2021-06-01 | CMO West 1 | DPF | Actual | 0
13 | 2021-06-01 | CMO West 1 | OMJ | Budget
13 | 2021-06-01 | CMO West 1 | OMJ | Forecast | 0
13 | 2021-06-01 | CMO West 1 | OMJ | Actual | 0
13 | 2021-06-01 | CMO West 1 | DHB Utilities | Budget
13 | 2021-06-01 | CMO West 1 | DHB Utilities | Forecast | 0
13 | 2021-06-01 | CMO West 1 | DHB Utilities | Actual | 0
13 | 2021-06-01 | CMO West 1 | JDT | Budget
13 | 2021-06-01 | CMO West 1 | JDT | Forecast | 0
13 | 2021-06-01 | CMO West 1 | JDT | Actual | 0
13 | 2021-06-01 | CMO West 1 | MURRAY | Budget
13 | 2021-06-01 | CMO West 1 | MURRAY | Forecast | 0
13 | 2021-06-01 | CMO West 1 | MURRAY | Actual | 0
13 | 2021-06-01 | CMO West 2 | Terra Firma | Budget
13 | 2021-06-01 | CMO West 2 | Terra Firma | Forecast | 0
13 | 2021-06-01 | CMO West 2 | Terra Firma | Actual | 0
13 | 2021-06-01 | CMO West 2 | KLT | Budget
13 | 2021-06-01 | CMO West 2 | KLT | Forecast | 0
13 | 2021-06-01 | CMO West 2 | KLT | Actual | 0
13 | 2021-06-01 | CMO West 2 | Forefront | Budget
13 | 2021-06-01 | CMO West 2 | Forefront | Forecast | 0
13 | 2021-06-01 | CMO West 2 | Forefront | Actual | 0
13 | 2021-06-01 | CMO West 2 | DPF | Budget
13 | 2021-06-01 | CMO West 2 | DPF | Forecast | 0
13 | 2021-06-01 | CMO West 2 | DPF | Actual | 0
13 | 2021-06-01 | CMO West 2 | OMJ | Budget
13 | 2021-06-01 | CMO West 2 | OMJ | Forecast | 0
13 | 2021-06-01 | CMO West 2 | OMJ | Actual | 0
13 | 2021-06-01 | CMO West 2 | DHB Utilities | Budget
13 | 2021-06-01 | CMO West 2 | DHB Utilities | Forecast | 0
13 | 2021-06-01 | CMO West 2 | DHB Utilities | Actual | 0
13 | 2021-06-01 | CMO West 2 | JDT | Budget
13 | 2021-06-01 | CMO West 2 | JDT | Forecast | 0
13 | 2021-06-01 | CMO West 2 | JDT | Actual | 0
13 | 2021-06-01 | CMO West 2 | MURRAY | Budget
13 | 2021-06-01 | CMO West 2 | MURRAY | Forecast | 0
13 | 2021-06-01 | CMO West 2 | MURRAY | Actual | 0
13 | 2021-06-01 | CMO East 1 | Terra Firma | Budget
13 | 2021-06-01 | CMO East 1 | Terra Firma | Forecast | 0
13 | 2021-06-01 | CMO East 1 | Terra Firma | Actual | 0
13 | 2021-06-01 | CMO East 1 | KLT | Budget
13 | 2021-06-01 | CMO East 1 | KLT | Forecast | 0
13 | 2021-06-01 | CMO East 1 | KLT | Actual | 0
13 | 2021-06-01 | CMO East 1 | Forefront | Budget
13 | 2021-06-01 | CMO East 1 | Forefront | Forecast | 0
13 | 2021-06-01 | CMO East 1 | Forefront | Actual | 0
13 | 2021-06-01 | CMO East 1 | DPF | Budget
13 | 2021-06-01 | CMO East 1 | DPF | Forecast | 0
13 | 2021-06-01 | CMO East 1 | DPF | Actual | 0
13 | 2021-06-01 | CMO East 1 | OMJ | Budget
13 | 2021-06-01 | CMO East 1 | OMJ | Forecast | 0
13 | 2021-06-01 | CMO East 1 | OMJ | Actual | 0
13 | 2021-06-01 | CMO East 1 | DHB Utilities | Budget
13 | 2021-06-01 | CMO East 1 | DHB Utilities | Forecast | 0
13 | 2021-06-01 | CMO East 1 | DHB Utilities | Actual | 0
13 | 2021-06-01 | CMO East 1 | JDT | Budget
13 | 2021-06-01 | CMO East 1 | JDT | Forecast | 0
13 | 2021-06-01 | CMO East 1 | JDT | Actual | 0
13 | 2021-06-01 | CMO East 1 | MURRAY | Budget
13 | 2021-06-01 | CMO East 1 | MURRAY | Forecast | 0
13 | 2021-06-01 | CMO East 1 | MURRAY | Actual | 0
13 | 2021-06-01 | CMO East 2 | Terra Firma | Budget
13 | 2021-06-01 | CMO East 2 | Terra Firma | Forecast | 0
13 | 2021-06-01 | CMO East 2 | Terra Firma | Actual | 0
13 | 2021-06-01 | CMO East 2 | KLT | Budget
13 | 2021-06-01 | CMO East 2 | KLT | Forecast | 0
13 | 2021-06-01 | CMO East 2 | KLT | Actual | 0
13 | 2021-06-01 | CMO East 2 | Forefront | Budget
13 | 2021-06-01 | CMO East 2 | Forefront | Forecast | 0
13 | 2021-06-01 | CMO East 2 | Forefront | Actual | 0
13 | 2021-06-01 | CMO East 2 | DPF | Budget
13 | 2021-06-01 | CMO East 2 | DPF | Forecast | 0
13 | 2021-06-01 | CMO East 2 | DPF | Actual | 0
13 | 2021-06-01 | CMO East 2 | OMJ | Budget
13 | 2021-06-01 | CMO East 2 | OMJ | Forecast | 0
13 | 2021-06-01 | CMO East 2 | OMJ | Actual | 0
13 | 2021-06-01 | CMO East 2 | DHB Utilities | Budget
13 | 2021-06-01 | CMO East 2 | DHB Utilities | Forecast | 0
13 | 2021-06-01 | CMO East 2 | DHB Utilities | Actual | 0
13 | 2021-06-01 | CMO East 2 | JDT | Budget
13 | 2021-06-01 | CMO East 2 | JDT | Forecast | 0
13 | 2021-06-01 | CMO East 2 | JDT | Actual | 0
13 | 2021-06-01 | CMO East 2 | MURRAY | Budget
13 | 2021-06-01 | CMO East 2 | MURRAY | Forecast | 0
13 | 2021-06-01 | CMO East 2 | MURRAY | Actual | 0
13 | 2021-06-01 | West | Terra Firma | Budget
13 | 2021-06-01 | West | Terra Firma | Forecast | 0
13 | 2021-06-01 | West | Terra Firma | Actual | 0
13 | 2021-06-01 | West | KLT | Budget
13 | 2021-06-01 | West | KLT | Forecast | 0
13 | 2021-06-01 | West | KLT | Actual | 0
13 | 2021-06-01 | West | Forefront | Budget
13 | 2021-06-01 | West | Forefront | Forecast | 0
13 | 2021-06-01 | West | Forefront | Actual | 0
13 | 2021-06-01 | West | DPF | Budget
13 | 2021-06-01 | West | DPF | Forecast | 0
13 | 2021-06-01 | West | DPF | Actual | 0
13 | 2021-06-01 | West | OMJ | Budget
13 | 2021-06-01 | West | OMJ | Forecast | 0
13 | 2021-06-01 | West | OMJ | Actual | 0
13 | 2021-06-01 | West | DHB Utilities | Budget
13 | 2021-06-01 | West | DHB Utilities | Forecast | 0
13 | 2021-06-01 | West | DHB Utilities | Actual | 0
13 | 2021-06-01 | West | JDT | Budget
13 | 2021-06-01 | West | JDT | Forecast | 0
13 | 2021-06-01 | West | JDT | Actual | 0
13 | 2021-06-01 | West | MURRAY | Budget
13 | 2021-06-01 | West | MURRAY | Forecast | 0
13 | 2021-06-01 | West | MURRAY | Actual | 0
13 | 2021-06-01 | East | Terra Firma | Budget
13 | 2021-06-01 | East | Terra Firma | Forecast | 0
13 | 2021-06-01 | East | Terra Firma | Actual | 0
13 | 2021-06-01 | East | KLT | Budget
13 | 2021-06-01 | East | KLT | Forecast | 0
13 | 2021-06-01 | East | KLT | Actual | 0
13 | 2021-06-01 | East | Forefront | Budget
13 | 2021-06-01 | East | Forefront | Forecast | 0
13 | 2021-06-01 | East | Forefront | Actual | 0
13 | 2021-06-01 | East | DPF | Budget
13 | 2021-06-01 | East | DPF | Forecast | 0
13 | 2021-06-01 | East | DPF | Actual | 0
13 | 2021-06-01 | East | OMJ | Budget
13 | 2021-06-01 | East | OMJ | Forecast | 0
13 | 2021-06-01 | East | OMJ | Actual | 0
13 | 2021-06-01 | East | DHB Utilities | Budget
13 | 2021-06-01 | East | DHB Utilities | Forecast | 0
13 | 2021-06-01 | East | DHB Utilities | Actual | 0
13 | 2021-06-01 | East | JDT | Budget
13 | 2021-06-01 | East | JDT | Forecast | 0
13 | 2021-06-01 | East | JDT | Actual | 0
13 | 2021-06-01 | East | MURRAY | Budget
13 | 2021-06-01 | East | MURRAY | Forecast | 0
13 | 2021-06-01 | East | MURRAY | Actual | 0
13 | 2021-06-01 | Central | Terra Firma | Budget
13 | 2021-06-01 | Central | Terra Firma | Forecast | 0
13 | 2021-06-01 | Central | Terra Firma | Actual | 0
13 | 2021-06-01 | Central | KLT | Budget
13 | 2021-06-01 | Central | KLT | Forecast | 0
13 | 2021-06-01 | Central | KLT | Actual | 0
13 | 2021-06-01 | Central | Forefront | Budget
13 | 2021-06-01 | Central | Forefront | Forecast | 0
13 | 2021-06-01 | Central | Forefront | Actual | 0
13 | 2021-06-01 | Central | DPF | Budget
13 | 2021-06-01 | Central | DPF | Forecast | 0
13 | 2021-06-01 | Central | DPF | Actual | 0
13 | 2021-06-01 | Central | OMJ | Budget
13 | 2021-06-01 | Central | OMJ | Forecast | 0
13 | 2021-06-01 | Central | OMJ | Actual | 0
13 | 2021-06-01 | Central | DHB Utilities | Budget
13 | 2021-06-01 | Central | DHB Utilities | Forecast | 0
13 | 2021-06-01 | Central | DHB Utilities | Actual | 0
13 | 2021-06-01 | Central | JDT | Budget
13 | 2021-06-01 | Central | JDT | Forecast | 0
13 | 2021-06-01 | Central | JDT | Actual | 0
13 | 2021-06-01 | Central | MURRAY | Budget
13 | 2021-06-01 | Central | MURRAY | Forecast | 0
13 | 2021-06-01 | Central | MURRAY | Actual | 0
13 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Budget
13 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | CMO West 1 | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Budget
13 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | CMO West 2 | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Budget
13 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | CMO East 1 | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Budget
13 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | CMO East 2 | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | West | DIRECT MOLE | Budget
13 | 2021-06-01 | West | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | West | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | East | DIRECT MOLE | Budget
13 | 2021-06-01 | East | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | East | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | Central | DIRECT MOLE | Budget
13 | 2021-06-01 | Central | DIRECT MOLE | Forecast | 0
13 | 2021-06-01 | Central | DIRECT MOLE | Actual | 0
13 | 2021-06-01 | CMO West 1 | SQS | Budget
13 | 2021-06-01 | CMO West 1 | SQS | Forecast | 0
13 | 2021-06-01 | CMO West 1 | SQS | Actual | 0
13 | 2021-06-01 | CMO West 2 | SQS | Budget
13 | 2021-06-01 | CMO West 2 | SQS | Forecast | 0
13 | 2021-06-01 | CMO West 2 | SQS | Actual | 0
13 | 2021-06-01 | CMO East 1 | SQS | Budget
13 | 2021-06-01 | CMO East 1 | SQS | Forecast | 0
13 | 2021-06-01 | CMO East 1 | SQS | Actual | 0
13 | 2021-06-01 | CMO East 2 | SQS | Budget
13 | 2021-06-01 | CMO East 2 | SQS | Forecast | 0
13 | 2021-06-01 | CMO East 2 | SQS | Actual | 0
13 | 2021-06-01 | West | SQS | Budget
13 | 2021-06-01 | West | SQS | Forecast | 0
13 | 2021-06-01 | West | SQS | Actual | 0
13 | 2021-06-01 | East | SQS | Budget
13 | 2021-06-01 | East | SQS | Forecast | 0
14 | 2021-06-01 | East | SQS | Actual | 0
14 | 2021-06-01 | Central | SQS | Budget
14 | 2021-06-01 | Central | SQS | Forecast | 0
13 | 2021-06-01 | Central | SQS | Actual | 0
14 | 2021-07-01 | CMO West 1 | Terra Firma | Budget
14 | 2021-07-01 | CMO West 1 | Terra Firma | Forecast | 0
14 | 2021-07-01 | CMO West 1 | Terra Firma | Actual | 0
14 | 2021-07-01 | CMO West 1 | KLT | Budget
14 | 2021-07-01 | CMO West 1 | KLT | Forecast | 0
14 | 2021-07-01 | CMO West 1 | KLT | Actual | 0
14 | 2021-07-01 | CMO West 1 | Forefront | Budget
14 | 2021-07-01 | CMO West 1 | Forefront | Forecast | 0
14 | 2021-07-01 | CMO West 1 | Forefront | Actual | 0
14 | 2021-07-01 | CMO West 1 | DPF | Budget
14 | 2021-07-01 | CMO West 1 | DPF | Forecast | 0
14 | 2021-07-01 | CMO West 1 | DPF | Actual | 0
14 | 2021-07-01 | CMO West 1 | OMJ | Budget
14 | 2021-07-01 | CMO West 1 | OMJ | Forecast | 0
14 | 2021-07-01 | CMO West 1 | OMJ | Actual | 0
14 | 2021-07-01 | CMO West 1 | DHB Utilities | Budget
14 | 2021-07-01 | CMO West 1 | DHB Utilities | Forecast | 0
14 | 2021-07-01 | CMO West 1 | DHB Utilities | Actual | 0
14 | 2021-07-01 | CMO West 1 | JDT | Budget
14 | 2021-07-01 | CMO West 1 | JDT | Forecast | 0
14 | 2021-07-01 | CMO West 1 | JDT | Actual | 0
14 | 2021-07-01 | CMO West 1 | MURRAY | Budget
14 | 2021-07-01 | CMO West 1 | MURRAY | Forecast | 0
14 | 2021-07-01 | CMO West 1 | MURRAY | Actual | 0
14 | 2021-07-01 | CMO West 2 | Terra Firma | Budget
14 | 2021-07-01 | CMO West 2 | Terra Firma | Forecast | 0
14 | 2021-07-01 | CMO West 2 | Terra Firma | Actual | 0
14 | 2021-07-01 | CMO West 2 | KLT | Budget
14 | 2021-07-01 | CMO West 2 | KLT | Forecast | 0
14 | 2021-07-01 | CMO West 2 | KLT | Actual | 0
14 | 2021-07-01 | CMO West 2 | Forefront | Budget
14 | 2021-07-01 | CMO West 2 | Forefront | Forecast | 0
14 | 2021-07-01 | CMO West 2 | Forefront | Actual | 0
14 | 2021-07-01 | CMO West 2 | DPF | Budget
14 | 2021-07-01 | CMO West 2 | DPF | Forecast | 0
14 | 2021-07-01 | CMO West 2 | DPF | Actual | 0
14 | 2021-07-01 | CMO West 2 | OMJ | Budget
14 | 2021-07-01 | CMO West 2 | OMJ | Forecast | 0
14 | 2021-07-01 | CMO West 2 | OMJ | Actual | 0
14 | 2021-07-01 | CMO West 2 | DHB Utilities | Budget
14 | 2021-07-01 | CMO West 2 | DHB Utilities | Forecast | 0
14 | 2021-07-01 | CMO West 2 | DHB Utilities | Actual | 0
14 | 2021-07-01 | CMO West 2 | JDT | Budget
14 | 2021-07-01 | CMO West 2 | JDT | Forecast | 0
14 | 2021-07-01 | CMO West 2 | JDT | Actual | 0
14 | 2021-07-01 | CMO West 2 | MURRAY | Budget
14 | 2021-07-01 | CMO West 2 | MURRAY | Forecast | 0
14 | 2021-07-01 | CMO West 2 | MURRAY | Actual | 0
14 | 2021-07-01 | CMO East 1 | Terra Firma | Budget
14 | 2021-07-01 | CMO East 1 | Terra Firma | Forecast | 0
14 | 2021-07-01 | CMO East 1 | Terra Firma | Actual | 0
14 | 2021-07-01 | CMO East 1 | KLT | Budget
14 | 2021-07-01 | CMO East 1 | KLT | Forecast | 0
14 | 2021-07-01 | CMO East 1 | KLT | Actual | 0
14 | 2021-07-01 | CMO East 1 | Forefront | Budget
14 | 2021-07-01 | CMO East 1 | Forefront | Forecast | 0
14 | 2021-07-01 | CMO East 1 | Forefront | Actual | 0
14 | 2021-07-01 | CMO East 1 | DPF | Budget
14 | 2021-07-01 | CMO East 1 | DPF | Forecast | 0
14 | 2021-07-01 | CMO East 1 | DPF | Actual | 0
14 | 2021-07-01 | CMO East 1 | OMJ | Budget
14 | 2021-07-01 | CMO East 1 | OMJ | Forecast | 0
14 | 2021-07-01 | CMO East 1 | OMJ | Actual | 0
14 | 2021-07-01 | CMO East 1 | DHB Utilities | Budget
14 | 2021-07-01 | CMO East 1 | DHB Utilities | Forecast | 0
14 | 2021-07-01 | CMO East 1 | DHB Utilities | Actual | 0
14 | 2021-07-01 | CMO East 1 | JDT | Budget
14 | 2021-07-01 | CMO East 1 | JDT | Forecast | 0
14 | 2021-07-01 | CMO East 1 | JDT | Actual | 0
14 | 2021-07-01 | CMO East 1 | MURRAY | Budget
14 | 2021-07-01 | CMO East 1 | MURRAY | Forecast | 0
14 | 2021-07-01 | CMO East 1 | MURRAY | Actual | 0
14 | 2021-07-01 | CMO East 2 | Terra Firma | Budget
14 | 2021-07-01 | CMO East 2 | Terra Firma | Forecast | 0
14 | 2021-07-01 | CMO East 2 | Terra Firma | Actual | 0
14 | 2021-07-01 | CMO East 2 | KLT | Budget
14 | 2021-07-01 | CMO East 2 | KLT | Forecast | 0
14 | 2021-07-01 | CMO East 2 | KLT | Actual | 0
14 | 2021-07-01 | CMO East 2 | Forefront | Budget
14 | 2021-07-01 | CMO East 2 | Forefront | Forecast | 0
14 | 2021-07-01 | CMO East 2 | Forefront | Actual | 0
14 | 2021-07-01 | CMO East 2 | DPF | Budget
14 | 2021-07-01 | CMO East 2 | DPF | Forecast | 0
14 | 2021-07-01 | CMO East 2 | DPF | Actual | 0
14 | 2021-07-01 | CMO East 2 | OMJ | Budget
14 | 2021-07-01 | CMO East 2 | OMJ | Forecast | 0
14 | 2021-07-01 | CMO East 2 | OMJ | Actual | 0
14 | 2021-07-01 | CMO East 2 | DHB Utilities | Budget
14 | 2021-07-01 | CMO East 2 | DHB Utilities | Forecast | 0
14 | 2021-07-01 | CMO East 2 | DHB Utilities | Actual | 0
14 | 2021-07-01 | CMO East 2 | JDT | Budget
14 | 2021-07-01 | CMO East 2 | JDT | Forecast | 0
14 | 2021-07-01 | CMO East 2 | JDT | Actual | 0
14 | 2021-07-01 | CMO East 2 | MURRAY | Budget
14 | 2021-07-01 | CMO East 2 | MURRAY | Forecast | 0
14 | 2021-07-01 | CMO East 2 | MURRAY | Actual | 0
14 | 2021-07-01 | West | Terra Firma | Budget
14 | 2021-07-01 | West | Terra Firma | Forecast | 0
14 | 2021-07-01 | West | Terra Firma | Actual | 0
14 | 2021-07-01 | West | KLT | Budget
14 | 2021-07-01 | West | KLT | Forecast | 0
14 | 2021-07-01 | West | KLT | Actual | 0
14 | 2021-07-01 | West | Forefront | Budget
14 | 2021-07-01 | West | Forefront | Forecast | 0
14 | 2021-07-01 | West | Forefront | Actual | 0
14 | 2021-07-01 | West | DPF | Budget
14 | 2021-07-01 | West | DPF | Forecast | 0
14 | 2021-07-01 | West | DPF | Actual | 0
14 | 2021-07-01 | West | OMJ | Budget
14 | 2021-07-01 | West | OMJ | Forecast | 0
14 | 2021-07-01 | West | OMJ | Actual | 0
14 | 2021-07-01 | West | DHB Utilities | Budget
14 | 2021-07-01 | West | DHB Utilities | Forecast | 0
14 | 2021-07-01 | West | DHB Utilities | Actual | 0
14 | 2021-07-01 | West | JDT | Budget
14 | 2021-07-01 | West | JDT | Forecast | 0
14 | 2021-07-01 | West | JDT | Actual | 0
14 | 2021-07-01 | West | MURRAY | Budget
14 | 2021-07-01 | West | MURRAY | Forecast | 0
14 | 2021-07-01 | West | MURRAY | Actual | 0
14 | 2021-07-01 | East | Terra Firma | Budget
14 | 2021-07-01 | East | Terra Firma | Forecast | 0
14 | 2021-07-01 | East | Terra Firma | Actual | 0
14 | 2021-07-01 | East | KLT | Budget
14 | 2021-07-01 | East | KLT | Forecast | 0
14 | 2021-07-01 | East | KLT | Actual | 0
14 | 2021-07-01 | East | Forefront | Budget
14 | 2021-07-01 | East | Forefront | Forecast | 0
14 | 2021-07-01 | East | Forefront | Actual | 0
14 | 2021-07-01 | East | DPF | Budget
14 | 2021-07-01 | East | DPF | Forecast | 0
14 | 2021-07-01 | East | DPF | Actual | 0
14 | 2021-07-01 | East | OMJ | Budget
14 | 2021-07-01 | East | OMJ | Forecast | 0
14 | 2021-07-01 | East | OMJ | Actual | 0
14 | 2021-07-01 | East | DHB Utilities | Budget
14 | 2021-07-01 | East | DHB Utilities | Forecast | 0
14 | 2021-07-01 | East | DHB Utilities | Actual | 0
14 | 2021-07-01 | East | JDT | Budget
14 | 2021-07-01 | East | JDT | Forecast | 0
14 | 2021-07-01 | East | JDT | Actual | 0
14 | 2021-07-01 | East | MURRAY | Budget
14 | 2021-07-01 | East | MURRAY | Forecast | 0
14 | 2021-07-01 | East | MURRAY | Actual | 0
14 | 2021-07-01 | Central | Terra Firma | Budget
14 | 2021-07-01 | Central | Terra Firma | Forecast | 0
14 | 2021-07-01 | Central | Terra Firma | Actual | 0
14 | 2021-07-01 | Central | KLT | Budget
14 | 2021-07-01 | Central | KLT | Forecast | 0
14 | 2021-07-01 | Central | KLT | Actual | 0
14 | 2021-07-01 | Central | Forefront | Budget
14 | 2021-07-01 | Central | Forefront | Forecast | 0
14 | 2021-07-01 | Central | Forefront | Actual | 0
14 | 2021-07-01 | Central | DPF | Budget
14 | 2021-07-01 | Central | DPF | Forecast | 0
14 | 2021-07-01 | Central | DPF | Actual | 0
14 | 2021-07-01 | Central | OMJ | Budget
14 | 2021-07-01 | Central | OMJ | Forecast | 0
14 | 2021-07-01 | Central | OMJ | Actual | 0
14 | 2021-07-01 | Central | DHB Utilities | Budget
14 | 2021-07-01 | Central | DHB Utilities | Forecast | 0
14 | 2021-07-01 | Central | DHB Utilities | Actual | 0
14 | 2021-07-01 | Central | JDT | Budget
14 | 2021-07-01 | Central | JDT | Forecast | 0
14 | 2021-07-01 | Central | JDT | Actual | 0
14 | 2021-07-01 | Central | MURRAY | Budget
14 | 2021-07-01 | Central | MURRAY | Forecast | 0
14 | 2021-07-01 | Central | MURRAY | Actual | 0
14 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Budget
14 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Budget
14 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Budget
14 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Budget
14 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | West | DIRECT MOLE | Budget
14 | 2021-07-01 | West | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | West | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | East | DIRECT MOLE | Budget
14 | 2021-07-01 | East | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | East | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | Central | DIRECT MOLE | Budget
14 | 2021-07-01 | Central | DIRECT MOLE | Forecast | 0
14 | 2021-07-01 | Central | DIRECT MOLE | Actual | 0
14 | 2021-07-01 | CMO West 1 | SQS | Budget
14 | 2021-07-01 | CMO West 1 | SQS | Forecast | 0
14 | 2021-07-01 | CMO West 1 | SQS | Actual | 0
14 | 2021-07-01 | CMO West 2 | SQS | Budget
14 | 2021-07-01 | CMO West 2 | SQS | Forecast | 0
14 | 2021-07-01 | CMO West 2 | SQS | Actual | 0
14 | 2021-07-01 | CMO East 1 | SQS | Budget
14 | 2021-07-01 | CMO East 1 | SQS | Forecast | 0
14 | 2021-07-01 | CMO East 1 | SQS | Actual | 0
14 | 2021-07-01 | CMO East 2 | SQS | Budget
14 | 2021-07-01 | CMO East 2 | SQS | Forecast | 0
14 | 2021-07-01 | CMO East 2 | SQS | Actual | 0
14 | 2021-07-01 | West | SQS | Budget
14 | 2021-07-01 | West | SQS | Forecast | 0
14 | 2021-07-01 | West | SQS | Actual | 0
14 | 2021-07-01 | East | SQS | Budget
14 | 2021-07-01 | East | SQS | Forecast | 0
15 | 2021-07-01 | East | SQS | Actual | 0
15 | 2021-07-01 | Central | SQS | Budget
15 | 2021-07-01 | Central | SQS | Forecast | 0
14 | 2021-07-01 | Central | SQS | Actual | 0
15 | 2021-07-01 | CMO West 1 | Terra Firma | Budget
15 | 2021-07-01 | CMO West 1 | Terra Firma | Forecast | 0
15 | 2021-07-01 | CMO West 1 | Terra Firma | Actual | 0
15 | 2021-07-01 | CMO West 1 | KLT | Budget
15 | 2021-07-01 | CMO West 1 | KLT | Forecast | 0
15 | 2021-07-01 | CMO West 1 | KLT | Actual | 0
15 | 2021-07-01 | CMO West 1 | Forefront | Budget
15 | 2021-07-01 | CMO West 1 | Forefront | Forecast | 0
15 | 2021-07-01 | CMO West 1 | Forefront | Actual | 0
15 | 2021-07-01 | CMO West 1 | DPF | Budget
15 | 2021-07-01 | CMO West 1 | DPF | Forecast | 0
15 | 2021-07-01 | CMO West 1 | DPF | Actual | 0
15 | 2021-07-01 | CMO West 1 | OMJ | Budget
15 | 2021-07-01 | CMO West 1 | OMJ | Forecast | 0
15 | 2021-07-01 | CMO West 1 | OMJ | Actual | 0
15 | 2021-07-01 | CMO West 1 | DHB Utilities | Budget
15 | 2021-07-01 | CMO West 1 | DHB Utilities | Forecast | 0
15 | 2021-07-01 | CMO West 1 | DHB Utilities | Actual | 0
15 | 2021-07-01 | CMO West 1 | JDT | Budget
15 | 2021-07-01 | CMO West 1 | JDT | Forecast | 0
15 | 2021-07-01 | CMO West 1 | JDT | Actual | 0
15 | 2021-07-01 | CMO West 1 | MURRAY | Budget
15 | 2021-07-01 | CMO West 1 | MURRAY | Forecast | 0
15 | 2021-07-01 | CMO West 1 | MURRAY | Actual | 0
15 | 2021-07-01 | CMO West 2 | Terra Firma | Budget
15 | 2021-07-01 | CMO West 2 | Terra Firma | Forecast | 0
15 | 2021-07-01 | CMO West 2 | Terra Firma | Actual | 0
15 | 2021-07-01 | CMO West 2 | KLT | Budget
15 | 2021-07-01 | CMO West 2 | KLT | Forecast | 0
15 | 2021-07-01 | CMO West 2 | KLT | Actual | 0
15 | 2021-07-01 | CMO West 2 | Forefront | Budget
15 | 2021-07-01 | CMO West 2 | Forefront | Forecast | 0
15 | 2021-07-01 | CMO West 2 | Forefront | Actual | 0
15 | 2021-07-01 | CMO West 2 | DPF | Budget
15 | 2021-07-01 | CMO West 2 | DPF | Forecast | 0
15 | 2021-07-01 | CMO West 2 | DPF | Actual | 0
15 | 2021-07-01 | CMO West 2 | OMJ | Budget
15 | 2021-07-01 | CMO West 2 | OMJ | Forecast | 0
15 | 2021-07-01 | CMO West 2 | OMJ | Actual | 0
15 | 2021-07-01 | CMO West 2 | DHB Utilities | Budget
15 | 2021-07-01 | CMO West 2 | DHB Utilities | Forecast | 0
15 | 2021-07-01 | CMO West 2 | DHB Utilities | Actual | 0
15 | 2021-07-01 | CMO West 2 | JDT | Budget
15 | 2021-07-01 | CMO West 2 | JDT | Forecast | 0
15 | 2021-07-01 | CMO West 2 | JDT | Actual | 0
15 | 2021-07-01 | CMO West 2 | MURRAY | Budget
15 | 2021-07-01 | CMO West 2 | MURRAY | Forecast | 0
15 | 2021-07-01 | CMO West 2 | MURRAY | Actual | 0
15 | 2021-07-01 | CMO East 1 | Terra Firma | Budget
15 | 2021-07-01 | CMO East 1 | Terra Firma | Forecast | 0
15 | 2021-07-01 | CMO East 1 | Terra Firma | Actual | 0
15 | 2021-07-01 | CMO East 1 | KLT | Budget
15 | 2021-07-01 | CMO East 1 | KLT | Forecast | 0
15 | 2021-07-01 | CMO East 1 | KLT | Actual | 0
15 | 2021-07-01 | CMO East 1 | Forefront | Budget
15 | 2021-07-01 | CMO East 1 | Forefront | Forecast | 0
15 | 2021-07-01 | CMO East 1 | Forefront | Actual | 0
15 | 2021-07-01 | CMO East 1 | DPF | Budget
15 | 2021-07-01 | CMO East 1 | DPF | Forecast | 0
15 | 2021-07-01 | CMO East 1 | DPF | Actual | 0
15 | 2021-07-01 | CMO East 1 | OMJ | Budget
15 | 2021-07-01 | CMO East 1 | OMJ | Forecast | 0
15 | 2021-07-01 | CMO East 1 | OMJ | Actual | 0
15 | 2021-07-01 | CMO East 1 | DHB Utilities | Budget
15 | 2021-07-01 | CMO East 1 | DHB Utilities | Forecast | 0
15 | 2021-07-01 | CMO East 1 | DHB Utilities | Actual | 0
15 | 2021-07-01 | CMO East 1 | JDT | Budget
15 | 2021-07-01 | CMO East 1 | JDT | Forecast | 0
15 | 2021-07-01 | CMO East 1 | JDT | Actual | 0
15 | 2021-07-01 | CMO East 1 | MURRAY | Budget
15 | 2021-07-01 | CMO East 1 | MURRAY | Forecast | 0
15 | 2021-07-01 | CMO East 1 | MURRAY | Actual | 0
15 | 2021-07-01 | CMO East 2 | Terra Firma | Budget
15 | 2021-07-01 | CMO East 2 | Terra Firma | Forecast | 0
15 | 2021-07-01 | CMO East 2 | Terra Firma | Actual | 0
15 | 2021-07-01 | CMO East 2 | KLT | Budget
15 | 2021-07-01 | CMO East 2 | KLT | Forecast | 0
15 | 2021-07-01 | CMO East 2 | KLT | Actual | 0
15 | 2021-07-01 | CMO East 2 | Forefront | Budget
15 | 2021-07-01 | CMO East 2 | Forefront | Forecast | 0
15 | 2021-07-01 | CMO East 2 | Forefront | Actual | 0
15 | 2021-07-01 | CMO East 2 | DPF | Budget
15 | 2021-07-01 | CMO East 2 | DPF | Forecast | 0
15 | 2021-07-01 | CMO East 2 | DPF | Actual | 0
15 | 2021-07-01 | CMO East 2 | OMJ | Budget
15 | 2021-07-01 | CMO East 2 | OMJ | Forecast | 0
15 | 2021-07-01 | CMO East 2 | OMJ | Actual | 0
15 | 2021-07-01 | CMO East 2 | DHB Utilities | Budget
15 | 2021-07-01 | CMO East 2 | DHB Utilities | Forecast | 0
15 | 2021-07-01 | CMO East 2 | DHB Utilities | Actual | 0
15 | 2021-07-01 | CMO East 2 | JDT | Budget
15 | 2021-07-01 | CMO East 2 | JDT | Forecast | 0
15 | 2021-07-01 | CMO East 2 | JDT | Actual | 0
15 | 2021-07-01 | CMO East 2 | MURRAY | Budget
15 | 2021-07-01 | CMO East 2 | MURRAY | Forecast | 0
15 | 2021-07-01 | CMO East 2 | MURRAY | Actual | 0
15 | 2021-07-01 | West | Terra Firma | Budget
15 | 2021-07-01 | West | Terra Firma | Forecast | 0
15 | 2021-07-01 | West | Terra Firma | Actual | 0
15 | 2021-07-01 | West | KLT | Budget
15 | 2021-07-01 | West | KLT | Forecast | 0
15 | 2021-07-01 | West | KLT | Actual | 0
15 | 2021-07-01 | West | Forefront | Budget
15 | 2021-07-01 | West | Forefront | Forecast | 0
15 | 2021-07-01 | West | Forefront | Actual | 0
15 | 2021-07-01 | West | DPF | Budget
15 | 2021-07-01 | West | DPF | Forecast | 0
15 | 2021-07-01 | West | DPF | Actual | 0
15 | 2021-07-01 | West | OMJ | Budget
15 | 2021-07-01 | West | OMJ | Forecast | 0
15 | 2021-07-01 | West | OMJ | Actual | 0
15 | 2021-07-01 | West | DHB Utilities | Budget
15 | 2021-07-01 | West | DHB Utilities | Forecast | 0
15 | 2021-07-01 | West | DHB Utilities | Actual | 0
15 | 2021-07-01 | West | JDT | Budget
15 | 2021-07-01 | West | JDT | Forecast | 0
15 | 2021-07-01 | West | JDT | Actual | 0
15 | 2021-07-01 | West | MURRAY | Budget
15 | 2021-07-01 | West | MURRAY | Forecast | 0
15 | 2021-07-01 | West | MURRAY | Actual | 0
15 | 2021-07-01 | East | Terra Firma | Budget
15 | 2021-07-01 | East | Terra Firma | Forecast | 0
15 | 2021-07-01 | East | Terra Firma | Actual | 0
15 | 2021-07-01 | East | KLT | Budget
15 | 2021-07-01 | East | KLT | Forecast | 0
15 | 2021-07-01 | East | KLT | Actual | 0
15 | 2021-07-01 | East | Forefront | Budget
15 | 2021-07-01 | East | Forefront | Forecast | 0
15 | 2021-07-01 | East | Forefront | Actual | 0
15 | 2021-07-01 | East | DPF | Budget
15 | 2021-07-01 | East | DPF | Forecast | 0
15 | 2021-07-01 | East | DPF | Actual | 0
15 | 2021-07-01 | East | OMJ | Budget
15 | 2021-07-01 | East | OMJ | Forecast | 0
15 | 2021-07-01 | East | OMJ | Actual | 0
15 | 2021-07-01 | East | DHB Utilities | Budget
15 | 2021-07-01 | East | DHB Utilities | Forecast | 0
15 | 2021-07-01 | East | DHB Utilities | Actual | 0
15 | 2021-07-01 | East | JDT | Budget
15 | 2021-07-01 | East | JDT | Forecast | 0
15 | 2021-07-01 | East | JDT | Actual | 0
15 | 2021-07-01 | East | MURRAY | Budget
15 | 2021-07-01 | East | MURRAY | Forecast | 0
15 | 2021-07-01 | East | MURRAY | Actual | 0
15 | 2021-07-01 | Central | Terra Firma | Budget
15 | 2021-07-01 | Central | Terra Firma | Forecast | 0
15 | 2021-07-01 | Central | Terra Firma | Actual | 0
15 | 2021-07-01 | Central | KLT | Budget
15 | 2021-07-01 | Central | KLT | Forecast | 0
15 | 2021-07-01 | Central | KLT | Actual | 0
15 | 2021-07-01 | Central | Forefront | Budget
15 | 2021-07-01 | Central | Forefront | Forecast | 0
15 | 2021-07-01 | Central | Forefront | Actual | 0
15 | 2021-07-01 | Central | DPF | Budget
15 | 2021-07-01 | Central | DPF | Forecast | 0
15 | 2021-07-01 | Central | DPF | Actual | 0
15 | 2021-07-01 | Central | OMJ | Budget
15 | 2021-07-01 | Central | OMJ | Forecast | 0
15 | 2021-07-01 | Central | OMJ | Actual | 0
15 | 2021-07-01 | Central | DHB Utilities | Budget
15 | 2021-07-01 | Central | DHB Utilities | Forecast | 0
15 | 2021-07-01 | Central | DHB Utilities | Actual | 0
15 | 2021-07-01 | Central | JDT | Budget
15 | 2021-07-01 | Central | JDT | Forecast | 0
15 | 2021-07-01 | Central | JDT | Actual | 0
15 | 2021-07-01 | Central | MURRAY | Budget
15 | 2021-07-01 | Central | MURRAY | Forecast | 0
15 | 2021-07-01 | Central | MURRAY | Actual | 0
15 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Budget
15 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Budget
15 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Budget
15 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Budget
15 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | West | DIRECT MOLE | Budget
15 | 2021-07-01 | West | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | West | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | East | DIRECT MOLE | Budget
15 | 2021-07-01 | East | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | East | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | Central | DIRECT MOLE | Budget
15 | 2021-07-01 | Central | DIRECT MOLE | Forecast | 0
15 | 2021-07-01 | Central | DIRECT MOLE | Actual | 0
15 | 2021-07-01 | CMO West 1 | SQS | Budget
15 | 2021-07-01 | CMO West 1 | SQS | Forecast | 0
15 | 2021-07-01 | CMO West 1 | SQS | Actual | 0
15 | 2021-07-01 | CMO West 2 | SQS | Budget
15 | 2021-07-01 | CMO West 2 | SQS | Forecast | 0
15 | 2021-07-01 | CMO West 2 | SQS | Actual | 0
15 | 2021-07-01 | CMO East 1 | SQS | Budget
15 | 2021-07-01 | CMO East 1 | SQS | Forecast | 0
15 | 2021-07-01 | CMO East 1 | SQS | Actual | 0
15 | 2021-07-01 | CMO East 2 | SQS | Budget
15 | 2021-07-01 | CMO East 2 | SQS | Forecast | 0
15 | 2021-07-01 | CMO East 2 | SQS | Actual | 0
15 | 2021-07-01 | West | SQS | Budget
15 | 2021-07-01 | West | SQS | Forecast | 0
15 | 2021-07-01 | West | SQS | Actual | 0
15 | 2021-07-01 | East | SQS | Budget
15 | 2021-07-01 | East | SQS | Forecast | 0
16 | 2021-07-01 | East | SQS | Actual | 0
16 | 2021-07-01 | Central | SQS | Budget
16 | 2021-07-01 | Central | SQS | Forecast | 0
15 | 2021-07-01 | Central | SQS | Actual | 0
16 | 2021-07-01 | CMO West 1 | Terra Firma | Budget
16 | 2021-07-01 | CMO West 1 | Terra Firma | Forecast | 0
16 | 2021-07-01 | CMO West 1 | Terra Firma | Actual | 0
16 | 2021-07-01 | CMO West 1 | KLT | Budget
16 | 2021-07-01 | CMO West 1 | KLT | Forecast | 0
16 | 2021-07-01 | CMO West 1 | KLT | Actual | 0
16 | 2021-07-01 | CMO West 1 | Forefront | Budget
16 | 2021-07-01 | CMO West 1 | Forefront | Forecast | 0
16 | 2021-07-01 | CMO West 1 | Forefront | Actual | 0
16 | 2021-07-01 | CMO West 1 | DPF | Budget
16 | 2021-07-01 | CMO West 1 | DPF | Forecast | 0
16 | 2021-07-01 | CMO West 1 | DPF | Actual | 0
16 | 2021-07-01 | CMO West 1 | OMJ | Budget
16 | 2021-07-01 | CMO West 1 | OMJ | Forecast | 0
16 | 2021-07-01 | CMO West 1 | OMJ | Actual | 0
16 | 2021-07-01 | CMO West 1 | DHB Utilities | Budget
16 | 2021-07-01 | CMO West 1 | DHB Utilities | Forecast | 0
16 | 2021-07-01 | CMO West 1 | DHB Utilities | Actual | 0
16 | 2021-07-01 | CMO West 1 | JDT | Budget
16 | 2021-07-01 | CMO West 1 | JDT | Forecast | 0
16 | 2021-07-01 | CMO West 1 | JDT | Actual | 0
16 | 2021-07-01 | CMO West 1 | MURRAY | Budget
16 | 2021-07-01 | CMO West 1 | MURRAY | Forecast | 0
16 | 2021-07-01 | CMO West 1 | MURRAY | Actual | 0
16 | 2021-07-01 | CMO West 2 | Terra Firma | Budget
16 | 2021-07-01 | CMO West 2 | Terra Firma | Forecast | 0
16 | 2021-07-01 | CMO West 2 | Terra Firma | Actual | 0
16 | 2021-07-01 | CMO West 2 | KLT | Budget
16 | 2021-07-01 | CMO West 2 | KLT | Forecast | 0
16 | 2021-07-01 | CMO West 2 | KLT | Actual | 0
16 | 2021-07-01 | CMO West 2 | Forefront | Budget
16 | 2021-07-01 | CMO West 2 | Forefront | Forecast | 0
16 | 2021-07-01 | CMO West 2 | Forefront | Actual | 0
16 | 2021-07-01 | CMO West 2 | DPF | Budget
16 | 2021-07-01 | CMO West 2 | DPF | Forecast | 0
16 | 2021-07-01 | CMO West 2 | DPF | Actual | 0
16 | 2021-07-01 | CMO West 2 | OMJ | Budget
16 | 2021-07-01 | CMO West 2 | OMJ | Forecast | 0
16 | 2021-07-01 | CMO West 2 | OMJ | Actual | 0
16 | 2021-07-01 | CMO West 2 | DHB Utilities | Budget
16 | 2021-07-01 | CMO West 2 | DHB Utilities | Forecast | 0
16 | 2021-07-01 | CMO West 2 | DHB Utilities | Actual | 0
16 | 2021-07-01 | CMO West 2 | JDT | Budget
16 | 2021-07-01 | CMO West 2 | JDT | Forecast | 0
16 | 2021-07-01 | CMO West 2 | JDT | Actual | 0
16 | 2021-07-01 | CMO West 2 | MURRAY | Budget
16 | 2021-07-01 | CMO West 2 | MURRAY | Forecast | 0
16 | 2021-07-01 | CMO West 2 | MURRAY | Actual | 0
16 | 2021-07-01 | CMO East 1 | Terra Firma | Budget
16 | 2021-07-01 | CMO East 1 | Terra Firma | Forecast | 0
16 | 2021-07-01 | CMO East 1 | Terra Firma | Actual | 0
16 | 2021-07-01 | CMO East 1 | KLT | Budget
16 | 2021-07-01 | CMO East 1 | KLT | Forecast | 0
16 | 2021-07-01 | CMO East 1 | KLT | Actual | 0
16 | 2021-07-01 | CMO East 1 | Forefront | Budget
16 | 2021-07-01 | CMO East 1 | Forefront | Forecast | 0
16 | 2021-07-01 | CMO East 1 | Forefront | Actual | 0
16 | 2021-07-01 | CMO East 1 | DPF | Budget
16 | 2021-07-01 | CMO East 1 | DPF | Forecast | 0
16 | 2021-07-01 | CMO East 1 | DPF | Actual | 0
16 | 2021-07-01 | CMO East 1 | OMJ | Budget
16 | 2021-07-01 | CMO East 1 | OMJ | Forecast | 0
16 | 2021-07-01 | CMO East 1 | OMJ | Actual | 0
16 | 2021-07-01 | CMO East 1 | DHB Utilities | Budget
16 | 2021-07-01 | CMO East 1 | DHB Utilities | Forecast | 0
16 | 2021-07-01 | CMO East 1 | DHB Utilities | Actual | 0
16 | 2021-07-01 | CMO East 1 | JDT | Budget
16 | 2021-07-01 | CMO East 1 | JDT | Forecast | 0
16 | 2021-07-01 | CMO East 1 | JDT | Actual | 0
16 | 2021-07-01 | CMO East 1 | MURRAY | Budget
16 | 2021-07-01 | CMO East 1 | MURRAY | Forecast | 0
16 | 2021-07-01 | CMO East 1 | MURRAY | Actual | 0
16 | 2021-07-01 | CMO East 2 | Terra Firma | Budget
16 | 2021-07-01 | CMO East 2 | Terra Firma | Forecast | 0
16 | 2021-07-01 | CMO East 2 | Terra Firma | Actual | 0
16 | 2021-07-01 | CMO East 2 | KLT | Budget
16 | 2021-07-01 | CMO East 2 | KLT | Forecast | 0
16 | 2021-07-01 | CMO East 2 | KLT | Actual | 0
16 | 2021-07-01 | CMO East 2 | Forefront | Budget
16 | 2021-07-01 | CMO East 2 | Forefront | Forecast | 0
16 | 2021-07-01 | CMO East 2 | Forefront | Actual | 0
16 | 2021-07-01 | CMO East 2 | DPF | Budget
16 | 2021-07-01 | CMO East 2 | DPF | Forecast | 0
16 | 2021-07-01 | CMO East 2 | DPF | Actual | 0
16 | 2021-07-01 | CMO East 2 | OMJ | Budget
16 | 2021-07-01 | CMO East 2 | OMJ | Forecast | 0
16 | 2021-07-01 | CMO East 2 | OMJ | Actual | 0
16 | 2021-07-01 | CMO East 2 | DHB Utilities | Budget
16 | 2021-07-01 | CMO East 2 | DHB Utilities | Forecast | 0
16 | 2021-07-01 | CMO East 2 | DHB Utilities | Actual | 0
16 | 2021-07-01 | CMO East 2 | JDT | Budget
16 | 2021-07-01 | CMO East 2 | JDT | Forecast | 0
16 | 2021-07-01 | CMO East 2 | JDT | Actual | 0
16 | 2021-07-01 | CMO East 2 | MURRAY | Budget
16 | 2021-07-01 | CMO East 2 | MURRAY | Forecast | 0
16 | 2021-07-01 | CMO East 2 | MURRAY | Actual | 0
16 | 2021-07-01 | West | Terra Firma | Budget
16 | 2021-07-01 | West | Terra Firma | Forecast | 0
16 | 2021-07-01 | West | Terra Firma | Actual | 0
16 | 2021-07-01 | West | KLT | Budget
16 | 2021-07-01 | West | KLT | Forecast | 0
16 | 2021-07-01 | West | KLT | Actual | 0
16 | 2021-07-01 | West | Forefront | Budget
16 | 2021-07-01 | West | Forefront | Forecast | 0
16 | 2021-07-01 | West | Forefront | Actual | 0
16 | 2021-07-01 | West | DPF | Budget
16 | 2021-07-01 | West | DPF | Forecast | 0
16 | 2021-07-01 | West | DPF | Actual | 0
16 | 2021-07-01 | West | OMJ | Budget
16 | 2021-07-01 | West | OMJ | Forecast | 0
16 | 2021-07-01 | West | OMJ | Actual | 0
16 | 2021-07-01 | West | DHB Utilities | Budget
16 | 2021-07-01 | West | DHB Utilities | Forecast | 0
16 | 2021-07-01 | West | DHB Utilities | Actual | 0
16 | 2021-07-01 | West | JDT | Budget
16 | 2021-07-01 | West | JDT | Forecast | 0
16 | 2021-07-01 | West | JDT | Actual | 0
16 | 2021-07-01 | West | MURRAY | Budget
16 | 2021-07-01 | West | MURRAY | Forecast | 0
16 | 2021-07-01 | West | MURRAY | Actual | 0
16 | 2021-07-01 | East | Terra Firma | Budget
16 | 2021-07-01 | East | Terra Firma | Forecast | 0
16 | 2021-07-01 | East | Terra Firma | Actual | 0
16 | 2021-07-01 | East | KLT | Budget
16 | 2021-07-01 | East | KLT | Forecast | 0
16 | 2021-07-01 | East | KLT | Actual | 0
16 | 2021-07-01 | East | Forefront | Budget
16 | 2021-07-01 | East | Forefront | Forecast | 0
16 | 2021-07-01 | East | Forefront | Actual | 0
16 | 2021-07-01 | East | DPF | Budget
16 | 2021-07-01 | East | DPF | Forecast | 0
16 | 2021-07-01 | East | DPF | Actual | 0
16 | 2021-07-01 | East | OMJ | Budget
16 | 2021-07-01 | East | OMJ | Forecast | 0
16 | 2021-07-01 | East | OMJ | Actual | 0
16 | 2021-07-01 | East | DHB Utilities | Budget
16 | 2021-07-01 | East | DHB Utilities | Forecast | 0
16 | 2021-07-01 | East | DHB Utilities | Actual | 0
16 | 2021-07-01 | East | JDT | Budget
16 | 2021-07-01 | East | JDT | Forecast | 0
16 | 2021-07-01 | East | JDT | Actual | 0
16 | 2021-07-01 | East | MURRAY | Budget
16 | 2021-07-01 | East | MURRAY | Forecast | 0
16 | 2021-07-01 | East | MURRAY | Actual | 0
16 | 2021-07-01 | Central | Terra Firma | Budget
16 | 2021-07-01 | Central | Terra Firma | Forecast | 0
16 | 2021-07-01 | Central | Terra Firma | Actual | 0
16 | 2021-07-01 | Central | KLT | Budget
16 | 2021-07-01 | Central | KLT | Forecast | 0
16 | 2021-07-01 | Central | KLT | Actual | 0
16 | 2021-07-01 | Central | Forefront | Budget
16 | 2021-07-01 | Central | Forefront | Forecast | 0
16 | 2021-07-01 | Central | Forefront | Actual | 0
16 | 2021-07-01 | Central | DPF | Budget
16 | 2021-07-01 | Central | DPF | Forecast | 0
16 | 2021-07-01 | Central | DPF | Actual | 0
16 | 2021-07-01 | Central | OMJ | Budget
16 | 2021-07-01 | Central | OMJ | Forecast | 0
16 | 2021-07-01 | Central | OMJ | Actual | 0
16 | 2021-07-01 | Central | DHB Utilities | Budget
16 | 2021-07-01 | Central | DHB Utilities | Forecast | 0
16 | 2021-07-01 | Central | DHB Utilities | Actual | 0
16 | 2021-07-01 | Central | JDT | Budget
16 | 2021-07-01 | Central | JDT | Forecast | 0
16 | 2021-07-01 | Central | JDT | Actual | 0
16 | 2021-07-01 | Central | MURRAY | Budget
16 | 2021-07-01 | Central | MURRAY | Forecast | 0
16 | 2021-07-01 | Central | MURRAY | Actual | 0
16 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Budget
16 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Budget
16 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Budget
16 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Budget
16 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | West | DIRECT MOLE | Budget
16 | 2021-07-01 | West | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | West | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | East | DIRECT MOLE | Budget
16 | 2021-07-01 | East | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | East | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | Central | DIRECT MOLE | Budget
16 | 2021-07-01 | Central | DIRECT MOLE | Forecast | 0
16 | 2021-07-01 | Central | DIRECT MOLE | Actual | 0
16 | 2021-07-01 | CMO West 1 | SQS | Budget
16 | 2021-07-01 | CMO West 1 | SQS | Forecast | 0
16 | 2021-07-01 | CMO West 1 | SQS | Actual | 0
16 | 2021-07-01 | CMO West 2 | SQS | Budget
16 | 2021-07-01 | CMO West 2 | SQS | Forecast | 0
16 | 2021-07-01 | CMO West 2 | SQS | Actual | 0
16 | 2021-07-01 | CMO East 1 | SQS | Budget
16 | 2021-07-01 | CMO East 1 | SQS | Forecast | 0
16 | 2021-07-01 | CMO East 1 | SQS | Actual | 0
16 | 2021-07-01 | CMO East 2 | SQS | Budget
16 | 2021-07-01 | CMO East 2 | SQS | Forecast | 0
16 | 2021-07-01 | CMO East 2 | SQS | Actual | 0
16 | 2021-07-01 | West | SQS | Budget
16 | 2021-07-01 | West | SQS | Forecast | 0
16 | 2021-07-01 | West | SQS | Actual | 0
16 | 2021-07-01 | East | SQS | Budget
16 | 2021-07-01 | East | SQS | Forecast | 0
17 | 2021-07-01 | East | SQS | Actual | 0
17 | 2021-07-01 | Central | SQS | Budget
17 | 2021-07-01 | Central | SQS | Forecast | 0
16 | 2021-07-01 | Central | SQS | Actual | 0
17 | 2021-07-01 | CMO West 1 | Terra Firma | Budget
17 | 2021-07-01 | CMO West 1 | Terra Firma | Forecast | 0
17 | 2021-07-01 | CMO West 1 | Terra Firma | Actual | 0
17 | 2021-07-01 | CMO West 1 | KLT | Budget
17 | 2021-07-01 | CMO West 1 | KLT | Forecast | 0
17 | 2021-07-01 | CMO West 1 | KLT | Actual | 0
17 | 2021-07-01 | CMO West 1 | Forefront | Budget
17 | 2021-07-01 | CMO West 1 | Forefront | Forecast | 0
17 | 2021-07-01 | CMO West 1 | Forefront | Actual | 0
17 | 2021-07-01 | CMO West 1 | DPF | Budget
17 | 2021-07-01 | CMO West 1 | DPF | Forecast | 0
17 | 2021-07-01 | CMO West 1 | DPF | Actual | 0
17 | 2021-07-01 | CMO West 1 | OMJ | Budget
17 | 2021-07-01 | CMO West 1 | OMJ | Forecast | 0
17 | 2021-07-01 | CMO West 1 | OMJ | Actual | 0
17 | 2021-07-01 | CMO West 1 | DHB Utilities | Budget
17 | 2021-07-01 | CMO West 1 | DHB Utilities | Forecast | 0
17 | 2021-07-01 | CMO West 1 | DHB Utilities | Actual | 0
17 | 2021-07-01 | CMO West 1 | JDT | Budget
17 | 2021-07-01 | CMO West 1 | JDT | Forecast | 0
17 | 2021-07-01 | CMO West 1 | JDT | Actual | 0
17 | 2021-07-01 | CMO West 1 | MURRAY | Budget
17 | 2021-07-01 | CMO West 1 | MURRAY | Forecast | 0
17 | 2021-07-01 | CMO West 1 | MURRAY | Actual | 0
17 | 2021-07-01 | CMO West 2 | Terra Firma | Budget
17 | 2021-07-01 | CMO West 2 | Terra Firma | Forecast | 0
17 | 2021-07-01 | CMO West 2 | Terra Firma | Actual | 0
17 | 2021-07-01 | CMO West 2 | KLT | Budget
17 | 2021-07-01 | CMO West 2 | KLT | Forecast | 0
17 | 2021-07-01 | CMO West 2 | KLT | Actual | 0
17 | 2021-07-01 | CMO West 2 | Forefront | Budget
17 | 2021-07-01 | CMO West 2 | Forefront | Forecast | 0
17 | 2021-07-01 | CMO West 2 | Forefront | Actual | 0
17 | 2021-07-01 | CMO West 2 | DPF | Budget
17 | 2021-07-01 | CMO West 2 | DPF | Forecast | 0
17 | 2021-07-01 | CMO West 2 | DPF | Actual | 0
17 | 2021-07-01 | CMO West 2 | OMJ | Budget
17 | 2021-07-01 | CMO West 2 | OMJ | Forecast | 0
17 | 2021-07-01 | CMO West 2 | OMJ | Actual | 0
17 | 2021-07-01 | CMO West 2 | DHB Utilities | Budget
17 | 2021-07-01 | CMO West 2 | DHB Utilities | Forecast | 0
17 | 2021-07-01 | CMO West 2 | DHB Utilities | Actual | 0
17 | 2021-07-01 | CMO West 2 | JDT | Budget
17 | 2021-07-01 | CMO West 2 | JDT | Forecast | 0
17 | 2021-07-01 | CMO West 2 | JDT | Actual | 0
17 | 2021-07-01 | CMO West 2 | MURRAY | Budget
17 | 2021-07-01 | CMO West 2 | MURRAY | Forecast | 0
17 | 2021-07-01 | CMO West 2 | MURRAY | Actual | 0
17 | 2021-07-01 | CMO East 1 | Terra Firma | Budget
17 | 2021-07-01 | CMO East 1 | Terra Firma | Forecast | 0
17 | 2021-07-01 | CMO East 1 | Terra Firma | Actual | 0
17 | 2021-07-01 | CMO East 1 | KLT | Budget
17 | 2021-07-01 | CMO East 1 | KLT | Forecast | 0
17 | 2021-07-01 | CMO East 1 | KLT | Actual | 0
17 | 2021-07-01 | CMO East 1 | Forefront | Budget
17 | 2021-07-01 | CMO East 1 | Forefront | Forecast | 0
17 | 2021-07-01 | CMO East 1 | Forefront | Actual | 0
17 | 2021-07-01 | CMO East 1 | DPF | Budget
17 | 2021-07-01 | CMO East 1 | DPF | Forecast | 0
17 | 2021-07-01 | CMO East 1 | DPF | Actual | 0
17 | 2021-07-01 | CMO East 1 | OMJ | Budget
17 | 2021-07-01 | CMO East 1 | OMJ | Forecast | 0
17 | 2021-07-01 | CMO East 1 | OMJ | Actual | 0
17 | 2021-07-01 | CMO East 1 | DHB Utilities | Budget
17 | 2021-07-01 | CMO East 1 | DHB Utilities | Forecast | 0
17 | 2021-07-01 | CMO East 1 | DHB Utilities | Actual | 0
17 | 2021-07-01 | CMO East 1 | JDT | Budget
17 | 2021-07-01 | CMO East 1 | JDT | Forecast | 0
17 | 2021-07-01 | CMO East 1 | JDT | Actual | 0
17 | 2021-07-01 | CMO East 1 | MURRAY | Budget
17 | 2021-07-01 | CMO East 1 | MURRAY | Forecast | 0
17 | 2021-07-01 | CMO East 1 | MURRAY | Actual | 0
17 | 2021-07-01 | CMO East 2 | Terra Firma | Budget
17 | 2021-07-01 | CMO East 2 | Terra Firma | Forecast | 0
17 | 2021-07-01 | CMO East 2 | Terra Firma | Actual | 0
17 | 2021-07-01 | CMO East 2 | KLT | Budget
17 | 2021-07-01 | CMO East 2 | KLT | Forecast | 0
17 | 2021-07-01 | CMO East 2 | KLT | Actual | 0
17 | 2021-07-01 | CMO East 2 | Forefront | Budget
17 | 2021-07-01 | CMO East 2 | Forefront | Forecast | 0
17 | 2021-07-01 | CMO East 2 | Forefront | Actual | 0
17 | 2021-07-01 | CMO East 2 | DPF | Budget
17 | 2021-07-01 | CMO East 2 | DPF | Forecast | 0
17 | 2021-07-01 | CMO East 2 | DPF | Actual | 0
17 | 2021-07-01 | CMO East 2 | OMJ | Budget
17 | 2021-07-01 | CMO East 2 | OMJ | Forecast | 0
17 | 2021-07-01 | CMO East 2 | OMJ | Actual | 0
17 | 2021-07-01 | CMO East 2 | DHB Utilities | Budget
17 | 2021-07-01 | CMO East 2 | DHB Utilities | Forecast | 0
17 | 2021-07-01 | CMO East 2 | DHB Utilities | Actual | 0
17 | 2021-07-01 | CMO East 2 | JDT | Budget
17 | 2021-07-01 | CMO East 2 | JDT | Forecast | 0
17 | 2021-07-01 | CMO East 2 | JDT | Actual | 0
17 | 2021-07-01 | CMO East 2 | MURRAY | Budget
17 | 2021-07-01 | CMO East 2 | MURRAY | Forecast | 0
17 | 2021-07-01 | CMO East 2 | MURRAY | Actual | 0
17 | 2021-07-01 | West | Terra Firma | Budget
17 | 2021-07-01 | West | Terra Firma | Forecast | 0
17 | 2021-07-01 | West | Terra Firma | Actual | 0
17 | 2021-07-01 | West | KLT | Budget
17 | 2021-07-01 | West | KLT | Forecast | 0
17 | 2021-07-01 | West | KLT | Actual | 0
17 | 2021-07-01 | West | Forefront | Budget
17 | 2021-07-01 | West | Forefront | Forecast | 0
17 | 2021-07-01 | West | Forefront | Actual | 0
17 | 2021-07-01 | West | DPF | Budget
17 | 2021-07-01 | West | DPF | Forecast | 0
17 | 2021-07-01 | West | DPF | Actual | 0
17 | 2021-07-01 | West | OMJ | Budget
17 | 2021-07-01 | West | OMJ | Forecast | 0
17 | 2021-07-01 | West | OMJ | Actual | 0
17 | 2021-07-01 | West | DHB Utilities | Budget
17 | 2021-07-01 | West | DHB Utilities | Forecast | 0
17 | 2021-07-01 | West | DHB Utilities | Actual | 0
17 | 2021-07-01 | West | JDT | Budget
17 | 2021-07-01 | West | JDT | Forecast | 0
17 | 2021-07-01 | West | JDT | Actual | 0
17 | 2021-07-01 | West | MURRAY | Budget
17 | 2021-07-01 | West | MURRAY | Forecast | 0
17 | 2021-07-01 | West | MURRAY | Actual | 0
17 | 2021-07-01 | East | Terra Firma | Budget
17 | 2021-07-01 | East | Terra Firma | Forecast | 0
17 | 2021-07-01 | East | Terra Firma | Actual | 0
17 | 2021-07-01 | East | KLT | Budget
17 | 2021-07-01 | East | KLT | Forecast | 0
17 | 2021-07-01 | East | KLT | Actual | 0
17 | 2021-07-01 | East | Forefront | Budget
17 | 2021-07-01 | East | Forefront | Forecast | 0
17 | 2021-07-01 | East | Forefront | Actual | 0
17 | 2021-07-01 | East | DPF | Budget
17 | 2021-07-01 | East | DPF | Forecast | 0
17 | 2021-07-01 | East | DPF | Actual | 0
17 | 2021-07-01 | East | OMJ | Budget
17 | 2021-07-01 | East | OMJ | Forecast | 0
17 | 2021-07-01 | East | OMJ | Actual | 0
17 | 2021-07-01 | East | DHB Utilities | Budget
17 | 2021-07-01 | East | DHB Utilities | Forecast | 0
17 | 2021-07-01 | East | DHB Utilities | Actual | 0
17 | 2021-07-01 | East | JDT | Budget
17 | 2021-07-01 | East | JDT | Forecast | 0
17 | 2021-07-01 | East | JDT | Actual | 0
17 | 2021-07-01 | East | MURRAY | Budget
17 | 2021-07-01 | East | MURRAY | Forecast | 0
17 | 2021-07-01 | East | MURRAY | Actual | 0
17 | 2021-07-01 | Central | Terra Firma | Budget
17 | 2021-07-01 | Central | Terra Firma | Forecast | 0
17 | 2021-07-01 | Central | Terra Firma | Actual | 0
17 | 2021-07-01 | Central | KLT | Budget
17 | 2021-07-01 | Central | KLT | Forecast | 0
17 | 2021-07-01 | Central | KLT | Actual | 0
17 | 2021-07-01 | Central | Forefront | Budget
17 | 2021-07-01 | Central | Forefront | Forecast | 0
17 | 2021-07-01 | Central | Forefront | Actual | 0
17 | 2021-07-01 | Central | DPF | Budget
17 | 2021-07-01 | Central | DPF | Forecast | 0
17 | 2021-07-01 | Central | DPF | Actual | 0
17 | 2021-07-01 | Central | OMJ | Budget
17 | 2021-07-01 | Central | OMJ | Forecast | 0
17 | 2021-07-01 | Central | OMJ | Actual | 0
17 | 2021-07-01 | Central | DHB Utilities | Budget
17 | 2021-07-01 | Central | DHB Utilities | Forecast | 0
17 | 2021-07-01 | Central | DHB Utilities | Actual | 0
17 | 2021-07-01 | Central | JDT | Budget
17 | 2021-07-01 | Central | JDT | Forecast | 0
17 | 2021-07-01 | Central | JDT | Actual | 0
17 | 2021-07-01 | Central | MURRAY | Budget
17 | 2021-07-01 | Central | MURRAY | Forecast | 0
17 | 2021-07-01 | Central | MURRAY | Actual | 0
17 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Budget
17 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Budget
17 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Budget
17 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Budget
17 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | West | DIRECT MOLE | Budget
17 | 2021-07-01 | West | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | West | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | East | DIRECT MOLE | Budget
17 | 2021-07-01 | East | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | East | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | Central | DIRECT MOLE | Budget
17 | 2021-07-01 | Central | DIRECT MOLE | Forecast | 0
17 | 2021-07-01 | Central | DIRECT MOLE | Actual | 0
17 | 2021-07-01 | CMO West 1 | SQS | Budget
17 | 2021-07-01 | CMO West 1 | SQS | Forecast | 0
17 | 2021-07-01 | CMO West 1 | SQS | Actual | 0
17 | 2021-07-01 | CMO West 2 | SQS | Budget
17 | 2021-07-01 | CMO West 2 | SQS | Forecast | 0
17 | 2021-07-01 | CMO West 2 | SQS | Actual | 0
17 | 2021-07-01 | CMO East 1 | SQS | Budget
17 | 2021-07-01 | CMO East 1 | SQS | Forecast | 0
17 | 2021-07-01 | CMO East 1 | SQS | Actual | 0
17 | 2021-07-01 | CMO East 2 | SQS | Budget
17 | 2021-07-01 | CMO East 2 | SQS | Forecast | 0
17 | 2021-07-01 | CMO East 2 | SQS | Actual | 0
17 | 2021-07-01 | West | SQS | Budget
17 | 2021-07-01 | West | SQS | Forecast | 0
17 | 2021-07-01 | West | SQS | Actual | 0
17 | 2021-07-01 | East | SQS | Budget
17 | 2021-07-01 | East | SQS | Forecast | 0
18 | 2021-07-01 | East | SQS | Actual | 0
18 | 2021-07-01 | Central | SQS | Budget
18 | 2021-07-01 | Central | SQS | Forecast | 0
17 | 2021-07-01 | Central | SQS | Actual | 0
18 | 2021-07-01 | CMO West 1 | Terra Firma | Budget
18 | 2021-07-01 | CMO West 1 | Terra Firma | Forecast | 0
18 | 2021-07-01 | CMO West 1 | Terra Firma | Actual | 0
18 | 2021-07-01 | CMO West 1 | KLT | Budget
18 | 2021-07-01 | CMO West 1 | KLT | Forecast | 0
18 | 2021-07-01 | CMO West 1 | KLT | Actual | 0
18 | 2021-07-01 | CMO West 1 | Forefront | Budget
18 | 2021-07-01 | CMO West 1 | Forefront | Forecast | 0
18 | 2021-07-01 | CMO West 1 | Forefront | Actual | 0
18 | 2021-07-01 | CMO West 1 | DPF | Budget
18 | 2021-07-01 | CMO West 1 | DPF | Forecast | 0
18 | 2021-07-01 | CMO West 1 | DPF | Actual | 0
18 | 2021-07-01 | CMO West 1 | OMJ | Budget
18 | 2021-07-01 | CMO West 1 | OMJ | Forecast | 0
18 | 2021-07-01 | CMO West 1 | OMJ | Actual | 0
18 | 2021-07-01 | CMO West 1 | DHB Utilities | Budget
18 | 2021-07-01 | CMO West 1 | DHB Utilities | Forecast | 0
18 | 2021-07-01 | CMO West 1 | DHB Utilities | Actual | 0
18 | 2021-07-01 | CMO West 1 | JDT | Budget
18 | 2021-07-01 | CMO West 1 | JDT | Forecast | 0
18 | 2021-07-01 | CMO West 1 | JDT | Actual | 0
18 | 2021-07-01 | CMO West 1 | MURRAY | Budget
18 | 2021-07-01 | CMO West 1 | MURRAY | Forecast | 0
18 | 2021-07-01 | CMO West 1 | MURRAY | Actual | 0
18 | 2021-07-01 | CMO West 2 | Terra Firma | Budget
18 | 2021-07-01 | CMO West 2 | Terra Firma | Forecast | 0
18 | 2021-07-01 | CMO West 2 | Terra Firma | Actual | 0
18 | 2021-07-01 | CMO West 2 | KLT | Budget
18 | 2021-07-01 | CMO West 2 | KLT | Forecast | 0
18 | 2021-07-01 | CMO West 2 | KLT | Actual | 0
18 | 2021-07-01 | CMO West 2 | Forefront | Budget
18 | 2021-07-01 | CMO West 2 | Forefront | Forecast | 0
18 | 2021-07-01 | CMO West 2 | Forefront | Actual | 0
18 | 2021-07-01 | CMO West 2 | DPF | Budget
18 | 2021-07-01 | CMO West 2 | DPF | Forecast | 0
18 | 2021-07-01 | CMO West 2 | DPF | Actual | 0
18 | 2021-07-01 | CMO West 2 | OMJ | Budget
18 | 2021-07-01 | CMO West 2 | OMJ | Forecast | 0
18 | 2021-07-01 | CMO West 2 | OMJ | Actual | 0
18 | 2021-07-01 | CMO West 2 | DHB Utilities | Budget
18 | 2021-07-01 | CMO West 2 | DHB Utilities | Forecast | 0
18 | 2021-07-01 | CMO West 2 | DHB Utilities | Actual | 0
18 | 2021-07-01 | CMO West 2 | JDT | Budget
18 | 2021-07-01 | CMO West 2 | JDT | Forecast | 0
18 | 2021-07-01 | CMO West 2 | JDT | Actual | 0
18 | 2021-07-01 | CMO West 2 | MURRAY | Budget
18 | 2021-07-01 | CMO West 2 | MURRAY | Forecast | 0
18 | 2021-07-01 | CMO West 2 | MURRAY | Actual | 0
18 | 2021-07-01 | CMO East 1 | Terra Firma | Budget
18 | 2021-07-01 | CMO East 1 | Terra Firma | Forecast | 0
18 | 2021-07-01 | CMO East 1 | Terra Firma | Actual | 0
18 | 2021-07-01 | CMO East 1 | KLT | Budget
18 | 2021-07-01 | CMO East 1 | KLT | Forecast | 0
18 | 2021-07-01 | CMO East 1 | KLT | Actual | 0
18 | 2021-07-01 | CMO East 1 | Forefront | Budget
18 | 2021-07-01 | CMO East 1 | Forefront | Forecast | 0
18 | 2021-07-01 | CMO East 1 | Forefront | Actual | 0
18 | 2021-07-01 | CMO East 1 | DPF | Budget
18 | 2021-07-01 | CMO East 1 | DPF | Forecast | 0
18 | 2021-07-01 | CMO East 1 | DPF | Actual | 0
18 | 2021-07-01 | CMO East 1 | OMJ | Budget
18 | 2021-07-01 | CMO East 1 | OMJ | Forecast | 0
18 | 2021-07-01 | CMO East 1 | OMJ | Actual | 0
18 | 2021-07-01 | CMO East 1 | DHB Utilities | Budget
18 | 2021-07-01 | CMO East 1 | DHB Utilities | Forecast | 0
18 | 2021-07-01 | CMO East 1 | DHB Utilities | Actual | 0
18 | 2021-07-01 | CMO East 1 | JDT | Budget
18 | 2021-07-01 | CMO East 1 | JDT | Forecast | 0
18 | 2021-07-01 | CMO East 1 | JDT | Actual | 0
18 | 2021-07-01 | CMO East 1 | MURRAY | Budget
18 | 2021-07-01 | CMO East 1 | MURRAY | Forecast | 0
18 | 2021-07-01 | CMO East 1 | MURRAY | Actual | 0
18 | 2021-07-01 | CMO East 2 | Terra Firma | Budget
18 | 2021-07-01 | CMO East 2 | Terra Firma | Forecast | 0
18 | 2021-07-01 | CMO East 2 | Terra Firma | Actual | 0
18 | 2021-07-01 | CMO East 2 | KLT | Budget
18 | 2021-07-01 | CMO East 2 | KLT | Forecast | 0
18 | 2021-07-01 | CMO East 2 | KLT | Actual | 0
18 | 2021-07-01 | CMO East 2 | Forefront | Budget
18 | 2021-07-01 | CMO East 2 | Forefront | Forecast | 0
18 | 2021-07-01 | CMO East 2 | Forefront | Actual | 0
18 | 2021-07-01 | CMO East 2 | DPF | Budget
18 | 2021-07-01 | CMO East 2 | DPF | Forecast | 0
18 | 2021-07-01 | CMO East 2 | DPF | Actual | 0
18 | 2021-07-01 | CMO East 2 | OMJ | Budget
18 | 2021-07-01 | CMO East 2 | OMJ | Forecast | 0
18 | 2021-07-01 | CMO East 2 | OMJ | Actual | 0
18 | 2021-07-01 | CMO East 2 | DHB Utilities | Budget
18 | 2021-07-01 | CMO East 2 | DHB Utilities | Forecast | 0
18 | 2021-07-01 | CMO East 2 | DHB Utilities | Actual | 0
18 | 2021-07-01 | CMO East 2 | JDT | Budget
18 | 2021-07-01 | CMO East 2 | JDT | Forecast | 0
18 | 2021-07-01 | CMO East 2 | JDT | Actual | 0
18 | 2021-07-01 | CMO East 2 | MURRAY | Budget
18 | 2021-07-01 | CMO East 2 | MURRAY | Forecast | 0
18 | 2021-07-01 | CMO East 2 | MURRAY | Actual | 0
18 | 2021-07-01 | West | Terra Firma | Budget
18 | 2021-07-01 | West | Terra Firma | Forecast | 0
18 | 2021-07-01 | West | Terra Firma | Actual | 0
18 | 2021-07-01 | West | KLT | Budget
18 | 2021-07-01 | West | KLT | Forecast | 0
18 | 2021-07-01 | West | KLT | Actual | 0
18 | 2021-07-01 | West | Forefront | Budget
18 | 2021-07-01 | West | Forefront | Forecast | 0
18 | 2021-07-01 | West | Forefront | Actual | 0
18 | 2021-07-01 | West | DPF | Budget
18 | 2021-07-01 | West | DPF | Forecast | 0
18 | 2021-07-01 | West | DPF | Actual | 0
18 | 2021-07-01 | West | OMJ | Budget
18 | 2021-07-01 | West | OMJ | Forecast | 0
18 | 2021-07-01 | West | OMJ | Actual | 0
18 | 2021-07-01 | West | DHB Utilities | Budget
18 | 2021-07-01 | West | DHB Utilities | Forecast | 0
18 | 2021-07-01 | West | DHB Utilities | Actual | 0
18 | 2021-07-01 | West | JDT | Budget
18 | 2021-07-01 | West | JDT | Forecast | 0
18 | 2021-07-01 | West | JDT | Actual | 0
18 | 2021-07-01 | West | MURRAY | Budget
18 | 2021-07-01 | West | MURRAY | Forecast | 0
18 | 2021-07-01 | West | MURRAY | Actual | 0
18 | 2021-07-01 | East | Terra Firma | Budget
18 | 2021-07-01 | East | Terra Firma | Forecast | 0
18 | 2021-07-01 | East | Terra Firma | Actual | 0
18 | 2021-07-01 | East | KLT | Budget
18 | 2021-07-01 | East | KLT | Forecast | 0
18 | 2021-07-01 | East | KLT | Actual | 0
18 | 2021-07-01 | East | Forefront | Budget
18 | 2021-07-01 | East | Forefront | Forecast | 0
18 | 2021-07-01 | East | Forefront | Actual | 0
18 | 2021-07-01 | East | DPF | Budget
18 | 2021-07-01 | East | DPF | Forecast | 0
18 | 2021-07-01 | East | DPF | Actual | 0
18 | 2021-07-01 | East | OMJ | Budget
18 | 2021-07-01 | East | OMJ | Forecast | 0
18 | 2021-07-01 | East | OMJ | Actual | 0
18 | 2021-07-01 | East | DHB Utilities | Budget
18 | 2021-07-01 | East | DHB Utilities | Forecast | 0
18 | 2021-07-01 | East | DHB Utilities | Actual | 0
18 | 2021-07-01 | East | JDT | Budget
18 | 2021-07-01 | East | JDT | Forecast | 0
18 | 2021-07-01 | East | JDT | Actual | 0
18 | 2021-07-01 | East | MURRAY | Budget
18 | 2021-07-01 | East | MURRAY | Forecast | 0
18 | 2021-07-01 | East | MURRAY | Actual | 0
18 | 2021-07-01 | Central | Terra Firma | Budget
18 | 2021-07-01 | Central | Terra Firma | Forecast | 0
18 | 2021-07-01 | Central | Terra Firma | Actual | 0
18 | 2021-07-01 | Central | KLT | Budget
18 | 2021-07-01 | Central | KLT | Forecast | 0
18 | 2021-07-01 | Central | KLT | Actual | 0
18 | 2021-07-01 | Central | Forefront | Budget
18 | 2021-07-01 | Central | Forefront | Forecast | 0
18 | 2021-07-01 | Central | Forefront | Actual | 0
18 | 2021-07-01 | Central | DPF | Budget
18 | 2021-07-01 | Central | DPF | Forecast | 0
18 | 2021-07-01 | Central | DPF | Actual | 0
18 | 2021-07-01 | Central | OMJ | Budget
18 | 2021-07-01 | Central | OMJ | Forecast | 0
18 | 2021-07-01 | Central | OMJ | Actual | 0
18 | 2021-07-01 | Central | DHB Utilities | Budget
18 | 2021-07-01 | Central | DHB Utilities | Forecast | 0
18 | 2021-07-01 | Central | DHB Utilities | Actual | 0
18 | 2021-07-01 | Central | JDT | Budget
18 | 2021-07-01 | Central | JDT | Forecast | 0
18 | 2021-07-01 | Central | JDT | Actual | 0
18 | 2021-07-01 | Central | MURRAY | Budget
18 | 2021-07-01 | Central | MURRAY | Forecast | 0
18 | 2021-07-01 | Central | MURRAY | Actual | 0
18 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Budget
18 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | CMO West 1 | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Budget
18 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | CMO West 2 | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Budget
18 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | CMO East 1 | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Budget
18 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | CMO East 2 | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | West | DIRECT MOLE | Budget
18 | 2021-07-01 | West | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | West | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | East | DIRECT MOLE | Budget
18 | 2021-07-01 | East | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | East | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | Central | DIRECT MOLE | Budget
18 | 2021-07-01 | Central | DIRECT MOLE | Forecast | 0
18 | 2021-07-01 | Central | DIRECT MOLE | Actual | 0
18 | 2021-07-01 | CMO West 1 | SQS | Budget
18 | 2021-07-01 | CMO West 1 | SQS | Forecast | 0
18 | 2021-07-01 | CMO West 1 | SQS | Actual | 0
18 | 2021-07-01 | CMO West 2 | SQS | Budget
18 | 2021-07-01 | CMO West 2 | SQS | Forecast | 0
18 | 2021-07-01 | CMO West 2 | SQS | Actual | 0
18 | 2021-07-01 | CMO East 1 | SQS | Budget
18 | 2021-07-01 | CMO East 1 | SQS | Forecast | 0
18 | 2021-07-01 | CMO East 1 | SQS | Actual | 0
18 | 2021-07-01 | CMO East 2 | SQS | Budget
18 | 2021-07-01 | CMO East 2 | SQS | Forecast | 0
18 | 2021-07-01 | CMO East 2 | SQS | Actual | 0
18 | 2021-07-01 | West | SQS | Budget
18 | 2021-07-01 | West | SQS | Forecast | 0
18 | 2021-07-01 | West | SQS | Actual | 0
18 | 2021-07-01 | East | SQS | Budget
18 | 2021-07-01 | East | SQS | Forecast | 0
19 | 2021-07-01 | East | SQS | Actual | 0
19 | 2021-07-01 | Central | SQS | Budget
19 | 2021-07-01 | Central | SQS | Forecast | 0
18 | 2021-07-01 | Central | SQS | Actual | 0
19 | 2021-08-01 | CMO West 1 | Terra Firma | Budget
19 | 2021-08-01 | CMO West 1 | Terra Firma | Forecast | 0
19 | 2021-08-01 | CMO West 1 | Terra Firma | Actual | 0
19 | 2021-08-01 | CMO West 1 | KLT | Budget
19 | 2021-08-01 | CMO West 1 | KLT | Forecast | 0
19 | 2021-08-01 | CMO West 1 | KLT | Actual | 0
19 | 2021-08-01 | CMO West 1 | Forefront | Budget
19 | 2021-08-01 | CMO West 1 | Forefront | Forecast | 0
19 | 2021-08-01 | CMO West 1 | Forefront | Actual | 0
19 | 2021-08-01 | CMO West 1 | DPF | Budget
19 | 2021-08-01 | CMO West 1 | DPF | Forecast | 0
19 | 2021-08-01 | CMO West 1 | DPF | Actual | 0
19 | 2021-08-01 | CMO West 1 | OMJ | Budget
19 | 2021-08-01 | CMO West 1 | OMJ | Forecast | 0
19 | 2021-08-01 | CMO West 1 | OMJ | Actual | 0
19 | 2021-08-01 | CMO West 1 | DHB Utilities | Budget
19 | 2021-08-01 | CMO West 1 | DHB Utilities | Forecast | 0
19 | 2021-08-01 | CMO West 1 | DHB Utilities | Actual | 0
19 | 2021-08-01 | CMO West 1 | JDT | Budget
19 | 2021-08-01 | CMO West 1 | JDT | Forecast | 0
19 | 2021-08-01 | CMO West 1 | JDT | Actual | 0
19 | 2021-08-01 | CMO West 1 | MURRAY | Budget
19 | 2021-08-01 | CMO West 1 | MURRAY | Forecast | 0
19 | 2021-08-01 | CMO West 1 | MURRAY | Actual | 0
19 | 2021-08-01 | CMO West 2 | Terra Firma | Budget
19 | 2021-08-01 | CMO West 2 | Terra Firma | Forecast | 0
19 | 2021-08-01 | CMO West 2 | Terra Firma | Actual | 0
19 | 2021-08-01 | CMO West 2 | KLT | Budget
19 | 2021-08-01 | CMO West 2 | KLT | Forecast | 0
19 | 2021-08-01 | CMO West 2 | KLT | Actual | 0
19 | 2021-08-01 | CMO West 2 | Forefront | Budget
19 | 2021-08-01 | CMO West 2 | Forefront | Forecast | 0
19 | 2021-08-01 | CMO West 2 | Forefront | Actual | 0
19 | 2021-08-01 | CMO West 2 | DPF | Budget
19 | 2021-08-01 | CMO West 2 | DPF | Forecast | 0
19 | 2021-08-01 | CMO West 2 | DPF | Actual | 0
19 | 2021-08-01 | CMO West 2 | OMJ | Budget
19 | 2021-08-01 | CMO West 2 | OMJ | Forecast | 0
19 | 2021-08-01 | CMO West 2 | OMJ | Actual | 0
19 | 2021-08-01 | CMO West 2 | DHB Utilities | Budget
19 | 2021-08-01 | CMO West 2 | DHB Utilities | Forecast | 0
19 | 2021-08-01 | CMO West 2 | DHB Utilities | Actual | 0
19 | 2021-08-01 | CMO West 2 | JDT | Budget
19 | 2021-08-01 | CMO West 2 | JDT | Forecast | 0
19 | 2021-08-01 | CMO West 2 | JDT | Actual | 0
19 | 2021-08-01 | CMO West 2 | MURRAY | Budget
19 | 2021-08-01 | CMO West 2 | MURRAY | Forecast | 0
19 | 2021-08-01 | CMO West 2 | MURRAY | Actual | 0
19 | 2021-08-01 | CMO East 1 | Terra Firma | Budget
19 | 2021-08-01 | CMO East 1 | Terra Firma | Forecast | 0
19 | 2021-08-01 | CMO East 1 | Terra Firma | Actual | 0
19 | 2021-08-01 | CMO East 1 | KLT | Budget
19 | 2021-08-01 | CMO East 1 | KLT | Forecast | 0
19 | 2021-08-01 | CMO East 1 | KLT | Actual | 0
19 | 2021-08-01 | CMO East 1 | Forefront | Budget
19 | 2021-08-01 | CMO East 1 | Forefront | Forecast | 0
19 | 2021-08-01 | CMO East 1 | Forefront | Actual | 0
19 | 2021-08-01 | CMO East 1 | DPF | Budget
19 | 2021-08-01 | CMO East 1 | DPF | Forecast | 0
19 | 2021-08-01 | CMO East 1 | DPF | Actual | 0
19 | 2021-08-01 | CMO East 1 | OMJ | Budget
19 | 2021-08-01 | CMO East 1 | OMJ | Forecast | 0
19 | 2021-08-01 | CMO East 1 | OMJ | Actual | 0
19 | 2021-08-01 | CMO East 1 | DHB Utilities | Budget
19 | 2021-08-01 | CMO East 1 | DHB Utilities | Forecast | 0
19 | 2021-08-01 | CMO East 1 | DHB Utilities | Actual | 0
19 | 2021-08-01 | CMO East 1 | JDT | Budget
19 | 2021-08-01 | CMO East 1 | JDT | Forecast | 0
19 | 2021-08-01 | CMO East 1 | JDT | Actual | 0
19 | 2021-08-01 | CMO East 1 | MURRAY | Budget
19 | 2021-08-01 | CMO East 1 | MURRAY | Forecast | 0
19 | 2021-08-01 | CMO East 1 | MURRAY | Actual | 0
19 | 2021-08-01 | CMO East 2 | Terra Firma | Budget
19 | 2021-08-01 | CMO East 2 | Terra Firma | Forecast | 0
19 | 2021-08-01 | CMO East 2 | Terra Firma | Actual | 0
19 | 2021-08-01 | CMO East 2 | KLT | Budget
19 | 2021-08-01 | CMO East 2 | KLT | Forecast | 0
19 | 2021-08-01 | CMO East 2 | KLT | Actual | 0
19 | 2021-08-01 | CMO East 2 | Forefront | Budget
19 | 2021-08-01 | CMO East 2 | Forefront | Forecast | 0
19 | 2021-08-01 | CMO East 2 | Forefront | Actual | 0
19 | 2021-08-01 | CMO East 2 | DPF | Budget
19 | 2021-08-01 | CMO East 2 | DPF | Forecast | 0
19 | 2021-08-01 | CMO East 2 | DPF | Actual | 0
19 | 2021-08-01 | CMO East 2 | OMJ | Budget
19 | 2021-08-01 | CMO East 2 | OMJ | Forecast | 0
19 | 2021-08-01 | CMO East 2 | OMJ | Actual | 0
19 | 2021-08-01 | CMO East 2 | DHB Utilities | Budget
19 | 2021-08-01 | CMO East 2 | DHB Utilities | Forecast | 0
19 | 2021-08-01 | CMO East 2 | DHB Utilities | Actual | 0
19 | 2021-08-01 | CMO East 2 | JDT | Budget
19 | 2021-08-01 | CMO East 2 | JDT | Forecast | 0
19 | 2021-08-01 | CMO East 2 | JDT | Actual | 0
19 | 2021-08-01 | CMO East 2 | MURRAY | Budget
19 | 2021-08-01 | CMO East 2 | MURRAY | Forecast | 0
19 | 2021-08-01 | CMO East 2 | MURRAY | Actual | 0
19 | 2021-08-01 | West | Terra Firma | Budget
19 | 2021-08-01 | West | Terra Firma | Forecast | 0
19 | 2021-08-01 | West | Terra Firma | Actual | 0
19 | 2021-08-01 | West | KLT | Budget
19 | 2021-08-01 | West | KLT | Forecast | 0
19 | 2021-08-01 | West | KLT | Actual | 0
19 | 2021-08-01 | West | Forefront | Budget
19 | 2021-08-01 | West | Forefront | Forecast | 0
19 | 2021-08-01 | West | Forefront | Actual | 0
19 | 2021-08-01 | West | DPF | Budget
19 | 2021-08-01 | West | DPF | Forecast | 0
19 | 2021-08-01 | West | DPF | Actual | 0
19 | 2021-08-01 | West | OMJ | Budget
19 | 2021-08-01 | West | OMJ | Forecast | 0
19 | 2021-08-01 | West | OMJ | Actual | 0
19 | 2021-08-01 | West | DHB Utilities | Budget
19 | 2021-08-01 | West | DHB Utilities | Forecast | 0
19 | 2021-08-01 | West | DHB Utilities | Actual | 0
19 | 2021-08-01 | West | JDT | Budget
19 | 2021-08-01 | West | JDT | Forecast | 0
19 | 2021-08-01 | West | JDT | Actual | 0
19 | 2021-08-01 | West | MURRAY | Budget
19 | 2021-08-01 | West | MURRAY | Forecast | 0
19 | 2021-08-01 | West | MURRAY | Actual | 0
19 | 2021-08-01 | East | Terra Firma | Budget
19 | 2021-08-01 | East | Terra Firma | Forecast | 0
19 | 2021-08-01 | East | Terra Firma | Actual | 0
19 | 2021-08-01 | East | KLT | Budget
19 | 2021-08-01 | East | KLT | Forecast | 0
19 | 2021-08-01 | East | KLT | Actual | 0
19 | 2021-08-01 | East | Forefront | Budget
19 | 2021-08-01 | East | Forefront | Forecast | 0
19 | 2021-08-01 | East | Forefront | Actual | 0
19 | 2021-08-01 | East | DPF | Budget
19 | 2021-08-01 | East | DPF | Forecast | 0
19 | 2021-08-01 | East | DPF | Actual | 0
19 | 2021-08-01 | East | OMJ | Budget
19 | 2021-08-01 | East | OMJ | Forecast | 0
19 | 2021-08-01 | East | OMJ | Actual | 0
19 | 2021-08-01 | East | DHB Utilities | Budget
19 | 2021-08-01 | East | DHB Utilities | Forecast | 0
19 | 2021-08-01 | East | DHB Utilities | Actual | 0
19 | 2021-08-01 | East | JDT | Budget
19 | 2021-08-01 | East | JDT | Forecast | 0
19 | 2021-08-01 | East | JDT | Actual | 0
19 | 2021-08-01 | East | MURRAY | Budget
19 | 2021-08-01 | East | MURRAY | Forecast | 0
19 | 2021-08-01 | East | MURRAY | Actual | 0
19 | 2021-08-01 | Central | Terra Firma | Budget
19 | 2021-08-01 | Central | Terra Firma | Forecast | 0
19 | 2021-08-01 | Central | Terra Firma | Actual | 0
19 | 2021-08-01 | Central | KLT | Budget
19 | 2021-08-01 | Central | KLT | Forecast | 0
19 | 2021-08-01 | Central | KLT | Actual | 0
19 | 2021-08-01 | Central | Forefront | Budget
19 | 2021-08-01 | Central | Forefront | Forecast | 0
19 | 2021-08-01 | Central | Forefront | Actual | 0
19 | 2021-08-01 | Central | DPF | Budget
19 | 2021-08-01 | Central | DPF | Forecast | 0
19 | 2021-08-01 | Central | DPF | Actual | 0
19 | 2021-08-01 | Central | OMJ | Budget
19 | 2021-08-01 | Central | OMJ | Forecast | 0
19 | 2021-08-01 | Central | OMJ | Actual | 0
19 | 2021-08-01 | Central | DHB Utilities | Budget
19 | 2021-08-01 | Central | DHB Utilities | Forecast | 0
19 | 2021-08-01 | Central | DHB Utilities | Actual | 0
19 | 2021-08-01 | Central | JDT | Budget
19 | 2021-08-01 | Central | JDT | Forecast | 0
19 | 2021-08-01 | Central | JDT | Actual | 0
19 | 2021-08-01 | Central | MURRAY | Budget
19 | 2021-08-01 | Central | MURRAY | Forecast | 0
19 | 2021-08-01 | Central | MURRAY | Actual | 0
19 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Budget
19 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Budget
19 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Budget
19 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Budget
19 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | West | DIRECT MOLE | Budget
19 | 2021-08-01 | West | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | West | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | East | DIRECT MOLE | Budget
19 | 2021-08-01 | East | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | East | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | Central | DIRECT MOLE | Budget
19 | 2021-08-01 | Central | DIRECT MOLE | Forecast | 0
19 | 2021-08-01 | Central | DIRECT MOLE | Actual | 0
19 | 2021-08-01 | CMO West 1 | SQS | Budget
19 | 2021-08-01 | CMO West 1 | SQS | Forecast | 0
19 | 2021-08-01 | CMO West 1 | SQS | Actual | 0
19 | 2021-08-01 | CMO West 2 | SQS | Budget
19 | 2021-08-01 | CMO West 2 | SQS | Forecast | 0
19 | 2021-08-01 | CMO West 2 | SQS | Actual | 0
19 | 2021-08-01 | CMO East 1 | SQS | Budget
19 | 2021-08-01 | CMO East 1 | SQS | Forecast | 0
19 | 2021-08-01 | CMO East 1 | SQS | Actual | 0
19 | 2021-08-01 | CMO East 2 | SQS | Budget
19 | 2021-08-01 | CMO East 2 | SQS | Forecast | 0
19 | 2021-08-01 | CMO East 2 | SQS | Actual | 0
19 | 2021-08-01 | West | SQS | Budget
19 | 2021-08-01 | West | SQS | Forecast | 0
19 | 2021-08-01 | West | SQS | Actual | 0
19 | 2021-08-01 | East | SQS | Budget
19 | 2021-08-01 | East | SQS | Forecast | 0
20 | 2021-08-01 | East | SQS | Actual | 0
20 | 2021-08-01 | Central | SQS | Budget
20 | 2021-08-01 | Central | SQS | Forecast | 0
19 | 2021-08-01 | Central | SQS | Actual | 0
20 | 2021-08-01 | CMO West 1 | Terra Firma | Budget
20 | 2021-08-01 | CMO West 1 | Terra Firma | Forecast | 0
20 | 2021-08-01 | CMO West 1 | Terra Firma | Actual | 0
20 | 2021-08-01 | CMO West 1 | KLT | Budget
20 | 2021-08-01 | CMO West 1 | KLT | Forecast | 0
20 | 2021-08-01 | CMO West 1 | KLT | Actual | 0
20 | 2021-08-01 | CMO West 1 | Forefront | Budget
20 | 2021-08-01 | CMO West 1 | Forefront | Forecast | 0
20 | 2021-08-01 | CMO West 1 | Forefront | Actual | 0
20 | 2021-08-01 | CMO West 1 | DPF | Budget
20 | 2021-08-01 | CMO West 1 | DPF | Forecast | 0
20 | 2021-08-01 | CMO West 1 | DPF | Actual | 0
20 | 2021-08-01 | CMO West 1 | OMJ | Budget
20 | 2021-08-01 | CMO West 1 | OMJ | Forecast | 0
20 | 2021-08-01 | CMO West 1 | OMJ | Actual | 0
20 | 2021-08-01 | CMO West 1 | DHB Utilities | Budget
20 | 2021-08-01 | CMO West 1 | DHB Utilities | Forecast | 0
20 | 2021-08-01 | CMO West 1 | DHB Utilities | Actual | 0
20 | 2021-08-01 | CMO West 1 | JDT | Budget
20 | 2021-08-01 | CMO West 1 | JDT | Forecast | 0
20 | 2021-08-01 | CMO West 1 | JDT | Actual | 0
20 | 2021-08-01 | CMO West 1 | MURRAY | Budget
20 | 2021-08-01 | CMO West 1 | MURRAY | Forecast | 0
20 | 2021-08-01 | CMO West 1 | MURRAY | Actual | 0
20 | 2021-08-01 | CMO West 2 | Terra Firma | Budget
20 | 2021-08-01 | CMO West 2 | Terra Firma | Forecast | 0
20 | 2021-08-01 | CMO West 2 | Terra Firma | Actual | 0
20 | 2021-08-01 | CMO West 2 | KLT | Budget
20 | 2021-08-01 | CMO West 2 | KLT | Forecast | 0
20 | 2021-08-01 | CMO West 2 | KLT | Actual | 0
20 | 2021-08-01 | CMO West 2 | Forefront | Budget
20 | 2021-08-01 | CMO West 2 | Forefront | Forecast | 0
20 | 2021-08-01 | CMO West 2 | Forefront | Actual | 0
20 | 2021-08-01 | CMO West 2 | DPF | Budget
20 | 2021-08-01 | CMO West 2 | DPF | Forecast | 0
20 | 2021-08-01 | CMO West 2 | DPF | Actual | 0
20 | 2021-08-01 | CMO West 2 | OMJ | Budget
20 | 2021-08-01 | CMO West 2 | OMJ | Forecast | 0
20 | 2021-08-01 | CMO West 2 | OMJ | Actual | 0
20 | 2021-08-01 | CMO West 2 | DHB Utilities | Budget
20 | 2021-08-01 | CMO West 2 | DHB Utilities | Forecast | 0
20 | 2021-08-01 | CMO West 2 | DHB Utilities | Actual | 0
20 | 2021-08-01 | CMO West 2 | JDT | Budget
20 | 2021-08-01 | CMO West 2 | JDT | Forecast | 0
20 | 2021-08-01 | CMO West 2 | JDT | Actual | 0
20 | 2021-08-01 | CMO West 2 | MURRAY | Budget
20 | 2021-08-01 | CMO West 2 | MURRAY | Forecast | 0
20 | 2021-08-01 | CMO West 2 | MURRAY | Actual | 0
20 | 2021-08-01 | CMO East 1 | Terra Firma | Budget
20 | 2021-08-01 | CMO East 1 | Terra Firma | Forecast | 0
20 | 2021-08-01 | CMO East 1 | Terra Firma | Actual | 0
20 | 2021-08-01 | CMO East 1 | KLT | Budget
20 | 2021-08-01 | CMO East 1 | KLT | Forecast | 0
20 | 2021-08-01 | CMO East 1 | KLT | Actual | 0
20 | 2021-08-01 | CMO East 1 | Forefront | Budget
20 | 2021-08-01 | CMO East 1 | Forefront | Forecast | 0
20 | 2021-08-01 | CMO East 1 | Forefront | Actual | 0
20 | 2021-08-01 | CMO East 1 | DPF | Budget
20 | 2021-08-01 | CMO East 1 | DPF | Forecast | 0
20 | 2021-08-01 | CMO East 1 | DPF | Actual | 0
20 | 2021-08-01 | CMO East 1 | OMJ | Budget
20 | 2021-08-01 | CMO East 1 | OMJ | Forecast | 0
20 | 2021-08-01 | CMO East 1 | OMJ | Actual | 0
20 | 2021-08-01 | CMO East 1 | DHB Utilities | Budget
20 | 2021-08-01 | CMO East 1 | DHB Utilities | Forecast | 0
20 | 2021-08-01 | CMO East 1 | DHB Utilities | Actual | 0
20 | 2021-08-01 | CMO East 1 | JDT | Budget
20 | 2021-08-01 | CMO East 1 | JDT | Forecast | 0
20 | 2021-08-01 | CMO East 1 | JDT | Actual | 0
20 | 2021-08-01 | CMO East 1 | MURRAY | Budget
20 | 2021-08-01 | CMO East 1 | MURRAY | Forecast | 0
20 | 2021-08-01 | CMO East 1 | MURRAY | Actual | 0
20 | 2021-08-01 | CMO East 2 | Terra Firma | Budget
20 | 2021-08-01 | CMO East 2 | Terra Firma | Forecast | 0
20 | 2021-08-01 | CMO East 2 | Terra Firma | Actual | 0
20 | 2021-08-01 | CMO East 2 | KLT | Budget
20 | 2021-08-01 | CMO East 2 | KLT | Forecast | 0
20 | 2021-08-01 | CMO East 2 | KLT | Actual | 0
20 | 2021-08-01 | CMO East 2 | Forefront | Budget
20 | 2021-08-01 | CMO East 2 | Forefront | Forecast | 0
20 | 2021-08-01 | CMO East 2 | Forefront | Actual | 0
20 | 2021-08-01 | CMO East 2 | DPF | Budget
20 | 2021-08-01 | CMO East 2 | DPF | Forecast | 0
20 | 2021-08-01 | CMO East 2 | DPF | Actual | 0
20 | 2021-08-01 | CMO East 2 | OMJ | Budget
20 | 2021-08-01 | CMO East 2 | OMJ | Forecast | 0
20 | 2021-08-01 | CMO East 2 | OMJ | Actual | 0
20 | 2021-08-01 | CMO East 2 | DHB Utilities | Budget
20 | 2021-08-01 | CMO East 2 | DHB Utilities | Forecast | 0
20 | 2021-08-01 | CMO East 2 | DHB Utilities | Actual | 0
20 | 2021-08-01 | CMO East 2 | JDT | Budget
20 | 2021-08-01 | CMO East 2 | JDT | Forecast | 0
20 | 2021-08-01 | CMO East 2 | JDT | Actual | 0
20 | 2021-08-01 | CMO East 2 | MURRAY | Budget
20 | 2021-08-01 | CMO East 2 | MURRAY | Forecast | 0
20 | 2021-08-01 | CMO East 2 | MURRAY | Actual | 0
20 | 2021-08-01 | West | Terra Firma | Budget
20 | 2021-08-01 | West | Terra Firma | Forecast | 0
20 | 2021-08-01 | West | Terra Firma | Actual | 0
20 | 2021-08-01 | West | KLT | Budget
20 | 2021-08-01 | West | KLT | Forecast | 0
20 | 2021-08-01 | West | KLT | Actual | 0
20 | 2021-08-01 | West | Forefront | Budget
20 | 2021-08-01 | West | Forefront | Forecast | 0
20 | 2021-08-01 | West | Forefront | Actual | 0
20 | 2021-08-01 | West | DPF | Budget
20 | 2021-08-01 | West | DPF | Forecast | 0
20 | 2021-08-01 | West | DPF | Actual | 0
20 | 2021-08-01 | West | OMJ | Budget
20 | 2021-08-01 | West | OMJ | Forecast | 0
20 | 2021-08-01 | West | OMJ | Actual | 0
20 | 2021-08-01 | West | DHB Utilities | Budget
20 | 2021-08-01 | West | DHB Utilities | Forecast | 0
20 | 2021-08-01 | West | DHB Utilities | Actual | 0
20 | 2021-08-01 | West | JDT | Budget
20 | 2021-08-01 | West | JDT | Forecast | 0
20 | 2021-08-01 | West | JDT | Actual | 0
20 | 2021-08-01 | West | MURRAY | Budget
20 | 2021-08-01 | West | MURRAY | Forecast | 0
20 | 2021-08-01 | West | MURRAY | Actual | 0
20 | 2021-08-01 | East | Terra Firma | Budget
20 | 2021-08-01 | East | Terra Firma | Forecast | 0
20 | 2021-08-01 | East | Terra Firma | Actual | 0
20 | 2021-08-01 | East | KLT | Budget
20 | 2021-08-01 | East | KLT | Forecast | 0
20 | 2021-08-01 | East | KLT | Actual | 0
20 | 2021-08-01 | East | Forefront | Budget
20 | 2021-08-01 | East | Forefront | Forecast | 0
20 | 2021-08-01 | East | Forefront | Actual | 0
20 | 2021-08-01 | East | DPF | Budget
20 | 2021-08-01 | East | DPF | Forecast | 0
20 | 2021-08-01 | East | DPF | Actual | 0
20 | 2021-08-01 | East | OMJ | Budget
20 | 2021-08-01 | East | OMJ | Forecast | 0
20 | 2021-08-01 | East | OMJ | Actual | 0
20 | 2021-08-01 | East | DHB Utilities | Budget
20 | 2021-08-01 | East | DHB Utilities | Forecast | 0
20 | 2021-08-01 | East | DHB Utilities | Actual | 0
20 | 2021-08-01 | East | JDT | Budget
20 | 2021-08-01 | East | JDT | Forecast | 0
20 | 2021-08-01 | East | JDT | Actual | 0
20 | 2021-08-01 | East | MURRAY | Budget
20 | 2021-08-01 | East | MURRAY | Forecast | 0
20 | 2021-08-01 | East | MURRAY | Actual | 0
20 | 2021-08-01 | Central | Terra Firma | Budget
20 | 2021-08-01 | Central | Terra Firma | Forecast | 0
20 | 2021-08-01 | Central | Terra Firma | Actual | 0
20 | 2021-08-01 | Central | KLT | Budget
20 | 2021-08-01 | Central | KLT | Forecast | 0
20 | 2021-08-01 | Central | KLT | Actual | 0
20 | 2021-08-01 | Central | Forefront | Budget
20 | 2021-08-01 | Central | Forefront | Forecast | 0
20 | 2021-08-01 | Central | Forefront | Actual | 0
20 | 2021-08-01 | Central | DPF | Budget
20 | 2021-08-01 | Central | DPF | Forecast | 0
20 | 2021-08-01 | Central | DPF | Actual | 0
20 | 2021-08-01 | Central | OMJ | Budget
20 | 2021-08-01 | Central | OMJ | Forecast | 0
20 | 2021-08-01 | Central | OMJ | Actual | 0
20 | 2021-08-01 | Central | DHB Utilities | Budget
20 | 2021-08-01 | Central | DHB Utilities | Forecast | 0
20 | 2021-08-01 | Central | DHB Utilities | Actual | 0
20 | 2021-08-01 | Central | JDT | Budget
20 | 2021-08-01 | Central | JDT | Forecast | 0
20 | 2021-08-01 | Central | JDT | Actual | 0
20 | 2021-08-01 | Central | MURRAY | Budget
20 | 2021-08-01 | Central | MURRAY | Forecast | 0
20 | 2021-08-01 | Central | MURRAY | Actual | 0
20 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Budget
20 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Budget
20 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Budget
20 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Budget
20 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | West | DIRECT MOLE | Budget
20 | 2021-08-01 | West | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | West | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | East | DIRECT MOLE | Budget
20 | 2021-08-01 | East | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | East | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | Central | DIRECT MOLE | Budget
20 | 2021-08-01 | Central | DIRECT MOLE | Forecast | 0
20 | 2021-08-01 | Central | DIRECT MOLE | Actual | 0
20 | 2021-08-01 | CMO West 1 | SQS | Budget
20 | 2021-08-01 | CMO West 1 | SQS | Forecast | 0
20 | 2021-08-01 | CMO West 1 | SQS | Actual | 0
20 | 2021-08-01 | CMO West 2 | SQS | Budget
20 | 2021-08-01 | CMO West 2 | SQS | Forecast | 0
20 | 2021-08-01 | CMO West 2 | SQS | Actual | 0
20 | 2021-08-01 | CMO East 1 | SQS | Budget
20 | 2021-08-01 | CMO East 1 | SQS | Forecast | 0
20 | 2021-08-01 | CMO East 1 | SQS | Actual | 0
20 | 2021-08-01 | CMO East 2 | SQS | Budget
20 | 2021-08-01 | CMO East 2 | SQS | Forecast | 0
20 | 2021-08-01 | CMO East 2 | SQS | Actual | 0
20 | 2021-08-01 | West | SQS | Budget
20 | 2021-08-01 | West | SQS | Forecast | 0
20 | 2021-08-01 | West | SQS | Actual | 0
20 | 2021-08-01 | East | SQS | Budget
20 | 2021-08-01 | East | SQS | Forecast | 0
21 | 2021-08-01 | East | SQS | Actual | 0
21 | 2021-08-01 | Central | SQS | Budget
21 | 2021-08-01 | Central | SQS | Forecast | 0
20 | 2021-08-01 | Central | SQS | Actual | 0
21 | 2021-08-01 | CMO West 1 | Terra Firma | Budget
21 | 2021-08-01 | CMO West 1 | Terra Firma | Forecast | 0
21 | 2021-08-01 | CMO West 1 | Terra Firma | Actual | 0
21 | 2021-08-01 | CMO West 1 | KLT | Budget
21 | 2021-08-01 | CMO West 1 | KLT | Forecast | 0
21 | 2021-08-01 | CMO West 1 | KLT | Actual | 0
21 | 2021-08-01 | CMO West 1 | Forefront | Budget
21 | 2021-08-01 | CMO West 1 | Forefront | Forecast | 0
21 | 2021-08-01 | CMO West 1 | Forefront | Actual | 0
21 | 2021-08-01 | CMO West 1 | DPF | Budget
21 | 2021-08-01 | CMO West 1 | DPF | Forecast | 0
21 | 2021-08-01 | CMO West 1 | DPF | Actual | 0
21 | 2021-08-01 | CMO West 1 | OMJ | Budget
21 | 2021-08-01 | CMO West 1 | OMJ | Forecast | 0
21 | 2021-08-01 | CMO West 1 | OMJ | Actual | 0
21 | 2021-08-01 | CMO West 1 | DHB Utilities | Budget
21 | 2021-08-01 | CMO West 1 | DHB Utilities | Forecast | 0
21 | 2021-08-01 | CMO West 1 | DHB Utilities | Actual | 0
21 | 2021-08-01 | CMO West 1 | JDT | Budget
21 | 2021-08-01 | CMO West 1 | JDT | Forecast | 0
21 | 2021-08-01 | CMO West 1 | JDT | Actual | 0
21 | 2021-08-01 | CMO West 1 | MURRAY | Budget
21 | 2021-08-01 | CMO West 1 | MURRAY | Forecast | 0
21 | 2021-08-01 | CMO West 1 | MURRAY | Actual | 0
21 | 2021-08-01 | CMO West 2 | Terra Firma | Budget
21 | 2021-08-01 | CMO West 2 | Terra Firma | Forecast | 0
21 | 2021-08-01 | CMO West 2 | Terra Firma | Actual | 0
21 | 2021-08-01 | CMO West 2 | KLT | Budget
21 | 2021-08-01 | CMO West 2 | KLT | Forecast | 0
21 | 2021-08-01 | CMO West 2 | KLT | Actual | 0
21 | 2021-08-01 | CMO West 2 | Forefront | Budget
21 | 2021-08-01 | CMO West 2 | Forefront | Forecast | 0
21 | 2021-08-01 | CMO West 2 | Forefront | Actual | 0
21 | 2021-08-01 | CMO West 2 | DPF | Budget
21 | 2021-08-01 | CMO West 2 | DPF | Forecast | 0
21 | 2021-08-01 | CMO West 2 | DPF | Actual | 0
21 | 2021-08-01 | CMO West 2 | OMJ | Budget
21 | 2021-08-01 | CMO West 2 | OMJ | Forecast | 0
21 | 2021-08-01 | CMO West 2 | OMJ | Actual | 0
21 | 2021-08-01 | CMO West 2 | DHB Utilities | Budget
21 | 2021-08-01 | CMO West 2 | DHB Utilities | Forecast | 0
21 | 2021-08-01 | CMO West 2 | DHB Utilities | Actual | 0
21 | 2021-08-01 | CMO West 2 | JDT | Budget
21 | 2021-08-01 | CMO West 2 | JDT | Forecast | 0
21 | 2021-08-01 | CMO West 2 | JDT | Actual | 0
21 | 2021-08-01 | CMO West 2 | MURRAY | Budget
21 | 2021-08-01 | CMO West 2 | MURRAY | Forecast | 0
21 | 2021-08-01 | CMO West 2 | MURRAY | Actual | 0
21 | 2021-08-01 | CMO East 1 | Terra Firma | Budget
21 | 2021-08-01 | CMO East 1 | Terra Firma | Forecast | 0
21 | 2021-08-01 | CMO East 1 | Terra Firma | Actual | 0
21 | 2021-08-01 | CMO East 1 | KLT | Budget
21 | 2021-08-01 | CMO East 1 | KLT | Forecast | 0
21 | 2021-08-01 | CMO East 1 | KLT | Actual | 0
21 | 2021-08-01 | CMO East 1 | Forefront | Budget
21 | 2021-08-01 | CMO East 1 | Forefront | Forecast | 0
21 | 2021-08-01 | CMO East 1 | Forefront | Actual | 0
21 | 2021-08-01 | CMO East 1 | DPF | Budget
21 | 2021-08-01 | CMO East 1 | DPF | Forecast | 0
21 | 2021-08-01 | CMO East 1 | DPF | Actual | 0
21 | 2021-08-01 | CMO East 1 | OMJ | Budget
21 | 2021-08-01 | CMO East 1 | OMJ | Forecast | 0
21 | 2021-08-01 | CMO East 1 | OMJ | Actual | 0
21 | 2021-08-01 | CMO East 1 | DHB Utilities | Budget
21 | 2021-08-01 | CMO East 1 | DHB Utilities | Forecast | 0
21 | 2021-08-01 | CMO East 1 | DHB Utilities | Actual | 0
21 | 2021-08-01 | CMO East 1 | JDT | Budget
21 | 2021-08-01 | CMO East 1 | JDT | Forecast | 0
21 | 2021-08-01 | CMO East 1 | JDT | Actual | 0
21 | 2021-08-01 | CMO East 1 | MURRAY | Budget
21 | 2021-08-01 | CMO East 1 | MURRAY | Forecast | 0
21 | 2021-08-01 | CMO East 1 | MURRAY | Actual | 0
21 | 2021-08-01 | CMO East 2 | Terra Firma | Budget
21 | 2021-08-01 | CMO East 2 | Terra Firma | Forecast | 0
21 | 2021-08-01 | CMO East 2 | Terra Firma | Actual | 0
21 | 2021-08-01 | CMO East 2 | KLT | Budget
21 | 2021-08-01 | CMO East 2 | KLT | Forecast | 0
21 | 2021-08-01 | CMO East 2 | KLT | Actual | 0
21 | 2021-08-01 | CMO East 2 | Forefront | Budget
21 | 2021-08-01 | CMO East 2 | Forefront | Forecast | 0
21 | 2021-08-01 | CMO East 2 | Forefront | Actual | 0
21 | 2021-08-01 | CMO East 2 | DPF | Budget
21 | 2021-08-01 | CMO East 2 | DPF | Forecast | 0
21 | 2021-08-01 | CMO East 2 | DPF | Actual | 0
21 | 2021-08-01 | CMO East 2 | OMJ | Budget
21 | 2021-08-01 | CMO East 2 | OMJ | Forecast | 0
21 | 2021-08-01 | CMO East 2 | OMJ | Actual | 0
21 | 2021-08-01 | CMO East 2 | DHB Utilities | Budget
21 | 2021-08-01 | CMO East 2 | DHB Utilities | Forecast | 0
21 | 2021-08-01 | CMO East 2 | DHB Utilities | Actual | 0
21 | 2021-08-01 | CMO East 2 | JDT | Budget
21 | 2021-08-01 | CMO East 2 | JDT | Forecast | 0
21 | 2021-08-01 | CMO East 2 | JDT | Actual | 0
21 | 2021-08-01 | CMO East 2 | MURRAY | Budget
21 | 2021-08-01 | CMO East 2 | MURRAY | Forecast | 0
21 | 2021-08-01 | CMO East 2 | MURRAY | Actual | 0
21 | 2021-08-01 | West | Terra Firma | Budget
21 | 2021-08-01 | West | Terra Firma | Forecast | 0
21 | 2021-08-01 | West | Terra Firma | Actual | 0
21 | 2021-08-01 | West | KLT | Budget
21 | 2021-08-01 | West | KLT | Forecast | 0
21 | 2021-08-01 | West | KLT | Actual | 0
21 | 2021-08-01 | West | Forefront | Budget
21 | 2021-08-01 | West | Forefront | Forecast | 0
21 | 2021-08-01 | West | Forefront | Actual | 0
21 | 2021-08-01 | West | DPF | Budget
21 | 2021-08-01 | West | DPF | Forecast | 0
21 | 2021-08-01 | West | DPF | Actual | 0
21 | 2021-08-01 | West | OMJ | Budget
21 | 2021-08-01 | West | OMJ | Forecast | 0
21 | 2021-08-01 | West | OMJ | Actual | 0
21 | 2021-08-01 | West | DHB Utilities | Budget
21 | 2021-08-01 | West | DHB Utilities | Forecast | 0
21 | 2021-08-01 | West | DHB Utilities | Actual | 0
21 | 2021-08-01 | West | JDT | Budget
21 | 2021-08-01 | West | JDT | Forecast | 0
21 | 2021-08-01 | West | JDT | Actual | 0
21 | 2021-08-01 | West | MURRAY | Budget
21 | 2021-08-01 | West | MURRAY | Forecast | 0
21 | 2021-08-01 | West | MURRAY | Actual | 0
21 | 2021-08-01 | East | Terra Firma | Budget
21 | 2021-08-01 | East | Terra Firma | Forecast | 0
21 | 2021-08-01 | East | Terra Firma | Actual | 0
21 | 2021-08-01 | East | KLT | Budget
21 | 2021-08-01 | East | KLT | Forecast | 0
21 | 2021-08-01 | East | KLT | Actual | 0
21 | 2021-08-01 | East | Forefront | Budget
21 | 2021-08-01 | East | Forefront | Forecast | 0
21 | 2021-08-01 | East | Forefront | Actual | 0
21 | 2021-08-01 | East | DPF | Budget
21 | 2021-08-01 | East | DPF | Forecast | 0
21 | 2021-08-01 | East | DPF | Actual | 0
21 | 2021-08-01 | East | OMJ | Budget
21 | 2021-08-01 | East | OMJ | Forecast | 0
21 | 2021-08-01 | East | OMJ | Actual | 0
21 | 2021-08-01 | East | DHB Utilities | Budget
21 | 2021-08-01 | East | DHB Utilities | Forecast | 0
21 | 2021-08-01 | East | DHB Utilities | Actual | 0
21 | 2021-08-01 | East | JDT | Budget
21 | 2021-08-01 | East | JDT | Forecast | 0
21 | 2021-08-01 | East | JDT | Actual | 0
21 | 2021-08-01 | East | MURRAY | Budget
21 | 2021-08-01 | East | MURRAY | Forecast | 0
21 | 2021-08-01 | East | MURRAY | Actual | 0
21 | 2021-08-01 | Central | Terra Firma | Budget
21 | 2021-08-01 | Central | Terra Firma | Forecast | 0
21 | 2021-08-01 | Central | Terra Firma | Actual | 0
21 | 2021-08-01 | Central | KLT | Budget
21 | 2021-08-01 | Central | KLT | Forecast | 0
21 | 2021-08-01 | Central | KLT | Actual | 0
21 | 2021-08-01 | Central | Forefront | Budget
21 | 2021-08-01 | Central | Forefront | Forecast | 0
21 | 2021-08-01 | Central | Forefront | Actual | 0
21 | 2021-08-01 | Central | DPF | Budget
21 | 2021-08-01 | Central | DPF | Forecast | 0
21 | 2021-08-01 | Central | DPF | Actual | 0
21 | 2021-08-01 | Central | OMJ | Budget
21 | 2021-08-01 | Central | OMJ | Forecast | 0
21 | 2021-08-01 | Central | OMJ | Actual | 0
21 | 2021-08-01 | Central | DHB Utilities | Budget
21 | 2021-08-01 | Central | DHB Utilities | Forecast | 0
21 | 2021-08-01 | Central | DHB Utilities | Actual | 0
21 | 2021-08-01 | Central | JDT | Budget
21 | 2021-08-01 | Central | JDT | Forecast | 0
21 | 2021-08-01 | Central | JDT | Actual | 0
21 | 2021-08-01 | Central | MURRAY | Budget
21 | 2021-08-01 | Central | MURRAY | Forecast | 0
21 | 2021-08-01 | Central | MURRAY | Actual | 0
21 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Budget
21 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Budget
21 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Budget
21 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Budget
21 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | West | DIRECT MOLE | Budget
21 | 2021-08-01 | West | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | West | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | East | DIRECT MOLE | Budget
21 | 2021-08-01 | East | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | East | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | Central | DIRECT MOLE | Budget
21 | 2021-08-01 | Central | DIRECT MOLE | Forecast | 0
21 | 2021-08-01 | Central | DIRECT MOLE | Actual | 0
21 | 2021-08-01 | CMO West 1 | SQS | Budget
21 | 2021-08-01 | CMO West 1 | SQS | Forecast | 0
21 | 2021-08-01 | CMO West 1 | SQS | Actual | 0
21 | 2021-08-01 | CMO West 2 | SQS | Budget
21 | 2021-08-01 | CMO West 2 | SQS | Forecast | 0
21 | 2021-08-01 | CMO West 2 | SQS | Actual | 0
21 | 2021-08-01 | CMO East 1 | SQS | Budget
21 | 2021-08-01 | CMO East 1 | SQS | Forecast | 0
21 | 2021-08-01 | CMO East 1 | SQS | Actual | 0
21 | 2021-08-01 | CMO East 2 | SQS | Budget
21 | 2021-08-01 | CMO East 2 | SQS | Forecast | 0
21 | 2021-08-01 | CMO East 2 | SQS | Actual | 0
21 | 2021-08-01 | West | SQS | Budget
21 | 2021-08-01 | West | SQS | Forecast | 0
21 | 2021-08-01 | West | SQS | Actual | 0
21 | 2021-08-01 | East | SQS | Budget
21 | 2021-08-01 | East | SQS | Forecast | 0
22 | 2021-08-01 | East | SQS | Actual | 0
22 | 2021-08-01 | Central | SQS | Budget
22 | 2021-08-01 | Central | SQS | Forecast | 0
21 | 2021-08-01 | Central | SQS | Actual | 0
22 | 2021-08-01 | CMO West 1 | Terra Firma | Budget
22 | 2021-08-01 | CMO West 1 | Terra Firma | Forecast | 0
22 | 2021-08-01 | CMO West 1 | Terra Firma | Actual | 0
22 | 2021-08-01 | CMO West 1 | KLT | Budget
22 | 2021-08-01 | CMO West 1 | KLT | Forecast | 0
22 | 2021-08-01 | CMO West 1 | KLT | Actual | 0
22 | 2021-08-01 | CMO West 1 | Forefront | Budget
22 | 2021-08-01 | CMO West 1 | Forefront | Forecast | 0
22 | 2021-08-01 | CMO West 1 | Forefront | Actual | 0
22 | 2021-08-01 | CMO West 1 | DPF | Budget
22 | 2021-08-01 | CMO West 1 | DPF | Forecast | 0
22 | 2021-08-01 | CMO West 1 | DPF | Actual | 0
22 | 2021-08-01 | CMO West 1 | OMJ | Budget
22 | 2021-08-01 | CMO West 1 | OMJ | Forecast | 0
22 | 2021-08-01 | CMO West 1 | OMJ | Actual | 0
22 | 2021-08-01 | CMO West 1 | DHB Utilities | Budget
22 | 2021-08-01 | CMO West 1 | DHB Utilities | Forecast | 0
22 | 2021-08-01 | CMO West 1 | DHB Utilities | Actual | 0
22 | 2021-08-01 | CMO West 1 | JDT | Budget
22 | 2021-08-01 | CMO West 1 | JDT | Forecast | 0
22 | 2021-08-01 | CMO West 1 | JDT | Actual | 0
22 | 2021-08-01 | CMO West 1 | MURRAY | Budget
22 | 2021-08-01 | CMO West 1 | MURRAY | Forecast | 0
22 | 2021-08-01 | CMO West 1 | MURRAY | Actual | 0
22 | 2021-08-01 | CMO West 2 | Terra Firma | Budget
22 | 2021-08-01 | CMO West 2 | Terra Firma | Forecast | 0
22 | 2021-08-01 | CMO West 2 | Terra Firma | Actual | 0
22 | 2021-08-01 | CMO West 2 | KLT | Budget
22 | 2021-08-01 | CMO West 2 | KLT | Forecast | 0
22 | 2021-08-01 | CMO West 2 | KLT | Actual | 0
22 | 2021-08-01 | CMO West 2 | Forefront | Budget
22 | 2021-08-01 | CMO West 2 | Forefront | Forecast | 0
22 | 2021-08-01 | CMO West 2 | Forefront | Actual | 0
22 | 2021-08-01 | CMO West 2 | DPF | Budget
22 | 2021-08-01 | CMO West 2 | DPF | Forecast | 0
22 | 2021-08-01 | CMO West 2 | DPF | Actual | 0
22 | 2021-08-01 | CMO West 2 | OMJ | Budget
22 | 2021-08-01 | CMO West 2 | OMJ | Forecast | 0
22 | 2021-08-01 | CMO West 2 | OMJ | Actual | 0
22 | 2021-08-01 | CMO West 2 | DHB Utilities | Budget
22 | 2021-08-01 | CMO West 2 | DHB Utilities | Forecast | 0
22 | 2021-08-01 | CMO West 2 | DHB Utilities | Actual | 0
22 | 2021-08-01 | CMO West 2 | JDT | Budget
22 | 2021-08-01 | CMO West 2 | JDT | Forecast | 0
22 | 2021-08-01 | CMO West 2 | JDT | Actual | 0
22 | 2021-08-01 | CMO West 2 | MURRAY | Budget
22 | 2021-08-01 | CMO West 2 | MURRAY | Forecast | 0
22 | 2021-08-01 | CMO West 2 | MURRAY | Actual | 0
22 | 2021-08-01 | CMO East 1 | Terra Firma | Budget
22 | 2021-08-01 | CMO East 1 | Terra Firma | Forecast | 0
22 | 2021-08-01 | CMO East 1 | Terra Firma | Actual | 0
22 | 2021-08-01 | CMO East 1 | KLT | Budget
22 | 2021-08-01 | CMO East 1 | KLT | Forecast | 0
22 | 2021-08-01 | CMO East 1 | KLT | Actual | 0
22 | 2021-08-01 | CMO East 1 | Forefront | Budget
22 | 2021-08-01 | CMO East 1 | Forefront | Forecast | 0
22 | 2021-08-01 | CMO East 1 | Forefront | Actual | 0
22 | 2021-08-01 | CMO East 1 | DPF | Budget
22 | 2021-08-01 | CMO East 1 | DPF | Forecast | 0
22 | 2021-08-01 | CMO East 1 | DPF | Actual | 0
22 | 2021-08-01 | CMO East 1 | OMJ | Budget
22 | 2021-08-01 | CMO East 1 | OMJ | Forecast | 0
22 | 2021-08-01 | CMO East 1 | OMJ | Actual | 0
22 | 2021-08-01 | CMO East 1 | DHB Utilities | Budget
22 | 2021-08-01 | CMO East 1 | DHB Utilities | Forecast | 0
22 | 2021-08-01 | CMO East 1 | DHB Utilities | Actual | 0
22 | 2021-08-01 | CMO East 1 | JDT | Budget
22 | 2021-08-01 | CMO East 1 | JDT | Forecast | 0
22 | 2021-08-01 | CMO East 1 | JDT | Actual | 0
22 | 2021-08-01 | CMO East 1 | MURRAY | Budget
22 | 2021-08-01 | CMO East 1 | MURRAY | Forecast | 0
22 | 2021-08-01 | CMO East 1 | MURRAY | Actual | 0
22 | 2021-08-01 | CMO East 2 | Terra Firma | Budget
22 | 2021-08-01 | CMO East 2 | Terra Firma | Forecast | 0
22 | 2021-08-01 | CMO East 2 | Terra Firma | Actual | 0
22 | 2021-08-01 | CMO East 2 | KLT | Budget
22 | 2021-08-01 | CMO East 2 | KLT | Forecast | 0
22 | 2021-08-01 | CMO East 2 | KLT | Actual | 0
22 | 2021-08-01 | CMO East 2 | Forefront | Budget
22 | 2021-08-01 | CMO East 2 | Forefront | Forecast | 0
22 | 2021-08-01 | CMO East 2 | Forefront | Actual | 0
22 | 2021-08-01 | CMO East 2 | DPF | Budget
22 | 2021-08-01 | CMO East 2 | DPF | Forecast | 0
22 | 2021-08-01 | CMO East 2 | DPF | Actual | 0
22 | 2021-08-01 | CMO East 2 | OMJ | Budget
22 | 2021-08-01 | CMO East 2 | OMJ | Forecast | 0
22 | 2021-08-01 | CMO East 2 | OMJ | Actual | 0
22 | 2021-08-01 | CMO East 2 | DHB Utilities | Budget
22 | 2021-08-01 | CMO East 2 | DHB Utilities | Forecast | 0
22 | 2021-08-01 | CMO East 2 | DHB Utilities | Actual | 0
22 | 2021-08-01 | CMO East 2 | JDT | Budget
22 | 2021-08-01 | CMO East 2 | JDT | Forecast | 0
22 | 2021-08-01 | CMO East 2 | JDT | Actual | 0
22 | 2021-08-01 | CMO East 2 | MURRAY | Budget
22 | 2021-08-01 | CMO East 2 | MURRAY | Forecast | 0
22 | 2021-08-01 | CMO East 2 | MURRAY | Actual | 0
22 | 2021-08-01 | West | Terra Firma | Budget
22 | 2021-08-01 | West | Terra Firma | Forecast | 0
22 | 2021-08-01 | West | Terra Firma | Actual | 0
22 | 2021-08-01 | West | KLT | Budget
22 | 2021-08-01 | West | KLT | Forecast | 0
22 | 2021-08-01 | West | KLT | Actual | 0
22 | 2021-08-01 | West | Forefront | Budget
22 | 2021-08-01 | West | Forefront | Forecast | 0
22 | 2021-08-01 | West | Forefront | Actual | 0
22 | 2021-08-01 | West | DPF | Budget
22 | 2021-08-01 | West | DPF | Forecast | 0
22 | 2021-08-01 | West | DPF | Actual | 0
22 | 2021-08-01 | West | OMJ | Budget
22 | 2021-08-01 | West | OMJ | Forecast | 0
22 | 2021-08-01 | West | OMJ | Actual | 0
22 | 2021-08-01 | West | DHB Utilities | Budget
22 | 2021-08-01 | West | DHB Utilities | Forecast | 0
22 | 2021-08-01 | West | DHB Utilities | Actual | 0
22 | 2021-08-01 | West | JDT | Budget
22 | 2021-08-01 | West | JDT | Forecast | 0
22 | 2021-08-01 | West | JDT | Actual | 0
22 | 2021-08-01 | West | MURRAY | Budget
22 | 2021-08-01 | West | MURRAY | Forecast | 0
22 | 2021-08-01 | West | MURRAY | Actual | 0
22 | 2021-08-01 | East | Terra Firma | Budget
22 | 2021-08-01 | East | Terra Firma | Forecast | 0
22 | 2021-08-01 | East | Terra Firma | Actual | 0
22 | 2021-08-01 | East | KLT | Budget
22 | 2021-08-01 | East | KLT | Forecast | 0
22 | 2021-08-01 | East | KLT | Actual | 0
22 | 2021-08-01 | East | Forefront | Budget
22 | 2021-08-01 | East | Forefront | Forecast | 0
22 | 2021-08-01 | East | Forefront | Actual | 0
22 | 2021-08-01 | East | DPF | Budget
22 | 2021-08-01 | East | DPF | Forecast | 0
22 | 2021-08-01 | East | DPF | Actual | 0
22 | 2021-08-01 | East | OMJ | Budget
22 | 2021-08-01 | East | OMJ | Forecast | 0
22 | 2021-08-01 | East | OMJ | Actual | 0
22 | 2021-08-01 | East | DHB Utilities | Budget
22 | 2021-08-01 | East | DHB Utilities | Forecast | 0
22 | 2021-08-01 | East | DHB Utilities | Actual | 0
22 | 2021-08-01 | East | JDT | Budget
22 | 2021-08-01 | East | JDT | Forecast | 0
22 | 2021-08-01 | East | JDT | Actual | 0
22 | 2021-08-01 | East | MURRAY | Budget
22 | 2021-08-01 | East | MURRAY | Forecast | 0
22 | 2021-08-01 | East | MURRAY | Actual | 0
22 | 2021-08-01 | Central | Terra Firma | Budget
22 | 2021-08-01 | Central | Terra Firma | Forecast | 0
22 | 2021-08-01 | Central | Terra Firma | Actual | 0
22 | 2021-08-01 | Central | KLT | Budget
22 | 2021-08-01 | Central | KLT | Forecast | 0
22 | 2021-08-01 | Central | KLT | Actual | 0
22 | 2021-08-01 | Central | Forefront | Budget
22 | 2021-08-01 | Central | Forefront | Forecast | 0
22 | 2021-08-01 | Central | Forefront | Actual | 0
22 | 2021-08-01 | Central | DPF | Budget
22 | 2021-08-01 | Central | DPF | Forecast | 0
22 | 2021-08-01 | Central | DPF | Actual | 0
22 | 2021-08-01 | Central | OMJ | Budget
22 | 2021-08-01 | Central | OMJ | Forecast | 0
22 | 2021-08-01 | Central | OMJ | Actual | 0
22 | 2021-08-01 | Central | DHB Utilities | Budget
22 | 2021-08-01 | Central | DHB Utilities | Forecast | 0
22 | 2021-08-01 | Central | DHB Utilities | Actual | 0
22 | 2021-08-01 | Central | JDT | Budget
22 | 2021-08-01 | Central | JDT | Forecast | 0
22 | 2021-08-01 | Central | JDT | Actual | 0
22 | 2021-08-01 | Central | MURRAY | Budget
22 | 2021-08-01 | Central | MURRAY | Forecast | 0
22 | 2021-08-01 | Central | MURRAY | Actual | 0
22 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Budget
22 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | CMO West 1 | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Budget
22 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | CMO West 2 | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Budget
22 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | CMO East 1 | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Budget
22 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | CMO East 2 | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | West | DIRECT MOLE | Budget
22 | 2021-08-01 | West | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | West | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | East | DIRECT MOLE | Budget
22 | 2021-08-01 | East | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | East | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | Central | DIRECT MOLE | Budget
22 | 2021-08-01 | Central | DIRECT MOLE | Forecast | 0
22 | 2021-08-01 | Central | DIRECT MOLE | Actual | 0
22 | 2021-08-01 | CMO West 1 | SQS | Budget
22 | 2021-08-01 | CMO West 1 | SQS | Forecast | 0
22 | 2021-08-01 | CMO West 1 | SQS | Actual | 0
22 | 2021-08-01 | CMO West 2 | SQS | Budget
22 | 2021-08-01 | CMO West 2 | SQS | Forecast | 0
22 | 2021-08-01 | CMO West 2 | SQS | Actual | 0
22 | 2021-08-01 | CMO East 1 | SQS | Budget
22 | 2021-08-01 | CMO East 1 | SQS | Forecast | 0
22 | 2021-08-01 | CMO East 1 | SQS | Actual | 0
22 | 2021-08-01 | CMO East 2 | SQS | Budget
22 | 2021-08-01 | CMO East 2 | SQS | Forecast | 0
22 | 2021-08-01 | CMO East 2 | SQS | Actual | 0
22 | 2021-08-01 | West | SQS | Budget
22 | 2021-08-01 | West | SQS | Forecast | 0
22 | 2021-08-01 | West | SQS | Actual | 0
22 | 2021-08-01 | East | SQS | Budget
22 | 2021-08-01 | East | SQS | Forecast | 0
23 | 2021-08-01 | East | SQS | Actual | 0
23 | 2021-08-01 | Central | SQS | Budget
23 | 2021-08-01 | Central | SQS | Forecast | 0
22 | 2021-08-01 | Central | SQS | Actual | 0
23 | 2021-09-01 | CMO West 1 | Terra Firma | Budget
23 | 2021-09-01 | CMO West 1 | Terra Firma | Forecast | 0
23 | 2021-09-01 | CMO West 1 | Terra Firma | Actual | 0
23 | 2021-09-01 | CMO West 1 | KLT | Budget
23 | 2021-09-01 | CMO West 1 | KLT | Forecast | 0
23 | 2021-09-01 | CMO West 1 | KLT | Actual | 0
23 | 2021-09-01 | CMO West 1 | Forefront | Budget
23 | 2021-09-01 | CMO West 1 | Forefront | Forecast | 0
23 | 2021-09-01 | CMO West 1 | Forefront | Actual | 0
23 | 2021-09-01 | CMO West 1 | DPF | Budget
23 | 2021-09-01 | CMO West 1 | DPF | Forecast | 0
23 | 2021-09-01 | CMO West 1 | DPF | Actual | 0
23 | 2021-09-01 | CMO West 1 | OMJ | Budget
23 | 2021-09-01 | CMO West 1 | OMJ | Forecast | 0
23 | 2021-09-01 | CMO West 1 | OMJ | Actual | 0
23 | 2021-09-01 | CMO West 1 | DHB Utilities | Budget
23 | 2021-09-01 | CMO West 1 | DHB Utilities | Forecast | 0
23 | 2021-09-01 | CMO West 1 | DHB Utilities | Actual | 0
23 | 2021-09-01 | CMO West 1 | JDT | Budget
23 | 2021-09-01 | CMO West 1 | JDT | Forecast | 0
23 | 2021-09-01 | CMO West 1 | JDT | Actual | 0
23 | 2021-09-01 | CMO West 1 | MURRAY | Budget
23 | 2021-09-01 | CMO West 1 | MURRAY | Forecast | 0
23 | 2021-09-01 | CMO West 1 | MURRAY | Actual | 0
23 | 2021-09-01 | CMO West 2 | Terra Firma | Budget
23 | 2021-09-01 | CMO West 2 | Terra Firma | Forecast | 0
23 | 2021-09-01 | CMO West 2 | Terra Firma | Actual | 0
23 | 2021-09-01 | CMO West 2 | KLT | Budget
23 | 2021-09-01 | CMO West 2 | KLT | Forecast | 0
23 | 2021-09-01 | CMO West 2 | KLT | Actual | 0
23 | 2021-09-01 | CMO West 2 | Forefront | Budget
23 | 2021-09-01 | CMO West 2 | Forefront | Forecast | 0
23 | 2021-09-01 | CMO West 2 | Forefront | Actual | 0
23 | 2021-09-01 | CMO West 2 | DPF | Budget
23 | 2021-09-01 | CMO West 2 | DPF | Forecast | 0
23 | 2021-09-01 | CMO West 2 | DPF | Actual | 0
23 | 2021-09-01 | CMO West 2 | OMJ | Budget
23 | 2021-09-01 | CMO West 2 | OMJ | Forecast | 0
23 | 2021-09-01 | CMO West 2 | OMJ | Actual | 0
23 | 2021-09-01 | CMO West 2 | DHB Utilities | Budget
23 | 2021-09-01 | CMO West 2 | DHB Utilities | Forecast | 0
23 | 2021-09-01 | CMO West 2 | DHB Utilities | Actual | 0
23 | 2021-09-01 | CMO West 2 | JDT | Budget
23 | 2021-09-01 | CMO West 2 | JDT | Forecast | 0
23 | 2021-09-01 | CMO West 2 | JDT | Actual | 0
23 | 2021-09-01 | CMO West 2 | MURRAY | Budget
23 | 2021-09-01 | CMO West 2 | MURRAY | Forecast | 0
23 | 2021-09-01 | CMO West 2 | MURRAY | Actual | 0
23 | 2021-09-01 | CMO East 1 | Terra Firma | Budget
23 | 2021-09-01 | CMO East 1 | Terra Firma | Forecast | 0
23 | 2021-09-01 | CMO East 1 | Terra Firma | Actual | 0
23 | 2021-09-01 | CMO East 1 | KLT | Budget
23 | 2021-09-01 | CMO East 1 | KLT | Forecast | 0
23 | 2021-09-01 | CMO East 1 | KLT | Actual | 0
23 | 2021-09-01 | CMO East 1 | Forefront | Budget
23 | 2021-09-01 | CMO East 1 | Forefront | Forecast | 0
23 | 2021-09-01 | CMO East 1 | Forefront | Actual | 0
23 | 2021-09-01 | CMO East 1 | DPF | Budget
23 | 2021-09-01 | CMO East 1 | DPF | Forecast | 0
23 | 2021-09-01 | CMO East 1 | DPF | Actual | 0
23 | 2021-09-01 | CMO East 1 | OMJ | Budget
23 | 2021-09-01 | CMO East 1 | OMJ | Forecast | 0
23 | 2021-09-01 | CMO East 1 | OMJ | Actual | 0
23 | 2021-09-01 | CMO East 1 | DHB Utilities | Budget
23 | 2021-09-01 | CMO East 1 | DHB Utilities | Forecast | 0
23 | 2021-09-01 | CMO East 1 | DHB Utilities | Actual | 0
23 | 2021-09-01 | CMO East 1 | JDT | Budget
23 | 2021-09-01 | CMO East 1 | JDT | Forecast | 0
23 | 2021-09-01 | CMO East 1 | JDT | Actual | 0
23 | 2021-09-01 | CMO East 1 | MURRAY | Budget
23 | 2021-09-01 | CMO East 1 | MURRAY | Forecast | 0
23 | 2021-09-01 | CMO East 1 | MURRAY | Actual | 0
23 | 2021-09-01 | CMO East 2 | Terra Firma | Budget
23 | 2021-09-01 | CMO East 2 | Terra Firma | Forecast | 0
23 | 2021-09-01 | CMO East 2 | Terra Firma | Actual | 0
23 | 2021-09-01 | CMO East 2 | KLT | Budget
23 | 2021-09-01 | CMO East 2 | KLT | Forecast | 0
23 | 2021-09-01 | CMO East 2 | KLT | Actual | 0
23 | 2021-09-01 | CMO East 2 | Forefront | Budget
23 | 2021-09-01 | CMO East 2 | Forefront | Forecast | 0
23 | 2021-09-01 | CMO East 2 | Forefront | Actual | 0
23 | 2021-09-01 | CMO East 2 | DPF | Budget
23 | 2021-09-01 | CMO East 2 | DPF | Forecast | 0
23 | 2021-09-01 | CMO East 2 | DPF | Actual | 0
23 | 2021-09-01 | CMO East 2 | OMJ | Budget
23 | 2021-09-01 | CMO East 2 | OMJ | Forecast | 0
23 | 2021-09-01 | CMO East 2 | OMJ | Actual | 0
23 | 2021-09-01 | CMO East 2 | DHB Utilities | Budget
23 | 2021-09-01 | CMO East 2 | DHB Utilities | Forecast | 0
23 | 2021-09-01 | CMO East 2 | DHB Utilities | Actual | 0
23 | 2021-09-01 | CMO East 2 | JDT | Budget
23 | 2021-09-01 | CMO East 2 | JDT | Forecast | 0
23 | 2021-09-01 | CMO East 2 | JDT | Actual | 0
23 | 2021-09-01 | CMO East 2 | MURRAY | Budget
23 | 2021-09-01 | CMO East 2 | MURRAY | Forecast | 0
23 | 2021-09-01 | CMO East 2 | MURRAY | Actual | 0
23 | 2021-09-01 | West | Terra Firma | Budget
23 | 2021-09-01 | West | Terra Firma | Forecast | 0
23 | 2021-09-01 | West | Terra Firma | Actual | 0
23 | 2021-09-01 | West | KLT | Budget
23 | 2021-09-01 | West | KLT | Forecast | 0
23 | 2021-09-01 | West | KLT | Actual | 0
23 | 2021-09-01 | West | Forefront | Budget
23 | 2021-09-01 | West | Forefront | Forecast | 0
23 | 2021-09-01 | West | Forefront | Actual | 0
23 | 2021-09-01 | West | DPF | Budget
23 | 2021-09-01 | West | DPF | Forecast | 0
23 | 2021-09-01 | West | DPF | Actual | 0
23 | 2021-09-01 | West | OMJ | Budget
23 | 2021-09-01 | West | OMJ | Forecast | 0
23 | 2021-09-01 | West | OMJ | Actual | 0
23 | 2021-09-01 | West | DHB Utilities | Budget
23 | 2021-09-01 | West | DHB Utilities | Forecast | 0
23 | 2021-09-01 | West | DHB Utilities | Actual | 0
23 | 2021-09-01 | West | JDT | Budget
23 | 2021-09-01 | West | JDT | Forecast | 0
23 | 2021-09-01 | West | JDT | Actual | 0
23 | 2021-09-01 | West | MURRAY | Budget
23 | 2021-09-01 | West | MURRAY | Forecast | 0
23 | 2021-09-01 | West | MURRAY | Actual | 0
23 | 2021-09-01 | East | Terra Firma | Budget
23 | 2021-09-01 | East | Terra Firma | Forecast | 0
23 | 2021-09-01 | East | Terra Firma | Actual | 0
23 | 2021-09-01 | East | KLT | Budget
23 | 2021-09-01 | East | KLT | Forecast | 0
23 | 2021-09-01 | East | KLT | Actual | 0
23 | 2021-09-01 | East | Forefront | Budget
23 | 2021-09-01 | East | Forefront | Forecast | 0
23 | 2021-09-01 | East | Forefront | Actual | 0
23 | 2021-09-01 | East | DPF | Budget
23 | 2021-09-01 | East | DPF | Forecast | 0
23 | 2021-09-01 | East | DPF | Actual | 0
23 | 2021-09-01 | East | OMJ | Budget
23 | 2021-09-01 | East | OMJ | Forecast | 0
23 | 2021-09-01 | East | OMJ | Actual | 0
23 | 2021-09-01 | East | DHB Utilities | Budget
23 | 2021-09-01 | East | DHB Utilities | Forecast | 0
23 | 2021-09-01 | East | DHB Utilities | Actual | 0
23 | 2021-09-01 | East | JDT | Budget
23 | 2021-09-01 | East | JDT | Forecast | 0
23 | 2021-09-01 | East | JDT | Actual | 0
23 | 2021-09-01 | East | MURRAY | Budget
23 | 2021-09-01 | East | MURRAY | Forecast | 0
23 | 2021-09-01 | East | MURRAY | Actual | 0
23 | 2021-09-01 | Central | Terra Firma | Budget
23 | 2021-09-01 | Central | Terra Firma | Forecast | 0
23 | 2021-09-01 | Central | Terra Firma | Actual | 0
23 | 2021-09-01 | Central | KLT | Budget
23 | 2021-09-01 | Central | KLT | Forecast | 0
23 | 2021-09-01 | Central | KLT | Actual | 0
23 | 2021-09-01 | Central | Forefront | Budget
23 | 2021-09-01 | Central | Forefront | Forecast | 0
23 | 2021-09-01 | Central | Forefront | Actual | 0
23 | 2021-09-01 | Central | DPF | Budget
23 | 2021-09-01 | Central | DPF | Forecast | 0
23 | 2021-09-01 | Central | DPF | Actual | 0
23 | 2021-09-01 | Central | OMJ | Budget
23 | 2021-09-01 | Central | OMJ | Forecast | 0
23 | 2021-09-01 | Central | OMJ | Actual | 0
23 | 2021-09-01 | Central | DHB Utilities | Budget
23 | 2021-09-01 | Central | DHB Utilities | Forecast | 0
23 | 2021-09-01 | Central | DHB Utilities | Actual | 0
23 | 2021-09-01 | Central | JDT | Budget
23 | 2021-09-01 | Central | JDT | Forecast | 0
23 | 2021-09-01 | Central | JDT | Actual | 0
23 | 2021-09-01 | Central | MURRAY | Budget
23 | 2021-09-01 | Central | MURRAY | Forecast | 0
23 | 2021-09-01 | Central | MURRAY | Actual | 0
23 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Budget
23 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Budget
23 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Budget
23 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Budget
23 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | West | DIRECT MOLE | Budget
23 | 2021-09-01 | West | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | West | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | East | DIRECT MOLE | Budget
23 | 2021-09-01 | East | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | East | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | Central | DIRECT MOLE | Budget
23 | 2021-09-01 | Central | DIRECT MOLE | Forecast | 0
23 | 2021-09-01 | Central | DIRECT MOLE | Actual | 0
23 | 2021-09-01 | CMO West 1 | SQS | Budget
23 | 2021-09-01 | CMO West 1 | SQS | Forecast | 0
23 | 2021-09-01 | CMO West 1 | SQS | Actual | 0
23 | 2021-09-01 | CMO West 2 | SQS | Budget
23 | 2021-09-01 | CMO West 2 | SQS | Forecast | 0
23 | 2021-09-01 | CMO West 2 | SQS | Actual | 0
23 | 2021-09-01 | CMO East 1 | SQS | Budget
23 | 2021-09-01 | CMO East 1 | SQS | Forecast | 0
23 | 2021-09-01 | CMO East 1 | SQS | Actual | 0
23 | 2021-09-01 | CMO East 2 | SQS | Budget
23 | 2021-09-01 | CMO East 2 | SQS | Forecast | 0
23 | 2021-09-01 | CMO East 2 | SQS | Actual | 0
23 | 2021-09-01 | West | SQS | Budget
23 | 2021-09-01 | West | SQS | Forecast | 0
23 | 2021-09-01 | West | SQS | Actual | 0
23 | 2021-09-01 | East | SQS | Budget
23 | 2021-09-01 | East | SQS | Forecast | 0
24 | 2021-09-01 | East | SQS | Actual | 0
24 | 2021-09-01 | Central | SQS | Budget
24 | 2021-09-01 | Central | SQS | Forecast | 0
23 | 2021-09-01 | Central | SQS | Actual | 0
24 | 2021-09-01 | CMO West 1 | Terra Firma | Budget
24 | 2021-09-01 | CMO West 1 | Terra Firma | Forecast | 0
24 | 2021-09-01 | CMO West 1 | Terra Firma | Actual | 0
24 | 2021-09-01 | CMO West 1 | KLT | Budget
24 | 2021-09-01 | CMO West 1 | KLT | Forecast | 0
24 | 2021-09-01 | CMO West 1 | KLT | Actual | 0
24 | 2021-09-01 | CMO West 1 | Forefront | Budget
24 | 2021-09-01 | CMO West 1 | Forefront | Forecast | 0
24 | 2021-09-01 | CMO West 1 | Forefront | Actual | 0
24 | 2021-09-01 | CMO West 1 | DPF | Budget
24 | 2021-09-01 | CMO West 1 | DPF | Forecast | 0
24 | 2021-09-01 | CMO West 1 | DPF | Actual | 0
24 | 2021-09-01 | CMO West 1 | OMJ | Budget
24 | 2021-09-01 | CMO West 1 | OMJ | Forecast | 0
24 | 2021-09-01 | CMO West 1 | OMJ | Actual | 0
24 | 2021-09-01 | CMO West 1 | DHB Utilities | Budget
24 | 2021-09-01 | CMO West 1 | DHB Utilities | Forecast | 0
24 | 2021-09-01 | CMO West 1 | DHB Utilities | Actual | 0
24 | 2021-09-01 | CMO West 1 | JDT | Budget
24 | 2021-09-01 | CMO West 1 | JDT | Forecast | 0
24 | 2021-09-01 | CMO West 1 | JDT | Actual | 0
24 | 2021-09-01 | CMO West 1 | MURRAY | Budget
24 | 2021-09-01 | CMO West 1 | MURRAY | Forecast | 0
24 | 2021-09-01 | CMO West 1 | MURRAY | Actual | 0
24 | 2021-09-01 | CMO West 2 | Terra Firma | Budget
24 | 2021-09-01 | CMO West 2 | Terra Firma | Forecast | 0
24 | 2021-09-01 | CMO West 2 | Terra Firma | Actual | 0
24 | 2021-09-01 | CMO West 2 | KLT | Budget
24 | 2021-09-01 | CMO West 2 | KLT | Forecast | 0
24 | 2021-09-01 | CMO West 2 | KLT | Actual | 0
24 | 2021-09-01 | CMO West 2 | Forefront | Budget
24 | 2021-09-01 | CMO West 2 | Forefront | Forecast | 0
24 | 2021-09-01 | CMO West 2 | Forefront | Actual | 0
24 | 2021-09-01 | CMO West 2 | DPF | Budget
24 | 2021-09-01 | CMO West 2 | DPF | Forecast | 0
24 | 2021-09-01 | CMO West 2 | DPF | Actual | 0
24 | 2021-09-01 | CMO West 2 | OMJ | Budget
24 | 2021-09-01 | CMO West 2 | OMJ | Forecast | 0
24 | 2021-09-01 | CMO West 2 | OMJ | Actual | 0
24 | 2021-09-01 | CMO West 2 | DHB Utilities | Budget
24 | 2021-09-01 | CMO West 2 | DHB Utilities | Forecast | 0
24 | 2021-09-01 | CMO West 2 | DHB Utilities | Actual | 0
24 | 2021-09-01 | CMO West 2 | JDT | Budget
24 | 2021-09-01 | CMO West 2 | JDT | Forecast | 0
24 | 2021-09-01 | CMO West 2 | JDT | Actual | 0
24 | 2021-09-01 | CMO West 2 | MURRAY | Budget
24 | 2021-09-01 | CMO West 2 | MURRAY | Forecast | 0
24 | 2021-09-01 | CMO West 2 | MURRAY | Actual | 0
24 | 2021-09-01 | CMO East 1 | Terra Firma | Budget
24 | 2021-09-01 | CMO East 1 | Terra Firma | Forecast | 0
24 | 2021-09-01 | CMO East 1 | Terra Firma | Actual | 0
24 | 2021-09-01 | CMO East 1 | KLT | Budget
24 | 2021-09-01 | CMO East 1 | KLT | Forecast | 0
24 | 2021-09-01 | CMO East 1 | KLT | Actual | 0
24 | 2021-09-01 | CMO East 1 | Forefront | Budget
24 | 2021-09-01 | CMO East 1 | Forefront | Forecast | 0
24 | 2021-09-01 | CMO East 1 | Forefront | Actual | 0
24 | 2021-09-01 | CMO East 1 | DPF | Budget
24 | 2021-09-01 | CMO East 1 | DPF | Forecast | 0
24 | 2021-09-01 | CMO East 1 | DPF | Actual | 0
24 | 2021-09-01 | CMO East 1 | OMJ | Budget
24 | 2021-09-01 | CMO East 1 | OMJ | Forecast | 0
24 | 2021-09-01 | CMO East 1 | OMJ | Actual | 0
24 | 2021-09-01 | CMO East 1 | DHB Utilities | Budget
24 | 2021-09-01 | CMO East 1 | DHB Utilities | Forecast | 0
24 | 2021-09-01 | CMO East 1 | DHB Utilities | Actual | 0
24 | 2021-09-01 | CMO East 1 | JDT | Budget
24 | 2021-09-01 | CMO East 1 | JDT | Forecast | 0
24 | 2021-09-01 | CMO East 1 | JDT | Actual | 0
24 | 2021-09-01 | CMO East 1 | MURRAY | Budget
24 | 2021-09-01 | CMO East 1 | MURRAY | Forecast | 0
24 | 2021-09-01 | CMO East 1 | MURRAY | Actual | 0
24 | 2021-09-01 | CMO East 2 | Terra Firma | Budget
24 | 2021-09-01 | CMO East 2 | Terra Firma | Forecast | 0
24 | 2021-09-01 | CMO East 2 | Terra Firma | Actual | 0
24 | 2021-09-01 | CMO East 2 | KLT | Budget
24 | 2021-09-01 | CMO East 2 | KLT | Forecast | 0
24 | 2021-09-01 | CMO East 2 | KLT | Actual | 0
24 | 2021-09-01 | CMO East 2 | Forefront | Budget
24 | 2021-09-01 | CMO East 2 | Forefront | Forecast | 0
24 | 2021-09-01 | CMO East 2 | Forefront | Actual | 0
24 | 2021-09-01 | CMO East 2 | DPF | Budget
24 | 2021-09-01 | CMO East 2 | DPF | Forecast | 0
24 | 2021-09-01 | CMO East 2 | DPF | Actual | 0
24 | 2021-09-01 | CMO East 2 | OMJ | Budget
24 | 2021-09-01 | CMO East 2 | OMJ | Forecast | 0
24 | 2021-09-01 | CMO East 2 | OMJ | Actual | 0
24 | 2021-09-01 | CMO East 2 | DHB Utilities | Budget
24 | 2021-09-01 | CMO East 2 | DHB Utilities | Forecast | 0
24 | 2021-09-01 | CMO East 2 | DHB Utilities | Actual | 0
24 | 2021-09-01 | CMO East 2 | JDT | Budget
24 | 2021-09-01 | CMO East 2 | JDT | Forecast | 0
24 | 2021-09-01 | CMO East 2 | JDT | Actual | 0
24 | 2021-09-01 | CMO East 2 | MURRAY | Budget
24 | 2021-09-01 | CMO East 2 | MURRAY | Forecast | 0
24 | 2021-09-01 | CMO East 2 | MURRAY | Actual | 0
24 | 2021-09-01 | West | Terra Firma | Budget
24 | 2021-09-01 | West | Terra Firma | Forecast | 0
24 | 2021-09-01 | West | Terra Firma | Actual | 0
24 | 2021-09-01 | West | KLT | Budget
24 | 2021-09-01 | West | KLT | Forecast | 0
24 | 2021-09-01 | West | KLT | Actual | 0
24 | 2021-09-01 | West | Forefront | Budget
24 | 2021-09-01 | West | Forefront | Forecast | 0
24 | 2021-09-01 | West | Forefront | Actual | 0
24 | 2021-09-01 | West | DPF | Budget
24 | 2021-09-01 | West | DPF | Forecast | 0
24 | 2021-09-01 | West | DPF | Actual | 0
24 | 2021-09-01 | West | OMJ | Budget
24 | 2021-09-01 | West | OMJ | Forecast | 0
24 | 2021-09-01 | West | OMJ | Actual | 0
24 | 2021-09-01 | West | DHB Utilities | Budget
24 | 2021-09-01 | West | DHB Utilities | Forecast | 0
24 | 2021-09-01 | West | DHB Utilities | Actual | 0
24 | 2021-09-01 | West | JDT | Budget
24 | 2021-09-01 | West | JDT | Forecast | 0
24 | 2021-09-01 | West | JDT | Actual | 0
24 | 2021-09-01 | West | MURRAY | Budget
24 | 2021-09-01 | West | MURRAY | Forecast | 0
24 | 2021-09-01 | West | MURRAY | Actual | 0
24 | 2021-09-01 | East | Terra Firma | Budget
24 | 2021-09-01 | East | Terra Firma | Forecast | 0
24 | 2021-09-01 | East | Terra Firma | Actual | 0
24 | 2021-09-01 | East | KLT | Budget
24 | 2021-09-01 | East | KLT | Forecast | 0
24 | 2021-09-01 | East | KLT | Actual | 0
24 | 2021-09-01 | East | Forefront | Budget
24 | 2021-09-01 | East | Forefront | Forecast | 0
24 | 2021-09-01 | East | Forefront | Actual | 0
24 | 2021-09-01 | East | DPF | Budget
24 | 2021-09-01 | East | DPF | Forecast | 0
24 | 2021-09-01 | East | DPF | Actual | 0
24 | 2021-09-01 | East | OMJ | Budget
24 | 2021-09-01 | East | OMJ | Forecast | 0
24 | 2021-09-01 | East | OMJ | Actual | 0
24 | 2021-09-01 | East | DHB Utilities | Budget
24 | 2021-09-01 | East | DHB Utilities | Forecast | 0
24 | 2021-09-01 | East | DHB Utilities | Actual | 0
24 | 2021-09-01 | East | JDT | Budget
24 | 2021-09-01 | East | JDT | Forecast | 0
24 | 2021-09-01 | East | JDT | Actual | 0
24 | 2021-09-01 | East | MURRAY | Budget
24 | 2021-09-01 | East | MURRAY | Forecast | 0
24 | 2021-09-01 | East | MURRAY | Actual | 0
24 | 2021-09-01 | Central | Terra Firma | Budget
24 | 2021-09-01 | Central | Terra Firma | Forecast | 0
24 | 2021-09-01 | Central | Terra Firma | Actual | 0
24 | 2021-09-01 | Central | KLT | Budget
24 | 2021-09-01 | Central | KLT | Forecast | 0
24 | 2021-09-01 | Central | KLT | Actual | 0
24 | 2021-09-01 | Central | Forefront | Budget
24 | 2021-09-01 | Central | Forefront | Forecast | 0
24 | 2021-09-01 | Central | Forefront | Actual | 0
24 | 2021-09-01 | Central | DPF | Budget
24 | 2021-09-01 | Central | DPF | Forecast | 0
24 | 2021-09-01 | Central | DPF | Actual | 0
24 | 2021-09-01 | Central | OMJ | Budget
24 | 2021-09-01 | Central | OMJ | Forecast | 0
24 | 2021-09-01 | Central | OMJ | Actual | 0
24 | 2021-09-01 | Central | DHB Utilities | Budget
24 | 2021-09-01 | Central | DHB Utilities | Forecast | 0
24 | 2021-09-01 | Central | DHB Utilities | Actual | 0
24 | 2021-09-01 | Central | JDT | Budget
24 | 2021-09-01 | Central | JDT | Forecast | 0
24 | 2021-09-01 | Central | JDT | Actual | 0
24 | 2021-09-01 | Central | MURRAY | Budget
24 | 2021-09-01 | Central | MURRAY | Forecast | 0
24 | 2021-09-01 | Central | MURRAY | Actual | 0
24 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Budget
24 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Budget
24 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Budget
24 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Budget
24 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | West | DIRECT MOLE | Budget
24 | 2021-09-01 | West | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | West | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | East | DIRECT MOLE | Budget
24 | 2021-09-01 | East | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | East | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | Central | DIRECT MOLE | Budget
24 | 2021-09-01 | Central | DIRECT MOLE | Forecast | 0
24 | 2021-09-01 | Central | DIRECT MOLE | Actual | 0
24 | 2021-09-01 | CMO West 1 | SQS | Budget
24 | 2021-09-01 | CMO West 1 | SQS | Forecast | 0
24 | 2021-09-01 | CMO West 1 | SQS | Actual | 0
24 | 2021-09-01 | CMO West 2 | SQS | Budget
24 | 2021-09-01 | CMO West 2 | SQS | Forecast | 0
24 | 2021-09-01 | CMO West 2 | SQS | Actual | 0
24 | 2021-09-01 | CMO East 1 | SQS | Budget
24 | 2021-09-01 | CMO East 1 | SQS | Forecast | 0
24 | 2021-09-01 | CMO East 1 | SQS | Actual | 0
24 | 2021-09-01 | CMO East 2 | SQS | Budget
24 | 2021-09-01 | CMO East 2 | SQS | Forecast | 0
24 | 2021-09-01 | CMO East 2 | SQS | Actual | 0
24 | 2021-09-01 | West | SQS | Budget
24 | 2021-09-01 | West | SQS | Forecast | 0
24 | 2021-09-01 | West | SQS | Actual | 0
24 | 2021-09-01 | East | SQS | Budget
24 | 2021-09-01 | East | SQS | Forecast | 0
25 | 2021-09-01 | East | SQS | Actual | 0
25 | 2021-09-01 | Central | SQS | Budget
25 | 2021-09-01 | Central | SQS | Forecast | 0
24 | 2021-09-01 | Central | SQS | Actual | 0
25 | 2021-09-01 | CMO West 1 | Terra Firma | Budget
25 | 2021-09-01 | CMO West 1 | Terra Firma | Forecast | 0
25 | 2021-09-01 | CMO West 1 | Terra Firma | Actual | 0
25 | 2021-09-01 | CMO West 1 | KLT | Budget
25 | 2021-09-01 | CMO West 1 | KLT | Forecast | 0
25 | 2021-09-01 | CMO West 1 | KLT | Actual | 0
25 | 2021-09-01 | CMO West 1 | Forefront | Budget
25 | 2021-09-01 | CMO West 1 | Forefront | Forecast | 0
25 | 2021-09-01 | CMO West 1 | Forefront | Actual | 0
25 | 2021-09-01 | CMO West 1 | DPF | Budget
25 | 2021-09-01 | CMO West 1 | DPF | Forecast | 0
25 | 2021-09-01 | CMO West 1 | DPF | Actual | 0
25 | 2021-09-01 | CMO West 1 | OMJ | Budget
25 | 2021-09-01 | CMO West 1 | OMJ | Forecast | 0
25 | 2021-09-01 | CMO West 1 | OMJ | Actual | 0
25 | 2021-09-01 | CMO West 1 | DHB Utilities | Budget
25 | 2021-09-01 | CMO West 1 | DHB Utilities | Forecast | 0
25 | 2021-09-01 | CMO West 1 | DHB Utilities | Actual | 0
25 | 2021-09-01 | CMO West 1 | JDT | Budget
25 | 2021-09-01 | CMO West 1 | JDT | Forecast | 0
25 | 2021-09-01 | CMO West 1 | JDT | Actual | 0
25 | 2021-09-01 | CMO West 1 | MURRAY | Budget
25 | 2021-09-01 | CMO West 1 | MURRAY | Forecast | 0
25 | 2021-09-01 | CMO West 1 | MURRAY | Actual | 0
25 | 2021-09-01 | CMO West 2 | Terra Firma | Budget
25 | 2021-09-01 | CMO West 2 | Terra Firma | Forecast | 0
25 | 2021-09-01 | CMO West 2 | Terra Firma | Actual | 0
25 | 2021-09-01 | CMO West 2 | KLT | Budget
25 | 2021-09-01 | CMO West 2 | KLT | Forecast | 0
25 | 2021-09-01 | CMO West 2 | KLT | Actual | 0
25 | 2021-09-01 | CMO West 2 | Forefront | Budget
25 | 2021-09-01 | CMO West 2 | Forefront | Forecast | 0
25 | 2021-09-01 | CMO West 2 | Forefront | Actual | 0
25 | 2021-09-01 | CMO West 2 | DPF | Budget
25 | 2021-09-01 | CMO West 2 | DPF | Forecast | 0
25 | 2021-09-01 | CMO West 2 | DPF | Actual | 0
25 | 2021-09-01 | CMO West 2 | OMJ | Budget
25 | 2021-09-01 | CMO West 2 | OMJ | Forecast | 0
25 | 2021-09-01 | CMO West 2 | OMJ | Actual | 0
25 | 2021-09-01 | CMO West 2 | DHB Utilities | Budget
25 | 2021-09-01 | CMO West 2 | DHB Utilities | Forecast | 0
25 | 2021-09-01 | CMO West 2 | DHB Utilities | Actual | 0
25 | 2021-09-01 | CMO West 2 | JDT | Budget
25 | 2021-09-01 | CMO West 2 | JDT | Forecast | 0
25 | 2021-09-01 | CMO West 2 | JDT | Actual | 0
25 | 2021-09-01 | CMO West 2 | MURRAY | Budget
25 | 2021-09-01 | CMO West 2 | MURRAY | Forecast | 0
25 | 2021-09-01 | CMO West 2 | MURRAY | Actual | 0
25 | 2021-09-01 | CMO East 1 | Terra Firma | Budget
25 | 2021-09-01 | CMO East 1 | Terra Firma | Forecast | 0
25 | 2021-09-01 | CMO East 1 | Terra Firma | Actual | 0
25 | 2021-09-01 | CMO East 1 | KLT | Budget
25 | 2021-09-01 | CMO East 1 | KLT | Forecast | 0
25 | 2021-09-01 | CMO East 1 | KLT | Actual | 0
25 | 2021-09-01 | CMO East 1 | Forefront | Budget
25 | 2021-09-01 | CMO East 1 | Forefront | Forecast | 0
25 | 2021-09-01 | CMO East 1 | Forefront | Actual | 0
25 | 2021-09-01 | CMO East 1 | DPF | Budget
25 | 2021-09-01 | CMO East 1 | DPF | Forecast | 0
25 | 2021-09-01 | CMO East 1 | DPF | Actual | 0
25 | 2021-09-01 | CMO East 1 | OMJ | Budget
25 | 2021-09-01 | CMO East 1 | OMJ | Forecast | 0
25 | 2021-09-01 | CMO East 1 | OMJ | Actual | 0
25 | 2021-09-01 | CMO East 1 | DHB Utilities | Budget
25 | 2021-09-01 | CMO East 1 | DHB Utilities | Forecast | 0
25 | 2021-09-01 | CMO East 1 | DHB Utilities | Actual | 0
25 | 2021-09-01 | CMO East 1 | JDT | Budget
25 | 2021-09-01 | CMO East 1 | JDT | Forecast | 0
25 | 2021-09-01 | CMO East 1 | JDT | Actual | 0
25 | 2021-09-01 | CMO East 1 | MURRAY | Budget
25 | 2021-09-01 | CMO East 1 | MURRAY | Forecast | 0
25 | 2021-09-01 | CMO East 1 | MURRAY | Actual | 0
25 | 2021-09-01 | CMO East 2 | Terra Firma | Budget
25 | 2021-09-01 | CMO East 2 | Terra Firma | Forecast | 0
25 | 2021-09-01 | CMO East 2 | Terra Firma | Actual | 0
25 | 2021-09-01 | CMO East 2 | KLT | Budget
25 | 2021-09-01 | CMO East 2 | KLT | Forecast | 0
25 | 2021-09-01 | CMO East 2 | KLT | Actual | 0
25 | 2021-09-01 | CMO East 2 | Forefront | Budget
25 | 2021-09-01 | CMO East 2 | Forefront | Forecast | 0
25 | 2021-09-01 | CMO East 2 | Forefront | Actual | 0
25 | 2021-09-01 | CMO East 2 | DPF | Budget
25 | 2021-09-01 | CMO East 2 | DPF | Forecast | 0
25 | 2021-09-01 | CMO East 2 | DPF | Actual | 0
25 | 2021-09-01 | CMO East 2 | OMJ | Budget
25 | 2021-09-01 | CMO East 2 | OMJ | Forecast | 0
25 | 2021-09-01 | CMO East 2 | OMJ | Actual | 0
25 | 2021-09-01 | CMO East 2 | DHB Utilities | Budget
25 | 2021-09-01 | CMO East 2 | DHB Utilities | Forecast | 0
25 | 2021-09-01 | CMO East 2 | DHB Utilities | Actual | 0
25 | 2021-09-01 | CMO East 2 | JDT | Budget
25 | 2021-09-01 | CMO East 2 | JDT | Forecast | 0
25 | 2021-09-01 | CMO East 2 | JDT | Actual | 0
25 | 2021-09-01 | CMO East 2 | MURRAY | Budget
25 | 2021-09-01 | CMO East 2 | MURRAY | Forecast | 0
25 | 2021-09-01 | CMO East 2 | MURRAY | Actual | 0
25 | 2021-09-01 | West | Terra Firma | Budget
25 | 2021-09-01 | West | Terra Firma | Forecast | 0
25 | 2021-09-01 | West | Terra Firma | Actual | 0
25 | 2021-09-01 | West | KLT | Budget
25 | 2021-09-01 | West | KLT | Forecast | 0
25 | 2021-09-01 | West | KLT | Actual | 0
25 | 2021-09-01 | West | Forefront | Budget
25 | 2021-09-01 | West | Forefront | Forecast | 0
25 | 2021-09-01 | West | Forefront | Actual | 0
25 | 2021-09-01 | West | DPF | Budget
25 | 2021-09-01 | West | DPF | Forecast | 0
25 | 2021-09-01 | West | DPF | Actual | 0
25 | 2021-09-01 | West | OMJ | Budget
25 | 2021-09-01 | West | OMJ | Forecast | 0
25 | 2021-09-01 | West | OMJ | Actual | 0
25 | 2021-09-01 | West | DHB Utilities | Budget
25 | 2021-09-01 | West | DHB Utilities | Forecast | 0
25 | 2021-09-01 | West | DHB Utilities | Actual | 0
25 | 2021-09-01 | West | JDT | Budget
25 | 2021-09-01 | West | JDT | Forecast | 0
25 | 2021-09-01 | West | JDT | Actual | 0
25 | 2021-09-01 | West | MURRAY | Budget
25 | 2021-09-01 | West | MURRAY | Forecast | 0
25 | 2021-09-01 | West | MURRAY | Actual | 0
25 | 2021-09-01 | East | Terra Firma | Budget
25 | 2021-09-01 | East | Terra Firma | Forecast | 0
25 | 2021-09-01 | East | Terra Firma | Actual | 0
25 | 2021-09-01 | East | KLT | Budget
25 | 2021-09-01 | East | KLT | Forecast | 0
25 | 2021-09-01 | East | KLT | Actual | 0
25 | 2021-09-01 | East | Forefront | Budget
25 | 2021-09-01 | East | Forefront | Forecast | 0
25 | 2021-09-01 | East | Forefront | Actual | 0
25 | 2021-09-01 | East | DPF | Budget
25 | 2021-09-01 | East | DPF | Forecast | 0
25 | 2021-09-01 | East | DPF | Actual | 0
25 | 2021-09-01 | East | OMJ | Budget
25 | 2021-09-01 | East | OMJ | Forecast | 0
25 | 2021-09-01 | East | OMJ | Actual | 0
25 | 2021-09-01 | East | DHB Utilities | Budget
25 | 2021-09-01 | East | DHB Utilities | Forecast | 0
25 | 2021-09-01 | East | DHB Utilities | Actual | 0
25 | 2021-09-01 | East | JDT | Budget
25 | 2021-09-01 | East | JDT | Forecast | 0
25 | 2021-09-01 | East | JDT | Actual | 0
25 | 2021-09-01 | East | MURRAY | Budget
25 | 2021-09-01 | East | MURRAY | Forecast | 0
25 | 2021-09-01 | East | MURRAY | Actual | 0
25 | 2021-09-01 | Central | Terra Firma | Budget
25 | 2021-09-01 | Central | Terra Firma | Forecast | 0
25 | 2021-09-01 | Central | Terra Firma | Actual | 0
25 | 2021-09-01 | Central | KLT | Budget
25 | 2021-09-01 | Central | KLT | Forecast | 0
25 | 2021-09-01 | Central | KLT | Actual | 0
25 | 2021-09-01 | Central | Forefront | Budget
25 | 2021-09-01 | Central | Forefront | Forecast | 0
25 | 2021-09-01 | Central | Forefront | Actual | 0
25 | 2021-09-01 | Central | DPF | Budget
25 | 2021-09-01 | Central | DPF | Forecast | 0
25 | 2021-09-01 | Central | DPF | Actual | 0
25 | 2021-09-01 | Central | OMJ | Budget
25 | 2021-09-01 | Central | OMJ | Forecast | 0
25 | 2021-09-01 | Central | OMJ | Actual | 0
25 | 2021-09-01 | Central | DHB Utilities | Budget
25 | 2021-09-01 | Central | DHB Utilities | Forecast | 0
25 | 2021-09-01 | Central | DHB Utilities | Actual | 0
25 | 2021-09-01 | Central | JDT | Budget
25 | 2021-09-01 | Central | JDT | Forecast | 0
25 | 2021-09-01 | Central | JDT | Actual | 0
25 | 2021-09-01 | Central | MURRAY | Budget
25 | 2021-09-01 | Central | MURRAY | Forecast | 0
25 | 2021-09-01 | Central | MURRAY | Actual | 0
25 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Budget
25 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Budget
25 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Budget
25 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Budget
25 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | West | DIRECT MOLE | Budget
25 | 2021-09-01 | West | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | West | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | East | DIRECT MOLE | Budget
25 | 2021-09-01 | East | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | East | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | Central | DIRECT MOLE | Budget
25 | 2021-09-01 | Central | DIRECT MOLE | Forecast | 0
25 | 2021-09-01 | Central | DIRECT MOLE | Actual | 0
25 | 2021-09-01 | CMO West 1 | SQS | Budget
25 | 2021-09-01 | CMO West 1 | SQS | Forecast | 0
25 | 2021-09-01 | CMO West 1 | SQS | Actual | 0
25 | 2021-09-01 | CMO West 2 | SQS | Budget
25 | 2021-09-01 | CMO West 2 | SQS | Forecast | 0
25 | 2021-09-01 | CMO West 2 | SQS | Actual | 0
25 | 2021-09-01 | CMO East 1 | SQS | Budget
25 | 2021-09-01 | CMO East 1 | SQS | Forecast | 0
25 | 2021-09-01 | CMO East 1 | SQS | Actual | 0
25 | 2021-09-01 | CMO East 2 | SQS | Budget
25 | 2021-09-01 | CMO East 2 | SQS | Forecast | 0
25 | 2021-09-01 | CMO East 2 | SQS | Actual | 0
25 | 2021-09-01 | West | SQS | Budget
25 | 2021-09-01 | West | SQS | Forecast | 0
25 | 2021-09-01 | West | SQS | Actual | 0
25 | 2021-09-01 | East | SQS | Budget
25 | 2021-09-01 | East | SQS | Forecast | 0
26 | 2021-09-01 | East | SQS | Actual | 0
26 | 2021-09-01 | Central | SQS | Budget
26 | 2021-09-01 | Central | SQS | Forecast | 0
25 | 2021-09-01 | Central | SQS | Actual | 0
26 | 2021-09-01 | CMO West 1 | Terra Firma | Budget
26 | 2021-09-01 | CMO West 1 | Terra Firma | Forecast | 0
26 | 2021-09-01 | CMO West 1 | Terra Firma | Actual | 0
26 | 2021-09-01 | CMO West 1 | KLT | Budget
26 | 2021-09-01 | CMO West 1 | KLT | Forecast | 0
26 | 2021-09-01 | CMO West 1 | KLT | Actual | 0
26 | 2021-09-01 | CMO West 1 | Forefront | Budget
26 | 2021-09-01 | CMO West 1 | Forefront | Forecast | 0
26 | 2021-09-01 | CMO West 1 | Forefront | Actual | 0
26 | 2021-09-01 | CMO West 1 | DPF | Budget
26 | 2021-09-01 | CMO West 1 | DPF | Forecast | 0
26 | 2021-09-01 | CMO West 1 | DPF | Actual | 0
26 | 2021-09-01 | CMO West 1 | OMJ | Budget
26 | 2021-09-01 | CMO West 1 | OMJ | Forecast | 0
26 | 2021-09-01 | CMO West 1 | OMJ | Actual | 0
26 | 2021-09-01 | CMO West 1 | DHB Utilities | Budget
26 | 2021-09-01 | CMO West 1 | DHB Utilities | Forecast | 0
26 | 2021-09-01 | CMO West 1 | DHB Utilities | Actual | 0
26 | 2021-09-01 | CMO West 1 | JDT | Budget
26 | 2021-09-01 | CMO West 1 | JDT | Forecast | 0
26 | 2021-09-01 | CMO West 1 | JDT | Actual | 0
26 | 2021-09-01 | CMO West 1 | MURRAY | Budget
26 | 2021-09-01 | CMO West 1 | MURRAY | Forecast | 0
26 | 2021-09-01 | CMO West 1 | MURRAY | Actual | 0
26 | 2021-09-01 | CMO West 2 | Terra Firma | Budget
26 | 2021-09-01 | CMO West 2 | Terra Firma | Forecast | 0
26 | 2021-09-01 | CMO West 2 | Terra Firma | Actual | 0
26 | 2021-09-01 | CMO West 2 | KLT | Budget
26 | 2021-09-01 | CMO West 2 | KLT | Forecast | 0
26 | 2021-09-01 | CMO West 2 | KLT | Actual | 0
26 | 2021-09-01 | CMO West 2 | Forefront | Budget
26 | 2021-09-01 | CMO West 2 | Forefront | Forecast | 0
26 | 2021-09-01 | CMO West 2 | Forefront | Actual | 0
26 | 2021-09-01 | CMO West 2 | DPF | Budget
26 | 2021-09-01 | CMO West 2 | DPF | Forecast | 0
26 | 2021-09-01 | CMO West 2 | DPF | Actual | 0
26 | 2021-09-01 | CMO West 2 | OMJ | Budget
26 | 2021-09-01 | CMO West 2 | OMJ | Forecast | 0
26 | 2021-09-01 | CMO West 2 | OMJ | Actual | 0
26 | 2021-09-01 | CMO West 2 | DHB Utilities | Budget
26 | 2021-09-01 | CMO West 2 | DHB Utilities | Forecast | 0
26 | 2021-09-01 | CMO West 2 | DHB Utilities | Actual | 0
26 | 2021-09-01 | CMO West 2 | JDT | Budget
26 | 2021-09-01 | CMO West 2 | JDT | Forecast | 0
26 | 2021-09-01 | CMO West 2 | JDT | Actual | 0
26 | 2021-09-01 | CMO West 2 | MURRAY | Budget
26 | 2021-09-01 | CMO West 2 | MURRAY | Forecast | 0
26 | 2021-09-01 | CMO West 2 | MURRAY | Actual | 0
26 | 2021-09-01 | CMO East 1 | Terra Firma | Budget
26 | 2021-09-01 | CMO East 1 | Terra Firma | Forecast | 0
26 | 2021-09-01 | CMO East 1 | Terra Firma | Actual | 0
26 | 2021-09-01 | CMO East 1 | KLT | Budget
26 | 2021-09-01 | CMO East 1 | KLT | Forecast | 0
26 | 2021-09-01 | CMO East 1 | KLT | Actual | 0
26 | 2021-09-01 | CMO East 1 | Forefront | Budget
26 | 2021-09-01 | CMO East 1 | Forefront | Forecast | 0
26 | 2021-09-01 | CMO East 1 | Forefront | Actual | 0
26 | 2021-09-01 | CMO East 1 | DPF | Budget
26 | 2021-09-01 | CMO East 1 | DPF | Forecast | 0
26 | 2021-09-01 | CMO East 1 | DPF | Actual | 0
26 | 2021-09-01 | CMO East 1 | OMJ | Budget
26 | 2021-09-01 | CMO East 1 | OMJ | Forecast | 0
26 | 2021-09-01 | CMO East 1 | OMJ | Actual | 0
26 | 2021-09-01 | CMO East 1 | DHB Utilities | Budget
26 | 2021-09-01 | CMO East 1 | DHB Utilities | Forecast | 0
26 | 2021-09-01 | CMO East 1 | DHB Utilities | Actual | 0
26 | 2021-09-01 | CMO East 1 | JDT | Budget
26 | 2021-09-01 | CMO East 1 | JDT | Forecast | 0
26 | 2021-09-01 | CMO East 1 | JDT | Actual | 0
26 | 2021-09-01 | CMO East 1 | MURRAY | Budget
26 | 2021-09-01 | CMO East 1 | MURRAY | Forecast | 0
26 | 2021-09-01 | CMO East 1 | MURRAY | Actual | 0
26 | 2021-09-01 | CMO East 2 | Terra Firma | Budget
26 | 2021-09-01 | CMO East 2 | Terra Firma | Forecast | 0
26 | 2021-09-01 | CMO East 2 | Terra Firma | Actual | 0
26 | 2021-09-01 | CMO East 2 | KLT | Budget
26 | 2021-09-01 | CMO East 2 | KLT | Forecast | 0
26 | 2021-09-01 | CMO East 2 | KLT | Actual | 0
26 | 2021-09-01 | CMO East 2 | Forefront | Budget
26 | 2021-09-01 | CMO East 2 | Forefront | Forecast | 0
26 | 2021-09-01 | CMO East 2 | Forefront | Actual | 0
26 | 2021-09-01 | CMO East 2 | DPF | Budget
26 | 2021-09-01 | CMO East 2 | DPF | Forecast | 0
26 | 2021-09-01 | CMO East 2 | DPF | Actual | 0
26 | 2021-09-01 | CMO East 2 | OMJ | Budget
26 | 2021-09-01 | CMO East 2 | OMJ | Forecast | 0
26 | 2021-09-01 | CMO East 2 | OMJ | Actual | 0
26 | 2021-09-01 | CMO East 2 | DHB Utilities | Budget
26 | 2021-09-01 | CMO East 2 | DHB Utilities | Forecast | 0
26 | 2021-09-01 | CMO East 2 | DHB Utilities | Actual | 0
26 | 2021-09-01 | CMO East 2 | JDT | Budget
26 | 2021-09-01 | CMO East 2 | JDT | Forecast | 0
26 | 2021-09-01 | CMO East 2 | JDT | Actual | 0
26 | 2021-09-01 | CMO East 2 | MURRAY | Budget
26 | 2021-09-01 | CMO East 2 | MURRAY | Forecast | 0
26 | 2021-09-01 | CMO East 2 | MURRAY | Actual | 0
26 | 2021-09-01 | West | Terra Firma | Budget
26 | 2021-09-01 | West | Terra Firma | Forecast | 0
26 | 2021-09-01 | West | Terra Firma | Actual | 0
26 | 2021-09-01 | West | KLT | Budget
26 | 2021-09-01 | West | KLT | Forecast | 0
26 | 2021-09-01 | West | KLT | Actual | 0
26 | 2021-09-01 | West | Forefront | Budget
26 | 2021-09-01 | West | Forefront | Forecast | 0
26 | 2021-09-01 | West | Forefront | Actual | 0
26 | 2021-09-01 | West | DPF | Budget
26 | 2021-09-01 | West | DPF | Forecast | 0
26 | 2021-09-01 | West | DPF | Actual | 0
26 | 2021-09-01 | West | OMJ | Budget
26 | 2021-09-01 | West | OMJ | Forecast | 0
26 | 2021-09-01 | West | OMJ | Actual | 0
26 | 2021-09-01 | West | DHB Utilities | Budget
26 | 2021-09-01 | West | DHB Utilities | Forecast | 0
26 | 2021-09-01 | West | DHB Utilities | Actual | 0
26 | 2021-09-01 | West | JDT | Budget
26 | 2021-09-01 | West | JDT | Forecast | 0
26 | 2021-09-01 | West | JDT | Actual | 0
26 | 2021-09-01 | West | MURRAY | Budget
26 | 2021-09-01 | West | MURRAY | Forecast | 0
26 | 2021-09-01 | West | MURRAY | Actual | 0
26 | 2021-09-01 | East | Terra Firma | Budget
26 | 2021-09-01 | East | Terra Firma | Forecast | 0
26 | 2021-09-01 | East | Terra Firma | Actual | 0
26 | 2021-09-01 | East | KLT | Budget
26 | 2021-09-01 | East | KLT | Forecast | 0
26 | 2021-09-01 | East | KLT | Actual | 0
26 | 2021-09-01 | East | Forefront | Budget
26 | 2021-09-01 | East | Forefront | Forecast | 0
26 | 2021-09-01 | East | Forefront | Actual | 0
26 | 2021-09-01 | East | DPF | Budget
26 | 2021-09-01 | East | DPF | Forecast | 0
26 | 2021-09-01 | East | DPF | Actual | 0
26 | 2021-09-01 | East | OMJ | Budget
26 | 2021-09-01 | East | OMJ | Forecast | 0
26 | 2021-09-01 | East | OMJ | Actual | 0
26 | 2021-09-01 | East | DHB Utilities | Budget
26 | 2021-09-01 | East | DHB Utilities | Forecast | 0
26 | 2021-09-01 | East | DHB Utilities | Actual | 0
26 | 2021-09-01 | East | JDT | Budget
26 | 2021-09-01 | East | JDT | Forecast | 0
26 | 2021-09-01 | East | JDT | Actual | 0
26 | 2021-09-01 | East | MURRAY | Budget
26 | 2021-09-01 | East | MURRAY | Forecast | 0
26 | 2021-09-01 | East | MURRAY | Actual | 0
26 | 2021-09-01 | Central | Terra Firma | Budget
26 | 2021-09-01 | Central | Terra Firma | Forecast | 0
26 | 2021-09-01 | Central | Terra Firma | Actual | 0
26 | 2021-09-01 | Central | KLT | Budget
26 | 2021-09-01 | Central | KLT | Forecast | 0
26 | 2021-09-01 | Central | KLT | Actual | 0
26 | 2021-09-01 | Central | Forefront | Budget
26 | 2021-09-01 | Central | Forefront | Forecast | 0
26 | 2021-09-01 | Central | Forefront | Actual | 0
26 | 2021-09-01 | Central | DPF | Budget
26 | 2021-09-01 | Central | DPF | Forecast | 0
26 | 2021-09-01 | Central | DPF | Actual | 0
26 | 2021-09-01 | Central | OMJ | Budget
26 | 2021-09-01 | Central | OMJ | Forecast | 0
26 | 2021-09-01 | Central | OMJ | Actual | 0
26 | 2021-09-01 | Central | DHB Utilities | Budget
26 | 2021-09-01 | Central | DHB Utilities | Forecast | 0
26 | 2021-09-01 | Central | DHB Utilities | Actual | 0
26 | 2021-09-01 | Central | JDT | Budget
26 | 2021-09-01 | Central | JDT | Forecast | 0
26 | 2021-09-01 | Central | JDT | Actual | 0
26 | 2021-09-01 | Central | MURRAY | Budget
26 | 2021-09-01 | Central | MURRAY | Forecast | 0
26 | 2021-09-01 | Central | MURRAY | Actual | 0
26 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Budget
26 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Budget
26 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Budget
26 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Budget
26 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | West | DIRECT MOLE | Budget
26 | 2021-09-01 | West | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | West | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | East | DIRECT MOLE | Budget
26 | 2021-09-01 | East | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | East | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | Central | DIRECT MOLE | Budget
26 | 2021-09-01 | Central | DIRECT MOLE | Forecast | 0
26 | 2021-09-01 | Central | DIRECT MOLE | Actual | 0
26 | 2021-09-01 | CMO West 1 | SQS | Budget
26 | 2021-09-01 | CMO West 1 | SQS | Forecast | 0
26 | 2021-09-01 | CMO West 1 | SQS | Actual | 0
26 | 2021-09-01 | CMO West 2 | SQS | Budget
26 | 2021-09-01 | CMO West 2 | SQS | Forecast | 0
26 | 2021-09-01 | CMO West 2 | SQS | Actual | 0
26 | 2021-09-01 | CMO East 1 | SQS | Budget
26 | 2021-09-01 | CMO East 1 | SQS | Forecast | 0
26 | 2021-09-01 | CMO East 1 | SQS | Actual | 0
26 | 2021-09-01 | CMO East 2 | SQS | Budget
26 | 2021-09-01 | CMO East 2 | SQS | Forecast | 0
26 | 2021-09-01 | CMO East 2 | SQS | Actual | 0
26 | 2021-09-01 | West | SQS | Budget
26 | 2021-09-01 | West | SQS | Forecast | 0
26 | 2021-09-01 | West | SQS | Actual | 0
26 | 2021-09-01 | East | SQS | Budget
26 | 2021-09-01 | East | SQS | Forecast | 0
27 | 2021-09-01 | East | SQS | Actual | 0
27 | 2021-09-01 | Central | SQS | Budget
27 | 2021-09-01 | Central | SQS | Forecast | 0
26 | 2021-09-01 | Central | SQS | Actual | 0
27 | 2021-09-01 | CMO West 1 | Terra Firma | Budget
27 | 2021-09-01 | CMO West 1 | Terra Firma | Forecast | 0
27 | 2021-09-01 | CMO West 1 | Terra Firma | Actual | 0
27 | 2021-09-01 | CMO West 1 | KLT | Budget
27 | 2021-09-01 | CMO West 1 | KLT | Forecast | 352.15
27 | 2021-09-01 | CMO West 1 | KLT | Actual | 0
27 | 2021-09-01 | CMO West 1 | Forefront | Budget
27 | 2021-09-01 | CMO West 1 | Forefront | Forecast | 0
27 | 2021-09-01 | CMO West 1 | Forefront | Actual | 0
27 | 2021-09-01 | CMO West 1 | DPF | Budget
27 | 2021-09-01 | CMO West 1 | DPF | Forecast | 10.27
27 | 2021-09-01 | CMO West 1 | DPF | Actual | 0
27 | 2021-09-01 | CMO West 1 | OMJ | Budget
27 | 2021-09-01 | CMO West 1 | OMJ | Forecast | 0
27 | 2021-09-01 | CMO West 1 | OMJ | Actual | 0
27 | 2021-09-01 | CMO West 1 | DHB Utilities | Budget
27 | 2021-09-01 | CMO West 1 | DHB Utilities | Forecast | 0
27 | 2021-09-01 | CMO West 1 | DHB Utilities | Actual | 0
27 | 2021-09-01 | CMO West 1 | JDT | Budget
27 | 2021-09-01 | CMO West 1 | JDT | Forecast | 0
27 | 2021-09-01 | CMO West 1 | JDT | Actual | 0
27 | 2021-09-01 | CMO West 1 | MURRAY | Budget
27 | 2021-09-01 | CMO West 1 | MURRAY | Forecast | 0
27 | 2021-09-01 | CMO West 1 | MURRAY | Actual | 0
27 | 2021-09-01 | CMO West 2 | Terra Firma | Budget
27 | 2021-09-01 | CMO West 2 | Terra Firma | Forecast | 0
27 | 2021-09-01 | CMO West 2 | Terra Firma | Actual | 0
27 | 2021-09-01 | CMO West 2 | KLT | Budget
27 | 2021-09-01 | CMO West 2 | KLT | Forecast | 696.405
27 | 2021-09-01 | CMO West 2 | KLT | Actual | 0
27 | 2021-09-01 | CMO West 2 | Forefront | Budget
27 | 2021-09-01 | CMO West 2 | Forefront | Forecast | 0
27 | 2021-09-01 | CMO West 2 | Forefront | Actual | 0
27 | 2021-09-01 | CMO West 2 | DPF | Budget
27 | 2021-09-01 | CMO West 2 | DPF | Forecast | 0
27 | 2021-09-01 | CMO West 2 | DPF | Actual | 0
27 | 2021-09-01 | CMO West 2 | OMJ | Budget
27 | 2021-09-01 | CMO West 2 | OMJ | Forecast | 310.67
27 | 2021-09-01 | CMO West 2 | OMJ | Actual | 0
27 | 2021-09-01 | CMO West 2 | DHB Utilities | Budget
27 | 2021-09-01 | CMO West 2 | DHB Utilities | Forecast | 901.91
27 | 2021-09-01 | CMO West 2 | DHB Utilities | Actual | 0
27 | 2021-09-01 | CMO West 2 | JDT | Budget
27 | 2021-09-01 | CMO West 2 | JDT | Forecast | 0
27 | 2021-09-01 | CMO West 2 | JDT | Actual | 0
27 | 2021-09-01 | CMO West 2 | MURRAY | Budget
27 | 2021-09-01 | CMO West 2 | MURRAY | Forecast | 0
27 | 2021-09-01 | CMO West 2 | MURRAY | Actual | 0
27 | 2021-09-01 | CMO East 1 | Terra Firma | Budget
27 | 2021-09-01 | CMO East 1 | Terra Firma | Forecast | 220.72
27 | 2021-09-01 | CMO East 1 | Terra Firma | Actual | 0
27 | 2021-09-01 | CMO East 1 | KLT | Budget
27 | 2021-09-01 | CMO East 1 | KLT | Forecast | 0
27 | 2021-09-01 | CMO East 1 | KLT | Actual | 0
27 | 2021-09-01 | CMO East 1 | Forefront | Budget
27 | 2021-09-01 | CMO East 1 | Forefront | Forecast | 0
27 | 2021-09-01 | CMO East 1 | Forefront | Actual | 0
27 | 2021-09-01 | CMO East 1 | DPF | Budget
27 | 2021-09-01 | CMO East 1 | DPF | Forecast | 181.01
27 | 2021-09-01 | CMO East 1 | DPF | Actual | 0
27 | 2021-09-01 | CMO East 1 | OMJ | Budget
27 | 2021-09-01 | CMO East 1 | OMJ | Forecast | 0
27 | 2021-09-01 | CMO East 1 | OMJ | Actual | 0
27 | 2021-09-01 | CMO East 1 | DHB Utilities | Budget
27 | 2021-09-01 | CMO East 1 | DHB Utilities | Forecast | 0
27 | 2021-09-01 | CMO East 1 | DHB Utilities | Actual | 0
27 | 2021-09-01 | CMO East 1 | JDT | Budget
27 | 2021-09-01 | CMO East 1 | JDT | Forecast | 0
27 | 2021-09-01 | CMO East 1 | JDT | Actual | 0
27 | 2021-09-01 | CMO East 1 | MURRAY | Budget
27 | 2021-09-01 | CMO East 1 | MURRAY | Forecast | 136.11
27 | 2021-09-01 | CMO East 1 | MURRAY | Actual | 0
27 | 2021-09-01 | CMO East 2 | Terra Firma | Budget
27 | 2021-09-01 | CMO East 2 | Terra Firma | Forecast | 471.01
27 | 2021-09-01 | CMO East 2 | Terra Firma | Actual | 0
27 | 2021-09-01 | CMO East 2 | KLT | Budget
27 | 2021-09-01 | CMO East 2 | KLT | Forecast | 0
27 | 2021-09-01 | CMO East 2 | KLT | Actual | 0
27 | 2021-09-01 | CMO East 2 | Forefront | Budget
27 | 2021-09-01 | CMO East 2 | Forefront | Forecast | 409.5
27 | 2021-09-01 | CMO East 2 | Forefront | Actual | 0
27 | 2021-09-01 | CMO East 2 | DPF | Budget
27 | 2021-09-01 | CMO East 2 | DPF | Forecast | 0
27 | 2021-09-01 | CMO East 2 | DPF | Actual | 0
27 | 2021-09-01 | CMO East 2 | OMJ | Budget
27 | 2021-09-01 | CMO East 2 | OMJ | Forecast | 0
27 | 2021-09-01 | CMO East 2 | OMJ | Actual | 0
27 | 2021-09-01 | CMO East 2 | DHB Utilities | Budget
27 | 2021-09-01 | CMO East 2 | DHB Utilities | Forecast | 0
27 | 2021-09-01 | CMO East 2 | DHB Utilities | Actual | 0
27 | 2021-09-01 | CMO East 2 | JDT | Budget
27 | 2021-09-01 | CMO East 2 | JDT | Forecast | 829.3
27 | 2021-09-01 | CMO East 2 | JDT | Actual | 0
27 | 2021-09-01 | CMO East 2 | MURRAY | Budget
27 | 2021-09-01 | CMO East 2 | MURRAY | Forecast | 144.81
27 | 2021-09-01 | CMO East 2 | MURRAY | Actual | 0
27 | 2021-09-01 | West | Terra Firma | Budget
27 | 2021-09-01 | West | Terra Firma | Forecast | 0
27 | 2021-09-01 | West | Terra Firma | Actual | 0
27 | 2021-09-01 | West | KLT | Budget
27 | 2021-09-01 | West | KLT | Forecast | 0
27 | 2021-09-01 | West | KLT | Actual | 0
27 | 2021-09-01 | West | Forefront | Budget
27 | 2021-09-01 | West | Forefront | Forecast | 0
27 | 2021-09-01 | West | Forefront | Actual | 0
27 | 2021-09-01 | West | DPF | Budget
27 | 2021-09-01 | West | DPF | Forecast | 0
27 | 2021-09-01 | West | DPF | Actual | 0
27 | 2021-09-01 | West | OMJ | Budget
27 | 2021-09-01 | West | OMJ | Forecast | 0
27 | 2021-09-01 | West | OMJ | Actual | 0
27 | 2021-09-01 | West | DHB Utilities | Budget
27 | 2021-09-01 | West | DHB Utilities | Forecast | 0
27 | 2021-09-01 | West | DHB Utilities | Actual | 0
27 | 2021-09-01 | West | JDT | Budget
27 | 2021-09-01 | West | JDT | Forecast | 0
27 | 2021-09-01 | West | JDT | Actual | 0
27 | 2021-09-01 | West | MURRAY | Budget
27 | 2021-09-01 | West | MURRAY | Forecast | 0
27 | 2021-09-01 | West | MURRAY | Actual | 0
27 | 2021-09-01 | East | Terra Firma | Budget
27 | 2021-09-01 | East | Terra Firma | Forecast | 0
27 | 2021-09-01 | East | Terra Firma | Actual | 0
27 | 2021-09-01 | East | KLT | Budget
27 | 2021-09-01 | East | KLT | Forecast | 0
27 | 2021-09-01 | East | KLT | Actual | 0
27 | 2021-09-01 | East | Forefront | Budget
27 | 2021-09-01 | East | Forefront | Forecast | 0
27 | 2021-09-01 | East | Forefront | Actual | 0
27 | 2021-09-01 | East | DPF | Budget
27 | 2021-09-01 | East | DPF | Forecast | 0
27 | 2021-09-01 | East | DPF | Actual | 0
27 | 2021-09-01 | East | OMJ | Budget
27 | 2021-09-01 | East | OMJ | Forecast | 0
27 | 2021-09-01 | East | OMJ | Actual | 0
27 | 2021-09-01 | East | DHB Utilities | Budget
27 | 2021-09-01 | East | DHB Utilities | Forecast | 0
27 | 2021-09-01 | East | DHB Utilities | Actual | 0
27 | 2021-09-01 | East | JDT | Budget
27 | 2021-09-01 | East | JDT | Forecast | 0
27 | 2021-09-01 | East | JDT | Actual | 0
27 | 2021-09-01 | East | MURRAY | Budget
27 | 2021-09-01 | East | MURRAY | Forecast | 0
27 | 2021-09-01 | East | MURRAY | Actual | 0
27 | 2021-09-01 | Central | Terra Firma | Budget
27 | 2021-09-01 | Central | Terra Firma | Forecast | 0
27 | 2021-09-01 | Central | Terra Firma | Actual | 0
27 | 2021-09-01 | Central | KLT | Budget
27 | 2021-09-01 | Central | KLT | Forecast | 0
27 | 2021-09-01 | Central | KLT | Actual | 0
27 | 2021-09-01 | Central | Forefront | Budget
27 | 2021-09-01 | Central | Forefront | Forecast | 0
27 | 2021-09-01 | Central | Forefront | Actual | 0
27 | 2021-09-01 | Central | DPF | Budget
27 | 2021-09-01 | Central | DPF | Forecast | 0
27 | 2021-09-01 | Central | DPF | Actual | 0
27 | 2021-09-01 | Central | OMJ | Budget
27 | 2021-09-01 | Central | OMJ | Forecast | 0
27 | 2021-09-01 | Central | OMJ | Actual | 0
27 | 2021-09-01 | Central | DHB Utilities | Budget
27 | 2021-09-01 | Central | DHB Utilities | Forecast | 0
27 | 2021-09-01 | Central | DHB Utilities | Actual | 0
27 | 2021-09-01 | Central | JDT | Budget
27 | 2021-09-01 | Central | JDT | Forecast | 0
27 | 2021-09-01 | Central | JDT | Actual | 0
27 | 2021-09-01 | Central | MURRAY | Budget
27 | 2021-09-01 | Central | MURRAY | Forecast | 0
27 | 2021-09-01 | Central | MURRAY | Actual | 0
27 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Budget
27 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Forecast | 155.21
27 | 2021-09-01 | CMO West 1 | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Budget
27 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
27 | 2021-09-01 | CMO West 2 | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Budget
27 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
27 | 2021-09-01 | CMO East 1 | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Budget
27 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
27 | 2021-09-01 | CMO East 2 | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | West | DIRECT MOLE | Budget
27 | 2021-09-01 | West | DIRECT MOLE | Forecast | 0
27 | 2021-09-01 | West | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | East | DIRECT MOLE | Budget
27 | 2021-09-01 | East | DIRECT MOLE | Forecast | 0
27 | 2021-09-01 | East | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | Central | DIRECT MOLE | Budget
27 | 2021-09-01 | Central | DIRECT MOLE | Forecast | 0
27 | 2021-09-01 | Central | DIRECT MOLE | Actual | 0
27 | 2021-09-01 | CMO West 1 | SQS | Budget
27 | 2021-09-01 | CMO West 1 | SQS | Forecast | 0
27 | 2021-09-01 | CMO West 1 | SQS | Actual | 0
27 | 2021-09-01 | CMO West 2 | SQS | Budget
27 | 2021-09-01 | CMO West 2 | SQS | Forecast | 339.95
27 | 2021-09-01 | CMO West 2 | SQS | Actual | 0
27 | 2021-09-01 | CMO East 1 | SQS | Budget
27 | 2021-09-01 | CMO East 1 | SQS | Forecast | 0
27 | 2021-09-01 | CMO East 1 | SQS | Actual | 0
27 | 2021-09-01 | CMO East 2 | SQS | Budget
27 | 2021-09-01 | CMO East 2 | SQS | Forecast | 0
27 | 2021-09-01 | CMO East 2 | SQS | Actual | 0
27 | 2021-09-01 | West | SQS | Budget
27 | 2021-09-01 | West | SQS | Forecast | 0
27 | 2021-09-01 | West | SQS | Actual | 0
27 | 2021-09-01 | East | SQS | Budget
27 | 2021-09-01 | East | SQS | Forecast | 0
28 | 2021-09-01 | East | SQS | Actual | 0
28 | 2021-09-01 | Central | SQS | Budget
28 | 2021-09-01 | Central | SQS | Forecast | 0
27 | 2021-09-01 | Central | SQS | Actual | 0
28 | 2021-10-01 | CMO West 1 | Terra Firma | Budget
28 | 2021-10-01 | CMO West 1 | Terra Firma | Forecast | 0
28 | 2021-10-01 | CMO West 1 | Terra Firma | Actual | 0
28 | 2021-10-01 | CMO West 1 | KLT | Budget
28 | 2021-10-01 | CMO West 1 | KLT | Forecast | 518.69
28 | 2021-10-01 | CMO West 1 | KLT | Actual | 0
28 | 2021-10-01 | CMO West 1 | Forefront | Budget
28 | 2021-10-01 | CMO West 1 | Forefront | Forecast | 0
28 | 2021-10-01 | CMO West 1 | Forefront | Actual | 0
28 | 2021-10-01 | CMO West 1 | DPF | Budget
28 | 2021-10-01 | CMO West 1 | DPF | Forecast | 61.1
28 | 2021-10-01 | CMO West 1 | DPF | Actual | 0
28 | 2021-10-01 | CMO West 1 | OMJ | Budget
28 | 2021-10-01 | CMO West 1 | OMJ | Forecast | 0
28 | 2021-10-01 | CMO West 1 | OMJ | Actual | 0
28 | 2021-10-01 | CMO West 1 | DHB Utilities | Budget
28 | 2021-10-01 | CMO West 1 | DHB Utilities | Forecast | 0
28 | 2021-10-01 | CMO West 1 | DHB Utilities | Actual | 0
28 | 2021-10-01 | CMO West 1 | JDT | Budget
28 | 2021-10-01 | CMO West 1 | JDT | Forecast | 0
28 | 2021-10-01 | CMO West 1 | JDT | Actual | 0
28 | 2021-10-01 | CMO West 1 | MURRAY | Budget
28 | 2021-10-01 | CMO West 1 | MURRAY | Forecast | 0
28 | 2021-10-01 | CMO West 1 | MURRAY | Actual | 0
28 | 2021-10-01 | CMO West 2 | Terra Firma | Budget
28 | 2021-10-01 | CMO West 2 | Terra Firma | Forecast | 0
28 | 2021-10-01 | CMO West 2 | Terra Firma | Actual | 0
28 | 2021-10-01 | CMO West 2 | KLT | Budget
28 | 2021-10-01 | CMO West 2 | KLT | Forecast | 965.165
28 | 2021-10-01 | CMO West 2 | KLT | Actual | 0
28 | 2021-10-01 | CMO West 2 | Forefront | Budget
28 | 2021-10-01 | CMO West 2 | Forefront | Forecast | 0
28 | 2021-10-01 | CMO West 2 | Forefront | Actual | 0
28 | 2021-10-01 | CMO West 2 | DPF | Budget
28 | 2021-10-01 | CMO West 2 | DPF | Forecast | 0
28 | 2021-10-01 | CMO West 2 | DPF | Actual | 0
28 | 2021-10-01 | CMO West 2 | OMJ | Budget
28 | 2021-10-01 | CMO West 2 | OMJ | Forecast | 393.55
28 | 2021-10-01 | CMO West 2 | OMJ | Actual | 0
28 | 2021-10-01 | CMO West 2 | DHB Utilities | Budget
28 | 2021-10-01 | CMO West 2 | DHB Utilities | Forecast | 892.42
28 | 2021-10-01 | CMO West 2 | DHB Utilities | Actual | 0
28 | 2021-10-01 | CMO West 2 | JDT | Budget
28 | 2021-10-01 | CMO West 2 | JDT | Forecast | 0
28 | 2021-10-01 | CMO West 2 | JDT | Actual | 0
28 | 2021-10-01 | CMO West 2 | MURRAY | Budget
28 | 2021-10-01 | CMO West 2 | MURRAY | Forecast | 0
28 | 2021-10-01 | CMO West 2 | MURRAY | Actual | 0
28 | 2021-10-01 | CMO East 1 | Terra Firma | Budget
28 | 2021-10-01 | CMO East 1 | Terra Firma | Forecast | 307.24
28 | 2021-10-01 | CMO East 1 | Terra Firma | Actual | 0
28 | 2021-10-01 | CMO East 1 | KLT | Budget
28 | 2021-10-01 | CMO East 1 | KLT | Forecast | 0
28 | 2021-10-01 | CMO East 1 | KLT | Actual | 0
28 | 2021-10-01 | CMO East 1 | Forefront | Budget
28 | 2021-10-01 | CMO East 1 | Forefront | Forecast | 0
28 | 2021-10-01 | CMO East 1 | Forefront | Actual | 0
28 | 2021-10-01 | CMO East 1 | DPF | Budget
28 | 2021-10-01 | CMO East 1 | DPF | Forecast | 181.01
28 | 2021-10-01 | CMO East 1 | DPF | Actual | 0
28 | 2021-10-01 | CMO East 1 | OMJ | Budget
28 | 2021-10-01 | CMO East 1 | OMJ | Forecast | 0
28 | 2021-10-01 | CMO East 1 | OMJ | Actual | 0
28 | 2021-10-01 | CMO East 1 | DHB Utilities | Budget
28 | 2021-10-01 | CMO East 1 | DHB Utilities | Forecast | 0
28 | 2021-10-01 | CMO East 1 | DHB Utilities | Actual | 0
28 | 2021-10-01 | CMO East 1 | JDT | Budget
28 | 2021-10-01 | CMO East 1 | JDT | Forecast | 0
28 | 2021-10-01 | CMO East 1 | JDT | Actual | 0
28 | 2021-10-01 | CMO East 1 | MURRAY | Budget
28 | 2021-10-01 | CMO East 1 | MURRAY | Forecast | 136.11
28 | 2021-10-01 | CMO East 1 | MURRAY | Actual | 0
28 | 2021-10-01 | CMO East 2 | Terra Firma | Budget
28 | 2021-10-01 | CMO East 2 | Terra Firma | Forecast | 471.01
28 | 2021-10-01 | CMO East 2 | Terra Firma | Actual | 0
28 | 2021-10-01 | CMO East 2 | KLT | Budget
28 | 2021-10-01 | CMO East 2 | KLT | Forecast | 0
28 | 2021-10-01 | CMO East 2 | KLT | Actual | 0
28 | 2021-10-01 | CMO East 2 | Forefront | Budget
28 | 2021-10-01 | CMO East 2 | Forefront | Forecast | 829.24
28 | 2021-10-01 | CMO East 2 | Forefront | Actual | 0
28 | 2021-10-01 | CMO East 2 | DPF | Budget
28 | 2021-10-01 | CMO East 2 | DPF | Forecast | 0
28 | 2021-10-01 | CMO East 2 | DPF | Actual | 0
28 | 2021-10-01 | CMO East 2 | OMJ | Budget
28 | 2021-10-01 | CMO East 2 | OMJ | Forecast | 0
28 | 2021-10-01 | CMO East 2 | OMJ | Actual | 0
28 | 2021-10-01 | CMO East 2 | DHB Utilities | Budget
28 | 2021-10-01 | CMO East 2 | DHB Utilities | Forecast | 0
28 | 2021-10-01 | CMO East 2 | DHB Utilities | Actual | 0
28 | 2021-10-01 | CMO East 2 | JDT | Budget
28 | 2021-10-01 | CMO East 2 | JDT | Forecast | 848.86
28 | 2021-10-01 | CMO East 2 | JDT | Actual | 0
28 | 2021-10-01 | CMO East 2 | MURRAY | Budget
28 | 2021-10-01 | CMO East 2 | MURRAY | Forecast | 0
28 | 2021-10-01 | CMO East 2 | MURRAY | Actual | 0
28 | 2021-10-01 | West | Terra Firma | Budget
28 | 2021-10-01 | West | Terra Firma | Forecast | 0
28 | 2021-10-01 | West | Terra Firma | Actual | 0
28 | 2021-10-01 | West | KLT | Budget
28 | 2021-10-01 | West | KLT | Forecast | 0
28 | 2021-10-01 | West | KLT | Actual | 0
28 | 2021-10-01 | West | Forefront | Budget
28 | 2021-10-01 | West | Forefront | Forecast | 0
28 | 2021-10-01 | West | Forefront | Actual | 0
28 | 2021-10-01 | West | DPF | Budget
28 | 2021-10-01 | West | DPF | Forecast | 0
28 | 2021-10-01 | West | DPF | Actual | 0
28 | 2021-10-01 | West | OMJ | Budget
28 | 2021-10-01 | West | OMJ | Forecast | 0
28 | 2021-10-01 | West | OMJ | Actual | 0
28 | 2021-10-01 | West | DHB Utilities | Budget
28 | 2021-10-01 | West | DHB Utilities | Forecast | 0
28 | 2021-10-01 | West | DHB Utilities | Actual | 0
28 | 2021-10-01 | West | JDT | Budget
28 | 2021-10-01 | West | JDT | Forecast | 0
28 | 2021-10-01 | West | JDT | Actual | 0
28 | 2021-10-01 | West | MURRAY | Budget
28 | 2021-10-01 | West | MURRAY | Forecast | 0
28 | 2021-10-01 | West | MURRAY | Actual | 0
28 | 2021-10-01 | East | Terra Firma | Budget
28 | 2021-10-01 | East | Terra Firma | Forecast | 0
28 | 2021-10-01 | East | Terra Firma | Actual | 0
28 | 2021-10-01 | East | KLT | Budget
28 | 2021-10-01 | East | KLT | Forecast | 0
28 | 2021-10-01 | East | KLT | Actual | 0
28 | 2021-10-01 | East | Forefront | Budget
28 | 2021-10-01 | East | Forefront | Forecast | 0
28 | 2021-10-01 | East | Forefront | Actual | 0
28 | 2021-10-01 | East | DPF | Budget
28 | 2021-10-01 | East | DPF | Forecast | 0
28 | 2021-10-01 | East | DPF | Actual | 0
28 | 2021-10-01 | East | OMJ | Budget
28 | 2021-10-01 | East | OMJ | Forecast | 0
28 | 2021-10-01 | East | OMJ | Actual | 0
28 | 2021-10-01 | East | DHB Utilities | Budget
28 | 2021-10-01 | East | DHB Utilities | Forecast | 0
28 | 2021-10-01 | East | DHB Utilities | Actual | 0
28 | 2021-10-01 | East | JDT | Budget
28 | 2021-10-01 | East | JDT | Forecast | 0
28 | 2021-10-01 | East | JDT | Actual | 0
28 | 2021-10-01 | East | MURRAY | Budget
28 | 2021-10-01 | East | MURRAY | Forecast | 0
28 | 2021-10-01 | East | MURRAY | Actual | 0
28 | 2021-10-01 | Central | Terra Firma | Budget
28 | 2021-10-01 | Central | Terra Firma | Forecast | 0
28 | 2021-10-01 | Central | Terra Firma | Actual | 0
28 | 2021-10-01 | Central | KLT | Budget
28 | 2021-10-01 | Central | KLT | Forecast | 0
28 | 2021-10-01 | Central | KLT | Actual | 0
28 | 2021-10-01 | Central | Forefront | Budget
28 | 2021-10-01 | Central | Forefront | Forecast | 0
28 | 2021-10-01 | Central | Forefront | Actual | 0
28 | 2021-10-01 | Central | DPF | Budget
28 | 2021-10-01 | Central | DPF | Forecast | 0
28 | 2021-10-01 | Central | DPF | Actual | 0
28 | 2021-10-01 | Central | OMJ | Budget
28 | 2021-10-01 | Central | OMJ | Forecast | 0
28 | 2021-10-01 | Central | OMJ | Actual | 0
28 | 2021-10-01 | Central | DHB Utilities | Budget
28 | 2021-10-01 | Central | DHB Utilities | Forecast | 0
28 | 2021-10-01 | Central | DHB Utilities | Actual | 0
28 | 2021-10-01 | Central | JDT | Budget
28 | 2021-10-01 | Central | JDT | Forecast | 0
28 | 2021-10-01 | Central | JDT | Actual | 0
28 | 2021-10-01 | Central | MURRAY | Budget
28 | 2021-10-01 | Central | MURRAY | Forecast | 0
28 | 2021-10-01 | Central | MURRAY | Actual | 0
28 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Budget
28 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Forecast | 192.5
28 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Budget
28 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
28 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Budget
28 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
28 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Budget
28 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
28 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | West | DIRECT MOLE | Budget
28 | 2021-10-01 | West | DIRECT MOLE | Forecast | 0
28 | 2021-10-01 | West | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | East | DIRECT MOLE | Budget
28 | 2021-10-01 | East | DIRECT MOLE | Forecast | 0
28 | 2021-10-01 | East | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | Central | DIRECT MOLE | Budget
28 | 2021-10-01 | Central | DIRECT MOLE | Forecast | 0
28 | 2021-10-01 | Central | DIRECT MOLE | Actual | 0
28 | 2021-10-01 | CMO West 1 | SQS | Budget
28 | 2021-10-01 | CMO West 1 | SQS | Forecast | 197.53
28 | 2021-10-01 | CMO West 1 | SQS | Actual | 0
28 | 2021-10-01 | CMO West 2 | SQS | Budget
28 | 2021-10-01 | CMO West 2 | SQS | Forecast | 611.85
28 | 2021-10-01 | CMO West 2 | SQS | Actual | 0
28 | 2021-10-01 | CMO East 1 | SQS | Budget
28 | 2021-10-01 | CMO East 1 | SQS | Forecast | 0
28 | 2021-10-01 | CMO East 1 | SQS | Actual | 0
28 | 2021-10-01 | CMO East 2 | SQS | Budget
28 | 2021-10-01 | CMO East 2 | SQS | Forecast | 0
28 | 2021-10-01 | CMO East 2 | SQS | Actual | 0
28 | 2021-10-01 | West | SQS | Budget
28 | 2021-10-01 | West | SQS | Forecast | 0
28 | 2021-10-01 | West | SQS | Actual | 0
28 | 2021-10-01 | East | SQS | Budget
28 | 2021-10-01 | East | SQS | Forecast | 0
29 | 2021-10-01 | East | SQS | Actual | 0
29 | 2021-10-01 | Central | SQS | Budget
29 | 2021-10-01 | Central | SQS | Forecast | 0
28 | 2021-10-01 | Central | SQS | Actual | 0
29 | 2021-10-01 | CMO West 1 | Terra Firma | Budget
29 | 2021-10-01 | CMO West 1 | Terra Firma | Forecast | 0
29 | 2021-10-01 | CMO West 1 | Terra Firma | Actual | 0
29 | 2021-10-01 | CMO West 1 | KLT | Budget
29 | 2021-10-01 | CMO West 1 | KLT | Forecast | 514.69
29 | 2021-10-01 | CMO West 1 | KLT | Actual | 0
29 | 2021-10-01 | CMO West 1 | Forefront | Budget
29 | 2021-10-01 | CMO West 1 | Forefront | Forecast | 0
29 | 2021-10-01 | CMO West 1 | Forefront | Actual | 0
29 | 2021-10-01 | CMO West 1 | DPF | Budget
29 | 2021-10-01 | CMO West 1 | DPF | Forecast | 61.1
29 | 2021-10-01 | CMO West 1 | DPF | Actual | 0
29 | 2021-10-01 | CMO West 1 | OMJ | Budget
29 | 2021-10-01 | CMO West 1 | OMJ | Forecast | 0
29 | 2021-10-01 | CMO West 1 | OMJ | Actual | 0
29 | 2021-10-01 | CMO West 1 | DHB Utilities | Budget
29 | 2021-10-01 | CMO West 1 | DHB Utilities | Forecast | 0
29 | 2021-10-01 | CMO West 1 | DHB Utilities | Actual | 0
29 | 2021-10-01 | CMO West 1 | JDT | Budget
29 | 2021-10-01 | CMO West 1 | JDT | Forecast | 0
29 | 2021-10-01 | CMO West 1 | JDT | Actual | 0
29 | 2021-10-01 | CMO West 1 | MURRAY | Budget
29 | 2021-10-01 | CMO West 1 | MURRAY | Forecast | 0
29 | 2021-10-01 | CMO West 1 | MURRAY | Actual | 0
29 | 2021-10-01 | CMO West 2 | Terra Firma | Budget
29 | 2021-10-01 | CMO West 2 | Terra Firma | Forecast | 0
29 | 2021-10-01 | CMO West 2 | Terra Firma | Actual | 0
29 | 2021-10-01 | CMO West 2 | KLT | Budget
29 | 2021-10-01 | CMO West 2 | KLT | Forecast | 739.965
29 | 2021-10-01 | CMO West 2 | KLT | Actual | 0
29 | 2021-10-01 | CMO West 2 | Forefront | Budget
29 | 2021-10-01 | CMO West 2 | Forefront | Forecast | 0
29 | 2021-10-01 | CMO West 2 | Forefront | Actual | 0
29 | 2021-10-01 | CMO West 2 | DPF | Budget
29 | 2021-10-01 | CMO West 2 | DPF | Forecast | 0
29 | 2021-10-01 | CMO West 2 | DPF | Actual | 0
29 | 2021-10-01 | CMO West 2 | OMJ | Budget
29 | 2021-10-01 | CMO West 2 | OMJ | Forecast | 393.55
29 | 2021-10-01 | CMO West 2 | OMJ | Actual | 0
29 | 2021-10-01 | CMO West 2 | DHB Utilities | Budget
29 | 2021-10-01 | CMO West 2 | DHB Utilities | Forecast | 763.29
29 | 2021-10-01 | CMO West 2 | DHB Utilities | Actual | 0
29 | 2021-10-01 | CMO West 2 | JDT | Budget
29 | 2021-10-01 | CMO West 2 | JDT | Forecast | 0
29 | 2021-10-01 | CMO West 2 | JDT | Actual | 0
29 | 2021-10-01 | CMO West 2 | MURRAY | Budget
29 | 2021-10-01 | CMO West 2 | MURRAY | Forecast | 0
29 | 2021-10-01 | CMO West 2 | MURRAY | Actual | 0
29 | 2021-10-01 | CMO East 1 | Terra Firma | Budget
29 | 2021-10-01 | CMO East 1 | Terra Firma | Forecast | 280
29 | 2021-10-01 | CMO East 1 | Terra Firma | Actual | 0
29 | 2021-10-01 | CMO East 1 | KLT | Budget
29 | 2021-10-01 | CMO East 1 | KLT | Forecast | 0
29 | 2021-10-01 | CMO East 1 | KLT | Actual | 0
29 | 2021-10-01 | CMO East 1 | Forefront | Budget
29 | 2021-10-01 | CMO East 1 | Forefront | Forecast | 0
29 | 2021-10-01 | CMO East 1 | Forefront | Actual | 0
29 | 2021-10-01 | CMO East 1 | DPF | Budget
29 | 2021-10-01 | CMO East 1 | DPF | Forecast | 181.01
29 | 2021-10-01 | CMO East 1 | DPF | Actual | 0
29 | 2021-10-01 | CMO East 1 | OMJ | Budget
29 | 2021-10-01 | CMO East 1 | OMJ | Forecast | 0
29 | 2021-10-01 | CMO East 1 | OMJ | Actual | 0
29 | 2021-10-01 | CMO East 1 | DHB Utilities | Budget
29 | 2021-10-01 | CMO East 1 | DHB Utilities | Forecast | 0
29 | 2021-10-01 | CMO East 1 | DHB Utilities | Actual | 0
29 | 2021-10-01 | CMO East 1 | JDT | Budget
29 | 2021-10-01 | CMO East 1 | JDT | Forecast | 0
29 | 2021-10-01 | CMO East 1 | JDT | Actual | 0
29 | 2021-10-01 | CMO East 1 | MURRAY | Budget
29 | 2021-10-01 | CMO East 1 | MURRAY | Forecast | 136.11
29 | 2021-10-01 | CMO East 1 | MURRAY | Actual | 0
29 | 2021-10-01 | CMO East 2 | Terra Firma | Budget
29 | 2021-10-01 | CMO East 2 | Terra Firma | Forecast | 524.77
29 | 2021-10-01 | CMO East 2 | Terra Firma | Actual | 0
29 | 2021-10-01 | CMO East 2 | KLT | Budget
29 | 2021-10-01 | CMO East 2 | KLT | Forecast | 0
29 | 2021-10-01 | CMO East 2 | KLT | Actual | 0
29 | 2021-10-01 | CMO East 2 | Forefront | Budget
29 | 2021-10-01 | CMO East 2 | Forefront | Forecast | 829.24
29 | 2021-10-01 | CMO East 2 | Forefront | Actual | 0
29 | 2021-10-01 | CMO East 2 | DPF | Budget
29 | 2021-10-01 | CMO East 2 | DPF | Forecast | 0
29 | 2021-10-01 | CMO East 2 | DPF | Actual | 0
29 | 2021-10-01 | CMO East 2 | OMJ | Budget
29 | 2021-10-01 | CMO East 2 | OMJ | Forecast | 0
29 | 2021-10-01 | CMO East 2 | OMJ | Actual | 0
29 | 2021-10-01 | CMO East 2 | DHB Utilities | Budget
29 | 2021-10-01 | CMO East 2 | DHB Utilities | Forecast | 0
29 | 2021-10-01 | CMO East 2 | DHB Utilities | Actual | 0
29 | 2021-10-01 | CMO East 2 | JDT | Budget
29 | 2021-10-01 | CMO East 2 | JDT | Forecast | 877.17
29 | 2021-10-01 | CMO East 2 | JDT | Actual | 0
29 | 2021-10-01 | CMO East 2 | MURRAY | Budget
29 | 2021-10-01 | CMO East 2 | MURRAY | Forecast | 0
29 | 2021-10-01 | CMO East 2 | MURRAY | Actual | 0
29 | 2021-10-01 | West | Terra Firma | Budget
29 | 2021-10-01 | West | Terra Firma | Forecast | 0
29 | 2021-10-01 | West | Terra Firma | Actual | 0
29 | 2021-10-01 | West | KLT | Budget
29 | 2021-10-01 | West | KLT | Forecast | 0
29 | 2021-10-01 | West | KLT | Actual | 0
29 | 2021-10-01 | West | Forefront | Budget
29 | 2021-10-01 | West | Forefront | Forecast | 0
29 | 2021-10-01 | West | Forefront | Actual | 0
29 | 2021-10-01 | West | DPF | Budget
29 | 2021-10-01 | West | DPF | Forecast | 0
29 | 2021-10-01 | West | DPF | Actual | 0
29 | 2021-10-01 | West | OMJ | Budget
29 | 2021-10-01 | West | OMJ | Forecast | 0
29 | 2021-10-01 | West | OMJ | Actual | 0
29 | 2021-10-01 | West | DHB Utilities | Budget
29 | 2021-10-01 | West | DHB Utilities | Forecast | 0
29 | 2021-10-01 | West | DHB Utilities | Actual | 0
29 | 2021-10-01 | West | JDT | Budget
29 | 2021-10-01 | West | JDT | Forecast | 0
29 | 2021-10-01 | West | JDT | Actual | 0
29 | 2021-10-01 | West | MURRAY | Budget
29 | 2021-10-01 | West | MURRAY | Forecast | 0
29 | 2021-10-01 | West | MURRAY | Actual | 0
29 | 2021-10-01 | East | Terra Firma | Budget
29 | 2021-10-01 | East | Terra Firma | Forecast | 0
29 | 2021-10-01 | East | Terra Firma | Actual | 0
29 | 2021-10-01 | East | KLT | Budget
29 | 2021-10-01 | East | KLT | Forecast | 0
29 | 2021-10-01 | East | KLT | Actual | 0
29 | 2021-10-01 | East | Forefront | Budget
29 | 2021-10-01 | East | Forefront | Forecast | 0
29 | 2021-10-01 | East | Forefront | Actual | 0
29 | 2021-10-01 | East | DPF | Budget
29 | 2021-10-01 | East | DPF | Forecast | 0
29 | 2021-10-01 | East | DPF | Actual | 0
29 | 2021-10-01 | East | OMJ | Budget
29 | 2021-10-01 | East | OMJ | Forecast | 0
29 | 2021-10-01 | East | OMJ | Actual | 0
29 | 2021-10-01 | East | DHB Utilities | Budget
29 | 2021-10-01 | East | DHB Utilities | Forecast | 0
29 | 2021-10-01 | East | DHB Utilities | Actual | 0
29 | 2021-10-01 | East | JDT | Budget
29 | 2021-10-01 | East | JDT | Forecast | 0
29 | 2021-10-01 | East | JDT | Actual | 0
29 | 2021-10-01 | East | MURRAY | Budget
29 | 2021-10-01 | East | MURRAY | Forecast | 0
29 | 2021-10-01 | East | MURRAY | Actual | 0
29 | 2021-10-01 | Central | Terra Firma | Budget
29 | 2021-10-01 | Central | Terra Firma | Forecast | 0
29 | 2021-10-01 | Central | Terra Firma | Actual | 0
29 | 2021-10-01 | Central | KLT | Budget
29 | 2021-10-01 | Central | KLT | Forecast | 0
29 | 2021-10-01 | Central | KLT | Actual | 0
29 | 2021-10-01 | Central | Forefront | Budget
29 | 2021-10-01 | Central | Forefront | Forecast | 0
29 | 2021-10-01 | Central | Forefront | Actual | 0
29 | 2021-10-01 | Central | DPF | Budget
29 | 2021-10-01 | Central | DPF | Forecast | 0
29 | 2021-10-01 | Central | DPF | Actual | 0
29 | 2021-10-01 | Central | OMJ | Budget
29 | 2021-10-01 | Central | OMJ | Forecast | 0
29 | 2021-10-01 | Central | OMJ | Actual | 0
29 | 2021-10-01 | Central | DHB Utilities | Budget
29 | 2021-10-01 | Central | DHB Utilities | Forecast | 0
29 | 2021-10-01 | Central | DHB Utilities | Actual | 0
29 | 2021-10-01 | Central | JDT | Budget
29 | 2021-10-01 | Central | JDT | Forecast | 0
29 | 2021-10-01 | Central | JDT | Actual | 0
29 | 2021-10-01 | Central | MURRAY | Budget
29 | 2021-10-01 | Central | MURRAY | Forecast | 0
29 | 2021-10-01 | Central | MURRAY | Actual | 0
29 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Budget
29 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Forecast | 192.5
29 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Budget
29 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
29 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Budget
29 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
29 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Budget
29 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
29 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | West | DIRECT MOLE | Budget
29 | 2021-10-01 | West | DIRECT MOLE | Forecast | 0
29 | 2021-10-01 | West | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | East | DIRECT MOLE | Budget
29 | 2021-10-01 | East | DIRECT MOLE | Forecast | 0
29 | 2021-10-01 | East | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | Central | DIRECT MOLE | Budget
29 | 2021-10-01 | Central | DIRECT MOLE | Forecast | 0
29 | 2021-10-01 | Central | DIRECT MOLE | Actual | 0
29 | 2021-10-01 | CMO West 1 | SQS | Budget
29 | 2021-10-01 | CMO West 1 | SQS | Forecast | 197.53
29 | 2021-10-01 | CMO West 1 | SQS | Actual | 0
29 | 2021-10-01 | CMO West 2 | SQS | Budget
29 | 2021-10-01 | CMO West 2 | SQS | Forecast | 596.64
29 | 2021-10-01 | CMO West 2 | SQS | Actual | 0
29 | 2021-10-01 | CMO East 1 | SQS | Budget
29 | 2021-10-01 | CMO East 1 | SQS | Forecast | 0
29 | 2021-10-01 | CMO East 1 | SQS | Actual | 0
29 | 2021-10-01 | CMO East 2 | SQS | Budget
29 | 2021-10-01 | CMO East 2 | SQS | Forecast | 0
29 | 2021-10-01 | CMO East 2 | SQS | Actual | 0
29 | 2021-10-01 | West | SQS | Budget
29 | 2021-10-01 | West | SQS | Forecast | 0
29 | 2021-10-01 | West | SQS | Actual | 0
29 | 2021-10-01 | East | SQS | Budget
29 | 2021-10-01 | East | SQS | Forecast | 0
30 | 2021-10-01 | East | SQS | Actual | 0
30 | 2021-10-01 | Central | SQS | Budget
30 | 2021-10-01 | Central | SQS | Forecast | 0
29 | 2021-10-01 | Central | SQS | Actual | 0
30 | 2021-10-01 | CMO West 1 | Terra Firma | Budget
30 | 2021-10-01 | CMO West 1 | Terra Firma | Forecast | 0
30 | 2021-10-01 | CMO West 1 | Terra Firma | Actual | 0
30 | 2021-10-01 | CMO West 1 | KLT | Budget
30 | 2021-10-01 | CMO West 1 | KLT | Forecast | 509.69
30 | 2021-10-01 | CMO West 1 | KLT | Actual | 0
30 | 2021-10-01 | CMO West 1 | Forefront | Budget
30 | 2021-10-01 | CMO West 1 | Forefront | Forecast | 0
30 | 2021-10-01 | CMO West 1 | Forefront | Actual | 0
30 | 2021-10-01 | CMO West 1 | DPF | Budget
30 | 2021-10-01 | CMO West 1 | DPF | Forecast | 61.1
30 | 2021-10-01 | CMO West 1 | DPF | Actual | 0
30 | 2021-10-01 | CMO West 1 | OMJ | Budget
30 | 2021-10-01 | CMO West 1 | OMJ | Forecast | 0
30 | 2021-10-01 | CMO West 1 | OMJ | Actual | 0
30 | 2021-10-01 | CMO West 1 | DHB Utilities | Budget
30 | 2021-10-01 | CMO West 1 | DHB Utilities | Forecast | 0
30 | 2021-10-01 | CMO West 1 | DHB Utilities | Actual | 0
30 | 2021-10-01 | CMO West 1 | JDT | Budget
30 | 2021-10-01 | CMO West 1 | JDT | Forecast | 0
30 | 2021-10-01 | CMO West 1 | JDT | Actual | 0
30 | 2021-10-01 | CMO West 1 | MURRAY | Budget
30 | 2021-10-01 | CMO West 1 | MURRAY | Forecast | 0
30 | 2021-10-01 | CMO West 1 | MURRAY | Actual | 0
30 | 2021-10-01 | CMO West 2 | Terra Firma | Budget
30 | 2021-10-01 | CMO West 2 | Terra Firma | Forecast | 0
30 | 2021-10-01 | CMO West 2 | Terra Firma | Actual | 0
30 | 2021-10-01 | CMO West 2 | KLT | Budget
30 | 2021-10-01 | CMO West 2 | KLT | Forecast | 741.895
30 | 2021-10-01 | CMO West 2 | KLT | Actual | 0
30 | 2021-10-01 | CMO West 2 | Forefront | Budget
30 | 2021-10-01 | CMO West 2 | Forefront | Forecast | 0
30 | 2021-10-01 | CMO West 2 | Forefront | Actual | 0
30 | 2021-10-01 | CMO West 2 | DPF | Budget
30 | 2021-10-01 | CMO West 2 | DPF | Forecast | 0
30 | 2021-10-01 | CMO West 2 | DPF | Actual | 0
30 | 2021-10-01 | CMO West 2 | OMJ | Budget
30 | 2021-10-01 | CMO West 2 | OMJ | Forecast | 393.55
30 | 2021-10-01 | CMO West 2 | OMJ | Actual | 0
30 | 2021-10-01 | CMO West 2 | DHB Utilities | Budget
30 | 2021-10-01 | CMO West 2 | DHB Utilities | Forecast | 776.77
30 | 2021-10-01 | CMO West 2 | DHB Utilities | Actual | 0
30 | 2021-10-01 | CMO West 2 | JDT | Budget
30 | 2021-10-01 | CMO West 2 | JDT | Forecast | 0
30 | 2021-10-01 | CMO West 2 | JDT | Actual | 0
30 | 2021-10-01 | CMO West 2 | MURRAY | Budget
30 | 2021-10-01 | CMO West 2 | MURRAY | Forecast | 0
30 | 2021-10-01 | CMO West 2 | MURRAY | Actual | 0
30 | 2021-10-01 | CMO East 1 | Terra Firma | Budget
30 | 2021-10-01 | CMO East 1 | Terra Firma | Forecast | 280
30 | 2021-10-01 | CMO East 1 | Terra Firma | Actual | 0
30 | 2021-10-01 | CMO East 1 | KLT | Budget
30 | 2021-10-01 | CMO East 1 | KLT | Forecast | 0
30 | 2021-10-01 | CMO East 1 | KLT | Actual | 0
30 | 2021-10-01 | CMO East 1 | Forefront | Budget
30 | 2021-10-01 | CMO East 1 | Forefront | Forecast | 0
30 | 2021-10-01 | CMO East 1 | Forefront | Actual | 0
30 | 2021-10-01 | CMO East 1 | DPF | Budget
30 | 2021-10-01 | CMO East 1 | DPF | Forecast | 227.38
30 | 2021-10-01 | CMO East 1 | DPF | Actual | 0
30 | 2021-10-01 | CMO East 1 | OMJ | Budget
30 | 2021-10-01 | CMO East 1 | OMJ | Forecast | 0
30 | 2021-10-01 | CMO East 1 | OMJ | Actual | 0
30 | 2021-10-01 | CMO East 1 | DHB Utilities | Budget
30 | 2021-10-01 | CMO East 1 | DHB Utilities | Forecast | 0
30 | 2021-10-01 | CMO East 1 | DHB Utilities | Actual | 0
30 | 2021-10-01 | CMO East 1 | JDT | Budget
30 | 2021-10-01 | CMO East 1 | JDT | Forecast | 0
30 | 2021-10-01 | CMO East 1 | JDT | Actual | 0
30 | 2021-10-01 | CMO East 1 | MURRAY | Budget
30 | 2021-10-01 | CMO East 1 | MURRAY | Forecast | 158.54
30 | 2021-10-01 | CMO East 1 | MURRAY | Actual | 0
30 | 2021-10-01 | CMO East 2 | Terra Firma | Budget
30 | 2021-10-01 | CMO East 2 | Terra Firma | Forecast | 519.61
30 | 2021-10-01 | CMO East 2 | Terra Firma | Actual | 0
30 | 2021-10-01 | CMO East 2 | KLT | Budget
30 | 2021-10-01 | CMO East 2 | KLT | Forecast | 0
30 | 2021-10-01 | CMO East 2 | KLT | Actual | 0
30 | 2021-10-01 | CMO East 2 | Forefront | Budget
30 | 2021-10-01 | CMO East 2 | Forefront | Forecast | 914.35
30 | 2021-10-01 | CMO East 2 | Forefront | Actual | 0
30 | 2021-10-01 | CMO East 2 | DPF | Budget
30 | 2021-10-01 | CMO East 2 | DPF | Forecast | 0
30 | 2021-10-01 | CMO East 2 | DPF | Actual | 0
30 | 2021-10-01 | CMO East 2 | OMJ | Budget
30 | 2021-10-01 | CMO East 2 | OMJ | Forecast | 0
30 | 2021-10-01 | CMO East 2 | OMJ | Actual | 0
30 | 2021-10-01 | CMO East 2 | DHB Utilities | Budget
30 | 2021-10-01 | CMO East 2 | DHB Utilities | Forecast | 0
30 | 2021-10-01 | CMO East 2 | DHB Utilities | Actual | 0
30 | 2021-10-01 | CMO East 2 | JDT | Budget
30 | 2021-10-01 | CMO East 2 | JDT | Forecast | 877.17
30 | 2021-10-01 | CMO East 2 | JDT | Actual | 0
30 | 2021-10-01 | CMO East 2 | MURRAY | Budget
30 | 2021-10-01 | CMO East 2 | MURRAY | Forecast | 0
30 | 2021-10-01 | CMO East 2 | MURRAY | Actual | 0
30 | 2021-10-01 | West | Terra Firma | Budget
30 | 2021-10-01 | West | Terra Firma | Forecast | 0
30 | 2021-10-01 | West | Terra Firma | Actual | 0
30 | 2021-10-01 | West | KLT | Budget
30 | 2021-10-01 | West | KLT | Forecast | 0
30 | 2021-10-01 | West | KLT | Actual | 0
30 | 2021-10-01 | West | Forefront | Budget
30 | 2021-10-01 | West | Forefront | Forecast | 0
30 | 2021-10-01 | West | Forefront | Actual | 0
30 | 2021-10-01 | West | DPF | Budget
30 | 2021-10-01 | West | DPF | Forecast | 0
30 | 2021-10-01 | West | DPF | Actual | 0
30 | 2021-10-01 | West | OMJ | Budget
30 | 2021-10-01 | West | OMJ | Forecast | 0
30 | 2021-10-01 | West | OMJ | Actual | 0
30 | 2021-10-01 | West | DHB Utilities | Budget
30 | 2021-10-01 | West | DHB Utilities | Forecast | 0
30 | 2021-10-01 | West | DHB Utilities | Actual | 0
30 | 2021-10-01 | West | JDT | Budget
30 | 2021-10-01 | West | JDT | Forecast | 0
30 | 2021-10-01 | West | JDT | Actual | 0
30 | 2021-10-01 | West | MURRAY | Budget
30 | 2021-10-01 | West | MURRAY | Forecast | 0
30 | 2021-10-01 | West | MURRAY | Actual | 0
30 | 2021-10-01 | East | Terra Firma | Budget
30 | 2021-10-01 | East | Terra Firma | Forecast | 0
30 | 2021-10-01 | East | Terra Firma | Actual | 0
30 | 2021-10-01 | East | KLT | Budget
30 | 2021-10-01 | East | KLT | Forecast | 0
30 | 2021-10-01 | East | KLT | Actual | 0
30 | 2021-10-01 | East | Forefront | Budget
30 | 2021-10-01 | East | Forefront | Forecast | 0
30 | 2021-10-01 | East | Forefront | Actual | 0
30 | 2021-10-01 | East | DPF | Budget
30 | 2021-10-01 | East | DPF | Forecast | 0
30 | 2021-10-01 | East | DPF | Actual | 0
30 | 2021-10-01 | East | OMJ | Budget
30 | 2021-10-01 | East | OMJ | Forecast | 0
30 | 2021-10-01 | East | OMJ | Actual | 0
30 | 2021-10-01 | East | DHB Utilities | Budget
30 | 2021-10-01 | East | DHB Utilities | Forecast | 0
30 | 2021-10-01 | East | DHB Utilities | Actual | 0
30 | 2021-10-01 | East | JDT | Budget
30 | 2021-10-01 | East | JDT | Forecast | 0
30 | 2021-10-01 | East | JDT | Actual | 0
30 | 2021-10-01 | East | MURRAY | Budget
30 | 2021-10-01 | East | MURRAY | Forecast | 0
30 | 2021-10-01 | East | MURRAY | Actual | 0
30 | 2021-10-01 | Central | Terra Firma | Budget
30 | 2021-10-01 | Central | Terra Firma | Forecast | 0
30 | 2021-10-01 | Central | Terra Firma | Actual | 0
30 | 2021-10-01 | Central | KLT | Budget
30 | 2021-10-01 | Central | KLT | Forecast | 0
30 | 2021-10-01 | Central | KLT | Actual | 0
30 | 2021-10-01 | Central | Forefront | Budget
30 | 2021-10-01 | Central | Forefront | Forecast | 0
30 | 2021-10-01 | Central | Forefront | Actual | 0
30 | 2021-10-01 | Central | DPF | Budget
30 | 2021-10-01 | Central | DPF | Forecast | 0
30 | 2021-10-01 | Central | DPF | Actual | 0
30 | 2021-10-01 | Central | OMJ | Budget
30 | 2021-10-01 | Central | OMJ | Forecast | 0
30 | 2021-10-01 | Central | OMJ | Actual | 0
30 | 2021-10-01 | Central | DHB Utilities | Budget
30 | 2021-10-01 | Central | DHB Utilities | Forecast | 0
30 | 2021-10-01 | Central | DHB Utilities | Actual | 0
30 | 2021-10-01 | Central | JDT | Budget
30 | 2021-10-01 | Central | JDT | Forecast | 0
30 | 2021-10-01 | Central | JDT | Actual | 0
30 | 2021-10-01 | Central | MURRAY | Budget
30 | 2021-10-01 | Central | MURRAY | Forecast | 0
30 | 2021-10-01 | Central | MURRAY | Actual | 0
30 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Budget
30 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Forecast | 192.5
30 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Budget
30 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
30 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Budget
30 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
30 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Budget
30 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
30 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | West | DIRECT MOLE | Budget
30 | 2021-10-01 | West | DIRECT MOLE | Forecast | 0
30 | 2021-10-01 | West | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | East | DIRECT MOLE | Budget
30 | 2021-10-01 | East | DIRECT MOLE | Forecast | 0
30 | 2021-10-01 | East | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | Central | DIRECT MOLE | Budget
30 | 2021-10-01 | Central | DIRECT MOLE | Forecast | 0
30 | 2021-10-01 | Central | DIRECT MOLE | Actual | 0
30 | 2021-10-01 | CMO West 1 | SQS | Budget
30 | 2021-10-01 | CMO West 1 | SQS | Forecast | 197.53
30 | 2021-10-01 | CMO West 1 | SQS | Actual | 0
30 | 2021-10-01 | CMO West 2 | SQS | Budget
30 | 2021-10-01 | CMO West 2 | SQS | Forecast | 610.39
30 | 2021-10-01 | CMO West 2 | SQS | Actual | 0
30 | 2021-10-01 | CMO East 1 | SQS | Budget
30 | 2021-10-01 | CMO East 1 | SQS | Forecast | 0
30 | 2021-10-01 | CMO East 1 | SQS | Actual | 0
30 | 2021-10-01 | CMO East 2 | SQS | Budget
30 | 2021-10-01 | CMO East 2 | SQS | Forecast | 0
30 | 2021-10-01 | CMO East 2 | SQS | Actual | 0
30 | 2021-10-01 | West | SQS | Budget
30 | 2021-10-01 | West | SQS | Forecast | 0
30 | 2021-10-01 | West | SQS | Actual | 0
30 | 2021-10-01 | East | SQS | Budget
30 | 2021-10-01 | East | SQS | Forecast | 0
31 | 2021-10-01 | East | SQS | Actual | 0
31 | 2021-10-01 | Central | SQS | Budget
31 | 2021-10-01 | Central | SQS | Forecast | 0
30 | 2021-10-01 | Central | SQS | Actual | 0
31 | 2021-10-01 | CMO West 1 | Terra Firma | Budget
31 | 2021-10-01 | CMO West 1 | Terra Firma | Forecast | 0
31 | 2021-10-01 | CMO West 1 | Terra Firma | Actual | 0
31 | 2021-10-01 | CMO West 1 | KLT | Budget
31 | 2021-10-01 | CMO West 1 | KLT | Forecast | 509.69
31 | 2021-10-01 | CMO West 1 | KLT | Actual | 0
31 | 2021-10-01 | CMO West 1 | Forefront | Budget
31 | 2021-10-01 | CMO West 1 | Forefront | Forecast | 0
31 | 2021-10-01 | CMO West 1 | Forefront | Actual | 0
31 | 2021-10-01 | CMO West 1 | DPF | Budget
31 | 2021-10-01 | CMO West 1 | DPF | Forecast | 61.1
31 | 2021-10-01 | CMO West 1 | DPF | Actual | 0
31 | 2021-10-01 | CMO West 1 | OMJ | Budget
31 | 2021-10-01 | CMO West 1 | OMJ | Forecast | 0
31 | 2021-10-01 | CMO West 1 | OMJ | Actual | 0
31 | 2021-10-01 | CMO West 1 | DHB Utilities | Budget
31 | 2021-10-01 | CMO West 1 | DHB Utilities | Forecast | 0
31 | 2021-10-01 | CMO West 1 | DHB Utilities | Actual | 0
31 | 2021-10-01 | CMO West 1 | JDT | Budget
31 | 2021-10-01 | CMO West 1 | JDT | Forecast | 0
31 | 2021-10-01 | CMO West 1 | JDT | Actual | 0
31 | 2021-10-01 | CMO West 1 | MURRAY | Budget
31 | 2021-10-01 | CMO West 1 | MURRAY | Forecast | 0
31 | 2021-10-01 | CMO West 1 | MURRAY | Actual | 0
31 | 2021-10-01 | CMO West 2 | Terra Firma | Budget
31 | 2021-10-01 | CMO West 2 | Terra Firma | Forecast | 0
31 | 2021-10-01 | CMO West 2 | Terra Firma | Actual | 0
31 | 2021-10-01 | CMO West 2 | KLT | Budget
31 | 2021-10-01 | CMO West 2 | KLT | Forecast | 914.18
31 | 2021-10-01 | CMO West 2 | KLT | Actual | 0
31 | 2021-10-01 | CMO West 2 | Forefront | Budget
31 | 2021-10-01 | CMO West 2 | Forefront | Forecast | 0
31 | 2021-10-01 | CMO West 2 | Forefront | Actual | 0
31 | 2021-10-01 | CMO West 2 | DPF | Budget
31 | 2021-10-01 | CMO West 2 | DPF | Forecast | 0
31 | 2021-10-01 | CMO West 2 | DPF | Actual | 0
31 | 2021-10-01 | CMO West 2 | OMJ | Budget
31 | 2021-10-01 | CMO West 2 | OMJ | Forecast | 393.55
31 | 2021-10-01 | CMO West 2 | OMJ | Actual | 0
31 | 2021-10-01 | CMO West 2 | DHB Utilities | Budget
31 | 2021-10-01 | CMO West 2 | DHB Utilities | Forecast | 408.85
31 | 2021-10-01 | CMO West 2 | DHB Utilities | Actual | 0
31 | 2021-10-01 | CMO West 2 | JDT | Budget
31 | 2021-10-01 | CMO West 2 | JDT | Forecast | 0
31 | 2021-10-01 | CMO West 2 | JDT | Actual | 0
31 | 2021-10-01 | CMO West 2 | MURRAY | Budget
31 | 2021-10-01 | CMO West 2 | MURRAY | Forecast | 0
31 | 2021-10-01 | CMO West 2 | MURRAY | Actual | 0
31 | 2021-10-01 | CMO East 1 | Terra Firma | Budget
31 | 2021-10-01 | CMO East 1 | Terra Firma | Forecast | 316.15
31 | 2021-10-01 | CMO East 1 | Terra Firma | Actual | 0
31 | 2021-10-01 | CMO East 1 | KLT | Budget
31 | 2021-10-01 | CMO East 1 | KLT | Forecast | 0
31 | 2021-10-01 | CMO East 1 | KLT | Actual | 0
31 | 2021-10-01 | CMO East 1 | Forefront | Budget
31 | 2021-10-01 | CMO East 1 | Forefront | Forecast | 0
31 | 2021-10-01 | CMO East 1 | Forefront | Actual | 0
31 | 2021-10-01 | CMO East 1 | DPF | Budget
31 | 2021-10-01 | CMO East 1 | DPF | Forecast | 257.9
31 | 2021-10-01 | CMO East 1 | DPF | Actual | 0
31 | 2021-10-01 | CMO East 1 | OMJ | Budget
31 | 2021-10-01 | CMO East 1 | OMJ | Forecast | 0
31 | 2021-10-01 | CMO East 1 | OMJ | Actual | 0
31 | 2021-10-01 | CMO East 1 | DHB Utilities | Budget
31 | 2021-10-01 | CMO East 1 | DHB Utilities | Forecast | 0
31 | 2021-10-01 | CMO East 1 | DHB Utilities | Actual | 0
31 | 2021-10-01 | CMO East 1 | JDT | Budget
31 | 2021-10-01 | CMO East 1 | JDT | Forecast | 0
31 | 2021-10-01 | CMO East 1 | JDT | Actual | 0
31 | 2021-10-01 | CMO East 1 | MURRAY | Budget
31 | 2021-10-01 | CMO East 1 | MURRAY | Forecast | 158.54
31 | 2021-10-01 | CMO East 1 | MURRAY | Actual | 0
31 | 2021-10-01 | CMO East 2 | Terra Firma | Budget
31 | 2021-10-01 | CMO East 2 | Terra Firma | Forecast | 554.9
31 | 2021-10-01 | CMO East 2 | Terra Firma | Actual | 0
31 | 2021-10-01 | CMO East 2 | KLT | Budget
31 | 2021-10-01 | CMO East 2 | KLT | Forecast | 0
31 | 2021-10-01 | CMO East 2 | KLT | Actual | 0
31 | 2021-10-01 | CMO East 2 | Forefront | Budget
31 | 2021-10-01 | CMO East 2 | Forefront | Forecast | 991.07
31 | 2021-10-01 | CMO East 2 | Forefront | Actual | 0
31 | 2021-10-01 | CMO East 2 | DPF | Budget
31 | 2021-10-01 | CMO East 2 | DPF | Forecast | 0
31 | 2021-10-01 | CMO East 2 | DPF | Actual | 0
31 | 2021-10-01 | CMO East 2 | OMJ | Budget
31 | 2021-10-01 | CMO East 2 | OMJ | Forecast | 0
31 | 2021-10-01 | CMO East 2 | OMJ | Actual | 0
31 | 2021-10-01 | CMO East 2 | DHB Utilities | Budget
31 | 2021-10-01 | CMO East 2 | DHB Utilities | Forecast | 0
31 | 2021-10-01 | CMO East 2 | DHB Utilities | Actual | 0
31 | 2021-10-01 | CMO East 2 | JDT | Budget
31 | 2021-10-01 | CMO East 2 | JDT | Forecast | 877.17
31 | 2021-10-01 | CMO East 2 | JDT | Actual | 0
31 | 2021-10-01 | CMO East 2 | MURRAY | Budget
31 | 2021-10-01 | CMO East 2 | MURRAY | Forecast | 0
31 | 2021-10-01 | CMO East 2 | MURRAY | Actual | 0
31 | 2021-10-01 | West | Terra Firma | Budget
31 | 2021-10-01 | West | Terra Firma | Forecast | 0
31 | 2021-10-01 | West | Terra Firma | Actual | 0
31 | 2021-10-01 | West | KLT | Budget
31 | 2021-10-01 | West | KLT | Forecast | 0
31 | 2021-10-01 | West | KLT | Actual | 0
31 | 2021-10-01 | West | Forefront | Budget
31 | 2021-10-01 | West | Forefront | Forecast | 0
31 | 2021-10-01 | West | Forefront | Actual | 0
31 | 2021-10-01 | West | DPF | Budget
31 | 2021-10-01 | West | DPF | Forecast | 0
31 | 2021-10-01 | West | DPF | Actual | 0
31 | 2021-10-01 | West | OMJ | Budget
31 | 2021-10-01 | West | OMJ | Forecast | 0
31 | 2021-10-01 | West | OMJ | Actual | 0
31 | 2021-10-01 | West | DHB Utilities | Budget
31 | 2021-10-01 | West | DHB Utilities | Forecast | 0
31 | 2021-10-01 | West | DHB Utilities | Actual | 0
31 | 2021-10-01 | West | JDT | Budget
31 | 2021-10-01 | West | JDT | Forecast | 0
31 | 2021-10-01 | West | JDT | Actual | 0
31 | 2021-10-01 | West | MURRAY | Budget
31 | 2021-10-01 | West | MURRAY | Forecast | 0
31 | 2021-10-01 | West | MURRAY | Actual | 0
31 | 2021-10-01 | East | Terra Firma | Budget
31 | 2021-10-01 | East | Terra Firma | Forecast | 0
31 | 2021-10-01 | East | Terra Firma | Actual | 0
31 | 2021-10-01 | East | KLT | Budget
31 | 2021-10-01 | East | KLT | Forecast | 0
31 | 2021-10-01 | East | KLT | Actual | 0
31 | 2021-10-01 | East | Forefront | Budget
31 | 2021-10-01 | East | Forefront | Forecast | 0
31 | 2021-10-01 | East | Forefront | Actual | 0
31 | 2021-10-01 | East | DPF | Budget
31 | 2021-10-01 | East | DPF | Forecast | 0
31 | 2021-10-01 | East | DPF | Actual | 0
31 | 2021-10-01 | East | OMJ | Budget
31 | 2021-10-01 | East | OMJ | Forecast | 0
31 | 2021-10-01 | East | OMJ | Actual | 0
31 | 2021-10-01 | East | DHB Utilities | Budget
31 | 2021-10-01 | East | DHB Utilities | Forecast | 0
31 | 2021-10-01 | East | DHB Utilities | Actual | 0
31 | 2021-10-01 | East | JDT | Budget
31 | 2021-10-01 | East | JDT | Forecast | 0
31 | 2021-10-01 | East | JDT | Actual | 0
31 | 2021-10-01 | East | MURRAY | Budget
31 | 2021-10-01 | East | MURRAY | Forecast | 0
31 | 2021-10-01 | East | MURRAY | Actual | 0
31 | 2021-10-01 | Central | Terra Firma | Budget
31 | 2021-10-01 | Central | Terra Firma | Forecast | 0
31 | 2021-10-01 | Central | Terra Firma | Actual | 0
31 | 2021-10-01 | Central | KLT | Budget
31 | 2021-10-01 | Central | KLT | Forecast | 0
31 | 2021-10-01 | Central | KLT | Actual | 0
31 | 2021-10-01 | Central | Forefront | Budget
31 | 2021-10-01 | Central | Forefront | Forecast | 0
31 | 2021-10-01 | Central | Forefront | Actual | 0
31 | 2021-10-01 | Central | DPF | Budget
31 | 2021-10-01 | Central | DPF | Forecast | 0
31 | 2021-10-01 | Central | DPF | Actual | 0
31 | 2021-10-01 | Central | OMJ | Budget
31 | 2021-10-01 | Central | OMJ | Forecast | 0
31 | 2021-10-01 | Central | OMJ | Actual | 0
31 | 2021-10-01 | Central | DHB Utilities | Budget
31 | 2021-10-01 | Central | DHB Utilities | Forecast | 0
31 | 2021-10-01 | Central | DHB Utilities | Actual | 0
31 | 2021-10-01 | Central | JDT | Budget
31 | 2021-10-01 | Central | JDT | Forecast | 0
31 | 2021-10-01 | Central | JDT | Actual | 0
31 | 2021-10-01 | Central | MURRAY | Budget
31 | 2021-10-01 | Central | MURRAY | Forecast | 0
31 | 2021-10-01 | Central | MURRAY | Actual | 0
31 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Budget
31 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Forecast | 192.5
31 | 2021-10-01 | CMO West 1 | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Budget
31 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
31 | 2021-10-01 | CMO West 2 | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Budget
31 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
31 | 2021-10-01 | CMO East 1 | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Budget
31 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
31 | 2021-10-01 | CMO East 2 | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | West | DIRECT MOLE | Budget
31 | 2021-10-01 | West | DIRECT MOLE | Forecast | 0
31 | 2021-10-01 | West | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | East | DIRECT MOLE | Budget
31 | 2021-10-01 | East | DIRECT MOLE | Forecast | 0
31 | 2021-10-01 | East | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | Central | DIRECT MOLE | Budget
31 | 2021-10-01 | Central | DIRECT MOLE | Forecast | 0
31 | 2021-10-01 | Central | DIRECT MOLE | Actual | 0
31 | 2021-10-01 | CMO West 1 | SQS | Budget
31 | 2021-10-01 | CMO West 1 | SQS | Forecast | 197.53
31 | 2021-10-01 | CMO West 1 | SQS | Actual | 0
31 | 2021-10-01 | CMO West 2 | SQS | Budget
31 | 2021-10-01 | CMO West 2 | SQS | Forecast | 405.33
31 | 2021-10-01 | CMO West 2 | SQS | Actual | 0
31 | 2021-10-01 | CMO East 1 | SQS | Budget
31 | 2021-10-01 | CMO East 1 | SQS | Forecast | 0
31 | 2021-10-01 | CMO East 1 | SQS | Actual | 0
31 | 2021-10-01 | CMO East 2 | SQS | Budget
31 | 2021-10-01 | CMO East 2 | SQS | Forecast | 0
31 | 2021-10-01 | CMO East 2 | SQS | Actual | 0
31 | 2021-10-01 | West | SQS | Budget
31 | 2021-10-01 | West | SQS | Forecast | 0
31 | 2021-10-01 | West | SQS | Actual | 0
31 | 2021-10-01 | East | SQS | Budget
31 | 2021-10-01 | East | SQS | Forecast | 0
32 | 2021-10-01 | East | SQS | Actual | 0
32 | 2021-10-01 | Central | SQS | Budget
32 | 2021-10-01 | Central | SQS | Forecast | 0
31 | 2021-10-01 | Central | SQS | Actual | 0
32 | 2021-11-01 | CMO West 1 | Terra Firma | Budget
32 | 2021-11-01 | CMO West 1 | Terra Firma | Forecast | 0
32 | 2021-11-01 | CMO West 1 | Terra Firma | Actual | 0
32 | 2021-11-01 | CMO West 1 | KLT | Budget
32 | 2021-11-01 | CMO West 1 | KLT | Forecast | 509.69
32 | 2021-11-01 | CMO West 1 | KLT | Actual | 0
32 | 2021-11-01 | CMO West 1 | Forefront | Budget
32 | 2021-11-01 | CMO West 1 | Forefront | Forecast | 0
32 | 2021-11-01 | CMO West 1 | Forefront | Actual | 0
32 | 2021-11-01 | CMO West 1 | DPF | Budget
32 | 2021-11-01 | CMO West 1 | DPF | Forecast | 61.1
32 | 2021-11-01 | CMO West 1 | DPF | Actual | 0
32 | 2021-11-01 | CMO West 1 | OMJ | Budget
32 | 2021-11-01 | CMO West 1 | OMJ | Forecast | 0
32 | 2021-11-01 | CMO West 1 | OMJ | Actual | 0
32 | 2021-11-01 | CMO West 1 | DHB Utilities | Budget
32 | 2021-11-01 | CMO West 1 | DHB Utilities | Forecast | 0
32 | 2021-11-01 | CMO West 1 | DHB Utilities | Actual | 0
32 | 2021-11-01 | CMO West 1 | JDT | Budget
32 | 2021-11-01 | CMO West 1 | JDT | Forecast | 0
32 | 2021-11-01 | CMO West 1 | JDT | Actual | 0
32 | 2021-11-01 | CMO West 1 | MURRAY | Budget
32 | 2021-11-01 | CMO West 1 | MURRAY | Forecast | 0
32 | 2021-11-01 | CMO West 1 | MURRAY | Actual | 0
32 | 2021-11-01 | CMO West 2 | Terra Firma | Budget
32 | 2021-11-01 | CMO West 2 | Terra Firma | Forecast | 0
32 | 2021-11-01 | CMO West 2 | Terra Firma | Actual | 0
32 | 2021-11-01 | CMO West 2 | KLT | Budget
32 | 2021-11-01 | CMO West 2 | KLT | Forecast | 706.09
32 | 2021-11-01 | CMO West 2 | KLT | Actual | 0
32 | 2021-11-01 | CMO West 2 | Forefront | Budget
32 | 2021-11-01 | CMO West 2 | Forefront | Forecast | 0
32 | 2021-11-01 | CMO West 2 | Forefront | Actual | 0
32 | 2021-11-01 | CMO West 2 | DPF | Budget
32 | 2021-11-01 | CMO West 2 | DPF | Forecast | 0
32 | 2021-11-01 | CMO West 2 | DPF | Actual | 0
32 | 2021-11-01 | CMO West 2 | OMJ | Budget
32 | 2021-11-01 | CMO West 2 | OMJ | Forecast | 374.7386
32 | 2021-11-01 | CMO West 2 | OMJ | Actual | 0
32 | 2021-11-01 | CMO West 2 | DHB Utilities | Budget
32 | 2021-11-01 | CMO West 2 | DHB Utilities | Forecast | 529.5457
32 | 2021-11-01 | CMO West 2 | DHB Utilities | Actual | 0
32 | 2021-11-01 | CMO West 2 | JDT | Budget
32 | 2021-11-01 | CMO West 2 | JDT | Forecast | 0
32 | 2021-11-01 | CMO West 2 | JDT | Actual | 0
32 | 2021-11-01 | CMO West 2 | MURRAY | Budget
32 | 2021-11-01 | CMO West 2 | MURRAY | Forecast | 0
32 | 2021-11-01 | CMO West 2 | MURRAY | Actual | 0
32 | 2021-11-01 | CMO East 1 | Terra Firma | Budget
32 | 2021-11-01 | CMO East 1 | Terra Firma | Forecast | 178.44
32 | 2021-11-01 | CMO East 1 | Terra Firma | Actual | 0
32 | 2021-11-01 | CMO East 1 | KLT | Budget
32 | 2021-11-01 | CMO East 1 | KLT | Forecast | 0
32 | 2021-11-01 | CMO East 1 | KLT | Actual | 0
32 | 2021-11-01 | CMO East 1 | Forefront | Budget
32 | 2021-11-01 | CMO East 1 | Forefront | Forecast | 0
32 | 2021-11-01 | CMO East 1 | Forefront | Actual | 0
32 | 2021-11-01 | CMO East 1 | DPF | Budget
32 | 2021-11-01 | CMO East 1 | DPF | Forecast | 257.9
32 | 2021-11-01 | CMO East 1 | DPF | Actual | 0
32 | 2021-11-01 | CMO East 1 | OMJ | Budget
32 | 2021-11-01 | CMO East 1 | OMJ | Forecast | 0
32 | 2021-11-01 | CMO East 1 | OMJ | Actual | 0
32 | 2021-11-01 | CMO East 1 | DHB Utilities | Budget
32 | 2021-11-01 | CMO East 1 | DHB Utilities | Forecast | 0
32 | 2021-11-01 | CMO East 1 | DHB Utilities | Actual | 0
32 | 2021-11-01 | CMO East 1 | JDT | Budget
32 | 2021-11-01 | CMO East 1 | JDT | Forecast | 0
32 | 2021-11-01 | CMO East 1 | JDT | Actual | 0
32 | 2021-11-01 | CMO East 1 | MURRAY | Budget
32 | 2021-11-01 | CMO East 1 | MURRAY | Forecast | 158.54
32 | 2021-11-01 | CMO East 1 | MURRAY | Actual | 0
32 | 2021-11-01 | CMO East 2 | Terra Firma | Budget
32 | 2021-11-01 | CMO East 2 | Terra Firma | Forecast | 580.14
32 | 2021-11-01 | CMO East 2 | Terra Firma | Actual | 0
32 | 2021-11-01 | CMO East 2 | KLT | Budget
32 | 2021-11-01 | CMO East 2 | KLT | Forecast | 0
32 | 2021-11-01 | CMO East 2 | KLT | Actual | 0
32 | 2021-11-01 | CMO East 2 | Forefront | Budget
32 | 2021-11-01 | CMO East 2 | Forefront | Forecast | 954.63
32 | 2021-11-01 | CMO East 2 | Forefront | Actual | 0
32 | 2021-11-01 | CMO East 2 | DPF | Budget
32 | 2021-11-01 | CMO East 2 | DPF | Forecast | 0
32 | 2021-11-01 | CMO East 2 | DPF | Actual | 0
32 | 2021-11-01 | CMO East 2 | OMJ | Budget
32 | 2021-11-01 | CMO East 2 | OMJ | Forecast | 0
32 | 2021-11-01 | CMO East 2 | OMJ | Actual | 0
32 | 2021-11-01 | CMO East 2 | DHB Utilities | Budget
32 | 2021-11-01 | CMO East 2 | DHB Utilities | Forecast | 0
32 | 2021-11-01 | CMO East 2 | DHB Utilities | Actual | 0
32 | 2021-11-01 | CMO East 2 | JDT | Budget
32 | 2021-11-01 | CMO East 2 | JDT | Forecast | 874.04
32 | 2021-11-01 | CMO East 2 | JDT | Actual | 0
32 | 2021-11-01 | CMO East 2 | MURRAY | Budget
32 | 2021-11-01 | CMO East 2 | MURRAY | Forecast | 0
32 | 2021-11-01 | CMO East 2 | MURRAY | Actual | 0
32 | 2021-11-01 | West | Terra Firma | Budget
32 | 2021-11-01 | West | Terra Firma | Forecast | 0
32 | 2021-11-01 | West | Terra Firma | Actual | 0
32 | 2021-11-01 | West | KLT | Budget
32 | 2021-11-01 | West | KLT | Forecast | 0
32 | 2021-11-01 | West | KLT | Actual | 0
32 | 2021-11-01 | West | Forefront | Budget
32 | 2021-11-01 | West | Forefront | Forecast | 0
32 | 2021-11-01 | West | Forefront | Actual | 0
32 | 2021-11-01 | West | DPF | Budget
32 | 2021-11-01 | West | DPF | Forecast | 0
32 | 2021-11-01 | West | DPF | Actual | 0
32 | 2021-11-01 | West | OMJ | Budget
32 | 2021-11-01 | West | OMJ | Forecast | 0
32 | 2021-11-01 | West | OMJ | Actual | 0
32 | 2021-11-01 | West | DHB Utilities | Budget
32 | 2021-11-01 | West | DHB Utilities | Forecast | 0
32 | 2021-11-01 | West | DHB Utilities | Actual | 0
32 | 2021-11-01 | West | JDT | Budget
32 | 2021-11-01 | West | JDT | Forecast | 0
32 | 2021-11-01 | West | JDT | Actual | 0
32 | 2021-11-01 | West | MURRAY | Budget
32 | 2021-11-01 | West | MURRAY | Forecast | 0
32 | 2021-11-01 | West | MURRAY | Actual | 0
32 | 2021-11-01 | East | Terra Firma | Budget
32 | 2021-11-01 | East | Terra Firma | Forecast | 0
32 | 2021-11-01 | East | Terra Firma | Actual | 0
32 | 2021-11-01 | East | KLT | Budget
32 | 2021-11-01 | East | KLT | Forecast | 0
32 | 2021-11-01 | East | KLT | Actual | 0
32 | 2021-11-01 | East | Forefront | Budget
32 | 2021-11-01 | East | Forefront | Forecast | 0
32 | 2021-11-01 | East | Forefront | Actual | 0
32 | 2021-11-01 | East | DPF | Budget
32 | 2021-11-01 | East | DPF | Forecast | 0
32 | 2021-11-01 | East | DPF | Actual | 0
32 | 2021-11-01 | East | OMJ | Budget
32 | 2021-11-01 | East | OMJ | Forecast | 0
32 | 2021-11-01 | East | OMJ | Actual | 0
32 | 2021-11-01 | East | DHB Utilities | Budget
32 | 2021-11-01 | East | DHB Utilities | Forecast | 0
32 | 2021-11-01 | East | DHB Utilities | Actual | 0
32 | 2021-11-01 | East | JDT | Budget
32 | 2021-11-01 | East | JDT | Forecast | 0
32 | 2021-11-01 | East | JDT | Actual | 0
32 | 2021-11-01 | East | MURRAY | Budget
32 | 2021-11-01 | East | MURRAY | Forecast | 0
32 | 2021-11-01 | East | MURRAY | Actual | 0
32 | 2021-11-01 | Central | Terra Firma | Budget
32 | 2021-11-01 | Central | Terra Firma | Forecast | 0
32 | 2021-11-01 | Central | Terra Firma | Actual | 0
32 | 2021-11-01 | Central | KLT | Budget
32 | 2021-11-01 | Central | KLT | Forecast | 0
32 | 2021-11-01 | Central | KLT | Actual | 0
32 | 2021-11-01 | Central | Forefront | Budget
32 | 2021-11-01 | Central | Forefront | Forecast | 0
32 | 2021-11-01 | Central | Forefront | Actual | 0
32 | 2021-11-01 | Central | DPF | Budget
32 | 2021-11-01 | Central | DPF | Forecast | 0
32 | 2021-11-01 | Central | DPF | Actual | 0
32 | 2021-11-01 | Central | OMJ | Budget
32 | 2021-11-01 | Central | OMJ | Forecast | 0
32 | 2021-11-01 | Central | OMJ | Actual | 0
32 | 2021-11-01 | Central | DHB Utilities | Budget
32 | 2021-11-01 | Central | DHB Utilities | Forecast | 0
32 | 2021-11-01 | Central | DHB Utilities | Actual | 0
32 | 2021-11-01 | Central | JDT | Budget
32 | 2021-11-01 | Central | JDT | Forecast | 0
32 | 2021-11-01 | Central | JDT | Actual | 0
32 | 2021-11-01 | Central | MURRAY | Budget
32 | 2021-11-01 | Central | MURRAY | Forecast | 0
32 | 2021-11-01 | Central | MURRAY | Actual | 0
32 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Budget
32 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Forecast | 81.74
32 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Budget
32 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
32 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Budget
32 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
32 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Budget
32 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
32 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | West | DIRECT MOLE | Budget
32 | 2021-11-01 | West | DIRECT MOLE | Forecast | 0
32 | 2021-11-01 | West | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | East | DIRECT MOLE | Budget
32 | 2021-11-01 | East | DIRECT MOLE | Forecast | 0
32 | 2021-11-01 | East | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | Central | DIRECT MOLE | Budget
32 | 2021-11-01 | Central | DIRECT MOLE | Forecast | 0
32 | 2021-11-01 | Central | DIRECT MOLE | Actual | 0
32 | 2021-11-01 | CMO West 1 | SQS | Budget
32 | 2021-11-01 | CMO West 1 | SQS | Forecast | 197.53
32 | 2021-11-01 | CMO West 1 | SQS | Actual | 0
32 | 2021-11-01 | CMO West 2 | SQS | Budget
32 | 2021-11-01 | CMO West 2 | SQS | Forecast | 360.24
32 | 2021-11-01 | CMO West 2 | SQS | Actual | 0
32 | 2021-11-01 | CMO East 1 | SQS | Budget
32 | 2021-11-01 | CMO East 1 | SQS | Forecast | 0
32 | 2021-11-01 | CMO East 1 | SQS | Actual | 0
32 | 2021-11-01 | CMO East 2 | SQS | Budget
32 | 2021-11-01 | CMO East 2 | SQS | Forecast | 0
32 | 2021-11-01 | CMO East 2 | SQS | Actual | 0
32 | 2021-11-01 | West | SQS | Budget
32 | 2021-11-01 | West | SQS | Forecast | 0
32 | 2021-11-01 | West | SQS | Actual | 0
32 | 2021-11-01 | East | SQS | Budget
32 | 2021-11-01 | East | SQS | Forecast | 0
33 | 2021-11-01 | East | SQS | Actual | 0
33 | 2021-11-01 | Central | SQS | Budget
33 | 2021-11-01 | Central | SQS | Forecast | 0
32 | 2021-11-01 | Central | SQS | Actual | 0
33 | 2021-11-01 | CMO West 1 | Terra Firma | Budget
33 | 2021-11-01 | CMO West 1 | Terra Firma | Forecast | 0
33 | 2021-11-01 | CMO West 1 | Terra Firma | Actual | 0
33 | 2021-11-01 | CMO West 1 | KLT | Budget
33 | 2021-11-01 | CMO West 1 | KLT | Forecast | 498.05
33 | 2021-11-01 | CMO West 1 | KLT | Actual | 0
33 | 2021-11-01 | CMO West 1 | Forefront | Budget
33 | 2021-11-01 | CMO West 1 | Forefront | Forecast | 0
33 | 2021-11-01 | CMO West 1 | Forefront | Actual | 0
33 | 2021-11-01 | CMO West 1 | DPF | Budget
33 | 2021-11-01 | CMO West 1 | DPF | Forecast | 10.27
33 | 2021-11-01 | CMO West 1 | DPF | Actual | 0
33 | 2021-11-01 | CMO West 1 | OMJ | Budget
33 | 2021-11-01 | CMO West 1 | OMJ | Forecast | 0
33 | 2021-11-01 | CMO West 1 | OMJ | Actual | 0
33 | 2021-11-01 | CMO West 1 | DHB Utilities | Budget
33 | 2021-11-01 | CMO West 1 | DHB Utilities | Forecast | 0
33 | 2021-11-01 | CMO West 1 | DHB Utilities | Actual | 0
33 | 2021-11-01 | CMO West 1 | JDT | Budget
33 | 2021-11-01 | CMO West 1 | JDT | Forecast | 0
33 | 2021-11-01 | CMO West 1 | JDT | Actual | 0
33 | 2021-11-01 | CMO West 1 | MURRAY | Budget
33 | 2021-11-01 | CMO West 1 | MURRAY | Forecast | 0
33 | 2021-11-01 | CMO West 1 | MURRAY | Actual | 0
33 | 2021-11-01 | CMO West 2 | Terra Firma | Budget
33 | 2021-11-01 | CMO West 2 | Terra Firma | Forecast | 0
33 | 2021-11-01 | CMO West 2 | Terra Firma | Actual | 0
33 | 2021-11-01 | CMO West 2 | KLT | Budget
33 | 2021-11-01 | CMO West 2 | KLT | Forecast | 828.53
33 | 2021-11-01 | CMO West 2 | KLT | Actual | 0
33 | 2021-11-01 | CMO West 2 | Forefront | Budget
33 | 2021-11-01 | CMO West 2 | Forefront | Forecast | 0
33 | 2021-11-01 | CMO West 2 | Forefront | Actual | 0
33 | 2021-11-01 | CMO West 2 | DPF | Budget
33 | 2021-11-01 | CMO West 2 | DPF | Forecast | 0
33 | 2021-11-01 | CMO West 2 | DPF | Actual | 0
33 | 2021-11-01 | CMO West 2 | OMJ | Budget
33 | 2021-11-01 | CMO West 2 | OMJ | Forecast | 393.3286
33 | 2021-11-01 | CMO West 2 | OMJ | Actual | 0
33 | 2021-11-01 | CMO West 2 | DHB Utilities | Budget
33 | 2021-11-01 | CMO West 2 | DHB Utilities | Forecast | 529.5457
33 | 2021-11-01 | CMO West 2 | DHB Utilities | Actual | 0
33 | 2021-11-01 | CMO West 2 | JDT | Budget
33 | 2021-11-01 | CMO West 2 | JDT | Forecast | 0
33 | 2021-11-01 | CMO West 2 | JDT | Actual | 0
33 | 2021-11-01 | CMO West 2 | MURRAY | Budget
33 | 2021-11-01 | CMO West 2 | MURRAY | Forecast | 0
33 | 2021-11-01 | CMO West 2 | MURRAY | Actual | 0
33 | 2021-11-01 | CMO East 1 | Terra Firma | Budget
33 | 2021-11-01 | CMO East 1 | Terra Firma | Forecast | 143.87
33 | 2021-11-01 | CMO East 1 | Terra Firma | Actual | 0
33 | 2021-11-01 | CMO East 1 | KLT | Budget
33 | 2021-11-01 | CMO East 1 | KLT | Forecast | 0
33 | 2021-11-01 | CMO East 1 | KLT | Actual | 0
33 | 2021-11-01 | CMO East 1 | Forefront | Budget
33 | 2021-11-01 | CMO East 1 | Forefront | Forecast | 0
33 | 2021-11-01 | CMO East 1 | Forefront | Actual | 0
33 | 2021-11-01 | CMO East 1 | DPF | Budget
33 | 2021-11-01 | CMO East 1 | DPF | Forecast | 283.36
33 | 2021-11-01 | CMO East 1 | DPF | Actual | 0
33 | 2021-11-01 | CMO East 1 | OMJ | Budget
33 | 2021-11-01 | CMO East 1 | OMJ | Forecast | 0
33 | 2021-11-01 | CMO East 1 | OMJ | Actual | 0
33 | 2021-11-01 | CMO East 1 | DHB Utilities | Budget
33 | 2021-11-01 | CMO East 1 | DHB Utilities | Forecast | 0
33 | 2021-11-01 | CMO East 1 | DHB Utilities | Actual | 0
33 | 2021-11-01 | CMO East 1 | JDT | Budget
33 | 2021-11-01 | CMO East 1 | JDT | Forecast | 0
33 | 2021-11-01 | CMO East 1 | JDT | Actual | 0
33 | 2021-11-01 | CMO East 1 | MURRAY | Budget
33 | 2021-11-01 | CMO East 1 | MURRAY | Forecast | 158.54
33 | 2021-11-01 | CMO East 1 | MURRAY | Actual | 0
33 | 2021-11-01 | CMO East 2 | Terra Firma | Budget
33 | 2021-11-01 | CMO East 2 | Terra Firma | Forecast | 498.2
33 | 2021-11-01 | CMO East 2 | Terra Firma | Actual | 0
33 | 2021-11-01 | CMO East 2 | KLT | Budget
33 | 2021-11-01 | CMO East 2 | KLT | Forecast | 0
33 | 2021-11-01 | CMO East 2 | KLT | Actual | 0
33 | 2021-11-01 | CMO East 2 | Forefront | Budget
33 | 2021-11-01 | CMO East 2 | Forefront | Forecast | 835.8
33 | 2021-11-01 | CMO East 2 | Forefront | Actual | 0
33 | 2021-11-01 | CMO East 2 | DPF | Budget
33 | 2021-11-01 | CMO East 2 | DPF | Forecast | 0
33 | 2021-11-01 | CMO East 2 | DPF | Actual | 0
33 | 2021-11-01 | CMO East 2 | OMJ | Budget
33 | 2021-11-01 | CMO East 2 | OMJ | Forecast | 0
33 | 2021-11-01 | CMO East 2 | OMJ | Actual | 0
33 | 2021-11-01 | CMO East 2 | DHB Utilities | Budget
33 | 2021-11-01 | CMO East 2 | DHB Utilities | Forecast | 0
33 | 2021-11-01 | CMO East 2 | DHB Utilities | Actual | 0
33 | 2021-11-01 | CMO East 2 | JDT | Budget
33 | 2021-11-01 | CMO East 2 | JDT | Forecast | 713.77
33 | 2021-11-01 | CMO East 2 | JDT | Actual | 0
33 | 2021-11-01 | CMO East 2 | MURRAY | Budget
33 | 2021-11-01 | CMO East 2 | MURRAY | Forecast | 0
33 | 2021-11-01 | CMO East 2 | MURRAY | Actual | 0
33 | 2021-11-01 | West | Terra Firma | Budget
33 | 2021-11-01 | West | Terra Firma | Forecast | 0
33 | 2021-11-01 | West | Terra Firma | Actual | 0
33 | 2021-11-01 | West | KLT | Budget
33 | 2021-11-01 | West | KLT | Forecast | 0
33 | 2021-11-01 | West | KLT | Actual | 0
33 | 2021-11-01 | West | Forefront | Budget
33 | 2021-11-01 | West | Forefront | Forecast | 0
33 | 2021-11-01 | West | Forefront | Actual | 0
33 | 2021-11-01 | West | DPF | Budget
33 | 2021-11-01 | West | DPF | Forecast | 0
33 | 2021-11-01 | West | DPF | Actual | 0
33 | 2021-11-01 | West | OMJ | Budget
33 | 2021-11-01 | West | OMJ | Forecast | 0
33 | 2021-11-01 | West | OMJ | Actual | 0
33 | 2021-11-01 | West | DHB Utilities | Budget
33 | 2021-11-01 | West | DHB Utilities | Forecast | 0
33 | 2021-11-01 | West | DHB Utilities | Actual | 0
33 | 2021-11-01 | West | JDT | Budget
33 | 2021-11-01 | West | JDT | Forecast | 0
33 | 2021-11-01 | West | JDT | Actual | 0
33 | 2021-11-01 | West | MURRAY | Budget
33 | 2021-11-01 | West | MURRAY | Forecast | 0
33 | 2021-11-01 | West | MURRAY | Actual | 0
33 | 2021-11-01 | East | Terra Firma | Budget
33 | 2021-11-01 | East | Terra Firma | Forecast | 0
33 | 2021-11-01 | East | Terra Firma | Actual | 0
33 | 2021-11-01 | East | KLT | Budget
33 | 2021-11-01 | East | KLT | Forecast | 0
33 | 2021-11-01 | East | KLT | Actual | 0
33 | 2021-11-01 | East | Forefront | Budget
33 | 2021-11-01 | East | Forefront | Forecast | 0
33 | 2021-11-01 | East | Forefront | Actual | 0
33 | 2021-11-01 | East | DPF | Budget
33 | 2021-11-01 | East | DPF | Forecast | 0
33 | 2021-11-01 | East | DPF | Actual | 0
33 | 2021-11-01 | East | OMJ | Budget
33 | 2021-11-01 | East | OMJ | Forecast | 0
33 | 2021-11-01 | East | OMJ | Actual | 0
33 | 2021-11-01 | East | DHB Utilities | Budget
33 | 2021-11-01 | East | DHB Utilities | Forecast | 0
33 | 2021-11-01 | East | DHB Utilities | Actual | 0
33 | 2021-11-01 | East | JDT | Budget
33 | 2021-11-01 | East | JDT | Forecast | 0
33 | 2021-11-01 | East | JDT | Actual | 0
33 | 2021-11-01 | East | MURRAY | Budget
33 | 2021-11-01 | East | MURRAY | Forecast | 0
33 | 2021-11-01 | East | MURRAY | Actual | 0
33 | 2021-11-01 | Central | Terra Firma | Budget
33 | 2021-11-01 | Central | Terra Firma | Forecast | 0
33 | 2021-11-01 | Central | Terra Firma | Actual | 0
33 | 2021-11-01 | Central | KLT | Budget
33 | 2021-11-01 | Central | KLT | Forecast | 0
33 | 2021-11-01 | Central | KLT | Actual | 0
33 | 2021-11-01 | Central | Forefront | Budget
33 | 2021-11-01 | Central | Forefront | Forecast | 0
33 | 2021-11-01 | Central | Forefront | Actual | 0
33 | 2021-11-01 | Central | DPF | Budget
33 | 2021-11-01 | Central | DPF | Forecast | 0
33 | 2021-11-01 | Central | DPF | Actual | 0
33 | 2021-11-01 | Central | OMJ | Budget
33 | 2021-11-01 | Central | OMJ | Forecast | 0
33 | 2021-11-01 | Central | OMJ | Actual | 0
33 | 2021-11-01 | Central | DHB Utilities | Budget
33 | 2021-11-01 | Central | DHB Utilities | Forecast | 0
33 | 2021-11-01 | Central | DHB Utilities | Actual | 0
33 | 2021-11-01 | Central | JDT | Budget
33 | 2021-11-01 | Central | JDT | Forecast | 0
33 | 2021-11-01 | Central | JDT | Actual | 0
33 | 2021-11-01 | Central | MURRAY | Budget
33 | 2021-11-01 | Central | MURRAY | Forecast | 0
33 | 2021-11-01 | Central | MURRAY | Actual | 0
33 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Budget
33 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Forecast | 81.74
33 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Budget
33 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
33 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Budget
33 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
33 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Budget
33 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
33 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | West | DIRECT MOLE | Budget
33 | 2021-11-01 | West | DIRECT MOLE | Forecast | 0
33 | 2021-11-01 | West | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | East | DIRECT MOLE | Budget
33 | 2021-11-01 | East | DIRECT MOLE | Forecast | 0
33 | 2021-11-01 | East | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | Central | DIRECT MOLE | Budget
33 | 2021-11-01 | Central | DIRECT MOLE | Forecast | 0
33 | 2021-11-01 | Central | DIRECT MOLE | Actual | 0
33 | 2021-11-01 | CMO West 1 | SQS | Budget
33 | 2021-11-01 | CMO West 1 | SQS | Forecast | 197.53
33 | 2021-11-01 | CMO West 1 | SQS | Actual | 0
33 | 2021-11-01 | CMO West 2 | SQS | Budget
33 | 2021-11-01 | CMO West 2 | SQS | Forecast | 417.52
33 | 2021-11-01 | CMO West 2 | SQS | Actual | 0
33 | 2021-11-01 | CMO East 1 | SQS | Budget
33 | 2021-11-01 | CMO East 1 | SQS | Forecast | 0
33 | 2021-11-01 | CMO East 1 | SQS | Actual | 0
33 | 2021-11-01 | CMO East 2 | SQS | Budget
33 | 2021-11-01 | CMO East 2 | SQS | Forecast | 0
33 | 2021-11-01 | CMO East 2 | SQS | Actual | 0
33 | 2021-11-01 | West | SQS | Budget
33 | 2021-11-01 | West | SQS | Forecast | 0
33 | 2021-11-01 | West | SQS | Actual | 0
33 | 2021-11-01 | East | SQS | Budget
33 | 2021-11-01 | East | SQS | Forecast | 0
34 | 2021-11-01 | East | SQS | Actual | 0
34 | 2021-11-01 | Central | SQS | Budget
34 | 2021-11-01 | Central | SQS | Forecast | 0
33 | 2021-11-01 | Central | SQS | Actual | 0
34 | 2021-11-01 | CMO West 1 | Terra Firma | Budget
34 | 2021-11-01 | CMO West 1 | Terra Firma | Forecast | 0
34 | 2021-11-01 | CMO West 1 | Terra Firma | Actual | 0
34 | 2021-11-01 | CMO West 1 | KLT | Budget
34 | 2021-11-01 | CMO West 1 | KLT | Forecast | 485.73
34 | 2021-11-01 | CMO West 1 | KLT | Actual | 0
34 | 2021-11-01 | CMO West 1 | Forefront | Budget
34 | 2021-11-01 | CMO West 1 | Forefront | Forecast | 0
34 | 2021-11-01 | CMO West 1 | Forefront | Actual | 0
34 | 2021-11-01 | CMO West 1 | DPF | Budget
34 | 2021-11-01 | CMO West 1 | DPF | Forecast | 65.49
34 | 2021-11-01 | CMO West 1 | DPF | Actual | 0
34 | 2021-11-01 | CMO West 1 | OMJ | Budget
34 | 2021-11-01 | CMO West 1 | OMJ | Forecast | 0
34 | 2021-11-01 | CMO West 1 | OMJ | Actual | 0
34 | 2021-11-01 | CMO West 1 | DHB Utilities | Budget
34 | 2021-11-01 | CMO West 1 | DHB Utilities | Forecast | 0
34 | 2021-11-01 | CMO West 1 | DHB Utilities | Actual | 0
34 | 2021-11-01 | CMO West 1 | JDT | Budget
34 | 2021-11-01 | CMO West 1 | JDT | Forecast | 0
34 | 2021-11-01 | CMO West 1 | JDT | Actual | 0
34 | 2021-11-01 | CMO West 1 | MURRAY | Budget
34 | 2021-11-01 | CMO West 1 | MURRAY | Forecast | 0
34 | 2021-11-01 | CMO West 1 | MURRAY | Actual | 0
34 | 2021-11-01 | CMO West 2 | Terra Firma | Budget
34 | 2021-11-01 | CMO West 2 | Terra Firma | Forecast | 0
34 | 2021-11-01 | CMO West 2 | Terra Firma | Actual | 0
34 | 2021-11-01 | CMO West 2 | KLT | Budget
34 | 2021-11-01 | CMO West 2 | KLT | Forecast | 828.53
34 | 2021-11-01 | CMO West 2 | KLT | Actual | 0
34 | 2021-11-01 | CMO West 2 | Forefront | Budget
34 | 2021-11-01 | CMO West 2 | Forefront | Forecast | 0
34 | 2021-11-01 | CMO West 2 | Forefront | Actual | 0
34 | 2021-11-01 | CMO West 2 | DPF | Budget
34 | 2021-11-01 | CMO West 2 | DPF | Forecast | 0
34 | 2021-11-01 | CMO West 2 | DPF | Actual | 0
34 | 2021-11-01 | CMO West 2 | OMJ | Budget
34 | 2021-11-01 | CMO West 2 | OMJ | Forecast | 496.1486
34 | 2021-11-01 | CMO West 2 | OMJ | Actual | 0
34 | 2021-11-01 | CMO West 2 | DHB Utilities | Budget
34 | 2021-11-01 | CMO West 2 | DHB Utilities | Forecast | 223.3857
34 | 2021-11-01 | CMO West 2 | DHB Utilities | Actual | 0
34 | 2021-11-01 | CMO West 2 | JDT | Budget
34 | 2021-11-01 | CMO West 2 | JDT | Forecast | 0
34 | 2021-11-01 | CMO West 2 | JDT | Actual | 0
34 | 2021-11-01 | CMO West 2 | MURRAY | Budget
34 | 2021-11-01 | CMO West 2 | MURRAY | Forecast | 0
34 | 2021-11-01 | CMO West 2 | MURRAY | Actual | 0
34 | 2021-11-01 | CMO East 1 | Terra Firma | Budget
34 | 2021-11-01 | CMO East 1 | Terra Firma | Forecast | 158.36
34 | 2021-11-01 | CMO East 1 | Terra Firma | Actual | 0
34 | 2021-11-01 | CMO East 1 | KLT | Budget
34 | 2021-11-01 | CMO East 1 | KLT | Forecast | 0
34 | 2021-11-01 | CMO East 1 | KLT | Actual | 0
34 | 2021-11-01 | CMO East 1 | Forefront | Budget
34 | 2021-11-01 | CMO East 1 | Forefront | Forecast | 0
34 | 2021-11-01 | CMO East 1 | Forefront | Actual | 0
34 | 2021-11-01 | CMO East 1 | DPF | Budget
34 | 2021-11-01 | CMO East 1 | DPF | Forecast | 283.36
34 | 2021-11-01 | CMO East 1 | DPF | Actual | 0
34 | 2021-11-01 | CMO East 1 | OMJ | Budget
34 | 2021-11-01 | CMO East 1 | OMJ | Forecast | 0
34 | 2021-11-01 | CMO East 1 | OMJ | Actual | 0
34 | 2021-11-01 | CMO East 1 | DHB Utilities | Budget
34 | 2021-11-01 | CMO East 1 | DHB Utilities | Forecast | 0
34 | 2021-11-01 | CMO East 1 | DHB Utilities | Actual | 0
34 | 2021-11-01 | CMO East 1 | JDT | Budget
34 | 2021-11-01 | CMO East 1 | JDT | Forecast | 0
34 | 2021-11-01 | CMO East 1 | JDT | Actual | 0
34 | 2021-11-01 | CMO East 1 | MURRAY | Budget
34 | 2021-11-01 | CMO East 1 | MURRAY | Forecast | 158.54
34 | 2021-11-01 | CMO East 1 | MURRAY | Actual | 0
34 | 2021-11-01 | CMO East 2 | Terra Firma | Budget
34 | 2021-11-01 | CMO East 2 | Terra Firma | Forecast | 546.26
34 | 2021-11-01 | CMO East 2 | Terra Firma | Actual | 0
34 | 2021-11-01 | CMO East 2 | KLT | Budget
34 | 2021-11-01 | CMO East 2 | KLT | Forecast | 0
34 | 2021-11-01 | CMO East 2 | KLT | Actual | 0
34 | 2021-11-01 | CMO East 2 | Forefront | Budget
34 | 2021-11-01 | CMO East 2 | Forefront | Forecast | 820.61
34 | 2021-11-01 | CMO East 2 | Forefront | Actual | 0
34 | 2021-11-01 | CMO East 2 | DPF | Budget
34 | 2021-11-01 | CMO East 2 | DPF | Forecast | 0
34 | 2021-11-01 | CMO East 2 | DPF | Actual | 0
34 | 2021-11-01 | CMO East 2 | OMJ | Budget
34 | 2021-11-01 | CMO East 2 | OMJ | Forecast | 0
34 | 2021-11-01 | CMO East 2 | OMJ | Actual | 0
34 | 2021-11-01 | CMO East 2 | DHB Utilities | Budget
34 | 2021-11-01 | CMO East 2 | DHB Utilities | Forecast | 0
34 | 2021-11-01 | CMO East 2 | DHB Utilities | Actual | 0
34 | 2021-11-01 | CMO East 2 | JDT | Budget
34 | 2021-11-01 | CMO East 2 | JDT | Forecast | 676.95
34 | 2021-11-01 | CMO East 2 | JDT | Actual | 0
34 | 2021-11-01 | CMO East 2 | MURRAY | Budget
34 | 2021-11-01 | CMO East 2 | MURRAY | Forecast | 0
34 | 2021-11-01 | CMO East 2 | MURRAY | Actual | 0
34 | 2021-11-01 | West | Terra Firma | Budget
34 | 2021-11-01 | West | Terra Firma | Forecast | 0
34 | 2021-11-01 | West | Terra Firma | Actual | 0
34 | 2021-11-01 | West | KLT | Budget
34 | 2021-11-01 | West | KLT | Forecast | 0
34 | 2021-11-01 | West | KLT | Actual | 0
34 | 2021-11-01 | West | Forefront | Budget
34 | 2021-11-01 | West | Forefront | Forecast | 0
34 | 2021-11-01 | West | Forefront | Actual | 0
34 | 2021-11-01 | West | DPF | Budget
34 | 2021-11-01 | West | DPF | Forecast | 0
34 | 2021-11-01 | West | DPF | Actual | 0
34 | 2021-11-01 | West | OMJ | Budget
34 | 2021-11-01 | West | OMJ | Forecast | 0
34 | 2021-11-01 | West | OMJ | Actual | 0
34 | 2021-11-01 | West | DHB Utilities | Budget
34 | 2021-11-01 | West | DHB Utilities | Forecast | 0
34 | 2021-11-01 | West | DHB Utilities | Actual | 0
34 | 2021-11-01 | West | JDT | Budget
34 | 2021-11-01 | West | JDT | Forecast | 0
34 | 2021-11-01 | West | JDT | Actual | 0
34 | 2021-11-01 | West | MURRAY | Budget
34 | 2021-11-01 | West | MURRAY | Forecast | 0
34 | 2021-11-01 | West | MURRAY | Actual | 0
34 | 2021-11-01 | East | Terra Firma | Budget
34 | 2021-11-01 | East | Terra Firma | Forecast | 0
34 | 2021-11-01 | East | Terra Firma | Actual | 0
34 | 2021-11-01 | East | KLT | Budget
34 | 2021-11-01 | East | KLT | Forecast | 0
34 | 2021-11-01 | East | KLT | Actual | 0
34 | 2021-11-01 | East | Forefront | Budget
34 | 2021-11-01 | East | Forefront | Forecast | 0
34 | 2021-11-01 | East | Forefront | Actual | 0
34 | 2021-11-01 | East | DPF | Budget
34 | 2021-11-01 | East | DPF | Forecast | 0
34 | 2021-11-01 | East | DPF | Actual | 0
34 | 2021-11-01 | East | OMJ | Budget
34 | 2021-11-01 | East | OMJ | Forecast | 0
34 | 2021-11-01 | East | OMJ | Actual | 0
34 | 2021-11-01 | East | DHB Utilities | Budget
34 | 2021-11-01 | East | DHB Utilities | Forecast | 0
34 | 2021-11-01 | East | DHB Utilities | Actual | 0
34 | 2021-11-01 | East | JDT | Budget
34 | 2021-11-01 | East | JDT | Forecast | 0
34 | 2021-11-01 | East | JDT | Actual | 0
34 | 2021-11-01 | East | MURRAY | Budget
34 | 2021-11-01 | East | MURRAY | Forecast | 0
34 | 2021-11-01 | East | MURRAY | Actual | 0
34 | 2021-11-01 | Central | Terra Firma | Budget
34 | 2021-11-01 | Central | Terra Firma | Forecast | 0
34 | 2021-11-01 | Central | Terra Firma | Actual | 0
34 | 2021-11-01 | Central | KLT | Budget
34 | 2021-11-01 | Central | KLT | Forecast | 0
34 | 2021-11-01 | Central | KLT | Actual | 0
34 | 2021-11-01 | Central | Forefront | Budget
34 | 2021-11-01 | Central | Forefront | Forecast | 0
34 | 2021-11-01 | Central | Forefront | Actual | 0
34 | 2021-11-01 | Central | DPF | Budget
34 | 2021-11-01 | Central | DPF | Forecast | 0
34 | 2021-11-01 | Central | DPF | Actual | 0
34 | 2021-11-01 | Central | OMJ | Budget
34 | 2021-11-01 | Central | OMJ | Forecast | 0
34 | 2021-11-01 | Central | OMJ | Actual | 0
34 | 2021-11-01 | Central | DHB Utilities | Budget
34 | 2021-11-01 | Central | DHB Utilities | Forecast | 0
34 | 2021-11-01 | Central | DHB Utilities | Actual | 0
34 | 2021-11-01 | Central | JDT | Budget
34 | 2021-11-01 | Central | JDT | Forecast | 0
34 | 2021-11-01 | Central | JDT | Actual | 0
34 | 2021-11-01 | Central | MURRAY | Budget
34 | 2021-11-01 | Central | MURRAY | Forecast | 0
34 | 2021-11-01 | Central | MURRAY | Actual | 0
34 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Budget
34 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Forecast | 81.74
34 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Budget
34 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
34 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Budget
34 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
34 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Budget
34 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
34 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | West | DIRECT MOLE | Budget
34 | 2021-11-01 | West | DIRECT MOLE | Forecast | 0
34 | 2021-11-01 | West | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | East | DIRECT MOLE | Budget
34 | 2021-11-01 | East | DIRECT MOLE | Forecast | 0
34 | 2021-11-01 | East | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | Central | DIRECT MOLE | Budget
34 | 2021-11-01 | Central | DIRECT MOLE | Forecast | 0
34 | 2021-11-01 | Central | DIRECT MOLE | Actual | 0
34 | 2021-11-01 | CMO West 1 | SQS | Budget
34 | 2021-11-01 | CMO West 1 | SQS | Forecast | 197.53
34 | 2021-11-01 | CMO West 1 | SQS | Actual | 0
34 | 2021-11-01 | CMO West 2 | SQS | Budget
34 | 2021-11-01 | CMO West 2 | SQS | Forecast | 303.97
34 | 2021-11-01 | CMO West 2 | SQS | Actual | 0
34 | 2021-11-01 | CMO East 1 | SQS | Budget
34 | 2021-11-01 | CMO East 1 | SQS | Forecast | 0
34 | 2021-11-01 | CMO East 1 | SQS | Actual | 0
34 | 2021-11-01 | CMO East 2 | SQS | Budget
34 | 2021-11-01 | CMO East 2 | SQS | Forecast | 0
34 | 2021-11-01 | CMO East 2 | SQS | Actual | 0
34 | 2021-11-01 | West | SQS | Budget
34 | 2021-11-01 | West | SQS | Forecast | 0
34 | 2021-11-01 | West | SQS | Actual | 0
34 | 2021-11-01 | East | SQS | Budget
34 | 2021-11-01 | East | SQS | Forecast | 0
35 | 2021-11-01 | East | SQS | Actual | 0
35 | 2021-11-01 | Central | SQS | Budget
35 | 2021-11-01 | Central | SQS | Forecast | 0
34 | 2021-11-01 | Central | SQS | Actual | 0
35 | 2021-11-01 | CMO West 1 | Terra Firma | Budget
35 | 2021-11-01 | CMO West 1 | Terra Firma | Forecast | 0
35 | 2021-11-01 | CMO West 1 | Terra Firma | Actual | 0
35 | 2021-11-01 | CMO West 1 | KLT | Budget
35 | 2021-11-01 | CMO West 1 | KLT | Forecast | 485.73
35 | 2021-11-01 | CMO West 1 | KLT | Actual | 0
35 | 2021-11-01 | CMO West 1 | Forefront | Budget
35 | 2021-11-01 | CMO West 1 | Forefront | Forecast | 0
35 | 2021-11-01 | CMO West 1 | Forefront | Actual | 0
35 | 2021-11-01 | CMO West 1 | DPF | Budget
35 | 2021-11-01 | CMO West 1 | DPF | Forecast | 65.49
35 | 2021-11-01 | CMO West 1 | DPF | Actual | 0
35 | 2021-11-01 | CMO West 1 | OMJ | Budget
35 | 2021-11-01 | CMO West 1 | OMJ | Forecast | 0
35 | 2021-11-01 | CMO West 1 | OMJ | Actual | 0
35 | 2021-11-01 | CMO West 1 | DHB Utilities | Budget
35 | 2021-11-01 | CMO West 1 | DHB Utilities | Forecast | 0
35 | 2021-11-01 | CMO West 1 | DHB Utilities | Actual | 0
35 | 2021-11-01 | CMO West 1 | JDT | Budget
35 | 2021-11-01 | CMO West 1 | JDT | Forecast | 0
35 | 2021-11-01 | CMO West 1 | JDT | Actual | 0
35 | 2021-11-01 | CMO West 1 | MURRAY | Budget
35 | 2021-11-01 | CMO West 1 | MURRAY | Forecast | 0
35 | 2021-11-01 | CMO West 1 | MURRAY | Actual | 0
35 | 2021-11-01 | CMO West 2 | Terra Firma | Budget
35 | 2021-11-01 | CMO West 2 | Terra Firma | Forecast | 0
35 | 2021-11-01 | CMO West 2 | Terra Firma | Actual | 0
35 | 2021-11-01 | CMO West 2 | KLT | Budget
35 | 2021-11-01 | CMO West 2 | KLT | Forecast | 838.93
35 | 2021-11-01 | CMO West 2 | KLT | Actual | 0
35 | 2021-11-01 | CMO West 2 | Forefront | Budget
35 | 2021-11-01 | CMO West 2 | Forefront | Forecast | 0
35 | 2021-11-01 | CMO West 2 | Forefront | Actual | 0
35 | 2021-11-01 | CMO West 2 | DPF | Budget
35 | 2021-11-01 | CMO West 2 | DPF | Forecast | 0
35 | 2021-11-01 | CMO West 2 | DPF | Actual | 0
35 | 2021-11-01 | CMO West 2 | OMJ | Budget
35 | 2021-11-01 | CMO West 2 | OMJ | Forecast | 562.8086
35 | 2021-11-01 | CMO West 2 | OMJ | Actual | 0
35 | 2021-11-01 | CMO West 2 | DHB Utilities | Budget
35 | 2021-11-01 | CMO West 2 | DHB Utilities | Forecast | 229.3857
35 | 2021-11-01 | CMO West 2 | DHB Utilities | Actual | 0
35 | 2021-11-01 | CMO West 2 | JDT | Budget
35 | 2021-11-01 | CMO West 2 | JDT | Forecast | 0
35 | 2021-11-01 | CMO West 2 | JDT | Actual | 0
35 | 2021-11-01 | CMO West 2 | MURRAY | Budget
35 | 2021-11-01 | CMO West 2 | MURRAY | Forecast | 0
35 | 2021-11-01 | CMO West 2 | MURRAY | Actual | 0
35 | 2021-11-01 | CMO East 1 | Terra Firma | Budget
35 | 2021-11-01 | CMO East 1 | Terra Firma | Forecast | 158.36
35 | 2021-11-01 | CMO East 1 | Terra Firma | Actual | 0
35 | 2021-11-01 | CMO East 1 | KLT | Budget
35 | 2021-11-01 | CMO East 1 | KLT | Forecast | 0
35 | 2021-11-01 | CMO East 1 | KLT | Actual | 0
35 | 2021-11-01 | CMO East 1 | Forefront | Budget
35 | 2021-11-01 | CMO East 1 | Forefront | Forecast | 0
35 | 2021-11-01 | CMO East 1 | Forefront | Actual | 0
35 | 2021-11-01 | CMO East 1 | DPF | Budget
35 | 2021-11-01 | CMO East 1 | DPF | Forecast | 223.62
35 | 2021-11-01 | CMO East 1 | DPF | Actual | 0
35 | 2021-11-01 | CMO East 1 | OMJ | Budget
35 | 2021-11-01 | CMO East 1 | OMJ | Forecast | 0
35 | 2021-11-01 | CMO East 1 | OMJ | Actual | 0
35 | 2021-11-01 | CMO East 1 | DHB Utilities | Budget
35 | 2021-11-01 | CMO East 1 | DHB Utilities | Forecast | 0
35 | 2021-11-01 | CMO East 1 | DHB Utilities | Actual | 0
35 | 2021-11-01 | CMO East 1 | JDT | Budget
35 | 2021-11-01 | CMO East 1 | JDT | Forecast | 0
35 | 2021-11-01 | CMO East 1 | JDT | Actual | 0
35 | 2021-11-01 | CMO East 1 | MURRAY | Budget
35 | 2021-11-01 | CMO East 1 | MURRAY | Forecast | 158.54
35 | 2021-11-01 | CMO East 1 | MURRAY | Actual | 0
35 | 2021-11-01 | CMO East 2 | Terra Firma | Budget
35 | 2021-11-01 | CMO East 2 | Terra Firma | Forecast | 546.26
35 | 2021-11-01 | CMO East 2 | Terra Firma | Actual | 0
35 | 2021-11-01 | CMO East 2 | KLT | Budget
35 | 2021-11-01 | CMO East 2 | KLT | Forecast | 0
35 | 2021-11-01 | CMO East 2 | KLT | Actual | 0
35 | 2021-11-01 | CMO East 2 | Forefront | Budget
35 | 2021-11-01 | CMO East 2 | Forefront | Forecast | 832.96
35 | 2021-11-01 | CMO East 2 | Forefront | Actual | 0
35 | 2021-11-01 | CMO East 2 | DPF | Budget
35 | 2021-11-01 | CMO East 2 | DPF | Forecast | 0
35 | 2021-11-01 | CMO East 2 | DPF | Actual | 0
35 | 2021-11-01 | CMO East 2 | OMJ | Budget
35 | 2021-11-01 | CMO East 2 | OMJ | Forecast | 0
35 | 2021-11-01 | CMO East 2 | OMJ | Actual | 0
35 | 2021-11-01 | CMO East 2 | DHB Utilities | Budget
35 | 2021-11-01 | CMO East 2 | DHB Utilities | Forecast | 0
35 | 2021-11-01 | CMO East 2 | DHB Utilities | Actual | 0
35 | 2021-11-01 | CMO East 2 | JDT | Budget
35 | 2021-11-01 | CMO East 2 | JDT | Forecast | 676.95
35 | 2021-11-01 | CMO East 2 | JDT | Actual | 0
35 | 2021-11-01 | CMO East 2 | MURRAY | Budget
35 | 2021-11-01 | CMO East 2 | MURRAY | Forecast | 0
35 | 2021-11-01 | CMO East 2 | MURRAY | Actual | 0
35 | 2021-11-01 | West | Terra Firma | Budget
35 | 2021-11-01 | West | Terra Firma | Forecast | 0
35 | 2021-11-01 | West | Terra Firma | Actual | 0
35 | 2021-11-01 | West | KLT | Budget
35 | 2021-11-01 | West | KLT | Forecast | 0
35 | 2021-11-01 | West | KLT | Actual | 0
35 | 2021-11-01 | West | Forefront | Budget
35 | 2021-11-01 | West | Forefront | Forecast | 0
35 | 2021-11-01 | West | Forefront | Actual | 0
35 | 2021-11-01 | West | DPF | Budget
35 | 2021-11-01 | West | DPF | Forecast | 0
35 | 2021-11-01 | West | DPF | Actual | 0
35 | 2021-11-01 | West | OMJ | Budget
35 | 2021-11-01 | West | OMJ | Forecast | 0
35 | 2021-11-01 | West | OMJ | Actual | 0
35 | 2021-11-01 | West | DHB Utilities | Budget
35 | 2021-11-01 | West | DHB Utilities | Forecast | 0
35 | 2021-11-01 | West | DHB Utilities | Actual | 0
35 | 2021-11-01 | West | JDT | Budget
35 | 2021-11-01 | West | JDT | Forecast | 0
35 | 2021-11-01 | West | JDT | Actual | 0
35 | 2021-11-01 | West | MURRAY | Budget
35 | 2021-11-01 | West | MURRAY | Forecast | 0
35 | 2021-11-01 | West | MURRAY | Actual | 0
35 | 2021-11-01 | East | Terra Firma | Budget
35 | 2021-11-01 | East | Terra Firma | Forecast | 0
35 | 2021-11-01 | East | Terra Firma | Actual | 0
35 | 2021-11-01 | East | KLT | Budget
35 | 2021-11-01 | East | KLT | Forecast | 0
35 | 2021-11-01 | East | KLT | Actual | 0
35 | 2021-11-01 | East | Forefront | Budget
35 | 2021-11-01 | East | Forefront | Forecast | 0
35 | 2021-11-01 | East | Forefront | Actual | 0
35 | 2021-11-01 | East | DPF | Budget
35 | 2021-11-01 | East | DPF | Forecast | 0
35 | 2021-11-01 | East | DPF | Actual | 0
35 | 2021-11-01 | East | OMJ | Budget
35 | 2021-11-01 | East | OMJ | Forecast | 0
35 | 2021-11-01 | East | OMJ | Actual | 0
35 | 2021-11-01 | East | DHB Utilities | Budget
35 | 2021-11-01 | East | DHB Utilities | Forecast | 0
35 | 2021-11-01 | East | DHB Utilities | Actual | 0
35 | 2021-11-01 | East | JDT | Budget
35 | 2021-11-01 | East | JDT | Forecast | 0
35 | 2021-11-01 | East | JDT | Actual | 0
35 | 2021-11-01 | East | MURRAY | Budget
35 | 2021-11-01 | East | MURRAY | Forecast | 0
35 | 2021-11-01 | East | MURRAY | Actual | 0
35 | 2021-11-01 | Central | Terra Firma | Budget
35 | 2021-11-01 | Central | Terra Firma | Forecast | 0
35 | 2021-11-01 | Central | Terra Firma | Actual | 0
35 | 2021-11-01 | Central | KLT | Budget
35 | 2021-11-01 | Central | KLT | Forecast | 0
35 | 2021-11-01 | Central | KLT | Actual | 0
35 | 2021-11-01 | Central | Forefront | Budget
35 | 2021-11-01 | Central | Forefront | Forecast | 0
35 | 2021-11-01 | Central | Forefront | Actual | 0
35 | 2021-11-01 | Central | DPF | Budget
35 | 2021-11-01 | Central | DPF | Forecast | 0
35 | 2021-11-01 | Central | DPF | Actual | 0
35 | 2021-11-01 | Central | OMJ | Budget
35 | 2021-11-01 | Central | OMJ | Forecast | 0
35 | 2021-11-01 | Central | OMJ | Actual | 0
35 | 2021-11-01 | Central | DHB Utilities | Budget
35 | 2021-11-01 | Central | DHB Utilities | Forecast | 0
35 | 2021-11-01 | Central | DHB Utilities | Actual | 0
35 | 2021-11-01 | Central | JDT | Budget
35 | 2021-11-01 | Central | JDT | Forecast | 0
35 | 2021-11-01 | Central | JDT | Actual | 0
35 | 2021-11-01 | Central | MURRAY | Budget
35 | 2021-11-01 | Central | MURRAY | Forecast | 0
35 | 2021-11-01 | Central | MURRAY | Actual | 0
35 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Budget
35 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Forecast | 81.74
35 | 2021-11-01 | CMO West 1 | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Budget
35 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
35 | 2021-11-01 | CMO West 2 | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Budget
35 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
35 | 2021-11-01 | CMO East 1 | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Budget
35 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
35 | 2021-11-01 | CMO East 2 | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | West | DIRECT MOLE | Budget
35 | 2021-11-01 | West | DIRECT MOLE | Forecast | 0
35 | 2021-11-01 | West | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | East | DIRECT MOLE | Budget
35 | 2021-11-01 | East | DIRECT MOLE | Forecast | 0
35 | 2021-11-01 | East | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | Central | DIRECT MOLE | Budget
35 | 2021-11-01 | Central | DIRECT MOLE | Forecast | 0
35 | 2021-11-01 | Central | DIRECT MOLE | Actual | 0
35 | 2021-11-01 | CMO West 1 | SQS | Budget
35 | 2021-11-01 | CMO West 1 | SQS | Forecast | 203.21
35 | 2021-11-01 | CMO West 1 | SQS | Actual | 0
35 | 2021-11-01 | CMO West 2 | SQS | Budget
35 | 2021-11-01 | CMO West 2 | SQS | Forecast | 397.7
35 | 2021-11-01 | CMO West 2 | SQS | Actual | 0
35 | 2021-11-01 | CMO East 1 | SQS | Budget
35 | 2021-11-01 | CMO East 1 | SQS | Forecast | 0
35 | 2021-11-01 | CMO East 1 | SQS | Actual | 0
35 | 2021-11-01 | CMO East 2 | SQS | Budget
35 | 2021-11-01 | CMO East 2 | SQS | Forecast | 0
35 | 2021-11-01 | CMO East 2 | SQS | Actual | 0
35 | 2021-11-01 | West | SQS | Budget
35 | 2021-11-01 | West | SQS | Forecast | 0
35 | 2021-11-01 | West | SQS | Actual | 0
35 | 2021-11-01 | East | SQS | Budget
35 | 2021-11-01 | East | SQS | Forecast | 0
36 | 2021-11-01 | East | SQS | Actual | 0
36 | 2021-11-01 | Central | SQS | Budget
36 | 2021-11-01 | Central | SQS | Forecast | 0
35 | 2021-11-01 | Central | SQS | Actual | 0
36 | 2021-12-01 | CMO West 1 | Terra Firma | Budget
36 | 2021-12-01 | CMO West 1 | Terra Firma | Forecast | 0
36 | 2021-12-01 | CMO West 1 | Terra Firma | Actual | 0
36 | 2021-12-01 | CMO West 1 | KLT | Budget
36 | 2021-12-01 | CMO West 1 | KLT | Forecast | 591.1933
36 | 2021-12-01 | CMO West 1 | KLT | Actual | 0
36 | 2021-12-01 | CMO West 1 | Forefront | Budget
36 | 2021-12-01 | CMO West 1 | Forefront | Forecast | 0
36 | 2021-12-01 | CMO West 1 | Forefront | Actual | 0
36 | 2021-12-01 | CMO West 1 | DPF | Budget
36 | 2021-12-01 | CMO West 1 | DPF | Forecast | 83.5933
36 | 2021-12-01 | CMO West 1 | DPF | Actual | 0
36 | 2021-12-01 | CMO West 1 | OMJ | Budget
36 | 2021-12-01 | CMO West 1 | OMJ | Forecast | 0
36 | 2021-12-01 | CMO West 1 | OMJ | Actual | 0
36 | 2021-12-01 | CMO West 1 | DHB Utilities | Budget
36 | 2021-12-01 | CMO West 1 | DHB Utilities | Forecast | 0
36 | 2021-12-01 | CMO West 1 | DHB Utilities | Actual | 0
36 | 2021-12-01 | CMO West 1 | JDT | Budget
36 | 2021-12-01 | CMO West 1 | JDT | Forecast | 0
36 | 2021-12-01 | CMO West 1 | JDT | Actual | 0
36 | 2021-12-01 | CMO West 1 | MURRAY | Budget
36 | 2021-12-01 | CMO West 1 | MURRAY | Forecast | 0
36 | 2021-12-01 | CMO West 1 | MURRAY | Actual | 0
36 | 2021-12-01 | CMO West 2 | Terra Firma | Budget
36 | 2021-12-01 | CMO West 2 | Terra Firma | Forecast | 0
36 | 2021-12-01 | CMO West 2 | Terra Firma | Actual | 0
36 | 2021-12-01 | CMO West 2 | KLT | Budget
36 | 2021-12-01 | CMO West 2 | KLT | Forecast | 663.51
36 | 2021-12-01 | CMO West 2 | KLT | Actual | 0
36 | 2021-12-01 | CMO West 2 | Forefront | Budget
36 | 2021-12-01 | CMO West 2 | Forefront | Forecast | 0
36 | 2021-12-01 | CMO West 2 | Forefront | Actual | 0
36 | 2021-12-01 | CMO West 2 | DPF | Budget
36 | 2021-12-01 | CMO West 2 | DPF | Forecast | 0
36 | 2021-12-01 | CMO West 2 | DPF | Actual | 0
36 | 2021-12-01 | CMO West 2 | OMJ | Budget
36 | 2021-12-01 | CMO West 2 | OMJ | Forecast | 514.1586
36 | 2021-12-01 | CMO West 2 | OMJ | Actual | 0
36 | 2021-12-01 | CMO West 2 | DHB Utilities | Budget
36 | 2021-12-01 | CMO West 2 | DHB Utilities | Forecast | 370.8457
36 | 2021-12-01 | CMO West 2 | DHB Utilities | Actual | 0
36 | 2021-12-01 | CMO West 2 | JDT | Budget
36 | 2021-12-01 | CMO West 2 | JDT | Forecast | 0
36 | 2021-12-01 | CMO West 2 | JDT | Actual | 0
36 | 2021-12-01 | CMO West 2 | MURRAY | Budget
36 | 2021-12-01 | CMO West 2 | MURRAY | Forecast | 0
36 | 2021-12-01 | CMO West 2 | MURRAY | Actual | 0
36 | 2021-12-01 | CMO East 1 | Terra Firma | Budget
36 | 2021-12-01 | CMO East 1 | Terra Firma | Forecast | 172.1633
36 | 2021-12-01 | CMO East 1 | Terra Firma | Actual | 0
36 | 2021-12-01 | CMO East 1 | KLT | Budget
36 | 2021-12-01 | CMO East 1 | KLT | Forecast | 0
36 | 2021-12-01 | CMO East 1 | KLT | Actual | 0
36 | 2021-12-01 | CMO East 1 | Forefront | Budget
36 | 2021-12-01 | CMO East 1 | Forefront | Forecast | 0
36 | 2021-12-01 | CMO East 1 | Forefront | Actual | 0
36 | 2021-12-01 | CMO East 1 | DPF | Budget
36 | 2021-12-01 | CMO East 1 | DPF | Forecast | 254.0833
36 | 2021-12-01 | CMO East 1 | DPF | Actual | 0
36 | 2021-12-01 | CMO East 1 | OMJ | Budget
36 | 2021-12-01 | CMO East 1 | OMJ | Forecast | 0
36 | 2021-12-01 | CMO East 1 | OMJ | Actual | 0
36 | 2021-12-01 | CMO East 1 | DHB Utilities | Budget
36 | 2021-12-01 | CMO East 1 | DHB Utilities | Forecast | 0
36 | 2021-12-01 | CMO East 1 | DHB Utilities | Actual | 0
36 | 2021-12-01 | CMO East 1 | JDT | Budget
36 | 2021-12-01 | CMO East 1 | JDT | Forecast | 0
36 | 2021-12-01 | CMO East 1 | JDT | Actual | 0
36 | 2021-12-01 | CMO East 1 | MURRAY | Budget
36 | 2021-12-01 | CMO East 1 | MURRAY | Forecast | 158.54
36 | 2021-12-01 | CMO East 1 | MURRAY | Actual | 0
36 | 2021-12-01 | CMO East 2 | Terra Firma | Budget
36 | 2021-12-01 | CMO East 2 | Terra Firma | Forecast | 481.75
36 | 2021-12-01 | CMO East 2 | Terra Firma | Actual | 0
36 | 2021-12-01 | CMO East 2 | KLT | Budget
36 | 2021-12-01 | CMO East 2 | KLT | Forecast | 0
36 | 2021-12-01 | CMO East 2 | KLT | Actual | 0
36 | 2021-12-01 | CMO East 2 | Forefront | Budget
36 | 2021-12-01 | CMO East 2 | Forefront | Forecast | 680.3
36 | 2021-12-01 | CMO East 2 | Forefront | Actual | 0
36 | 2021-12-01 | CMO East 2 | DPF | Budget
36 | 2021-12-01 | CMO East 2 | DPF | Forecast | 0
36 | 2021-12-01 | CMO East 2 | DPF | Actual | 0
36 | 2021-12-01 | CMO East 2 | OMJ | Budget
36 | 2021-12-01 | CMO East 2 | OMJ | Forecast | 0
36 | 2021-12-01 | CMO East 2 | OMJ | Actual | 0
36 | 2021-12-01 | CMO East 2 | DHB Utilities | Budget
36 | 2021-12-01 | CMO East 2 | DHB Utilities | Forecast | 0
36 | 2021-12-01 | CMO East 2 | DHB Utilities | Actual | 0
36 | 2021-12-01 | CMO East 2 | JDT | Budget
36 | 2021-12-01 | CMO East 2 | JDT | Forecast | 676.95
36 | 2021-12-01 | CMO East 2 | JDT | Actual | 0
36 | 2021-12-01 | CMO East 2 | MURRAY | Budget
36 | 2021-12-01 | CMO East 2 | MURRAY | Forecast | 0
36 | 2021-12-01 | CMO East 2 | MURRAY | Actual | 0
36 | 2021-12-01 | West | Terra Firma | Budget
36 | 2021-12-01 | West | Terra Firma | Forecast | 0
36 | 2021-12-01 | West | Terra Firma | Actual | 0
36 | 2021-12-01 | West | KLT | Budget
36 | 2021-12-01 | West | KLT | Forecast | 0
36 | 2021-12-01 | West | KLT | Actual | 0
36 | 2021-12-01 | West | Forefront | Budget
36 | 2021-12-01 | West | Forefront | Forecast | 0
36 | 2021-12-01 | West | Forefront | Actual | 0
36 | 2021-12-01 | West | DPF | Budget
36 | 2021-12-01 | West | DPF | Forecast | 0
36 | 2021-12-01 | West | DPF | Actual | 0
36 | 2021-12-01 | West | OMJ | Budget
36 | 2021-12-01 | West | OMJ | Forecast | 0
36 | 2021-12-01 | West | OMJ | Actual | 0
36 | 2021-12-01 | West | DHB Utilities | Budget
36 | 2021-12-01 | West | DHB Utilities | Forecast | 0
36 | 2021-12-01 | West | DHB Utilities | Actual | 0
36 | 2021-12-01 | West | JDT | Budget
36 | 2021-12-01 | West | JDT | Forecast | 0
36 | 2021-12-01 | West | JDT | Actual | 0
36 | 2021-12-01 | West | MURRAY | Budget
36 | 2021-12-01 | West | MURRAY | Forecast | 0
36 | 2021-12-01 | West | MURRAY | Actual | 0
36 | 2021-12-01 | East | Terra Firma | Budget
36 | 2021-12-01 | East | Terra Firma | Forecast | 0
36 | 2021-12-01 | East | Terra Firma | Actual | 0
36 | 2021-12-01 | East | KLT | Budget
36 | 2021-12-01 | East | KLT | Forecast | 0
36 | 2021-12-01 | East | KLT | Actual | 0
36 | 2021-12-01 | East | Forefront | Budget
36 | 2021-12-01 | East | Forefront | Forecast | 0
36 | 2021-12-01 | East | Forefront | Actual | 0
36 | 2021-12-01 | East | DPF | Budget
36 | 2021-12-01 | East | DPF | Forecast | 0
36 | 2021-12-01 | East | DPF | Actual | 0
36 | 2021-12-01 | East | OMJ | Budget
36 | 2021-12-01 | East | OMJ | Forecast | 0
36 | 2021-12-01 | East | OMJ | Actual | 0
36 | 2021-12-01 | East | DHB Utilities | Budget
36 | 2021-12-01 | East | DHB Utilities | Forecast | 0
36 | 2021-12-01 | East | DHB Utilities | Actual | 0
36 | 2021-12-01 | East | JDT | Budget
36 | 2021-12-01 | East | JDT | Forecast | 0
36 | 2021-12-01 | East | JDT | Actual | 0
36 | 2021-12-01 | East | MURRAY | Budget
36 | 2021-12-01 | East | MURRAY | Forecast | 0
36 | 2021-12-01 | East | MURRAY | Actual | 0
36 | 2021-12-01 | Central | Terra Firma | Budget
36 | 2021-12-01 | Central | Terra Firma | Forecast | 0
36 | 2021-12-01 | Central | Terra Firma | Actual | 0
36 | 2021-12-01 | Central | KLT | Budget
36 | 2021-12-01 | Central | KLT | Forecast | 0
36 | 2021-12-01 | Central | KLT | Actual | 0
36 | 2021-12-01 | Central | Forefront | Budget
36 | 2021-12-01 | Central | Forefront | Forecast | 0
36 | 2021-12-01 | Central | Forefront | Actual | 0
36 | 2021-12-01 | Central | DPF | Budget
36 | 2021-12-01 | Central | DPF | Forecast | 0
36 | 2021-12-01 | Central | DPF | Actual | 0
36 | 2021-12-01 | Central | OMJ | Budget
36 | 2021-12-01 | Central | OMJ | Forecast | 0
36 | 2021-12-01 | Central | OMJ | Actual | 0
36 | 2021-12-01 | Central | DHB Utilities | Budget
36 | 2021-12-01 | Central | DHB Utilities | Forecast | 0
36 | 2021-12-01 | Central | DHB Utilities | Actual | 0
36 | 2021-12-01 | Central | JDT | Budget
36 | 2021-12-01 | Central | JDT | Forecast | 0
36 | 2021-12-01 | Central | JDT | Actual | 0
36 | 2021-12-01 | Central | MURRAY | Budget
36 | 2021-12-01 | Central | MURRAY | Forecast | 0
36 | 2021-12-01 | Central | MURRAY | Actual | 0
36 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Budget
36 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Forecast | 37.29
36 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Budget
36 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
36 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Budget
36 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
36 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Budget
36 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
36 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | West | DIRECT MOLE | Budget
36 | 2021-12-01 | West | DIRECT MOLE | Forecast | 0
36 | 2021-12-01 | West | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | East | DIRECT MOLE | Budget
36 | 2021-12-01 | East | DIRECT MOLE | Forecast | 0
36 | 2021-12-01 | East | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | Central | DIRECT MOLE | Budget
36 | 2021-12-01 | Central | DIRECT MOLE | Forecast | 0
36 | 2021-12-01 | Central | DIRECT MOLE | Actual | 0
36 | 2021-12-01 | CMO West 1 | SQS | Budget
36 | 2021-12-01 | CMO West 1 | SQS | Forecast | 208.8533
36 | 2021-12-01 | CMO West 1 | SQS | Actual | 0
36 | 2021-12-01 | CMO West 2 | SQS | Budget
36 | 2021-12-01 | CMO West 2 | SQS | Forecast | 397.7
36 | 2021-12-01 | CMO West 2 | SQS | Actual | 0
36 | 2021-12-01 | CMO East 1 | SQS | Budget
36 | 2021-12-01 | CMO East 1 | SQS | Forecast | 0
36 | 2021-12-01 | CMO East 1 | SQS | Actual | 0
36 | 2021-12-01 | CMO East 2 | SQS | Budget
36 | 2021-12-01 | CMO East 2 | SQS | Forecast | 0
36 | 2021-12-01 | CMO East 2 | SQS | Actual | 0
36 | 2021-12-01 | West | SQS | Budget
36 | 2021-12-01 | West | SQS | Forecast | 0
36 | 2021-12-01 | West | SQS | Actual | 0
36 | 2021-12-01 | East | SQS | Budget
36 | 2021-12-01 | East | SQS | Forecast | 0
37 | 2021-12-01 | East | SQS | Actual | 0
37 | 2021-12-01 | Central | SQS | Budget
37 | 2021-12-01 | Central | SQS | Forecast | 0
36 | 2021-12-01 | Central | SQS | Actual | 0
37 | 2021-12-01 | CMO West 1 | Terra Firma | Budget
37 | 2021-12-01 | CMO West 1 | Terra Firma | Forecast | 0
37 | 2021-12-01 | CMO West 1 | Terra Firma | Actual | 0
37 | 2021-12-01 | CMO West 1 | KLT | Budget
37 | 2021-12-01 | CMO West 1 | KLT | Forecast | 591.1933
37 | 2021-12-01 | CMO West 1 | KLT | Actual | 0
37 | 2021-12-01 | CMO West 1 | Forefront | Budget
37 | 2021-12-01 | CMO West 1 | Forefront | Forecast | 0
37 | 2021-12-01 | CMO West 1 | Forefront | Actual | 0
37 | 2021-12-01 | CMO West 1 | DPF | Budget
37 | 2021-12-01 | CMO West 1 | DPF | Forecast | 83.5933
37 | 2021-12-01 | CMO West 1 | DPF | Actual | 0
37 | 2021-12-01 | CMO West 1 | OMJ | Budget
37 | 2021-12-01 | CMO West 1 | OMJ | Forecast | 0
37 | 2021-12-01 | CMO West 1 | OMJ | Actual | 0
37 | 2021-12-01 | CMO West 1 | DHB Utilities | Budget
37 | 2021-12-01 | CMO West 1 | DHB Utilities | Forecast | 0
37 | 2021-12-01 | CMO West 1 | DHB Utilities | Actual | 0
37 | 2021-12-01 | CMO West 1 | JDT | Budget
37 | 2021-12-01 | CMO West 1 | JDT | Forecast | 0
37 | 2021-12-01 | CMO West 1 | JDT | Actual | 0
37 | 2021-12-01 | CMO West 1 | MURRAY | Budget
37 | 2021-12-01 | CMO West 1 | MURRAY | Forecast | 0
37 | 2021-12-01 | CMO West 1 | MURRAY | Actual | 0
37 | 2021-12-01 | CMO West 2 | Terra Firma | Budget
37 | 2021-12-01 | CMO West 2 | Terra Firma | Forecast | 0
37 | 2021-12-01 | CMO West 2 | Terra Firma | Actual | 0
37 | 2021-12-01 | CMO West 2 | KLT | Budget
37 | 2021-12-01 | CMO West 2 | KLT | Forecast | 650.78
37 | 2021-12-01 | CMO West 2 | KLT | Actual | 0
37 | 2021-12-01 | CMO West 2 | Forefront | Budget
37 | 2021-12-01 | CMO West 2 | Forefront | Forecast | 0
37 | 2021-12-01 | CMO West 2 | Forefront | Actual | 0
37 | 2021-12-01 | CMO West 2 | DPF | Budget
37 | 2021-12-01 | CMO West 2 | DPF | Forecast | 0
37 | 2021-12-01 | CMO West 2 | DPF | Actual | 0
37 | 2021-12-01 | CMO West 2 | OMJ | Budget
37 | 2021-12-01 | CMO West 2 | OMJ | Forecast | 514.1586
37 | 2021-12-01 | CMO West 2 | OMJ | Actual | 0
37 | 2021-12-01 | CMO West 2 | DHB Utilities | Budget
37 | 2021-12-01 | CMO West 2 | DHB Utilities | Forecast | 248.8157
37 | 2021-12-01 | CMO West 2 | DHB Utilities | Actual | 0
37 | 2021-12-01 | CMO West 2 | JDT | Budget
37 | 2021-12-01 | CMO West 2 | JDT | Forecast | 0
37 | 2021-12-01 | CMO West 2 | JDT | Actual | 0
37 | 2021-12-01 | CMO West 2 | MURRAY | Budget
37 | 2021-12-01 | CMO West 2 | MURRAY | Forecast | 0
37 | 2021-12-01 | CMO West 2 | MURRAY | Actual | 0
37 | 2021-12-01 | CMO East 1 | Terra Firma | Budget
37 | 2021-12-01 | CMO East 1 | Terra Firma | Forecast | 185.8533
37 | 2021-12-01 | CMO East 1 | Terra Firma | Actual | 0
37 | 2021-12-01 | CMO East 1 | KLT | Budget
37 | 2021-12-01 | CMO East 1 | KLT | Forecast | 0
37 | 2021-12-01 | CMO East 1 | KLT | Actual | 0
37 | 2021-12-01 | CMO East 1 | Forefront | Budget
37 | 2021-12-01 | CMO East 1 | Forefront | Forecast | 0
37 | 2021-12-01 | CMO East 1 | Forefront | Actual | 0
37 | 2021-12-01 | CMO East 1 | DPF | Budget
37 | 2021-12-01 | CMO East 1 | DPF | Forecast | 254.0833
37 | 2021-12-01 | CMO East 1 | DPF | Actual | 0
37 | 2021-12-01 | CMO East 1 | OMJ | Budget
37 | 2021-12-01 | CMO East 1 | OMJ | Forecast | 0
37 | 2021-12-01 | CMO East 1 | OMJ | Actual | 0
37 | 2021-12-01 | CMO East 1 | DHB Utilities | Budget
37 | 2021-12-01 | CMO East 1 | DHB Utilities | Forecast | 0
37 | 2021-12-01 | CMO East 1 | DHB Utilities | Actual | 0
37 | 2021-12-01 | CMO East 1 | JDT | Budget
37 | 2021-12-01 | CMO East 1 | JDT | Forecast | 0
37 | 2021-12-01 | CMO East 1 | JDT | Actual | 0
37 | 2021-12-01 | CMO East 1 | MURRAY | Budget
37 | 2021-12-01 | CMO East 1 | MURRAY | Forecast | 65.74
37 | 2021-12-01 | CMO East 1 | MURRAY | Actual | 0
37 | 2021-12-01 | CMO East 2 | Terra Firma | Budget
37 | 2021-12-01 | CMO East 2 | Terra Firma | Forecast | 482.34
37 | 2021-12-01 | CMO East 2 | Terra Firma | Actual | 0
37 | 2021-12-01 | CMO East 2 | KLT | Budget
37 | 2021-12-01 | CMO East 2 | KLT | Forecast | 0
37 | 2021-12-01 | CMO East 2 | KLT | Actual | 0
37 | 2021-12-01 | CMO East 2 | Forefront | Budget
37 | 2021-12-01 | CMO East 2 | Forefront | Forecast | 541.73
37 | 2021-12-01 | CMO East 2 | Forefront | Actual | 0
37 | 2021-12-01 | CMO East 2 | DPF | Budget
37 | 2021-12-01 | CMO East 2 | DPF | Forecast | 0
37 | 2021-12-01 | CMO East 2 | DPF | Actual | 0
37 | 2021-12-01 | CMO East 2 | OMJ | Budget
37 | 2021-12-01 | CMO East 2 | OMJ | Forecast | 0
37 | 2021-12-01 | CMO East 2 | OMJ | Actual | 0
37 | 2021-12-01 | CMO East 2 | DHB Utilities | Budget
37 | 2021-12-01 | CMO East 2 | DHB Utilities | Forecast | 0
37 | 2021-12-01 | CMO East 2 | DHB Utilities | Actual | 0
37 | 2021-12-01 | CMO East 2 | JDT | Budget
37 | 2021-12-01 | CMO East 2 | JDT | Forecast | 676.95
37 | 2021-12-01 | CMO East 2 | JDT | Actual | 0
37 | 2021-12-01 | CMO East 2 | MURRAY | Budget
37 | 2021-12-01 | CMO East 2 | MURRAY | Forecast | 0
37 | 2021-12-01 | CMO East 2 | MURRAY | Actual | 0
37 | 2021-12-01 | West | Terra Firma | Budget
37 | 2021-12-01 | West | Terra Firma | Forecast | 0
37 | 2021-12-01 | West | Terra Firma | Actual | 0
37 | 2021-12-01 | West | KLT | Budget
37 | 2021-12-01 | West | KLT | Forecast | 0
37 | 2021-12-01 | West | KLT | Actual | 0
37 | 2021-12-01 | West | Forefront | Budget
37 | 2021-12-01 | West | Forefront | Forecast | 0
37 | 2021-12-01 | West | Forefront | Actual | 0
37 | 2021-12-01 | West | DPF | Budget
37 | 2021-12-01 | West | DPF | Forecast | 0
37 | 2021-12-01 | West | DPF | Actual | 0
37 | 2021-12-01 | West | OMJ | Budget
37 | 2021-12-01 | West | OMJ | Forecast | 0
37 | 2021-12-01 | West | OMJ | Actual | 0
37 | 2021-12-01 | West | DHB Utilities | Budget
37 | 2021-12-01 | West | DHB Utilities | Forecast | 0
37 | 2021-12-01 | West | DHB Utilities | Actual | 0
37 | 2021-12-01 | West | JDT | Budget
37 | 2021-12-01 | West | JDT | Forecast | 0
37 | 2021-12-01 | West | JDT | Actual | 0
37 | 2021-12-01 | West | MURRAY | Budget
37 | 2021-12-01 | West | MURRAY | Forecast | 0
37 | 2021-12-01 | West | MURRAY | Actual | 0
37 | 2021-12-01 | East | Terra Firma | Budget
37 | 2021-12-01 | East | Terra Firma | Forecast | 0
37 | 2021-12-01 | East | Terra Firma | Actual | 0
37 | 2021-12-01 | East | KLT | Budget
37 | 2021-12-01 | East | KLT | Forecast | 0
37 | 2021-12-01 | East | KLT | Actual | 0
37 | 2021-12-01 | East | Forefront | Budget
37 | 2021-12-01 | East | Forefront | Forecast | 0
37 | 2021-12-01 | East | Forefront | Actual | 0
37 | 2021-12-01 | East | DPF | Budget
37 | 2021-12-01 | East | DPF | Forecast | 0
37 | 2021-12-01 | East | DPF | Actual | 0
37 | 2021-12-01 | East | OMJ | Budget
37 | 2021-12-01 | East | OMJ | Forecast | 0
37 | 2021-12-01 | East | OMJ | Actual | 0
37 | 2021-12-01 | East | DHB Utilities | Budget
37 | 2021-12-01 | East | DHB Utilities | Forecast | 0
37 | 2021-12-01 | East | DHB Utilities | Actual | 0
37 | 2021-12-01 | East | JDT | Budget
37 | 2021-12-01 | East | JDT | Forecast | 0
37 | 2021-12-01 | East | JDT | Actual | 0
37 | 2021-12-01 | East | MURRAY | Budget
37 | 2021-12-01 | East | MURRAY | Forecast | 0
37 | 2021-12-01 | East | MURRAY | Actual | 0
37 | 2021-12-01 | Central | Terra Firma | Budget
37 | 2021-12-01 | Central | Terra Firma | Forecast | 0
37 | 2021-12-01 | Central | Terra Firma | Actual | 0
37 | 2021-12-01 | Central | KLT | Budget
37 | 2021-12-01 | Central | KLT | Forecast | 0
37 | 2021-12-01 | Central | KLT | Actual | 0
37 | 2021-12-01 | Central | Forefront | Budget
37 | 2021-12-01 | Central | Forefront | Forecast | 0
37 | 2021-12-01 | Central | Forefront | Actual | 0
37 | 2021-12-01 | Central | DPF | Budget
37 | 2021-12-01 | Central | DPF | Forecast | 0
37 | 2021-12-01 | Central | DPF | Actual | 0
37 | 2021-12-01 | Central | OMJ | Budget
37 | 2021-12-01 | Central | OMJ | Forecast | 0
37 | 2021-12-01 | Central | OMJ | Actual | 0
37 | 2021-12-01 | Central | DHB Utilities | Budget
37 | 2021-12-01 | Central | DHB Utilities | Forecast | 0
37 | 2021-12-01 | Central | DHB Utilities | Actual | 0
37 | 2021-12-01 | Central | JDT | Budget
37 | 2021-12-01 | Central | JDT | Forecast | 0
37 | 2021-12-01 | Central | JDT | Actual | 0
37 | 2021-12-01 | Central | MURRAY | Budget
37 | 2021-12-01 | Central | MURRAY | Forecast | 0
37 | 2021-12-01 | Central | MURRAY | Actual | 0
37 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Budget
37 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Forecast | 37.29
37 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Budget
37 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
37 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Budget
37 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
37 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Budget
37 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
37 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | West | DIRECT MOLE | Budget
37 | 2021-12-01 | West | DIRECT MOLE | Forecast | 0
37 | 2021-12-01 | West | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | East | DIRECT MOLE | Budget
37 | 2021-12-01 | East | DIRECT MOLE | Forecast | 0
37 | 2021-12-01 | East | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | Central | DIRECT MOLE | Budget
37 | 2021-12-01 | Central | DIRECT MOLE | Forecast | 0
37 | 2021-12-01 | Central | DIRECT MOLE | Actual | 0
37 | 2021-12-01 | CMO West 1 | SQS | Budget
37 | 2021-12-01 | CMO West 1 | SQS | Forecast | 208.8533
37 | 2021-12-01 | CMO West 1 | SQS | Actual | 0
37 | 2021-12-01 | CMO West 2 | SQS | Budget
37 | 2021-12-01 | CMO West 2 | SQS | Forecast | 436.45
37 | 2021-12-01 | CMO West 2 | SQS | Actual | 0
37 | 2021-12-01 | CMO East 1 | SQS | Budget
37 | 2021-12-01 | CMO East 1 | SQS | Forecast | 0
37 | 2021-12-01 | CMO East 1 | SQS | Actual | 0
37 | 2021-12-01 | CMO East 2 | SQS | Budget
37 | 2021-12-01 | CMO East 2 | SQS | Forecast | 0
37 | 2021-12-01 | CMO East 2 | SQS | Actual | 0
37 | 2021-12-01 | West | SQS | Budget
37 | 2021-12-01 | West | SQS | Forecast | 0
37 | 2021-12-01 | West | SQS | Actual | 0
37 | 2021-12-01 | East | SQS | Budget
37 | 2021-12-01 | East | SQS | Forecast | 0
38 | 2021-12-01 | East | SQS | Actual | 0
38 | 2021-12-01 | Central | SQS | Budget
38 | 2021-12-01 | Central | SQS | Forecast | 0
37 | 2021-12-01 | Central | SQS | Actual | 0
38 | 2021-12-01 | CMO West 1 | Terra Firma | Budget
38 | 2021-12-01 | CMO West 1 | Terra Firma | Forecast | 0
38 | 2021-12-01 | CMO West 1 | Terra Firma | Actual | 0
38 | 2021-12-01 | CMO West 1 | KLT | Budget
38 | 2021-12-01 | CMO West 1 | KLT | Forecast | 565.7733
38 | 2021-12-01 | CMO West 1 | KLT | Actual | 0
38 | 2021-12-01 | CMO West 1 | Forefront | Budget
38 | 2021-12-01 | CMO West 1 | Forefront | Forecast | 0
38 | 2021-12-01 | CMO West 1 | Forefront | Actual | 0
38 | 2021-12-01 | CMO West 1 | DPF | Budget
38 | 2021-12-01 | CMO West 1 | DPF | Forecast | 83.5933
38 | 2021-12-01 | CMO West 1 | DPF | Actual | 0
38 | 2021-12-01 | CMO West 1 | OMJ | Budget
38 | 2021-12-01 | CMO West 1 | OMJ | Forecast | 0
38 | 2021-12-01 | CMO West 1 | OMJ | Actual | 0
38 | 2021-12-01 | CMO West 1 | DHB Utilities | Budget
38 | 2021-12-01 | CMO West 1 | DHB Utilities | Forecast | 0
38 | 2021-12-01 | CMO West 1 | DHB Utilities | Actual | 0
38 | 2021-12-01 | CMO West 1 | JDT | Budget
38 | 2021-12-01 | CMO West 1 | JDT | Forecast | 0
38 | 2021-12-01 | CMO West 1 | JDT | Actual | 0
38 | 2021-12-01 | CMO West 1 | MURRAY | Budget
38 | 2021-12-01 | CMO West 1 | MURRAY | Forecast | 0
38 | 2021-12-01 | CMO West 1 | MURRAY | Actual | 0
38 | 2021-12-01 | CMO West 2 | Terra Firma | Budget
38 | 2021-12-01 | CMO West 2 | Terra Firma | Forecast | 0
38 | 2021-12-01 | CMO West 2 | Terra Firma | Actual | 0
38 | 2021-12-01 | CMO West 2 | KLT | Budget
38 | 2021-12-01 | CMO West 2 | KLT | Forecast | 726.09
38 | 2021-12-01 | CMO West 2 | KLT | Actual | 0
38 | 2021-12-01 | CMO West 2 | Forefront | Budget
38 | 2021-12-01 | CMO West 2 | Forefront | Forecast | 0
38 | 2021-12-01 | CMO West 2 | Forefront | Actual | 0
38 | 2021-12-01 | CMO West 2 | DPF | Budget
38 | 2021-12-01 | CMO West 2 | DPF | Forecast | 0
38 | 2021-12-01 | CMO West 2 | DPF | Actual | 0
38 | 2021-12-01 | CMO West 2 | OMJ | Budget
38 | 2021-12-01 | CMO West 2 | OMJ | Forecast | 417.9286
38 | 2021-12-01 | CMO West 2 | OMJ | Actual | 0
38 | 2021-12-01 | CMO West 2 | DHB Utilities | Budget
38 | 2021-12-01 | CMO West 2 | DHB Utilities | Forecast | 198.5057
38 | 2021-12-01 | CMO West 2 | DHB Utilities | Actual | 0
38 | 2021-12-01 | CMO West 2 | JDT | Budget
38 | 2021-12-01 | CMO West 2 | JDT | Forecast | 0
38 | 2021-12-01 | CMO West 2 | JDT | Actual | 0
38 | 2021-12-01 | CMO West 2 | MURRAY | Budget
38 | 2021-12-01 | CMO West 2 | MURRAY | Forecast | 0
38 | 2021-12-01 | CMO West 2 | MURRAY | Actual | 0
38 | 2021-12-01 | CMO East 1 | Terra Firma | Budget
38 | 2021-12-01 | CMO East 1 | Terra Firma | Forecast | 143.1433
38 | 2021-12-01 | CMO East 1 | Terra Firma | Actual | 0
38 | 2021-12-01 | CMO East 1 | KLT | Budget
38 | 2021-12-01 | CMO East 1 | KLT | Forecast | 0
38 | 2021-12-01 | CMO East 1 | KLT | Actual | 0
38 | 2021-12-01 | CMO East 1 | Forefront | Budget
38 | 2021-12-01 | CMO East 1 | Forefront | Forecast | 0
38 | 2021-12-01 | CMO East 1 | Forefront | Actual | 0
38 | 2021-12-01 | CMO East 1 | DPF | Budget
38 | 2021-12-01 | CMO East 1 | DPF | Forecast | 254.0833
38 | 2021-12-01 | CMO East 1 | DPF | Actual | 0
38 | 2021-12-01 | CMO East 1 | OMJ | Budget
38 | 2021-12-01 | CMO East 1 | OMJ | Forecast | 0
38 | 2021-12-01 | CMO East 1 | OMJ | Actual | 0
38 | 2021-12-01 | CMO East 1 | DHB Utilities | Budget
38 | 2021-12-01 | CMO East 1 | DHB Utilities | Forecast | 0
38 | 2021-12-01 | CMO East 1 | DHB Utilities | Actual | 0
38 | 2021-12-01 | CMO East 1 | JDT | Budget
38 | 2021-12-01 | CMO East 1 | JDT | Forecast | 0
38 | 2021-12-01 | CMO East 1 | JDT | Actual | 0
38 | 2021-12-01 | CMO East 1 | MURRAY | Budget
38 | 2021-12-01 | CMO East 1 | MURRAY | Forecast | 65.74
38 | 2021-12-01 | CMO East 1 | MURRAY | Actual | 0
38 | 2021-12-01 | CMO East 2 | Terra Firma | Budget
38 | 2021-12-01 | CMO East 2 | Terra Firma | Forecast | 225.77
38 | 2021-12-01 | CMO East 2 | Terra Firma | Actual | 0
38 | 2021-12-01 | CMO East 2 | KLT | Budget
38 | 2021-12-01 | CMO East 2 | KLT | Forecast | 0
38 | 2021-12-01 | CMO East 2 | KLT | Actual | 0
38 | 2021-12-01 | CMO East 2 | Forefront | Budget
38 | 2021-12-01 | CMO East 2 | Forefront | Forecast | 499.44
38 | 2021-12-01 | CMO East 2 | Forefront | Actual | 0
38 | 2021-12-01 | CMO East 2 | DPF | Budget
38 | 2021-12-01 | CMO East 2 | DPF | Forecast | 0
38 | 2021-12-01 | CMO East 2 | DPF | Actual | 0
38 | 2021-12-01 | CMO East 2 | OMJ | Budget
38 | 2021-12-01 | CMO East 2 | OMJ | Forecast | 0
38 | 2021-12-01 | CMO East 2 | OMJ | Actual | 0
38 | 2021-12-01 | CMO East 2 | DHB Utilities | Budget
38 | 2021-12-01 | CMO East 2 | DHB Utilities | Forecast | 0
38 | 2021-12-01 | CMO East 2 | DHB Utilities | Actual | 0
38 | 2021-12-01 | CMO East 2 | JDT | Budget
38 | 2021-12-01 | CMO East 2 | JDT | Forecast | 671.24
38 | 2021-12-01 | CMO East 2 | JDT | Actual | 0
38 | 2021-12-01 | CMO East 2 | MURRAY | Budget
38 | 2021-12-01 | CMO East 2 | MURRAY | Forecast | 0
38 | 2021-12-01 | CMO East 2 | MURRAY | Actual | 0
38 | 2021-12-01 | West | Terra Firma | Budget
38 | 2021-12-01 | West | Terra Firma | Forecast | 0
38 | 2021-12-01 | West | Terra Firma | Actual | 0
38 | 2021-12-01 | West | KLT | Budget
38 | 2021-12-01 | West | KLT | Forecast | 0
38 | 2021-12-01 | West | KLT | Actual | 0
38 | 2021-12-01 | West | Forefront | Budget
38 | 2021-12-01 | West | Forefront | Forecast | 0
38 | 2021-12-01 | West | Forefront | Actual | 0
38 | 2021-12-01 | West | DPF | Budget
38 | 2021-12-01 | West | DPF | Forecast | 0
38 | 2021-12-01 | West | DPF | Actual | 0
38 | 2021-12-01 | West | OMJ | Budget
38 | 2021-12-01 | West | OMJ | Forecast | 0
38 | 2021-12-01 | West | OMJ | Actual | 0
38 | 2021-12-01 | West | DHB Utilities | Budget
38 | 2021-12-01 | West | DHB Utilities | Forecast | 0
38 | 2021-12-01 | West | DHB Utilities | Actual | 0
38 | 2021-12-01 | West | JDT | Budget
38 | 2021-12-01 | West | JDT | Forecast | 0
38 | 2021-12-01 | West | JDT | Actual | 0
38 | 2021-12-01 | West | MURRAY | Budget
38 | 2021-12-01 | West | MURRAY | Forecast | 0
38 | 2021-12-01 | West | MURRAY | Actual | 0
38 | 2021-12-01 | East | Terra Firma | Budget
38 | 2021-12-01 | East | Terra Firma | Forecast | 0
38 | 2021-12-01 | East | Terra Firma | Actual | 0
38 | 2021-12-01 | East | KLT | Budget
38 | 2021-12-01 | East | KLT | Forecast | 0
38 | 2021-12-01 | East | KLT | Actual | 0
38 | 2021-12-01 | East | Forefront | Budget
38 | 2021-12-01 | East | Forefront | Forecast | 0
38 | 2021-12-01 | East | Forefront | Actual | 0
38 | 2021-12-01 | East | DPF | Budget
38 | 2021-12-01 | East | DPF | Forecast | 0
38 | 2021-12-01 | East | DPF | Actual | 0
38 | 2021-12-01 | East | OMJ | Budget
38 | 2021-12-01 | East | OMJ | Forecast | 0
38 | 2021-12-01 | East | OMJ | Actual | 0
38 | 2021-12-01 | East | DHB Utilities | Budget
38 | 2021-12-01 | East | DHB Utilities | Forecast | 0
38 | 2021-12-01 | East | DHB Utilities | Actual | 0
38 | 2021-12-01 | East | JDT | Budget
38 | 2021-12-01 | East | JDT | Forecast | 0
38 | 2021-12-01 | East | JDT | Actual | 0
38 | 2021-12-01 | East | MURRAY | Budget
38 | 2021-12-01 | East | MURRAY | Forecast | 0
38 | 2021-12-01 | East | MURRAY | Actual | 0
38 | 2021-12-01 | Central | Terra Firma | Budget
38 | 2021-12-01 | Central | Terra Firma | Forecast | 0
38 | 2021-12-01 | Central | Terra Firma | Actual | 0
38 | 2021-12-01 | Central | KLT | Budget
38 | 2021-12-01 | Central | KLT | Forecast | 0
38 | 2021-12-01 | Central | KLT | Actual | 0
38 | 2021-12-01 | Central | Forefront | Budget
38 | 2021-12-01 | Central | Forefront | Forecast | 0
38 | 2021-12-01 | Central | Forefront | Actual | 0
38 | 2021-12-01 | Central | DPF | Budget
38 | 2021-12-01 | Central | DPF | Forecast | 0
38 | 2021-12-01 | Central | DPF | Actual | 0
38 | 2021-12-01 | Central | OMJ | Budget
38 | 2021-12-01 | Central | OMJ | Forecast | 0
38 | 2021-12-01 | Central | OMJ | Actual | 0
38 | 2021-12-01 | Central | DHB Utilities | Budget
38 | 2021-12-01 | Central | DHB Utilities | Forecast | 0
38 | 2021-12-01 | Central | DHB Utilities | Actual | 0
38 | 2021-12-01 | Central | JDT | Budget
38 | 2021-12-01 | Central | JDT | Forecast | 0
38 | 2021-12-01 | Central | JDT | Actual | 0
38 | 2021-12-01 | Central | MURRAY | Budget
38 | 2021-12-01 | Central | MURRAY | Forecast | 0
38 | 2021-12-01 | Central | MURRAY | Actual | 0
38 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Budget
38 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Forecast | 37.29
38 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Budget
38 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
38 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Budget
38 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
38 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Budget
38 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
38 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | West | DIRECT MOLE | Budget
38 | 2021-12-01 | West | DIRECT MOLE | Forecast | 0
38 | 2021-12-01 | West | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | East | DIRECT MOLE | Budget
38 | 2021-12-01 | East | DIRECT MOLE | Forecast | 0
38 | 2021-12-01 | East | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | Central | DIRECT MOLE | Budget
38 | 2021-12-01 | Central | DIRECT MOLE | Forecast | 0
38 | 2021-12-01 | Central | DIRECT MOLE | Actual | 0
38 | 2021-12-01 | CMO West 1 | SQS | Budget
38 | 2021-12-01 | CMO West 1 | SQS | Forecast | 208.8533
38 | 2021-12-01 | CMO West 1 | SQS | Actual | 0
38 | 2021-12-01 | CMO West 2 | SQS | Budget
38 | 2021-12-01 | CMO West 2 | SQS | Forecast | 345.64
38 | 2021-12-01 | CMO West 2 | SQS | Actual | 0
38 | 2021-12-01 | CMO East 1 | SQS | Budget
38 | 2021-12-01 | CMO East 1 | SQS | Forecast | 0
38 | 2021-12-01 | CMO East 1 | SQS | Actual | 0
38 | 2021-12-01 | CMO East 2 | SQS | Budget
38 | 2021-12-01 | CMO East 2 | SQS | Forecast | 0
38 | 2021-12-01 | CMO East 2 | SQS | Actual | 0
38 | 2021-12-01 | West | SQS | Budget
38 | 2021-12-01 | West | SQS | Forecast | 0
38 | 2021-12-01 | West | SQS | Actual | 0
38 | 2021-12-01 | East | SQS | Budget
38 | 2021-12-01 | East | SQS | Forecast | 0
39 | 2021-12-01 | East | SQS | Actual | 0
39 | 2021-12-01 | Central | SQS | Budget
39 | 2021-12-01 | Central | SQS | Forecast | 0
38 | 2021-12-01 | Central | SQS | Actual | 0
39 | 2021-12-01 | CMO West 1 | Terra Firma | Budget
39 | 2021-12-01 | CMO West 1 | Terra Firma | Forecast | 0
39 | 2021-12-01 | CMO West 1 | Terra Firma | Actual | 0
39 | 2021-12-01 | CMO West 1 | KLT | Budget
39 | 2021-12-01 | CMO West 1 | KLT | Forecast | 0
39 | 2021-12-01 | CMO West 1 | KLT | Actual | 0
39 | 2021-12-01 | CMO West 1 | Forefront | Budget
39 | 2021-12-01 | CMO West 1 | Forefront | Forecast | 0
39 | 2021-12-01 | CMO West 1 | Forefront | Actual | 0
39 | 2021-12-01 | CMO West 1 | DPF | Budget
39 | 2021-12-01 | CMO West 1 | DPF | Forecast | 0
39 | 2021-12-01 | CMO West 1 | DPF | Actual | 0
39 | 2021-12-01 | CMO West 1 | OMJ | Budget
39 | 2021-12-01 | CMO West 1 | OMJ | Forecast | 0
39 | 2021-12-01 | CMO West 1 | OMJ | Actual | 0
39 | 2021-12-01 | CMO West 1 | DHB Utilities | Budget
39 | 2021-12-01 | CMO West 1 | DHB Utilities | Forecast | 0
39 | 2021-12-01 | CMO West 1 | DHB Utilities | Actual | 0
39 | 2021-12-01 | CMO West 1 | JDT | Budget
39 | 2021-12-01 | CMO West 1 | JDT | Forecast | 0
39 | 2021-12-01 | CMO West 1 | JDT | Actual | 0
39 | 2021-12-01 | CMO West 1 | MURRAY | Budget
39 | 2021-12-01 | CMO West 1 | MURRAY | Forecast | 0
39 | 2021-12-01 | CMO West 1 | MURRAY | Actual | 0
39 | 2021-12-01 | CMO West 2 | Terra Firma | Budget
39 | 2021-12-01 | CMO West 2 | Terra Firma | Forecast | 0
39 | 2021-12-01 | CMO West 2 | Terra Firma | Actual | 0
39 | 2021-12-01 | CMO West 2 | KLT | Budget
39 | 2021-12-01 | CMO West 2 | KLT | Forecast | 0
39 | 2021-12-01 | CMO West 2 | KLT | Actual | 0
39 | 2021-12-01 | CMO West 2 | Forefront | Budget
39 | 2021-12-01 | CMO West 2 | Forefront | Forecast | 0
39 | 2021-12-01 | CMO West 2 | Forefront | Actual | 0
39 | 2021-12-01 | CMO West 2 | DPF | Budget
39 | 2021-12-01 | CMO West 2 | DPF | Forecast | 0
39 | 2021-12-01 | CMO West 2 | DPF | Actual | 0
39 | 2021-12-01 | CMO West 2 | OMJ | Budget
39 | 2021-12-01 | CMO West 2 | OMJ | Forecast | 0
39 | 2021-12-01 | CMO West 2 | OMJ | Actual | 0
39 | 2021-12-01 | CMO West 2 | DHB Utilities | Budget
39 | 2021-12-01 | CMO West 2 | DHB Utilities | Forecast | 0
39 | 2021-12-01 | CMO West 2 | DHB Utilities | Actual | 0
39 | 2021-12-01 | CMO West 2 | JDT | Budget
39 | 2021-12-01 | CMO West 2 | JDT | Forecast | 0
39 | 2021-12-01 | CMO West 2 | JDT | Actual | 0
39 | 2021-12-01 | CMO West 2 | MURRAY | Budget
39 | 2021-12-01 | CMO West 2 | MURRAY | Forecast | 0
39 | 2021-12-01 | CMO West 2 | MURRAY | Actual | 0
39 | 2021-12-01 | CMO East 1 | Terra Firma | Budget
39 | 2021-12-01 | CMO East 1 | Terra Firma | Forecast | 0
39 | 2021-12-01 | CMO East 1 | Terra Firma | Actual | 0
39 | 2021-12-01 | CMO East 1 | KLT | Budget
39 | 2021-12-01 | CMO East 1 | KLT | Forecast | 0
39 | 2021-12-01 | CMO East 1 | KLT | Actual | 0
39 | 2021-12-01 | CMO East 1 | Forefront | Budget
39 | 2021-12-01 | CMO East 1 | Forefront | Forecast | 0
39 | 2021-12-01 | CMO East 1 | Forefront | Actual | 0
39 | 2021-12-01 | CMO East 1 | DPF | Budget
39 | 2021-12-01 | CMO East 1 | DPF | Forecast | 0
39 | 2021-12-01 | CMO East 1 | DPF | Actual | 0
39 | 2021-12-01 | CMO East 1 | OMJ | Budget
39 | 2021-12-01 | CMO East 1 | OMJ | Forecast | 0
39 | 2021-12-01 | CMO East 1 | OMJ | Actual | 0
39 | 2021-12-01 | CMO East 1 | DHB Utilities | Budget
39 | 2021-12-01 | CMO East 1 | DHB Utilities | Forecast | 0
39 | 2021-12-01 | CMO East 1 | DHB Utilities | Actual | 0
39 | 2021-12-01 | CMO East 1 | JDT | Budget
39 | 2021-12-01 | CMO East 1 | JDT | Forecast | 0
39 | 2021-12-01 | CMO East 1 | JDT | Actual | 0
39 | 2021-12-01 | CMO East 1 | MURRAY | Budget
39 | 2021-12-01 | CMO East 1 | MURRAY | Forecast | 0
39 | 2021-12-01 | CMO East 1 | MURRAY | Actual | 0
39 | 2021-12-01 | CMO East 2 | Terra Firma | Budget
39 | 2021-12-01 | CMO East 2 | Terra Firma | Forecast | 0
39 | 2021-12-01 | CMO East 2 | Terra Firma | Actual | 0
39 | 2021-12-01 | CMO East 2 | KLT | Budget
39 | 2021-12-01 | CMO East 2 | KLT | Forecast | 0
39 | 2021-12-01 | CMO East 2 | KLT | Actual | 0
39 | 2021-12-01 | CMO East 2 | Forefront | Budget
39 | 2021-12-01 | CMO East 2 | Forefront | Forecast | 0
39 | 2021-12-01 | CMO East 2 | Forefront | Actual | 0
39 | 2021-12-01 | CMO East 2 | DPF | Budget
39 | 2021-12-01 | CMO East 2 | DPF | Forecast | 0
39 | 2021-12-01 | CMO East 2 | DPF | Actual | 0
39 | 2021-12-01 | CMO East 2 | OMJ | Budget
39 | 2021-12-01 | CMO East 2 | OMJ | Forecast | 0
39 | 2021-12-01 | CMO East 2 | OMJ | Actual | 0
39 | 2021-12-01 | CMO East 2 | DHB Utilities | Budget
39 | 2021-12-01 | CMO East 2 | DHB Utilities | Forecast | 0
39 | 2021-12-01 | CMO East 2 | DHB Utilities | Actual | 0
39 | 2021-12-01 | CMO East 2 | JDT | Budget
39 | 2021-12-01 | CMO East 2 | JDT | Forecast | 0
39 | 2021-12-01 | CMO East 2 | JDT | Actual | 0
39 | 2021-12-01 | CMO East 2 | MURRAY | Budget
39 | 2021-12-01 | CMO East 2 | MURRAY | Forecast | 0
39 | 2021-12-01 | CMO East 2 | MURRAY | Actual | 0
39 | 2021-12-01 | West | Terra Firma | Budget
39 | 2021-12-01 | West | Terra Firma | Forecast | 0
39 | 2021-12-01 | West | Terra Firma | Actual | 0
39 | 2021-12-01 | West | KLT | Budget
39 | 2021-12-01 | West | KLT | Forecast | 0
39 | 2021-12-01 | West | KLT | Actual | 0
39 | 2021-12-01 | West | Forefront | Budget
39 | 2021-12-01 | West | Forefront | Forecast | 0
39 | 2021-12-01 | West | Forefront | Actual | 0
39 | 2021-12-01 | West | DPF | Budget
39 | 2021-12-01 | West | DPF | Forecast | 0
39 | 2021-12-01 | West | DPF | Actual | 0
39 | 2021-12-01 | West | OMJ | Budget
39 | 2021-12-01 | West | OMJ | Forecast | 0
39 | 2021-12-01 | West | OMJ | Actual | 0
39 | 2021-12-01 | West | DHB Utilities | Budget
39 | 2021-12-01 | West | DHB Utilities | Forecast | 0
39 | 2021-12-01 | West | DHB Utilities | Actual | 0
39 | 2021-12-01 | West | JDT | Budget
39 | 2021-12-01 | West | JDT | Forecast | 0
39 | 2021-12-01 | West | JDT | Actual | 0
39 | 2021-12-01 | West | MURRAY | Budget
39 | 2021-12-01 | West | MURRAY | Forecast | 0
39 | 2021-12-01 | West | MURRAY | Actual | 0
39 | 2021-12-01 | East | Terra Firma | Budget
39 | 2021-12-01 | East | Terra Firma | Forecast | 0
39 | 2021-12-01 | East | Terra Firma | Actual | 0
39 | 2021-12-01 | East | KLT | Budget
39 | 2021-12-01 | East | KLT | Forecast | 0
39 | 2021-12-01 | East | KLT | Actual | 0
39 | 2021-12-01 | East | Forefront | Budget
39 | 2021-12-01 | East | Forefront | Forecast | 0
39 | 2021-12-01 | East | Forefront | Actual | 0
39 | 2021-12-01 | East | DPF | Budget
39 | 2021-12-01 | East | DPF | Forecast | 0
39 | 2021-12-01 | East | DPF | Actual | 0
39 | 2021-12-01 | East | OMJ | Budget
39 | 2021-12-01 | East | OMJ | Forecast | 0
39 | 2021-12-01 | East | OMJ | Actual | 0
39 | 2021-12-01 | East | DHB Utilities | Budget
39 | 2021-12-01 | East | DHB Utilities | Forecast | 0
39 | 2021-12-01 | East | DHB Utilities | Actual | 0
39 | 2021-12-01 | East | JDT | Budget
39 | 2021-12-01 | East | JDT | Forecast | 0
39 | 2021-12-01 | East | JDT | Actual | 0
39 | 2021-12-01 | East | MURRAY | Budget
39 | 2021-12-01 | East | MURRAY | Forecast | 0
39 | 2021-12-01 | East | MURRAY | Actual | 0
39 | 2021-12-01 | Central | Terra Firma | Budget
39 | 2021-12-01 | Central | Terra Firma | Forecast | 0
39 | 2021-12-01 | Central | Terra Firma | Actual | 0
39 | 2021-12-01 | Central | KLT | Budget
39 | 2021-12-01 | Central | KLT | Forecast | 0
39 | 2021-12-01 | Central | KLT | Actual | 0
39 | 2021-12-01 | Central | Forefront | Budget
39 | 2021-12-01 | Central | Forefront | Forecast | 0
39 | 2021-12-01 | Central | Forefront | Actual | 0
39 | 2021-12-01 | Central | DPF | Budget
39 | 2021-12-01 | Central | DPF | Forecast | 0
39 | 2021-12-01 | Central | DPF | Actual | 0
39 | 2021-12-01 | Central | OMJ | Budget
39 | 2021-12-01 | Central | OMJ | Forecast | 0
39 | 2021-12-01 | Central | OMJ | Actual | 0
39 | 2021-12-01 | Central | DHB Utilities | Budget
39 | 2021-12-01 | Central | DHB Utilities | Forecast | 0
39 | 2021-12-01 | Central | DHB Utilities | Actual | 0
39 | 2021-12-01 | Central | JDT | Budget
39 | 2021-12-01 | Central | JDT | Forecast | 0
39 | 2021-12-01 | Central | JDT | Actual | 0
39 | 2021-12-01 | Central | MURRAY | Budget
39 | 2021-12-01 | Central | MURRAY | Forecast | 0
39 | 2021-12-01 | Central | MURRAY | Actual | 0
39 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Budget
39 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Budget
39 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Budget
39 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Budget
39 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | West | DIRECT MOLE | Budget
39 | 2021-12-01 | West | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | West | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | East | DIRECT MOLE | Budget
39 | 2021-12-01 | East | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | East | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | Central | DIRECT MOLE | Budget
39 | 2021-12-01 | Central | DIRECT MOLE | Forecast | 0
39 | 2021-12-01 | Central | DIRECT MOLE | Actual | 0
39 | 2021-12-01 | CMO West 1 | SQS | Budget
39 | 2021-12-01 | CMO West 1 | SQS | Forecast | 0
39 | 2021-12-01 | CMO West 1 | SQS | Actual | 0
39 | 2021-12-01 | CMO West 2 | SQS | Budget
39 | 2021-12-01 | CMO West 2 | SQS | Forecast | 0
39 | 2021-12-01 | CMO West 2 | SQS | Actual | 0
39 | 2021-12-01 | CMO East 1 | SQS | Budget
39 | 2021-12-01 | CMO East 1 | SQS | Forecast | 0
39 | 2021-12-01 | CMO East 1 | SQS | Actual | 0
39 | 2021-12-01 | CMO East 2 | SQS | Budget
39 | 2021-12-01 | CMO East 2 | SQS | Forecast | 0
39 | 2021-12-01 | CMO East 2 | SQS | Actual | 0
39 | 2021-12-01 | West | SQS | Budget
39 | 2021-12-01 | West | SQS | Forecast | 0
39 | 2021-12-01 | West | SQS | Actual | 0
39 | 2021-12-01 | East | SQS | Budget
39 | 2021-12-01 | East | SQS | Forecast | 0
40 | 2021-12-01 | East | SQS | Actual | 0
40 | 2021-12-01 | Central | SQS | Budget
40 | 2021-12-01 | Central | SQS | Forecast | 0
39 | 2021-12-01 | Central | SQS | Actual | 0
40 | 2021-12-01 | CMO West 1 | Terra Firma | Budget
40 | 2021-12-01 | CMO West 1 | Terra Firma | Forecast | 0
40 | 2021-12-01 | CMO West 1 | Terra Firma | Actual | 0
40 | 2021-12-01 | CMO West 1 | KLT | Budget
40 | 2021-12-01 | CMO West 1 | KLT | Forecast | 0
40 | 2021-12-01 | CMO West 1 | KLT | Actual | 0
40 | 2021-12-01 | CMO West 1 | Forefront | Budget
40 | 2021-12-01 | CMO West 1 | Forefront | Forecast | 0
40 | 2021-12-01 | CMO West 1 | Forefront | Actual | 0
40 | 2021-12-01 | CMO West 1 | DPF | Budget
40 | 2021-12-01 | CMO West 1 | DPF | Forecast | 0
40 | 2021-12-01 | CMO West 1 | DPF | Actual | 0
40 | 2021-12-01 | CMO West 1 | OMJ | Budget
40 | 2021-12-01 | CMO West 1 | OMJ | Forecast | 0
40 | 2021-12-01 | CMO West 1 | OMJ | Actual | 0
40 | 2021-12-01 | CMO West 1 | DHB Utilities | Budget
40 | 2021-12-01 | CMO West 1 | DHB Utilities | Forecast | 0
40 | 2021-12-01 | CMO West 1 | DHB Utilities | Actual | 0
40 | 2021-12-01 | CMO West 1 | JDT | Budget
40 | 2021-12-01 | CMO West 1 | JDT | Forecast | 0
40 | 2021-12-01 | CMO West 1 | JDT | Actual | 0
40 | 2021-12-01 | CMO West 1 | MURRAY | Budget
40 | 2021-12-01 | CMO West 1 | MURRAY | Forecast | 0
40 | 2021-12-01 | CMO West 1 | MURRAY | Actual | 0
40 | 2021-12-01 | CMO West 2 | Terra Firma | Budget
40 | 2021-12-01 | CMO West 2 | Terra Firma | Forecast | 0
40 | 2021-12-01 | CMO West 2 | Terra Firma | Actual | 0
40 | 2021-12-01 | CMO West 2 | KLT | Budget
40 | 2021-12-01 | CMO West 2 | KLT | Forecast | 0
40 | 2021-12-01 | CMO West 2 | KLT | Actual | 0
40 | 2021-12-01 | CMO West 2 | Forefront | Budget
40 | 2021-12-01 | CMO West 2 | Forefront | Forecast | 0
40 | 2021-12-01 | CMO West 2 | Forefront | Actual | 0
40 | 2021-12-01 | CMO West 2 | DPF | Budget
40 | 2021-12-01 | CMO West 2 | DPF | Forecast | 0
40 | 2021-12-01 | CMO West 2 | DPF | Actual | 0
40 | 2021-12-01 | CMO West 2 | OMJ | Budget
40 | 2021-12-01 | CMO West 2 | OMJ | Forecast | 0
40 | 2021-12-01 | CMO West 2 | OMJ | Actual | 0
40 | 2021-12-01 | CMO West 2 | DHB Utilities | Budget
40 | 2021-12-01 | CMO West 2 | DHB Utilities | Forecast | 0
40 | 2021-12-01 | CMO West 2 | DHB Utilities | Actual | 0
40 | 2021-12-01 | CMO West 2 | JDT | Budget
40 | 2021-12-01 | CMO West 2 | JDT | Forecast | 0
40 | 2021-12-01 | CMO West 2 | JDT | Actual | 0
40 | 2021-12-01 | CMO West 2 | MURRAY | Budget
40 | 2021-12-01 | CMO West 2 | MURRAY | Forecast | 0
40 | 2021-12-01 | CMO West 2 | MURRAY | Actual | 0
40 | 2021-12-01 | CMO East 1 | Terra Firma | Budget
40 | 2021-12-01 | CMO East 1 | Terra Firma | Forecast | 0
40 | 2021-12-01 | CMO East 1 | Terra Firma | Actual | 0
40 | 2021-12-01 | CMO East 1 | KLT | Budget
40 | 2021-12-01 | CMO East 1 | KLT | Forecast | 0
40 | 2021-12-01 | CMO East 1 | KLT | Actual | 0
40 | 2021-12-01 | CMO East 1 | Forefront | Budget
40 | 2021-12-01 | CMO East 1 | Forefront | Forecast | 0
40 | 2021-12-01 | CMO East 1 | Forefront | Actual | 0
40 | 2021-12-01 | CMO East 1 | DPF | Budget
40 | 2021-12-01 | CMO East 1 | DPF | Forecast | 0
40 | 2021-12-01 | CMO East 1 | DPF | Actual | 0
40 | 2021-12-01 | CMO East 1 | OMJ | Budget
40 | 2021-12-01 | CMO East 1 | OMJ | Forecast | 0
40 | 2021-12-01 | CMO East 1 | OMJ | Actual | 0
40 | 2021-12-01 | CMO East 1 | DHB Utilities | Budget
40 | 2021-12-01 | CMO East 1 | DHB Utilities | Forecast | 0
40 | 2021-12-01 | CMO East 1 | DHB Utilities | Actual | 0
40 | 2021-12-01 | CMO East 1 | JDT | Budget
40 | 2021-12-01 | CMO East 1 | JDT | Forecast | 0
40 | 2021-12-01 | CMO East 1 | JDT | Actual | 0
40 | 2021-12-01 | CMO East 1 | MURRAY | Budget
40 | 2021-12-01 | CMO East 1 | MURRAY | Forecast | 0
40 | 2021-12-01 | CMO East 1 | MURRAY | Actual | 0
40 | 2021-12-01 | CMO East 2 | Terra Firma | Budget
40 | 2021-12-01 | CMO East 2 | Terra Firma | Forecast | 0
40 | 2021-12-01 | CMO East 2 | Terra Firma | Actual | 0
40 | 2021-12-01 | CMO East 2 | KLT | Budget
40 | 2021-12-01 | CMO East 2 | KLT | Forecast | 0
40 | 2021-12-01 | CMO East 2 | KLT | Actual | 0
40 | 2021-12-01 | CMO East 2 | Forefront | Budget
40 | 2021-12-01 | CMO East 2 | Forefront | Forecast | 0
40 | 2021-12-01 | CMO East 2 | Forefront | Actual | 0
40 | 2021-12-01 | CMO East 2 | DPF | Budget
40 | 2021-12-01 | CMO East 2 | DPF | Forecast | 0
40 | 2021-12-01 | CMO East 2 | DPF | Actual | 0
40 | 2021-12-01 | CMO East 2 | OMJ | Budget
40 | 2021-12-01 | CMO East 2 | OMJ | Forecast | 0
40 | 2021-12-01 | CMO East 2 | OMJ | Actual | 0
40 | 2021-12-01 | CMO East 2 | DHB Utilities | Budget
40 | 2021-12-01 | CMO East 2 | DHB Utilities | Forecast | 0
40 | 2021-12-01 | CMO East 2 | DHB Utilities | Actual | 0
40 | 2021-12-01 | CMO East 2 | JDT | Budget
40 | 2021-12-01 | CMO East 2 | JDT | Forecast | 0
40 | 2021-12-01 | CMO East 2 | JDT | Actual | 0
40 | 2021-12-01 | CMO East 2 | MURRAY | Budget
40 | 2021-12-01 | CMO East 2 | MURRAY | Forecast | 0
40 | 2021-12-01 | CMO East 2 | MURRAY | Actual | 0
40 | 2021-12-01 | West | Terra Firma | Budget
40 | 2021-12-01 | West | Terra Firma | Forecast | 0
40 | 2021-12-01 | West | Terra Firma | Actual | 0
40 | 2021-12-01 | West | KLT | Budget
40 | 2021-12-01 | West | KLT | Forecast | 0
40 | 2021-12-01 | West | KLT | Actual | 0
40 | 2021-12-01 | West | Forefront | Budget
40 | 2021-12-01 | West | Forefront | Forecast | 0
40 | 2021-12-01 | West | Forefront | Actual | 0
40 | 2021-12-01 | West | DPF | Budget
40 | 2021-12-01 | West | DPF | Forecast | 0
40 | 2021-12-01 | West | DPF | Actual | 0
40 | 2021-12-01 | West | OMJ | Budget
40 | 2021-12-01 | West | OMJ | Forecast | 0
40 | 2021-12-01 | West | OMJ | Actual | 0
40 | 2021-12-01 | West | DHB Utilities | Budget
40 | 2021-12-01 | West | DHB Utilities | Forecast | 0
40 | 2021-12-01 | West | DHB Utilities | Actual | 0
40 | 2021-12-01 | West | JDT | Budget
40 | 2021-12-01 | West | JDT | Forecast | 0
40 | 2021-12-01 | West | JDT | Actual | 0
40 | 2021-12-01 | West | MURRAY | Budget
40 | 2021-12-01 | West | MURRAY | Forecast | 0
40 | 2021-12-01 | West | MURRAY | Actual | 0
40 | 2021-12-01 | East | Terra Firma | Budget
40 | 2021-12-01 | East | Terra Firma | Forecast | 0
40 | 2021-12-01 | East | Terra Firma | Actual | 0
40 | 2021-12-01 | East | KLT | Budget
40 | 2021-12-01 | East | KLT | Forecast | 0
40 | 2021-12-01 | East | KLT | Actual | 0
40 | 2021-12-01 | East | Forefront | Budget
40 | 2021-12-01 | East | Forefront | Forecast | 0
40 | 2021-12-01 | East | Forefront | Actual | 0
40 | 2021-12-01 | East | DPF | Budget
40 | 2021-12-01 | East | DPF | Forecast | 0
40 | 2021-12-01 | East | DPF | Actual | 0
40 | 2021-12-01 | East | OMJ | Budget
40 | 2021-12-01 | East | OMJ | Forecast | 0
40 | 2021-12-01 | East | OMJ | Actual | 0
40 | 2021-12-01 | East | DHB Utilities | Budget
40 | 2021-12-01 | East | DHB Utilities | Forecast | 0
40 | 2021-12-01 | East | DHB Utilities | Actual | 0
40 | 2021-12-01 | East | JDT | Budget
40 | 2021-12-01 | East | JDT | Forecast | 0
40 | 2021-12-01 | East | JDT | Actual | 0
40 | 2021-12-01 | East | MURRAY | Budget
40 | 2021-12-01 | East | MURRAY | Forecast | 0
40 | 2021-12-01 | East | MURRAY | Actual | 0
40 | 2021-12-01 | Central | Terra Firma | Budget
40 | 2021-12-01 | Central | Terra Firma | Forecast | 0
40 | 2021-12-01 | Central | Terra Firma | Actual | 0
40 | 2021-12-01 | Central | KLT | Budget
40 | 2021-12-01 | Central | KLT | Forecast | 0
40 | 2021-12-01 | Central | KLT | Actual | 0
40 | 2021-12-01 | Central | Forefront | Budget
40 | 2021-12-01 | Central | Forefront | Forecast | 0
40 | 2021-12-01 | Central | Forefront | Actual | 0
40 | 2021-12-01 | Central | DPF | Budget
40 | 2021-12-01 | Central | DPF | Forecast | 0
40 | 2021-12-01 | Central | DPF | Actual | 0
40 | 2021-12-01 | Central | OMJ | Budget
40 | 2021-12-01 | Central | OMJ | Forecast | 0
40 | 2021-12-01 | Central | OMJ | Actual | 0
40 | 2021-12-01 | Central | DHB Utilities | Budget
40 | 2021-12-01 | Central | DHB Utilities | Forecast | 0
40 | 2021-12-01 | Central | DHB Utilities | Actual | 0
40 | 2021-12-01 | Central | JDT | Budget
40 | 2021-12-01 | Central | JDT | Forecast | 0
40 | 2021-12-01 | Central | JDT | Actual | 0
40 | 2021-12-01 | Central | MURRAY | Budget
40 | 2021-12-01 | Central | MURRAY | Forecast | 0
40 | 2021-12-01 | Central | MURRAY | Actual | 0
40 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Budget
40 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | CMO West 1 | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Budget
40 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | CMO West 2 | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Budget
40 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | CMO East 1 | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Budget
40 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | CMO East 2 | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | West | DIRECT MOLE | Budget
40 | 2021-12-01 | West | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | West | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | East | DIRECT MOLE | Budget
40 | 2021-12-01 | East | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | East | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | Central | DIRECT MOLE | Budget
40 | 2021-12-01 | Central | DIRECT MOLE | Forecast | 0
40 | 2021-12-01 | Central | DIRECT MOLE | Actual | 0
40 | 2021-12-01 | CMO West 1 | SQS | Budget
40 | 2021-12-01 | CMO West 1 | SQS | Forecast | 0
40 | 2021-12-01 | CMO West 1 | SQS | Actual | 0
40 | 2021-12-01 | CMO West 2 | SQS | Budget
40 | 2021-12-01 | CMO West 2 | SQS | Forecast | 0
40 | 2021-12-01 | CMO West 2 | SQS | Actual | 0
40 | 2021-12-01 | CMO East 1 | SQS | Budget
40 | 2021-12-01 | CMO East 1 | SQS | Forecast | 0
40 | 2021-12-01 | CMO East 1 | SQS | Actual | 0
40 | 2021-12-01 | CMO East 2 | SQS | Budget
40 | 2021-12-01 | CMO East 2 | SQS | Forecast | 0
40 | 2021-12-01 | CMO East 2 | SQS | Actual | 0
40 | 2021-12-01 | West | SQS | Budget
40 | 2021-12-01 | West | SQS | Forecast | 0
40 | 2021-12-01 | West | SQS | Actual | 0
40 | 2021-12-01 | East | SQS | Budget
40 | 2021-12-01 | East | SQS | Forecast | 0
41 | 2021-12-01 | East | SQS | Actual | 0
41 | 2021-12-01 | Central | SQS | Budget
41 | 2021-12-01 | Central | SQS | Forecast | 0
40 | 2021-12-01 | Central | SQS | Actual | 0
41 | 2021-12-01 | CMO West 1 | Terra Firma | Budget
41 | 2022-01-01 | CMO West 1 | Terra Firma | Forecast | 0
41 | 2022-01-01 | CMO West 1 | Terra Firma | Actual | 0
41 | 2022-01-01 | CMO West 1 | KLT | Budget
41 | 2022-01-01 | CMO West 1 | KLT | Forecast | 351.46
41 | 2022-01-01 | CMO West 1 | KLT | Actual | 0
41 | 2022-01-01 | CMO West 1 | Forefront | Budget
41 | 2022-01-01 | CMO West 1 | Forefront | Forecast | 0
41 | 2022-01-01 | CMO West 1 | Forefront | Actual | 0
41 | 2022-01-01 | CMO West 1 | DPF | Budget
41 | 2022-01-01 | CMO West 1 | DPF | Forecast | 41.9
41 | 2022-01-01 | CMO West 1 | DPF | Actual | 0
41 | 2022-01-01 | CMO West 1 | OMJ | Budget
41 | 2022-01-01 | CMO West 1 | OMJ | Forecast | 0
41 | 2022-01-01 | CMO West 1 | OMJ | Actual | 0
41 | 2022-01-01 | CMO West 1 | DHB Utilities | Budget
41 | 2022-01-01 | CMO West 1 | DHB Utilities | Forecast | 0
41 | 2022-01-01 | CMO West 1 | DHB Utilities | Actual | 0
41 | 2022-01-01 | CMO West 1 | JDT | Budget
41 | 2022-01-01 | CMO West 1 | JDT | Forecast | 0
41 | 2022-01-01 | CMO West 1 | JDT | Actual | 0
41 | 2022-01-01 | CMO West 1 | MURRAY | Budget
41 | 2022-01-01 | CMO West 1 | MURRAY | Forecast | 0
41 | 2022-01-01 | CMO West 1 | MURRAY | Actual | 0
41 | 2022-01-01 | CMO West 2 | Terra Firma | Budget
41 | 2022-01-01 | CMO West 2 | Terra Firma | Forecast | 0
41 | 2022-01-01 | CMO West 2 | Terra Firma | Actual | 0
41 | 2022-01-01 | CMO West 2 | KLT | Budget
41 | 2022-01-01 | CMO West 2 | KLT | Forecast | 540.82
41 | 2022-01-01 | CMO West 2 | KLT | Actual | 0
41 | 2022-01-01 | CMO West 2 | Forefront | Budget
41 | 2022-01-01 | CMO West 2 | Forefront | Forecast | 0
41 | 2022-01-01 | CMO West 2 | Forefront | Actual | 0
41 | 2022-01-01 | CMO West 2 | DPF | Budget
41 | 2022-01-01 | CMO West 2 | DPF | Forecast | 0
41 | 2022-01-01 | CMO West 2 | DPF | Actual | 0
41 | 2022-01-01 | CMO West 2 | OMJ | Budget
41 | 2022-01-01 | CMO West 2 | OMJ | Forecast | 509.71
41 | 2022-01-01 | CMO West 2 | OMJ | Actual | 0
41 | 2022-01-01 | CMO West 2 | DHB Utilities | Budget
41 | 2022-01-01 | CMO West 2 | DHB Utilities | Forecast | 187.86
41 | 2022-01-01 | CMO West 2 | DHB Utilities | Actual | 0
41 | 2022-01-01 | CMO West 2 | JDT | Budget
41 | 2022-01-01 | CMO West 2 | JDT | Forecast | 0
41 | 2022-01-01 | CMO West 2 | JDT | Actual | 0
41 | 2022-01-01 | CMO West 2 | MURRAY | Budget
41 | 2022-01-01 | CMO West 2 | MURRAY | Forecast | 0
41 | 2022-01-01 | CMO West 2 | MURRAY | Actual | 0
41 | 2022-01-01 | CMO East 1 | Terra Firma | Budget
41 | 2022-01-01 | CMO East 1 | Terra Firma | Forecast | 115.26
41 | 2022-01-01 | CMO East 1 | Terra Firma | Actual | 0
41 | 2022-01-01 | CMO East 1 | KLT | Budget
41 | 2022-01-01 | CMO East 1 | KLT | Forecast | 0
41 | 2022-01-01 | CMO East 1 | KLT | Actual | 0
41 | 2022-01-01 | CMO East 1 | Forefront | Budget
41 | 2022-01-01 | CMO East 1 | Forefront | Forecast | 93.4
41 | 2022-01-01 | CMO East 1 | Forefront | Actual | 0
41 | 2022-01-01 | CMO East 1 | DPF | Budget
41 | 2022-01-01 | CMO East 1 | DPF | Forecast | 245.32
41 | 2022-01-01 | CMO East 1 | DPF | Actual | 0
41 | 2022-01-01 | CMO East 1 | OMJ | Budget
41 | 2022-01-01 | CMO East 1 | OMJ | Forecast | 0
41 | 2022-01-01 | CMO East 1 | OMJ | Actual | 0
41 | 2022-01-01 | CMO East 1 | DHB Utilities | Budget
41 | 2022-01-01 | CMO East 1 | DHB Utilities | Forecast | 0
41 | 2022-01-01 | CMO East 1 | DHB Utilities | Actual | 0
41 | 2022-01-01 | CMO East 1 | JDT | Budget
41 | 2022-01-01 | CMO East 1 | JDT | Forecast | 0
41 | 2022-01-01 | CMO East 1 | JDT | Actual | 0
41 | 2022-01-01 | CMO East 1 | MURRAY | Budget
41 | 2022-01-01 | CMO East 1 | MURRAY | Forecast | 343.53
41 | 2022-01-01 | CMO East 1 | MURRAY | Actual | 0
41 | 2022-01-01 | CMO East 2 | Terra Firma | Budget
41 | 2022-01-01 | CMO East 2 | Terra Firma | Forecast | 498.6
41 | 2022-01-01 | CMO East 2 | Terra Firma | Actual | 0
41 | 2022-01-01 | CMO East 2 | KLT | Budget
41 | 2022-01-01 | CMO East 2 | KLT | Forecast | 0
41 | 2022-01-01 | CMO East 2 | KLT | Actual | 0
41 | 2022-01-01 | CMO East 2 | Forefront | Budget
41 | 2022-01-01 | CMO East 2 | Forefront | Forecast | 495.57
41 | 2022-01-01 | CMO East 2 | Forefront | Actual | 0
41 | 2022-01-01 | CMO East 2 | DPF | Budget
41 | 2022-01-01 | CMO East 2 | DPF | Forecast | 0
41 | 2022-01-01 | CMO East 2 | DPF | Actual | 0
41 | 2022-01-01 | CMO East 2 | OMJ | Budget
41 | 2022-01-01 | CMO East 2 | OMJ | Forecast | 0
41 | 2022-01-01 | CMO East 2 | OMJ | Actual | 0
41 | 2022-01-01 | CMO East 2 | DHB Utilities | Budget
41 | 2022-01-01 | CMO East 2 | DHB Utilities | Forecast | 0
41 | 2022-01-01 | CMO East 2 | DHB Utilities | Actual | 0
41 | 2022-01-01 | CMO East 2 | JDT | Budget
41 | 2022-01-01 | CMO East 2 | JDT | Forecast | 546.88
41 | 2022-01-01 | CMO East 2 | JDT | Actual | 0
41 | 2022-01-01 | CMO East 2 | MURRAY | Budget
41 | 2022-01-01 | CMO East 2 | MURRAY | Forecast | 0
41 | 2022-01-01 | CMO East 2 | MURRAY | Actual | 0
41 | 2022-01-01 | West | Terra Firma | Budget
41 | 2022-01-01 | West | Terra Firma | Forecast | 0
41 | 2022-01-01 | West | Terra Firma | Actual | 0
41 | 2022-01-01 | West | KLT | Budget
41 | 2022-01-01 | West | KLT | Forecast | 0
41 | 2022-01-01 | West | KLT | Actual | 0
41 | 2022-01-01 | West | Forefront | Budget
41 | 2022-01-01 | West | Forefront | Forecast | 0
41 | 2022-01-01 | West | Forefront | Actual | 0
41 | 2022-01-01 | West | DPF | Budget
41 | 2022-01-01 | West | DPF | Forecast | 0
41 | 2022-01-01 | West | DPF | Actual | 0
41 | 2022-01-01 | West | OMJ | Budget
41 | 2022-01-01 | West | OMJ | Forecast | 0
41 | 2022-01-01 | West | OMJ | Actual | 0
41 | 2022-01-01 | West | DHB Utilities | Budget
41 | 2022-01-01 | West | DHB Utilities | Forecast | 0
41 | 2022-01-01 | West | DHB Utilities | Actual | 0
41 | 2022-01-01 | West | JDT | Budget
41 | 2022-01-01 | West | JDT | Forecast | 0
41 | 2022-01-01 | West | JDT | Actual | 0
41 | 2022-01-01 | West | MURRAY | Budget
41 | 2022-01-01 | West | MURRAY | Forecast | 0
41 | 2022-01-01 | West | MURRAY | Actual | 0
41 | 2022-01-01 | East | Terra Firma | Budget
41 | 2022-01-01 | East | Terra Firma | Forecast | 0
41 | 2022-01-01 | East | Terra Firma | Actual | 0
41 | 2022-01-01 | East | KLT | Budget
41 | 2022-01-01 | East | KLT | Forecast | 0
41 | 2022-01-01 | East | KLT | Actual | 0
41 | 2022-01-01 | East | Forefront | Budget
41 | 2022-01-01 | East | Forefront | Forecast | 0
41 | 2022-01-01 | East | Forefront | Actual | 0
41 | 2022-01-01 | East | DPF | Budget
41 | 2022-01-01 | East | DPF | Forecast | 0
41 | 2022-01-01 | East | DPF | Actual | 0
41 | 2022-01-01 | East | OMJ | Budget
41 | 2022-01-01 | East | OMJ | Forecast | 0
41 | 2022-01-01 | East | OMJ | Actual | 0
41 | 2022-01-01 | East | DHB Utilities | Budget
41 | 2022-01-01 | East | DHB Utilities | Forecast | 0
41 | 2022-01-01 | East | DHB Utilities | Actual | 0
41 | 2022-01-01 | East | JDT | Budget
41 | 2022-01-01 | East | JDT | Forecast | 0
41 | 2022-01-01 | East | JDT | Actual | 0
41 | 2022-01-01 | East | MURRAY | Budget
41 | 2022-01-01 | East | MURRAY | Forecast | 0
41 | 2022-01-01 | East | MURRAY | Actual | 0
41 | 2022-01-01 | Central | Terra Firma | Budget
41 | 2022-01-01 | Central | Terra Firma | Forecast | 0
41 | 2022-01-01 | Central | Terra Firma | Actual | 0
41 | 2022-01-01 | Central | KLT | Budget
41 | 2022-01-01 | Central | KLT | Forecast | 0
41 | 2022-01-01 | Central | KLT | Actual | 0
41 | 2022-01-01 | Central | Forefront | Budget
41 | 2022-01-01 | Central | Forefront | Forecast | 0
41 | 2022-01-01 | Central | Forefront | Actual | 0
41 | 2022-01-01 | Central | DPF | Budget
41 | 2022-01-01 | Central | DPF | Forecast | 0
41 | 2022-01-01 | Central | DPF | Actual | 0
41 | 2022-01-01 | Central | OMJ | Budget
41 | 2022-01-01 | Central | OMJ | Forecast | 0
41 | 2022-01-01 | Central | OMJ | Actual | 0
41 | 2022-01-01 | Central | DHB Utilities | Budget
41 | 2022-01-01 | Central | DHB Utilities | Forecast | 0
41 | 2022-01-01 | Central | DHB Utilities | Actual | 0
41 | 2022-01-01 | Central | JDT | Budget
41 | 2022-01-01 | Central | JDT | Forecast | 0
41 | 2022-01-01 | Central | JDT | Actual | 0
41 | 2022-01-01 | Central | MURRAY | Budget
41 | 2022-01-01 | Central | MURRAY | Forecast | 0
41 | 2022-01-01 | Central | MURRAY | Actual | 0
41 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Budget
41 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Budget
41 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Budget
41 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Budget
41 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | West | DIRECT MOLE | Budget
41 | 2022-01-01 | West | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | West | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | East | DIRECT MOLE | Budget
41 | 2022-01-01 | East | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | East | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | Central | DIRECT MOLE | Budget
41 | 2022-01-01 | Central | DIRECT MOLE | Forecast | 0
41 | 2022-01-01 | Central | DIRECT MOLE | Actual | 0
41 | 2022-01-01 | CMO West 1 | SQS | Budget
41 | 2022-01-01 | CMO West 1 | SQS | Forecast | 46.56
41 | 2022-01-01 | CMO West 1 | SQS | Actual | 0
41 | 2022-01-01 | CMO West 2 | SQS | Budget
41 | 2022-01-01 | CMO West 2 | SQS | Forecast | 314.42
41 | 2022-01-01 | CMO West 2 | SQS | Actual | 0
41 | 2022-01-01 | CMO East 1 | SQS | Budget
41 | 2022-01-01 | CMO East 1 | SQS | Forecast | 0
41 | 2022-01-01 | CMO East 1 | SQS | Actual | 0
41 | 2022-01-01 | CMO East 2 | SQS | Budget
41 | 2022-01-01 | CMO East 2 | SQS | Forecast | 0
41 | 2022-01-01 | CMO East 2 | SQS | Actual | 0
41 | 2022-01-01 | West | SQS | Budget
41 | 2022-01-01 | West | SQS | Forecast | 0
41 | 2022-01-01 | West | SQS | Actual | 0
41 | 2022-01-01 | East | SQS | Budget
41 | 2022-01-01 | East | SQS | Forecast | 0
42 | 2022-01-01 | East | SQS | Actual | 0
42 | 2022-01-01 | Central | SQS | Budget
42 | 2022-01-01 | Central | SQS | Forecast | 0
41 | 2022-01-01 | Central | SQS | Actual | 0
42 | 2022-01-01 | CMO West 1 | Terra Firma | Budget
42 | 2022-01-01 | CMO West 1 | Terra Firma | Forecast | 0
42 | 2022-01-01 | CMO West 1 | Terra Firma | Actual | 0
42 | 2022-01-01 | CMO West 1 | KLT | Budget
42 | 2022-01-01 | CMO West 1 | KLT | Forecast | 244.97
42 | 2022-01-01 | CMO West 1 | KLT | Actual | 0
42 | 2022-01-01 | CMO West 1 | Forefront | Budget
42 | 2022-01-01 | CMO West 1 | Forefront | Forecast | 0
42 | 2022-01-01 | CMO West 1 | Forefront | Actual | 0
42 | 2022-01-01 | CMO West 1 | DPF | Budget
42 | 2022-01-01 | CMO West 1 | DPF | Forecast | 41.9
42 | 2022-01-01 | CMO West 1 | DPF | Actual | 0
42 | 2022-01-01 | CMO West 1 | OMJ | Budget
42 | 2022-01-01 | CMO West 1 | OMJ | Forecast | 0
42 | 2022-01-01 | CMO West 1 | OMJ | Actual | 0
42 | 2022-01-01 | CMO West 1 | DHB Utilities | Budget
42 | 2022-01-01 | CMO West 1 | DHB Utilities | Forecast | 0
42 | 2022-01-01 | CMO West 1 | DHB Utilities | Actual | 0
42 | 2022-01-01 | CMO West 1 | JDT | Budget
42 | 2022-01-01 | CMO West 1 | JDT | Forecast | 0
42 | 2022-01-01 | CMO West 1 | JDT | Actual | 0
42 | 2022-01-01 | CMO West 1 | MURRAY | Budget
42 | 2022-01-01 | CMO West 1 | MURRAY | Forecast | 0
42 | 2022-01-01 | CMO West 1 | MURRAY | Actual | 0
42 | 2022-01-01 | CMO West 2 | Terra Firma | Budget
42 | 2022-01-01 | CMO West 2 | Terra Firma | Forecast | 0
42 | 2022-01-01 | CMO West 2 | Terra Firma | Actual | 0
42 | 2022-01-01 | CMO West 2 | KLT | Budget
42 | 2022-01-01 | CMO West 2 | KLT | Forecast | 540.82
42 | 2022-01-01 | CMO West 2 | KLT | Actual | 0
42 | 2022-01-01 | CMO West 2 | Forefront | Budget
42 | 2022-01-01 | CMO West 2 | Forefront | Forecast | 0
42 | 2022-01-01 | CMO West 2 | Forefront | Actual | 0
42 | 2022-01-01 | CMO West 2 | DPF | Budget
42 | 2022-01-01 | CMO West 2 | DPF | Forecast | 0
42 | 2022-01-01 | CMO West 2 | DPF | Actual | 0
42 | 2022-01-01 | CMO West 2 | OMJ | Budget
42 | 2022-01-01 | CMO West 2 | OMJ | Forecast | 510.92
42 | 2022-01-01 | CMO West 2 | OMJ | Actual | 0
42 | 2022-01-01 | CMO West 2 | DHB Utilities | Budget
42 | 2022-01-01 | CMO West 2 | DHB Utilities | Forecast | 311.39
42 | 2022-01-01 | CMO West 2 | DHB Utilities | Actual | 0
42 | 2022-01-01 | CMO West 2 | JDT | Budget
42 | 2022-01-01 | CMO West 2 | JDT | Forecast | 0
42 | 2022-01-01 | CMO West 2 | JDT | Actual | 0
42 | 2022-01-01 | CMO West 2 | MURRAY | Budget
42 | 2022-01-01 | CMO West 2 | MURRAY | Forecast | 0
42 | 2022-01-01 | CMO West 2 | MURRAY | Actual | 0
42 | 2022-01-01 | CMO East 1 | Terra Firma | Budget
42 | 2022-01-01 | CMO East 1 | Terra Firma | Forecast | 115.26
42 | 2022-01-01 | CMO East 1 | Terra Firma | Actual | 0
42 | 2022-01-01 | CMO East 1 | KLT | Budget
42 | 2022-01-01 | CMO East 1 | KLT | Forecast | 0
42 | 2022-01-01 | CMO East 1 | KLT | Actual | 0
42 | 2022-01-01 | CMO East 1 | Forefront | Budget
42 | 2022-01-01 | CMO East 1 | Forefront | Forecast | 93.4
42 | 2022-01-01 | CMO East 1 | Forefront | Actual | 0
42 | 2022-01-01 | CMO East 1 | DPF | Budget
42 | 2022-01-01 | CMO East 1 | DPF | Forecast | 288.82
42 | 2022-01-01 | CMO East 1 | DPF | Actual | 0
42 | 2022-01-01 | CMO East 1 | OMJ | Budget
42 | 2022-01-01 | CMO East 1 | OMJ | Forecast | 0
42 | 2022-01-01 | CMO East 1 | OMJ | Actual | 0
42 | 2022-01-01 | CMO East 1 | DHB Utilities | Budget
42 | 2022-01-01 | CMO East 1 | DHB Utilities | Forecast | 0
42 | 2022-01-01 | CMO East 1 | DHB Utilities | Actual | 0
42 | 2022-01-01 | CMO East 1 | JDT | Budget
42 | 2022-01-01 | CMO East 1 | JDT | Forecast | 0
42 | 2022-01-01 | CMO East 1 | JDT | Actual | 0
42 | 2022-01-01 | CMO East 1 | MURRAY | Budget
42 | 2022-01-01 | CMO East 1 | MURRAY | Forecast | 343.53
42 | 2022-01-01 | CMO East 1 | MURRAY | Actual | 0
42 | 2022-01-01 | CMO East 2 | Terra Firma | Budget
42 | 2022-01-01 | CMO East 2 | Terra Firma | Forecast | 498.6
42 | 2022-01-01 | CMO East 2 | Terra Firma | Actual | 0
42 | 2022-01-01 | CMO East 2 | KLT | Budget
42 | 2022-01-01 | CMO East 2 | KLT | Forecast | 0
42 | 2022-01-01 | CMO East 2 | KLT | Actual | 0
42 | 2022-01-01 | CMO East 2 | Forefront | Budget
42 | 2022-01-01 | CMO East 2 | Forefront | Forecast | 495.57
42 | 2022-01-01 | CMO East 2 | Forefront | Actual | 0
42 | 2022-01-01 | CMO East 2 | DPF | Budget
42 | 2022-01-01 | CMO East 2 | DPF | Forecast | 0
42 | 2022-01-01 | CMO East 2 | DPF | Actual | 0
42 | 2022-01-01 | CMO East 2 | OMJ | Budget
42 | 2022-01-01 | CMO East 2 | OMJ | Forecast | 0
42 | 2022-01-01 | CMO East 2 | OMJ | Actual | 0
42 | 2022-01-01 | CMO East 2 | DHB Utilities | Budget
42 | 2022-01-01 | CMO East 2 | DHB Utilities | Forecast | 0
42 | 2022-01-01 | CMO East 2 | DHB Utilities | Actual | 0
42 | 2022-01-01 | CMO East 2 | JDT | Budget
42 | 2022-01-01 | CMO East 2 | JDT | Forecast | 546.88
42 | 2022-01-01 | CMO East 2 | JDT | Actual | 0
42 | 2022-01-01 | CMO East 2 | MURRAY | Budget
42 | 2022-01-01 | CMO East 2 | MURRAY | Forecast | 0
42 | 2022-01-01 | CMO East 2 | MURRAY | Actual | 0
42 | 2022-01-01 | West | Terra Firma | Budget
42 | 2022-01-01 | West | Terra Firma | Forecast | 0
42 | 2022-01-01 | West | Terra Firma | Actual | 0
42 | 2022-01-01 | West | KLT | Budget
42 | 2022-01-01 | West | KLT | Forecast | 0
42 | 2022-01-01 | West | KLT | Actual | 0
42 | 2022-01-01 | West | Forefront | Budget
42 | 2022-01-01 | West | Forefront | Forecast | 0
42 | 2022-01-01 | West | Forefront | Actual | 0
42 | 2022-01-01 | West | DPF | Budget
42 | 2022-01-01 | West | DPF | Forecast | 0
42 | 2022-01-01 | West | DPF | Actual | 0
42 | 2022-01-01 | West | OMJ | Budget
42 | 2022-01-01 | West | OMJ | Forecast | 0
42 | 2022-01-01 | West | OMJ | Actual | 0
42 | 2022-01-01 | West | DHB Utilities | Budget
42 | 2022-01-01 | West | DHB Utilities | Forecast | 0
42 | 2022-01-01 | West | DHB Utilities | Actual | 0
42 | 2022-01-01 | West | JDT | Budget
42 | 2022-01-01 | West | JDT | Forecast | 0
42 | 2022-01-01 | West | JDT | Actual | 0
42 | 2022-01-01 | West | MURRAY | Budget
42 | 2022-01-01 | West | MURRAY | Forecast | 0
42 | 2022-01-01 | West | MURRAY | Actual | 0
42 | 2022-01-01 | East | Terra Firma | Budget
42 | 2022-01-01 | East | Terra Firma | Forecast | 0
42 | 2022-01-01 | East | Terra Firma | Actual | 0
42 | 2022-01-01 | East | KLT | Budget
42 | 2022-01-01 | East | KLT | Forecast | 0
42 | 2022-01-01 | East | KLT | Actual | 0
42 | 2022-01-01 | East | Forefront | Budget
42 | 2022-01-01 | East | Forefront | Forecast | 0
42 | 2022-01-01 | East | Forefront | Actual | 0
42 | 2022-01-01 | East | DPF | Budget
42 | 2022-01-01 | East | DPF | Forecast | 0
42 | 2022-01-01 | East | DPF | Actual | 0
42 | 2022-01-01 | East | OMJ | Budget
42 | 2022-01-01 | East | OMJ | Forecast | 0
42 | 2022-01-01 | East | OMJ | Actual | 0
42 | 2022-01-01 | East | DHB Utilities | Budget
42 | 2022-01-01 | East | DHB Utilities | Forecast | 0
42 | 2022-01-01 | East | DHB Utilities | Actual | 0
42 | 2022-01-01 | East | JDT | Budget
42 | 2022-01-01 | East | JDT | Forecast | 0
42 | 2022-01-01 | East | JDT | Actual | 0
42 | 2022-01-01 | East | MURRAY | Budget
42 | 2022-01-01 | East | MURRAY | Forecast | 0
42 | 2022-01-01 | East | MURRAY | Actual | 0
42 | 2022-01-01 | Central | Terra Firma | Budget
42 | 2022-01-01 | Central | Terra Firma | Forecast | 0
42 | 2022-01-01 | Central | Terra Firma | Actual | 0
42 | 2022-01-01 | Central | KLT | Budget
42 | 2022-01-01 | Central | KLT | Forecast | 0
42 | 2022-01-01 | Central | KLT | Actual | 0
42 | 2022-01-01 | Central | Forefront | Budget
42 | 2022-01-01 | Central | Forefront | Forecast | 0
42 | 2022-01-01 | Central | Forefront | Actual | 0
42 | 2022-01-01 | Central | DPF | Budget
42 | 2022-01-01 | Central | DPF | Forecast | 0
42 | 2022-01-01 | Central | DPF | Actual | 0
42 | 2022-01-01 | Central | OMJ | Budget
42 | 2022-01-01 | Central | OMJ | Forecast | 0
42 | 2022-01-01 | Central | OMJ | Actual | 0
42 | 2022-01-01 | Central | DHB Utilities | Budget
42 | 2022-01-01 | Central | DHB Utilities | Forecast | 0
42 | 2022-01-01 | Central | DHB Utilities | Actual | 0
42 | 2022-01-01 | Central | JDT | Budget
42 | 2022-01-01 | Central | JDT | Forecast | 0
42 | 2022-01-01 | Central | JDT | Actual | 0
42 | 2022-01-01 | Central | MURRAY | Budget
42 | 2022-01-01 | Central | MURRAY | Forecast | 0
42 | 2022-01-01 | Central | MURRAY | Actual | 0
42 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Budget
42 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Budget
42 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Budget
42 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Budget
42 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | West | DIRECT MOLE | Budget
42 | 2022-01-01 | West | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | West | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | East | DIRECT MOLE | Budget
42 | 2022-01-01 | East | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | East | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | Central | DIRECT MOLE | Budget
42 | 2022-01-01 | Central | DIRECT MOLE | Forecast | 0
42 | 2022-01-01 | Central | DIRECT MOLE | Actual | 0
42 | 2022-01-01 | CMO West 1 | SQS | Budget
42 | 2022-01-01 | CMO West 1 | SQS | Forecast | 46.56
42 | 2022-01-01 | CMO West 1 | SQS | Actual | 0
42 | 2022-01-01 | CMO West 2 | SQS | Budget
42 | 2022-01-01 | CMO West 2 | SQS | Forecast | 441.63
42 | 2022-01-01 | CMO West 2 | SQS | Actual | 0
42 | 2022-01-01 | CMO East 1 | SQS | Budget
42 | 2022-01-01 | CMO East 1 | SQS | Forecast | 0
42 | 2022-01-01 | CMO East 1 | SQS | Actual | 0
42 | 2022-01-01 | CMO East 2 | SQS | Budget
42 | 2022-01-01 | CMO East 2 | SQS | Forecast | 0
42 | 2022-01-01 | CMO East 2 | SQS | Actual | 0
42 | 2022-01-01 | West | SQS | Budget
42 | 2022-01-01 | West | SQS | Forecast | 0
42 | 2022-01-01 | West | SQS | Actual | 0
42 | 2022-01-01 | East | SQS | Budget
42 | 2022-01-01 | East | SQS | Forecast | 0
43 | 2022-01-01 | East | SQS | Actual | 0
43 | 2022-01-01 | Central | SQS | Budget
43 | 2022-01-01 | Central | SQS | Forecast | 0
42 | 2022-01-01 | Central | SQS | Actual | 0
43 | 2022-01-01 | CMO West 1 | Terra Firma | Budget
43 | 2022-01-01 | CMO West 1 | Terra Firma | Forecast | 0
43 | 2022-01-01 | CMO West 1 | Terra Firma | Actual | 0
43 | 2022-01-01 | CMO West 1 | KLT | Budget
43 | 2022-01-01 | CMO West 1 | KLT | Forecast | 293.33
43 | 2022-01-01 | CMO West 1 | KLT | Actual | 0
43 | 2022-01-01 | CMO West 1 | Forefront | Budget
43 | 2022-01-01 | CMO West 1 | Forefront | Forecast | 0
43 | 2022-01-01 | CMO West 1 | Forefront | Actual | 0
43 | 2022-01-01 | CMO West 1 | DPF | Budget
43 | 2022-01-01 | CMO West 1 | DPF | Forecast | 60.67
43 | 2022-01-01 | CMO West 1 | DPF | Actual | 0
43 | 2022-01-01 | CMO West 1 | OMJ | Budget
43 | 2022-01-01 | CMO West 1 | OMJ | Forecast | 0
43 | 2022-01-01 | CMO West 1 | OMJ | Actual | 0
43 | 2022-01-01 | CMO West 1 | DHB Utilities | Budget
43 | 2022-01-01 | CMO West 1 | DHB Utilities | Forecast | 0
43 | 2022-01-01 | CMO West 1 | DHB Utilities | Actual | 0
43 | 2022-01-01 | CMO West 1 | JDT | Budget
43 | 2022-01-01 | CMO West 1 | JDT | Forecast | 0
43 | 2022-01-01 | CMO West 1 | JDT | Actual | 0
43 | 2022-01-01 | CMO West 1 | MURRAY | Budget
43 | 2022-01-01 | CMO West 1 | MURRAY | Forecast | 0
43 | 2022-01-01 | CMO West 1 | MURRAY | Actual | 0
43 | 2022-01-01 | CMO West 2 | Terra Firma | Budget
43 | 2022-01-01 | CMO West 2 | Terra Firma | Forecast | 0
43 | 2022-01-01 | CMO West 2 | Terra Firma | Actual | 0
43 | 2022-01-01 | CMO West 2 | KLT | Budget
43 | 2022-01-01 | CMO West 2 | KLT | Forecast | 547.66
43 | 2022-01-01 | CMO West 2 | KLT | Actual | 0
43 | 2022-01-01 | CMO West 2 | Forefront | Budget
43 | 2022-01-01 | CMO West 2 | Forefront | Forecast | 0
43 | 2022-01-01 | CMO West 2 | Forefront | Actual | 0
43 | 2022-01-01 | CMO West 2 | DPF | Budget
43 | 2022-01-01 | CMO West 2 | DPF | Forecast | 0
43 | 2022-01-01 | CMO West 2 | DPF | Actual | 0
43 | 2022-01-01 | CMO West 2 | OMJ | Budget
43 | 2022-01-01 | CMO West 2 | OMJ | Forecast | 641.55
43 | 2022-01-01 | CMO West 2 | OMJ | Actual | 0
43 | 2022-01-01 | CMO West 2 | DHB Utilities | Budget
43 | 2022-01-01 | CMO West 2 | DHB Utilities | Forecast | 77.72
43 | 2022-01-01 | CMO West 2 | DHB Utilities | Actual | 0
43 | 2022-01-01 | CMO West 2 | JDT | Budget
43 | 2022-01-01 | CMO West 2 | JDT | Forecast | 0
43 | 2022-01-01 | CMO West 2 | JDT | Actual | 0
43 | 2022-01-01 | CMO West 2 | MURRAY | Budget
43 | 2022-01-01 | CMO West 2 | MURRAY | Forecast | 0
43 | 2022-01-01 | CMO West 2 | MURRAY | Actual | 0
43 | 2022-01-01 | CMO East 1 | Terra Firma | Budget
43 | 2022-01-01 | CMO East 1 | Terra Firma | Forecast | 115.26
43 | 2022-01-01 | CMO East 1 | Terra Firma | Actual | 0
43 | 2022-01-01 | CMO East 1 | KLT | Budget
43 | 2022-01-01 | CMO East 1 | KLT | Forecast | 0
43 | 2022-01-01 | CMO East 1 | KLT | Actual | 0
43 | 2022-01-01 | CMO East 1 | Forefront | Budget
43 | 2022-01-01 | CMO East 1 | Forefront | Forecast | 93.4
43 | 2022-01-01 | CMO East 1 | Forefront | Actual | 0
43 | 2022-01-01 | CMO East 1 | DPF | Budget
43 | 2022-01-01 | CMO East 1 | DPF | Forecast | 288.82
43 | 2022-01-01 | CMO East 1 | DPF | Actual | 0
43 | 2022-01-01 | CMO East 1 | OMJ | Budget
43 | 2022-01-01 | CMO East 1 | OMJ | Forecast | 0
43 | 2022-01-01 | CMO East 1 | OMJ | Actual | 0
43 | 2022-01-01 | CMO East 1 | DHB Utilities | Budget
43 | 2022-01-01 | CMO East 1 | DHB Utilities | Forecast | 0
43 | 2022-01-01 | CMO East 1 | DHB Utilities | Actual | 0
43 | 2022-01-01 | CMO East 1 | JDT | Budget
43 | 2022-01-01 | CMO East 1 | JDT | Forecast | 0
43 | 2022-01-01 | CMO East 1 | JDT | Actual | 0
43 | 2022-01-01 | CMO East 1 | MURRAY | Budget
43 | 2022-01-01 | CMO East 1 | MURRAY | Forecast | 343.53
43 | 2022-01-01 | CMO East 1 | MURRAY | Actual | 0
43 | 2022-01-01 | CMO East 2 | Terra Firma | Budget
43 | 2022-01-01 | CMO East 2 | Terra Firma | Forecast | 498.6
43 | 2022-01-01 | CMO East 2 | Terra Firma | Actual | 0
43 | 2022-01-01 | CMO East 2 | KLT | Budget
43 | 2022-01-01 | CMO East 2 | KLT | Forecast | 0
43 | 2022-01-01 | CMO East 2 | KLT | Actual | 0
43 | 2022-01-01 | CMO East 2 | Forefront | Budget
43 | 2022-01-01 | CMO East 2 | Forefront | Forecast | 534.76
43 | 2022-01-01 | CMO East 2 | Forefront | Actual | 0
43 | 2022-01-01 | CMO East 2 | DPF | Budget
43 | 2022-01-01 | CMO East 2 | DPF | Forecast | 0
43 | 2022-01-01 | CMO East 2 | DPF | Actual | 0
43 | 2022-01-01 | CMO East 2 | OMJ | Budget
43 | 2022-01-01 | CMO East 2 | OMJ | Forecast | 0
43 | 2022-01-01 | CMO East 2 | OMJ | Actual | 0
43 | 2022-01-01 | CMO East 2 | DHB Utilities | Budget
43 | 2022-01-01 | CMO East 2 | DHB Utilities | Forecast | 0
43 | 2022-01-01 | CMO East 2 | DHB Utilities | Actual | 0
43 | 2022-01-01 | CMO East 2 | JDT | Budget
43 | 2022-01-01 | CMO East 2 | JDT | Forecast | 421.87
43 | 2022-01-01 | CMO East 2 | JDT | Actual | 0
43 | 2022-01-01 | CMO East 2 | MURRAY | Budget
43 | 2022-01-01 | CMO East 2 | MURRAY | Forecast | 0
43 | 2022-01-01 | CMO East 2 | MURRAY | Actual | 0
43 | 2022-01-01 | West | Terra Firma | Budget
43 | 2022-01-01 | West | Terra Firma | Forecast | 0
43 | 2022-01-01 | West | Terra Firma | Actual | 0
43 | 2022-01-01 | West | KLT | Budget
43 | 2022-01-01 | West | KLT | Forecast | 0
43 | 2022-01-01 | West | KLT | Actual | 0
43 | 2022-01-01 | West | Forefront | Budget
43 | 2022-01-01 | West | Forefront | Forecast | 0
43 | 2022-01-01 | West | Forefront | Actual | 0
43 | 2022-01-01 | West | DPF | Budget
43 | 2022-01-01 | West | DPF | Forecast | 0
43 | 2022-01-01 | West | DPF | Actual | 0
43 | 2022-01-01 | West | OMJ | Budget
43 | 2022-01-01 | West | OMJ | Forecast | 0
43 | 2022-01-01 | West | OMJ | Actual | 0
43 | 2022-01-01 | West | DHB Utilities | Budget
43 | 2022-01-01 | West | DHB Utilities | Forecast | 0
43 | 2022-01-01 | West | DHB Utilities | Actual | 0
43 | 2022-01-01 | West | JDT | Budget
43 | 2022-01-01 | West | JDT | Forecast | 0
43 | 2022-01-01 | West | JDT | Actual | 0
43 | 2022-01-01 | West | MURRAY | Budget
43 | 2022-01-01 | West | MURRAY | Forecast | 0
43 | 2022-01-01 | West | MURRAY | Actual | 0
43 | 2022-01-01 | East | Terra Firma | Budget
43 | 2022-01-01 | East | Terra Firma | Forecast | 0
43 | 2022-01-01 | East | Terra Firma | Actual | 0
43 | 2022-01-01 | East | KLT | Budget
43 | 2022-01-01 | East | KLT | Forecast | 0
43 | 2022-01-01 | East | KLT | Actual | 0
43 | 2022-01-01 | East | Forefront | Budget
43 | 2022-01-01 | East | Forefront | Forecast | 0
43 | 2022-01-01 | East | Forefront | Actual | 0
43 | 2022-01-01 | East | DPF | Budget
43 | 2022-01-01 | East | DPF | Forecast | 0
43 | 2022-01-01 | East | DPF | Actual | 0
43 | 2022-01-01 | East | OMJ | Budget
43 | 2022-01-01 | East | OMJ | Forecast | 0
43 | 2022-01-01 | East | OMJ | Actual | 0
43 | 2022-01-01 | East | DHB Utilities | Budget
43 | 2022-01-01 | East | DHB Utilities | Forecast | 0
43 | 2022-01-01 | East | DHB Utilities | Actual | 0
43 | 2022-01-01 | East | JDT | Budget
43 | 2022-01-01 | East | JDT | Forecast | 0
43 | 2022-01-01 | East | JDT | Actual | 0
43 | 2022-01-01 | East | MURRAY | Budget
43 | 2022-01-01 | East | MURRAY | Forecast | 0
43 | 2022-01-01 | East | MURRAY | Actual | 0
43 | 2022-01-01 | Central | Terra Firma | Budget
43 | 2022-01-01 | Central | Terra Firma | Forecast | 0
43 | 2022-01-01 | Central | Terra Firma | Actual | 0
43 | 2022-01-01 | Central | KLT | Budget
43 | 2022-01-01 | Central | KLT | Forecast | 0
43 | 2022-01-01 | Central | KLT | Actual | 0
43 | 2022-01-01 | Central | Forefront | Budget
43 | 2022-01-01 | Central | Forefront | Forecast | 0
43 | 2022-01-01 | Central | Forefront | Actual | 0
43 | 2022-01-01 | Central | DPF | Budget
43 | 2022-01-01 | Central | DPF | Forecast | 0
43 | 2022-01-01 | Central | DPF | Actual | 0
43 | 2022-01-01 | Central | OMJ | Budget
43 | 2022-01-01 | Central | OMJ | Forecast | 0
43 | 2022-01-01 | Central | OMJ | Actual | 0
43 | 2022-01-01 | Central | DHB Utilities | Budget
43 | 2022-01-01 | Central | DHB Utilities | Forecast | 0
43 | 2022-01-01 | Central | DHB Utilities | Actual | 0
43 | 2022-01-01 | Central | JDT | Budget
43 | 2022-01-01 | Central | JDT | Forecast | 0
43 | 2022-01-01 | Central | JDT | Actual | 0
43 | 2022-01-01 | Central | MURRAY | Budget
43 | 2022-01-01 | Central | MURRAY | Forecast | 0
43 | 2022-01-01 | Central | MURRAY | Actual | 0
43 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Budget
43 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Budget
43 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Budget
43 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Budget
43 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | West | DIRECT MOLE | Budget
43 | 2022-01-01 | West | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | West | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | East | DIRECT MOLE | Budget
43 | 2022-01-01 | East | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | East | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | Central | DIRECT MOLE | Budget
43 | 2022-01-01 | Central | DIRECT MOLE | Forecast | 0
43 | 2022-01-01 | Central | DIRECT MOLE | Actual | 0
43 | 2022-01-01 | CMO West 1 | SQS | Budget
43 | 2022-01-01 | CMO West 1 | SQS | Forecast | 42.07
43 | 2022-01-01 | CMO West 1 | SQS | Actual | 0
43 | 2022-01-01 | CMO West 2 | SQS | Budget
43 | 2022-01-01 | CMO West 2 | SQS | Forecast | 366.9
43 | 2022-01-01 | CMO West 2 | SQS | Actual | 0
43 | 2022-01-01 | CMO East 1 | SQS | Budget
43 | 2022-01-01 | CMO East 1 | SQS | Forecast | 0
43 | 2022-01-01 | CMO East 1 | SQS | Actual | 0
43 | 2022-01-01 | CMO East 2 | SQS | Budget
43 | 2022-01-01 | CMO East 2 | SQS | Forecast | 0
43 | 2022-01-01 | CMO East 2 | SQS | Actual | 0
43 | 2022-01-01 | West | SQS | Budget
43 | 2022-01-01 | West | SQS | Forecast | 0
43 | 2022-01-01 | West | SQS | Actual | 0
43 | 2022-01-01 | East | SQS | Budget
43 | 2022-01-01 | East | SQS | Forecast | 0
44 | 2022-01-01 | East | SQS | Actual | 0
44 | 2022-01-01 | Central | SQS | Budget
44 | 2022-01-01 | Central | SQS | Forecast | 0
43 | 2022-01-01 | Central | SQS | Actual | 0
44 | 2022-01-01 | CMO West 1 | Terra Firma | Budget
44 | 2022-01-01 | CMO West 1 | Terra Firma | Forecast | 0
44 | 2022-01-01 | CMO West 1 | Terra Firma | Actual | 0
44 | 2022-01-01 | CMO West 1 | KLT | Budget
44 | 2022-01-01 | CMO West 1 | KLT | Forecast | 403.69
44 | 2022-01-01 | CMO West 1 | KLT | Actual | 0
44 | 2022-01-01 | CMO West 1 | Forefront | Budget
44 | 2022-01-01 | CMO West 1 | Forefront | Forecast | 0
44 | 2022-01-01 | CMO West 1 | Forefront | Actual | 0
44 | 2022-01-01 | CMO West 1 | DPF | Budget
44 | 2022-01-01 | CMO West 1 | DPF | Forecast | 34.78
44 | 2022-01-01 | CMO West 1 | DPF | Actual | 0
44 | 2022-01-01 | CMO West 1 | OMJ | Budget
44 | 2022-01-01 | CMO West 1 | OMJ | Forecast | 0
44 | 2022-01-01 | CMO West 1 | OMJ | Actual | 0
44 | 2022-01-01 | CMO West 1 | DHB Utilities | Budget
44 | 2022-01-01 | CMO West 1 | DHB Utilities | Forecast | 0
44 | 2022-01-01 | CMO West 1 | DHB Utilities | Actual | 0
44 | 2022-01-01 | CMO West 1 | JDT | Budget
44 | 2022-01-01 | CMO West 1 | JDT | Forecast | 0
44 | 2022-01-01 | CMO West 1 | JDT | Actual | 0
44 | 2022-01-01 | CMO West 1 | MURRAY | Budget
44 | 2022-01-01 | CMO West 1 | MURRAY | Forecast | 0
44 | 2022-01-01 | CMO West 1 | MURRAY | Actual | 0
44 | 2022-01-01 | CMO West 2 | Terra Firma | Budget
44 | 2022-01-01 | CMO West 2 | Terra Firma | Forecast | 0
44 | 2022-01-01 | CMO West 2 | Terra Firma | Actual | 0
44 | 2022-01-01 | CMO West 2 | KLT | Budget
44 | 2022-01-01 | CMO West 2 | KLT | Forecast | 547.66
44 | 2022-01-01 | CMO West 2 | KLT | Actual | 0
44 | 2022-01-01 | CMO West 2 | Forefront | Budget
44 | 2022-01-01 | CMO West 2 | Forefront | Forecast | 0
44 | 2022-01-01 | CMO West 2 | Forefront | Actual | 0
44 | 2022-01-01 | CMO West 2 | DPF | Budget
44 | 2022-01-01 | CMO West 2 | DPF | Forecast | 0
44 | 2022-01-01 | CMO West 2 | DPF | Actual | 0
44 | 2022-01-01 | CMO West 2 | OMJ | Budget
44 | 2022-01-01 | CMO West 2 | OMJ | Forecast | 496.77
44 | 2022-01-01 | CMO West 2 | OMJ | Actual | 0
44 | 2022-01-01 | CMO West 2 | DHB Utilities | Budget
44 | 2022-01-01 | CMO West 2 | DHB Utilities | Forecast | 47.75
44 | 2022-01-01 | CMO West 2 | DHB Utilities | Actual | 0
44 | 2022-01-01 | CMO West 2 | JDT | Budget
44 | 2022-01-01 | CMO West 2 | JDT | Forecast | 0
44 | 2022-01-01 | CMO West 2 | JDT | Actual | 0
44 | 2022-01-01 | CMO West 2 | MURRAY | Budget
44 | 2022-01-01 | CMO West 2 | MURRAY | Forecast | 0
44 | 2022-01-01 | CMO West 2 | MURRAY | Actual | 0
44 | 2022-01-01 | CMO East 1 | Terra Firma | Budget
44 | 2022-01-01 | CMO East 1 | Terra Firma | Forecast | 78.94
44 | 2022-01-01 | CMO East 1 | Terra Firma | Actual | 0
44 | 2022-01-01 | CMO East 1 | KLT | Budget
44 | 2022-01-01 | CMO East 1 | KLT | Forecast | 0
44 | 2022-01-01 | CMO East 1 | KLT | Actual | 0
44 | 2022-01-01 | CMO East 1 | Forefront | Budget
44 | 2022-01-01 | CMO East 1 | Forefront | Forecast | 93.4
44 | 2022-01-01 | CMO East 1 | Forefront | Actual | 0
44 | 2022-01-01 | CMO East 1 | DPF | Budget
44 | 2022-01-01 | CMO East 1 | DPF | Forecast | 288.82
44 | 2022-01-01 | CMO East 1 | DPF | Actual | 0
44 | 2022-01-01 | CMO East 1 | OMJ | Budget
44 | 2022-01-01 | CMO East 1 | OMJ | Forecast | 0
44 | 2022-01-01 | CMO East 1 | OMJ | Actual | 0
44 | 2022-01-01 | CMO East 1 | DHB Utilities | Budget
44 | 2022-01-01 | CMO East 1 | DHB Utilities | Forecast | 0
44 | 2022-01-01 | CMO East 1 | DHB Utilities | Actual | 0
44 | 2022-01-01 | CMO East 1 | JDT | Budget
44 | 2022-01-01 | CMO East 1 | JDT | Forecast | 0
44 | 2022-01-01 | CMO East 1 | JDT | Actual | 0
44 | 2022-01-01 | CMO East 1 | MURRAY | Budget
44 | 2022-01-01 | CMO East 1 | MURRAY | Forecast | 343.53
44 | 2022-01-01 | CMO East 1 | MURRAY | Actual | 0
44 | 2022-01-01 | CMO East 2 | Terra Firma | Budget
44 | 2022-01-01 | CMO East 2 | Terra Firma | Forecast | 498.6
44 | 2022-01-01 | CMO East 2 | Terra Firma | Actual | 0
44 | 2022-01-01 | CMO East 2 | KLT | Budget
44 | 2022-01-01 | CMO East 2 | KLT | Forecast | 0
44 | 2022-01-01 | CMO East 2 | KLT | Actual | 0
44 | 2022-01-01 | CMO East 2 | Forefront | Budget
44 | 2022-01-01 | CMO East 2 | Forefront | Forecast | 534.76
44 | 2022-01-01 | CMO East 2 | Forefront | Actual | 0
44 | 2022-01-01 | CMO East 2 | DPF | Budget
44 | 2022-01-01 | CMO East 2 | DPF | Forecast | 0
44 | 2022-01-01 | CMO East 2 | DPF | Actual | 0
44 | 2022-01-01 | CMO East 2 | OMJ | Budget
44 | 2022-01-01 | CMO East 2 | OMJ | Forecast | 0
44 | 2022-01-01 | CMO East 2 | OMJ | Actual | 0
44 | 2022-01-01 | CMO East 2 | DHB Utilities | Budget
44 | 2022-01-01 | CMO East 2 | DHB Utilities | Forecast | 0
44 | 2022-01-01 | CMO East 2 | DHB Utilities | Actual | 0
44 | 2022-01-01 | CMO East 2 | JDT | Budget
44 | 2022-01-01 | CMO East 2 | JDT | Forecast | 359.56
44 | 2022-01-01 | CMO East 2 | JDT | Actual | 0
44 | 2022-01-01 | CMO East 2 | MURRAY | Budget
44 | 2022-01-01 | CMO East 2 | MURRAY | Forecast | 0
44 | 2022-01-01 | CMO East 2 | MURRAY | Actual | 0
44 | 2022-01-01 | West | Terra Firma | Budget
44 | 2022-01-01 | West | Terra Firma | Forecast | 0
44 | 2022-01-01 | West | Terra Firma | Actual | 0
44 | 2022-01-01 | West | KLT | Budget
44 | 2022-01-01 | West | KLT | Forecast | 0
44 | 2022-01-01 | West | KLT | Actual | 0
44 | 2022-01-01 | West | Forefront | Budget
44 | 2022-01-01 | West | Forefront | Forecast | 0
44 | 2022-01-01 | West | Forefront | Actual | 0
44 | 2022-01-01 | West | DPF | Budget
44 | 2022-01-01 | West | DPF | Forecast | 0
44 | 2022-01-01 | West | DPF | Actual | 0
44 | 2022-01-01 | West | OMJ | Budget
44 | 2022-01-01 | West | OMJ | Forecast | 0
44 | 2022-01-01 | West | OMJ | Actual | 0
44 | 2022-01-01 | West | DHB Utilities | Budget
44 | 2022-01-01 | West | DHB Utilities | Forecast | 0
44 | 2022-01-01 | West | DHB Utilities | Actual | 0
44 | 2022-01-01 | West | JDT | Budget
44 | 2022-01-01 | West | JDT | Forecast | 0
44 | 2022-01-01 | West | JDT | Actual | 0
44 | 2022-01-01 | West | MURRAY | Budget
44 | 2022-01-01 | West | MURRAY | Forecast | 0
44 | 2022-01-01 | West | MURRAY | Actual | 0
44 | 2022-01-01 | East | Terra Firma | Budget
44 | 2022-01-01 | East | Terra Firma | Forecast | 0
44 | 2022-01-01 | East | Terra Firma | Actual | 0
44 | 2022-01-01 | East | KLT | Budget
44 | 2022-01-01 | East | KLT | Forecast | 0
44 | 2022-01-01 | East | KLT | Actual | 0
44 | 2022-01-01 | East | Forefront | Budget
44 | 2022-01-01 | East | Forefront | Forecast | 0
44 | 2022-01-01 | East | Forefront | Actual | 0
44 | 2022-01-01 | East | DPF | Budget
44 | 2022-01-01 | East | DPF | Forecast | 0
44 | 2022-01-01 | East | DPF | Actual | 0
44 | 2022-01-01 | East | OMJ | Budget
44 | 2022-01-01 | East | OMJ | Forecast | 0
44 | 2022-01-01 | East | OMJ | Actual | 0
44 | 2022-01-01 | East | DHB Utilities | Budget
44 | 2022-01-01 | East | DHB Utilities | Forecast | 0
44 | 2022-01-01 | East | DHB Utilities | Actual | 0
44 | 2022-01-01 | East | JDT | Budget
44 | 2022-01-01 | East | JDT | Forecast | 0
44 | 2022-01-01 | East | JDT | Actual | 0
44 | 2022-01-01 | East | MURRAY | Budget
44 | 2022-01-01 | East | MURRAY | Forecast | 0
44 | 2022-01-01 | East | MURRAY | Actual | 0
44 | 2022-01-01 | Central | Terra Firma | Budget
44 | 2022-01-01 | Central | Terra Firma | Forecast | 0
44 | 2022-01-01 | Central | Terra Firma | Actual | 0
44 | 2022-01-01 | Central | KLT | Budget
44 | 2022-01-01 | Central | KLT | Forecast | 0
44 | 2022-01-01 | Central | KLT | Actual | 0
44 | 2022-01-01 | Central | Forefront | Budget
44 | 2022-01-01 | Central | Forefront | Forecast | 0
44 | 2022-01-01 | Central | Forefront | Actual | 0
44 | 2022-01-01 | Central | DPF | Budget
44 | 2022-01-01 | Central | DPF | Forecast | 0
44 | 2022-01-01 | Central | DPF | Actual | 0
44 | 2022-01-01 | Central | OMJ | Budget
44 | 2022-01-01 | Central | OMJ | Forecast | 0
44 | 2022-01-01 | Central | OMJ | Actual | 0
44 | 2022-01-01 | Central | DHB Utilities | Budget
44 | 2022-01-01 | Central | DHB Utilities | Forecast | 0
44 | 2022-01-01 | Central | DHB Utilities | Actual | 0
44 | 2022-01-01 | Central | JDT | Budget
44 | 2022-01-01 | Central | JDT | Forecast | 0
44 | 2022-01-01 | Central | JDT | Actual | 0
44 | 2022-01-01 | Central | MURRAY | Budget
44 | 2022-01-01 | Central | MURRAY | Forecast | 0
44 | 2022-01-01 | Central | MURRAY | Actual | 0
44 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Budget
44 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | CMO West 1 | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Budget
44 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | CMO West 2 | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Budget
44 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | CMO East 1 | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Budget
44 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | CMO East 2 | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | West | DIRECT MOLE | Budget
44 | 2022-01-01 | West | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | West | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | East | DIRECT MOLE | Budget
44 | 2022-01-01 | East | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | East | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | Central | DIRECT MOLE | Budget
44 | 2022-01-01 | Central | DIRECT MOLE | Forecast | 0
44 | 2022-01-01 | Central | DIRECT MOLE | Actual | 0
44 | 2022-01-01 | CMO West 1 | SQS | Budget
44 | 2022-01-01 | CMO West 1 | SQS | Forecast | 42.07
44 | 2022-01-01 | CMO West 1 | SQS | Actual | 0
44 | 2022-01-01 | CMO West 2 | SQS | Budget
44 | 2022-01-01 | CMO West 2 | SQS | Forecast | 321.58
44 | 2022-01-01 | CMO West 2 | SQS | Actual | 0
44 | 2022-01-01 | CMO East 1 | SQS | Budget
44 | 2022-01-01 | CMO East 1 | SQS | Forecast | 0
44 | 2022-01-01 | CMO East 1 | SQS | Actual | 0
44 | 2022-01-01 | CMO East 2 | SQS | Budget
44 | 2022-01-01 | CMO East 2 | SQS | Forecast | 0
44 | 2022-01-01 | CMO East 2 | SQS | Actual | 0
44 | 2022-01-01 | West | SQS | Budget
44 | 2022-01-01 | West | SQS | Forecast | 0
44 | 2022-01-01 | West | SQS | Actual | 0
44 | 2022-01-01 | East | SQS | Budget
44 | 2022-01-01 | East | SQS | Forecast | 0
45 | 2022-01-01 | East | SQS | Actual | 0
45 | 2022-01-01 | Central | SQS | Budget
45 | 2022-01-01 | Central | SQS | Forecast | 0
44 | 2022-01-01 | Central | SQS | Actual | 0
45 | 2022-02-01 | CMO West 1 | Terra Firma | Budget
45 | 2022-02-01 | CMO West 1 | Terra Firma | Forecast | 0
45 | 2022-02-01 | CMO West 1 | Terra Firma | Actual | 0
45 | 2022-02-01 | CMO West 1 | KLT | Budget
45 | 2022-02-01 | CMO West 1 | KLT | Forecast | 244.85
45 | 2022-02-01 | CMO West 1 | KLT | Actual | 0
45 | 2022-02-01 | CMO West 1 | Forefront | Budget
45 | 2022-02-01 | CMO West 1 | Forefront | Forecast | 0
45 | 2022-02-01 | CMO West 1 | Forefront | Actual | 0
45 | 2022-02-01 | CMO West 1 | DPF | Budget
45 | 2022-02-01 | CMO West 1 | DPF | Forecast | 16.01
45 | 2022-02-01 | CMO West 1 | DPF | Actual | 0
45 | 2022-02-01 | CMO West 1 | OMJ | Budget
45 | 2022-02-01 | CMO West 1 | OMJ | Forecast | 0
45 | 2022-02-01 | CMO West 1 | OMJ | Actual | 0
45 | 2022-02-01 | CMO West 1 | DHB Utilities | Budget
45 | 2022-02-01 | CMO West 1 | DHB Utilities | Forecast | 0
45 | 2022-02-01 | CMO West 1 | DHB Utilities | Actual | 0
45 | 2022-02-01 | CMO West 1 | JDT | Budget
45 | 2022-02-01 | CMO West 1 | JDT | Forecast | 0
45 | 2022-02-01 | CMO West 1 | JDT | Actual | 0
45 | 2022-02-01 | CMO West 1 | MURRAY | Budget
45 | 2022-02-01 | CMO West 1 | MURRAY | Forecast | 0
45 | 2022-02-01 | CMO West 1 | MURRAY | Actual | 0
45 | 2022-02-01 | CMO West 2 | Terra Firma | Budget
45 | 2022-02-01 | CMO West 2 | Terra Firma | Forecast | 0
45 | 2022-02-01 | CMO West 2 | Terra Firma | Actual | 0
45 | 2022-02-01 | CMO West 2 | KLT | Budget
45 | 2022-02-01 | CMO West 2 | KLT | Forecast | 570.43
45 | 2022-02-01 | CMO West 2 | KLT | Actual | 0
45 | 2022-02-01 | CMO West 2 | Forefront | Budget
45 | 2022-02-01 | CMO West 2 | Forefront | Forecast | 0
45 | 2022-02-01 | CMO West 2 | Forefront | Actual | 0
45 | 2022-02-01 | CMO West 2 | DPF | Budget
45 | 2022-02-01 | CMO West 2 | DPF | Forecast | 0
45 | 2022-02-01 | CMO West 2 | DPF | Actual | 0
45 | 2022-02-01 | CMO West 2 | OMJ | Budget
45 | 2022-02-01 | CMO West 2 | OMJ | Forecast | 539.12
45 | 2022-02-01 | CMO West 2 | OMJ | Actual | 0
45 | 2022-02-01 | CMO West 2 | DHB Utilities | Budget
45 | 2022-02-01 | CMO West 2 | DHB Utilities | Forecast | 47.75
45 | 2022-02-01 | CMO West 2 | DHB Utilities | Actual | 0
45 | 2022-02-01 | CMO West 2 | JDT | Budget
45 | 2022-02-01 | CMO West 2 | JDT | Forecast | 0
45 | 2022-02-01 | CMO West 2 | JDT | Actual | 0
45 | 2022-02-01 | CMO West 2 | MURRAY | Budget
45 | 2022-02-01 | CMO West 2 | MURRAY | Forecast | 0
45 | 2022-02-01 | CMO West 2 | MURRAY | Actual | 0
45 | 2022-02-01 | CMO East 1 | Terra Firma | Budget
45 | 2022-02-01 | CMO East 1 | Terra Firma | Forecast | 142.69
45 | 2022-02-01 | CMO East 1 | Terra Firma | Actual | 0
45 | 2022-02-01 | CMO East 1 | KLT | Budget
45 | 2022-02-01 | CMO East 1 | KLT | Forecast | 0
45 | 2022-02-01 | CMO East 1 | KLT | Actual | 0
45 | 2022-02-01 | CMO East 1 | Forefront | Budget
45 | 2022-02-01 | CMO East 1 | Forefront | Forecast | 93.4
45 | 2022-02-01 | CMO East 1 | Forefront | Actual | 0
45 | 2022-02-01 | CMO East 1 | DPF | Budget
45 | 2022-02-01 | CMO East 1 | DPF | Forecast | 250.76
45 | 2022-02-01 | CMO East 1 | DPF | Actual | 0
45 | 2022-02-01 | CMO East 1 | OMJ | Budget
45 | 2022-02-01 | CMO East 1 | OMJ | Forecast | 0
45 | 2022-02-01 | CMO East 1 | OMJ | Actual | 0
45 | 2022-02-01 | CMO East 1 | DHB Utilities | Budget
45 | 2022-02-01 | CMO East 1 | DHB Utilities | Forecast | 0
45 | 2022-02-01 | CMO East 1 | DHB Utilities | Actual | 0
45 | 2022-02-01 | CMO East 1 | JDT | Budget
45 | 2022-02-01 | CMO East 1 | JDT | Forecast | 0
45 | 2022-02-01 | CMO East 1 | JDT | Actual | 0
45 | 2022-02-01 | CMO East 1 | MURRAY | Budget
45 | 2022-02-01 | CMO East 1 | MURRAY | Forecast | 68.79
45 | 2022-02-01 | CMO East 1 | MURRAY | Actual | 0
45 | 2022-02-01 | CMO East 2 | Terra Firma | Budget
45 | 2022-02-01 | CMO East 2 | Terra Firma | Forecast | 555.77
45 | 2022-02-01 | CMO East 2 | Terra Firma | Actual | 0
45 | 2022-02-01 | CMO East 2 | KLT | Budget
45 | 2022-02-01 | CMO East 2 | KLT | Forecast | 0
45 | 2022-02-01 | CMO East 2 | KLT | Actual | 0
45 | 2022-02-01 | CMO East 2 | Forefront | Budget
45 | 2022-02-01 | CMO East 2 | Forefront | Forecast | 612.32
45 | 2022-02-01 | CMO East 2 | Forefront | Actual | 0
45 | 2022-02-01 | CMO East 2 | DPF | Budget
45 | 2022-02-01 | CMO East 2 | DPF | Forecast | 0
45 | 2022-02-01 | CMO East 2 | DPF | Actual | 0
45 | 2022-02-01 | CMO East 2 | OMJ | Budget
45 | 2022-02-01 | CMO East 2 | OMJ | Forecast | 0
45 | 2022-02-01 | CMO East 2 | OMJ | Actual | 0
45 | 2022-02-01 | CMO East 2 | DHB Utilities | Budget
45 | 2022-02-01 | CMO East 2 | DHB Utilities | Forecast | 0
45 | 2022-02-01 | CMO East 2 | DHB Utilities | Actual | 0
45 | 2022-02-01 | CMO East 2 | JDT | Budget
45 | 2022-02-01 | CMO East 2 | JDT | Forecast | 378.07
45 | 2022-02-01 | CMO East 2 | JDT | Actual | 0
45 | 2022-02-01 | CMO East 2 | MURRAY | Budget
45 | 2022-02-01 | CMO East 2 | MURRAY | Forecast | 0
45 | 2022-02-01 | CMO East 2 | MURRAY | Actual | 0
45 | 2022-02-01 | West | Terra Firma | Budget
45 | 2022-02-01 | West | Terra Firma | Forecast | 0
45 | 2022-02-01 | West | Terra Firma | Actual | 0
45 | 2022-02-01 | West | KLT | Budget
45 | 2022-02-01 | West | KLT | Forecast | 0
45 | 2022-02-01 | West | KLT | Actual | 0
45 | 2022-02-01 | West | Forefront | Budget
45 | 2022-02-01 | West | Forefront | Forecast | 0
45 | 2022-02-01 | West | Forefront | Actual | 0
45 | 2022-02-01 | West | DPF | Budget
45 | 2022-02-01 | West | DPF | Forecast | 0
45 | 2022-02-01 | West | DPF | Actual | 0
45 | 2022-02-01 | West | OMJ | Budget
45 | 2022-02-01 | West | OMJ | Forecast | 0
45 | 2022-02-01 | West | OMJ | Actual | 0
45 | 2022-02-01 | West | DHB Utilities | Budget
45 | 2022-02-01 | West | DHB Utilities | Forecast | 0
45 | 2022-02-01 | West | DHB Utilities | Actual | 0
45 | 2022-02-01 | West | JDT | Budget
45 | 2022-02-01 | West | JDT | Forecast | 0
45 | 2022-02-01 | West | JDT | Actual | 0
45 | 2022-02-01 | West | MURRAY | Budget
45 | 2022-02-01 | West | MURRAY | Forecast | 0
45 | 2022-02-01 | West | MURRAY | Actual | 0
45 | 2022-02-01 | East | Terra Firma | Budget
45 | 2022-02-01 | East | Terra Firma | Forecast | 0
45 | 2022-02-01 | East | Terra Firma | Actual | 0
45 | 2022-02-01 | East | KLT | Budget
45 | 2022-02-01 | East | KLT | Forecast | 0
45 | 2022-02-01 | East | KLT | Actual | 0
45 | 2022-02-01 | East | Forefront | Budget
45 | 2022-02-01 | East | Forefront | Forecast | 0
45 | 2022-02-01 | East | Forefront | Actual | 0
45 | 2022-02-01 | East | DPF | Budget
45 | 2022-02-01 | East | DPF | Forecast | 0
45 | 2022-02-01 | East | DPF | Actual | 0
45 | 2022-02-01 | East | OMJ | Budget
45 | 2022-02-01 | East | OMJ | Forecast | 0
45 | 2022-02-01 | East | OMJ | Actual | 0
45 | 2022-02-01 | East | DHB Utilities | Budget
45 | 2022-02-01 | East | DHB Utilities | Forecast | 0
45 | 2022-02-01 | East | DHB Utilities | Actual | 0
45 | 2022-02-01 | East | JDT | Budget
45 | 2022-02-01 | East | JDT | Forecast | 0
45 | 2022-02-01 | East | JDT | Actual | 0
45 | 2022-02-01 | East | MURRAY | Budget
45 | 2022-02-01 | East | MURRAY | Forecast | 0
45 | 2022-02-01 | East | MURRAY | Actual | 0
45 | 2022-02-01 | Central | Terra Firma | Budget
45 | 2022-02-01 | Central | Terra Firma | Forecast | 0
45 | 2022-02-01 | Central | Terra Firma | Actual | 0
45 | 2022-02-01 | Central | KLT | Budget
45 | 2022-02-01 | Central | KLT | Forecast | 0
45 | 2022-02-01 | Central | KLT | Actual | 0
45 | 2022-02-01 | Central | Forefront | Budget
45 | 2022-02-01 | Central | Forefront | Forecast | 0
45 | 2022-02-01 | Central | Forefront | Actual | 0
45 | 2022-02-01 | Central | DPF | Budget
45 | 2022-02-01 | Central | DPF | Forecast | 0
45 | 2022-02-01 | Central | DPF | Actual | 0
45 | 2022-02-01 | Central | OMJ | Budget
45 | 2022-02-01 | Central | OMJ | Forecast | 0
45 | 2022-02-01 | Central | OMJ | Actual | 0
45 | 2022-02-01 | Central | DHB Utilities | Budget
45 | 2022-02-01 | Central | DHB Utilities | Forecast | 0
45 | 2022-02-01 | Central | DHB Utilities | Actual | 0
45 | 2022-02-01 | Central | JDT | Budget
45 | 2022-02-01 | Central | JDT | Forecast | 0
45 | 2022-02-01 | Central | JDT | Actual | 0
45 | 2022-02-01 | Central | MURRAY | Budget
45 | 2022-02-01 | Central | MURRAY | Forecast | 0
45 | 2022-02-01 | Central | MURRAY | Actual | 0
45 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Budget
45 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Budget
45 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Budget
45 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Budget
45 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | West | DIRECT MOLE | Budget
45 | 2022-02-01 | West | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | West | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | East | DIRECT MOLE | Budget
45 | 2022-02-01 | East | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | East | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | Central | DIRECT MOLE | Budget
45 | 2022-02-01 | Central | DIRECT MOLE | Forecast | 0
45 | 2022-02-01 | Central | DIRECT MOLE | Actual | 0
45 | 2022-02-01 | CMO West 1 | SQS | Budget
45 | 2022-02-01 | CMO West 1 | SQS | Forecast | 42.07
45 | 2022-02-01 | CMO West 1 | SQS | Actual | 0
45 | 2022-02-01 | CMO West 2 | SQS | Budget
45 | 2022-02-01 | CMO West 2 | SQS | Forecast | 216.3
45 | 2022-02-01 | CMO West 2 | SQS | Actual | 0
45 | 2022-02-01 | CMO East 1 | SQS | Budget
45 | 2022-02-01 | CMO East 1 | SQS | Forecast | 0
45 | 2022-02-01 | CMO East 1 | SQS | Actual | 0
45 | 2022-02-01 | CMO East 2 | SQS | Budget
45 | 2022-02-01 | CMO East 2 | SQS | Forecast | 0
45 | 2022-02-01 | CMO East 2 | SQS | Actual | 0
45 | 2022-02-01 | West | SQS | Budget
45 | 2022-02-01 | West | SQS | Forecast | 0
45 | 2022-02-01 | West | SQS | Actual | 0
45 | 2022-02-01 | East | SQS | Budget
45 | 2022-02-01 | East | SQS | Forecast | 0
46 | 2022-02-01 | East | SQS | Actual | 0
46 | 2022-02-01 | Central | SQS | Budget
46 | 2022-02-01 | Central | SQS | Forecast | 0
45 | 2022-02-01 | Central | SQS | Actual | 0
46 | 2022-02-01 | CMO West 1 | Terra Firma | Budget
46 | 2022-02-01 | CMO West 1 | Terra Firma | Forecast | 0
46 | 2022-02-01 | CMO West 1 | Terra Firma | Actual | 0
46 | 2022-02-01 | CMO West 1 | KLT | Budget
46 | 2022-02-01 | CMO West 1 | KLT | Forecast | 89.14
46 | 2022-02-01 | CMO West 1 | KLT | Actual | 0
46 | 2022-02-01 | CMO West 1 | Forefront | Budget
46 | 2022-02-01 | CMO West 1 | Forefront | Forecast | 0
46 | 2022-02-01 | CMO West 1 | Forefront | Actual | 0
46 | 2022-02-01 | CMO West 1 | DPF | Budget
46 | 2022-02-01 | CMO West 1 | DPF | Forecast | 16.01
46 | 2022-02-01 | CMO West 1 | DPF | Actual | 0
46 | 2022-02-01 | CMO West 1 | OMJ | Budget
46 | 2022-02-01 | CMO West 1 | OMJ | Forecast | 0
46 | 2022-02-01 | CMO West 1 | OMJ | Actual | 0
46 | 2022-02-01 | CMO West 1 | DHB Utilities | Budget
46 | 2022-02-01 | CMO West 1 | DHB Utilities | Forecast | 0
46 | 2022-02-01 | CMO West 1 | DHB Utilities | Actual | 0
46 | 2022-02-01 | CMO West 1 | JDT | Budget
46 | 2022-02-01 | CMO West 1 | JDT | Forecast | 0
46 | 2022-02-01 | CMO West 1 | JDT | Actual | 0
46 | 2022-02-01 | CMO West 1 | MURRAY | Budget
46 | 2022-02-01 | CMO West 1 | MURRAY | Forecast | 0
46 | 2022-02-01 | CMO West 1 | MURRAY | Actual | 0
46 | 2022-02-01 | CMO West 2 | Terra Firma | Budget
46 | 2022-02-01 | CMO West 2 | Terra Firma | Forecast | 0
46 | 2022-02-01 | CMO West 2 | Terra Firma | Actual | 0
46 | 2022-02-01 | CMO West 2 | KLT | Budget
46 | 2022-02-01 | CMO West 2 | KLT | Forecast | 519.45
46 | 2022-02-01 | CMO West 2 | KLT | Actual | 0
46 | 2022-02-01 | CMO West 2 | Forefront | Budget
46 | 2022-02-01 | CMO West 2 | Forefront | Forecast | 0
46 | 2022-02-01 | CMO West 2 | Forefront | Actual | 0
46 | 2022-02-01 | CMO West 2 | DPF | Budget
46 | 2022-02-01 | CMO West 2 | DPF | Forecast | 0
46 | 2022-02-01 | CMO West 2 | DPF | Actual | 0
46 | 2022-02-01 | CMO West 2 | OMJ | Budget
46 | 2022-02-01 | CMO West 2 | OMJ | Forecast | 726.13
46 | 2022-02-01 | CMO West 2 | OMJ | Actual | 0
46 | 2022-02-01 | CMO West 2 | DHB Utilities | Budget
46 | 2022-02-01 | CMO West 2 | DHB Utilities | Forecast | 53
46 | 2022-02-01 | CMO West 2 | DHB Utilities | Actual | 0
46 | 2022-02-01 | CMO West 2 | JDT | Budget
46 | 2022-02-01 | CMO West 2 | JDT | Forecast | 0
46 | 2022-02-01 | CMO West 2 | JDT | Actual | 0
46 | 2022-02-01 | CMO West 2 | MURRAY | Budget
46 | 2022-02-01 | CMO West 2 | MURRAY | Forecast | 0
46 | 2022-02-01 | CMO West 2 | MURRAY | Actual | 0
46 | 2022-02-01 | CMO East 1 | Terra Firma | Budget
46 | 2022-02-01 | CMO East 1 | Terra Firma | Forecast | 152.29
46 | 2022-02-01 | CMO East 1 | Terra Firma | Actual | 0
46 | 2022-02-01 | CMO East 1 | KLT | Budget
46 | 2022-02-01 | CMO East 1 | KLT | Forecast | 0
46 | 2022-02-01 | CMO East 1 | KLT | Actual | 0
46 | 2022-02-01 | CMO East 1 | Forefront | Budget
46 | 2022-02-01 | CMO East 1 | Forefront | Forecast | 93.4
46 | 2022-02-01 | CMO East 1 | Forefront | Actual | 0
46 | 2022-02-01 | CMO East 1 | DPF | Budget
46 | 2022-02-01 | CMO East 1 | DPF | Forecast | 250.76
46 | 2022-02-01 | CMO East 1 | DPF | Actual | 0
46 | 2022-02-01 | CMO East 1 | OMJ | Budget
46 | 2022-02-01 | CMO East 1 | OMJ | Forecast | 0
46 | 2022-02-01 | CMO East 1 | OMJ | Actual | 0
46 | 2022-02-01 | CMO East 1 | DHB Utilities | Budget
46 | 2022-02-01 | CMO East 1 | DHB Utilities | Forecast | 0
46 | 2022-02-01 | CMO East 1 | DHB Utilities | Actual | 0
46 | 2022-02-01 | CMO East 1 | JDT | Budget
46 | 2022-02-01 | CMO East 1 | JDT | Forecast | 0
46 | 2022-02-01 | CMO East 1 | JDT | Actual | 0
46 | 2022-02-01 | CMO East 1 | MURRAY | Budget
46 | 2022-02-01 | CMO East 1 | MURRAY | Forecast | 68.79
46 | 2022-02-01 | CMO East 1 | MURRAY | Actual | 0
46 | 2022-02-01 | CMO East 2 | Terra Firma | Budget
46 | 2022-02-01 | CMO East 2 | Terra Firma | Forecast | 506.99
46 | 2022-02-01 | CMO East 2 | Terra Firma | Actual | 0
46 | 2022-02-01 | CMO East 2 | KLT | Budget
46 | 2022-02-01 | CMO East 2 | KLT | Forecast | 0
46 | 2022-02-01 | CMO East 2 | KLT | Actual | 0
46 | 2022-02-01 | CMO East 2 | Forefront | Budget
46 | 2022-02-01 | CMO East 2 | Forefront | Forecast | 514.74
46 | 2022-02-01 | CMO East 2 | Forefront | Actual | 0
46 | 2022-02-01 | CMO East 2 | DPF | Budget
46 | 2022-02-01 | CMO East 2 | DPF | Forecast | 0
46 | 2022-02-01 | CMO East 2 | DPF | Actual | 0
46 | 2022-02-01 | CMO East 2 | OMJ | Budget
46 | 2022-02-01 | CMO East 2 | OMJ | Forecast | 0
46 | 2022-02-01 | CMO East 2 | OMJ | Actual | 0
46 | 2022-02-01 | CMO East 2 | DHB Utilities | Budget
46 | 2022-02-01 | CMO East 2 | DHB Utilities | Forecast | 0
46 | 2022-02-01 | CMO East 2 | DHB Utilities | Actual | 0
46 | 2022-02-01 | CMO East 2 | JDT | Budget
46 | 2022-02-01 | CMO East 2 | JDT | Forecast | 378.07
46 | 2022-02-01 | CMO East 2 | JDT | Actual | 0
46 | 2022-02-01 | CMO East 2 | MURRAY | Budget
46 | 2022-02-01 | CMO East 2 | MURRAY | Forecast | 0
46 | 2022-02-01 | CMO East 2 | MURRAY | Actual | 0
46 | 2022-02-01 | West | Terra Firma | Budget
46 | 2022-02-01 | West | Terra Firma | Forecast | 0
46 | 2022-02-01 | West | Terra Firma | Actual | 0
46 | 2022-02-01 | West | KLT | Budget
46 | 2022-02-01 | West | KLT | Forecast | 0
46 | 2022-02-01 | West | KLT | Actual | 0
46 | 2022-02-01 | West | Forefront | Budget
46 | 2022-02-01 | West | Forefront | Forecast | 0
46 | 2022-02-01 | West | Forefront | Actual | 0
46 | 2022-02-01 | West | DPF | Budget
46 | 2022-02-01 | West | DPF | Forecast | 0
46 | 2022-02-01 | West | DPF | Actual | 0
46 | 2022-02-01 | West | OMJ | Budget
46 | 2022-02-01 | West | OMJ | Forecast | 0
46 | 2022-02-01 | West | OMJ | Actual | 0
46 | 2022-02-01 | West | DHB Utilities | Budget
46 | 2022-02-01 | West | DHB Utilities | Forecast | 0
46 | 2022-02-01 | West | DHB Utilities | Actual | 0
46 | 2022-02-01 | West | JDT | Budget
46 | 2022-02-01 | West | JDT | Forecast | 0
46 | 2022-02-01 | West | JDT | Actual | 0
46 | 2022-02-01 | West | MURRAY | Budget
46 | 2022-02-01 | West | MURRAY | Forecast | 0
46 | 2022-02-01 | West | MURRAY | Actual | 0
46 | 2022-02-01 | East | Terra Firma | Budget
46 | 2022-02-01 | East | Terra Firma | Forecast | 0
46 | 2022-02-01 | East | Terra Firma | Actual | 0
46 | 2022-02-01 | East | KLT | Budget
46 | 2022-02-01 | East | KLT | Forecast | 0
46 | 2022-02-01 | East | KLT | Actual | 0
46 | 2022-02-01 | East | Forefront | Budget
46 | 2022-02-01 | East | Forefront | Forecast | 0
46 | 2022-02-01 | East | Forefront | Actual | 0
46 | 2022-02-01 | East | DPF | Budget
46 | 2022-02-01 | East | DPF | Forecast | 0
46 | 2022-02-01 | East | DPF | Actual | 0
46 | 2022-02-01 | East | OMJ | Budget
46 | 2022-02-01 | East | OMJ | Forecast | 0
46 | 2022-02-01 | East | OMJ | Actual | 0
46 | 2022-02-01 | East | DHB Utilities | Budget
46 | 2022-02-01 | East | DHB Utilities | Forecast | 0
46 | 2022-02-01 | East | DHB Utilities | Actual | 0
46 | 2022-02-01 | East | JDT | Budget
46 | 2022-02-01 | East | JDT | Forecast | 0
46 | 2022-02-01 | East | JDT | Actual | 0
46 | 2022-02-01 | East | MURRAY | Budget
46 | 2022-02-01 | East | MURRAY | Forecast | 0
46 | 2022-02-01 | East | MURRAY | Actual | 0
46 | 2022-02-01 | Central | Terra Firma | Budget
46 | 2022-02-01 | Central | Terra Firma | Forecast | 0
46 | 2022-02-01 | Central | Terra Firma | Actual | 0
46 | 2022-02-01 | Central | KLT | Budget
46 | 2022-02-01 | Central | KLT | Forecast | 0
46 | 2022-02-01 | Central | KLT | Actual | 0
46 | 2022-02-01 | Central | Forefront | Budget
46 | 2022-02-01 | Central | Forefront | Forecast | 0
46 | 2022-02-01 | Central | Forefront | Actual | 0
46 | 2022-02-01 | Central | DPF | Budget
46 | 2022-02-01 | Central | DPF | Forecast | 0
46 | 2022-02-01 | Central | DPF | Actual | 0
46 | 2022-02-01 | Central | OMJ | Budget
46 | 2022-02-01 | Central | OMJ | Forecast | 0
46 | 2022-02-01 | Central | OMJ | Actual | 0
46 | 2022-02-01 | Central | DHB Utilities | Budget
46 | 2022-02-01 | Central | DHB Utilities | Forecast | 0
46 | 2022-02-01 | Central | DHB Utilities | Actual | 0
46 | 2022-02-01 | Central | JDT | Budget
46 | 2022-02-01 | Central | JDT | Forecast | 0
46 | 2022-02-01 | Central | JDT | Actual | 0
46 | 2022-02-01 | Central | MURRAY | Budget
46 | 2022-02-01 | Central | MURRAY | Forecast | 0
46 | 2022-02-01 | Central | MURRAY | Actual | 0
46 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Budget
46 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Budget
46 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Budget
46 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Budget
46 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | West | DIRECT MOLE | Budget
46 | 2022-02-01 | West | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | West | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | East | DIRECT MOLE | Budget
46 | 2022-02-01 | East | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | East | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | Central | DIRECT MOLE | Budget
46 | 2022-02-01 | Central | DIRECT MOLE | Forecast | 0
46 | 2022-02-01 | Central | DIRECT MOLE | Actual | 0
46 | 2022-02-01 | CMO West 1 | SQS | Budget
46 | 2022-02-01 | CMO West 1 | SQS | Forecast | 42.07
46 | 2022-02-01 | CMO West 1 | SQS | Actual | 0
46 | 2022-02-01 | CMO West 2 | SQS | Budget
46 | 2022-02-01 | CMO West 2 | SQS | Forecast | 307.18
46 | 2022-02-01 | CMO West 2 | SQS | Actual | 0
46 | 2022-02-01 | CMO East 1 | SQS | Budget
46 | 2022-02-01 | CMO East 1 | SQS | Forecast | 0
46 | 2022-02-01 | CMO East 1 | SQS | Actual | 0
46 | 2022-02-01 | CMO East 2 | SQS | Budget
46 | 2022-02-01 | CMO East 2 | SQS | Forecast | 0
46 | 2022-02-01 | CMO East 2 | SQS | Actual | 0
46 | 2022-02-01 | West | SQS | Budget
46 | 2022-02-01 | West | SQS | Forecast | 0
46 | 2022-02-01 | West | SQS | Actual | 0
46 | 2022-02-01 | East | SQS | Budget
46 | 2022-02-01 | East | SQS | Forecast | 0
47 | 2022-02-01 | East | SQS | Actual | 0
47 | 2022-02-01 | Central | SQS | Budget
47 | 2022-02-01 | Central | SQS | Forecast | 0
46 | 2022-02-01 | Central | SQS | Actual | 0
47 | 2022-02-01 | CMO West 1 | Terra Firma | Budget
47 | 2022-02-01 | CMO West 1 | Terra Firma | Forecast | 0
47 | 2022-02-01 | CMO West 1 | Terra Firma | Actual | 0
47 | 2022-02-01 | CMO West 1 | KLT | Budget
47 | 2022-02-01 | CMO West 1 | KLT | Forecast | 102.02
47 | 2022-02-01 | CMO West 1 | KLT | Actual | 0
47 | 2022-02-01 | CMO West 1 | Forefront | Budget
47 | 2022-02-01 | CMO West 1 | Forefront | Forecast | 0
47 | 2022-02-01 | CMO West 1 | Forefront | Actual | 0
47 | 2022-02-01 | CMO West 1 | DPF | Budget
47 | 2022-02-01 | CMO West 1 | DPF | Forecast | 16.01
47 | 2022-02-01 | CMO West 1 | DPF | Actual | 0
47 | 2022-02-01 | CMO West 1 | OMJ | Budget
47 | 2022-02-01 | CMO West 1 | OMJ | Forecast | 0
47 | 2022-02-01 | CMO West 1 | OMJ | Actual | 0
47 | 2022-02-01 | CMO West 1 | DHB Utilities | Budget
47 | 2022-02-01 | CMO West 1 | DHB Utilities | Forecast | 0
47 | 2022-02-01 | CMO West 1 | DHB Utilities | Actual | 0
47 | 2022-02-01 | CMO West 1 | JDT | Budget
47 | 2022-02-01 | CMO West 1 | JDT | Forecast | 0
47 | 2022-02-01 | CMO West 1 | JDT | Actual | 0
47 | 2022-02-01 | CMO West 1 | MURRAY | Budget
47 | 2022-02-01 | CMO West 1 | MURRAY | Forecast | 0
47 | 2022-02-01 | CMO West 1 | MURRAY | Actual | 0
47 | 2022-02-01 | CMO West 2 | Terra Firma | Budget
47 | 2022-02-01 | CMO West 2 | Terra Firma | Forecast | 0
47 | 2022-02-01 | CMO West 2 | Terra Firma | Actual | 0
47 | 2022-02-01 | CMO West 2 | KLT | Budget
47 | 2022-02-01 | CMO West 2 | KLT | Forecast | 519.45
47 | 2022-02-01 | CMO West 2 | KLT | Actual | 0
47 | 2022-02-01 | CMO West 2 | Forefront | Budget
47 | 2022-02-01 | CMO West 2 | Forefront | Forecast | 0
47 | 2022-02-01 | CMO West 2 | Forefront | Actual | 0
47 | 2022-02-01 | CMO West 2 | DPF | Budget
47 | 2022-02-01 | CMO West 2 | DPF | Forecast | 0
47 | 2022-02-01 | CMO West 2 | DPF | Actual | 0
47 | 2022-02-01 | CMO West 2 | OMJ | Budget
47 | 2022-02-01 | CMO West 2 | OMJ | Forecast | 541.99
47 | 2022-02-01 | CMO West 2 | OMJ | Actual | 0
47 | 2022-02-01 | CMO West 2 | DHB Utilities | Budget
47 | 2022-02-01 | CMO West 2 | DHB Utilities | Forecast | 407.48
47 | 2022-02-01 | CMO West 2 | DHB Utilities | Actual | 0
47 | 2022-02-01 | CMO West 2 | JDT | Budget
47 | 2022-02-01 | CMO West 2 | JDT | Forecast | 0
47 | 2022-02-01 | CMO West 2 | JDT | Actual | 0
47 | 2022-02-01 | CMO West 2 | MURRAY | Budget
47 | 2022-02-01 | CMO West 2 | MURRAY | Forecast | 0
47 | 2022-02-01 | CMO West 2 | MURRAY | Actual | 0
47 | 2022-02-01 | CMO East 1 | Terra Firma | Budget
47 | 2022-02-01 | CMO East 1 | Terra Firma | Forecast | 152.29
47 | 2022-02-01 | CMO East 1 | Terra Firma | Actual | 0
47 | 2022-02-01 | CMO East 1 | KLT | Budget
47 | 2022-02-01 | CMO East 1 | KLT | Forecast | 0
47 | 2022-02-01 | CMO East 1 | KLT | Actual | 0
47 | 2022-02-01 | CMO East 1 | Forefront | Budget
47 | 2022-02-01 | CMO East 1 | Forefront | Forecast | 93.4
47 | 2022-02-01 | CMO East 1 | Forefront | Actual | 0
47 | 2022-02-01 | CMO East 1 | DPF | Budget
47 | 2022-02-01 | CMO East 1 | DPF | Forecast | 262.75
47 | 2022-02-01 | CMO East 1 | DPF | Actual | 0
47 | 2022-02-01 | CMO East 1 | OMJ | Budget
47 | 2022-02-01 | CMO East 1 | OMJ | Forecast | 0
47 | 2022-02-01 | CMO East 1 | OMJ | Actual | 0
47 | 2022-02-01 | CMO East 1 | DHB Utilities | Budget
47 | 2022-02-01 | CMO East 1 | DHB Utilities | Forecast | 0
47 | 2022-02-01 | CMO East 1 | DHB Utilities | Actual | 0
47 | 2022-02-01 | CMO East 1 | JDT | Budget
47 | 2022-02-01 | CMO East 1 | JDT | Forecast | 0
47 | 2022-02-01 | CMO East 1 | JDT | Actual | 0
47 | 2022-02-01 | CMO East 1 | MURRAY | Budget
47 | 2022-02-01 | CMO East 1 | MURRAY | Forecast | 0
47 | 2022-02-01 | CMO East 1 | MURRAY | Actual | 0
47 | 2022-02-01 | CMO East 2 | Terra Firma | Budget
47 | 2022-02-01 | CMO East 2 | Terra Firma | Forecast | 506.99
47 | 2022-02-01 | CMO East 2 | Terra Firma | Actual | 0
47 | 2022-02-01 | CMO East 2 | KLT | Budget
47 | 2022-02-01 | CMO East 2 | KLT | Forecast | 0
47 | 2022-02-01 | CMO East 2 | KLT | Actual | 0
47 | 2022-02-01 | CMO East 2 | Forefront | Budget
47 | 2022-02-01 | CMO East 2 | Forefront | Forecast | 495.29
47 | 2022-02-01 | CMO East 2 | Forefront | Actual | 0
47 | 2022-02-01 | CMO East 2 | DPF | Budget
47 | 2022-02-01 | CMO East 2 | DPF | Forecast | 0
47 | 2022-02-01 | CMO East 2 | DPF | Actual | 0
47 | 2022-02-01 | CMO East 2 | OMJ | Budget
47 | 2022-02-01 | CMO East 2 | OMJ | Forecast | 0
47 | 2022-02-01 | CMO East 2 | OMJ | Actual | 0
47 | 2022-02-01 | CMO East 2 | DHB Utilities | Budget
47 | 2022-02-01 | CMO East 2 | DHB Utilities | Forecast | 0
47 | 2022-02-01 | CMO East 2 | DHB Utilities | Actual | 0
47 | 2022-02-01 | CMO East 2 | JDT | Budget
47 | 2022-02-01 | CMO East 2 | JDT | Forecast | 384.25
47 | 2022-02-01 | CMO East 2 | JDT | Actual | 0
47 | 2022-02-01 | CMO East 2 | MURRAY | Budget
47 | 2022-02-01 | CMO East 2 | MURRAY | Forecast | 0
47 | 2022-02-01 | CMO East 2 | MURRAY | Actual | 0
47 | 2022-02-01 | West | Terra Firma | Budget
47 | 2022-02-01 | West | Terra Firma | Forecast | 0
47 | 2022-02-01 | West | Terra Firma | Actual | 0
47 | 2022-02-01 | West | KLT | Budget
47 | 2022-02-01 | West | KLT | Forecast | 0
47 | 2022-02-01 | West | KLT | Actual | 0
47 | 2022-02-01 | West | Forefront | Budget
47 | 2022-02-01 | West | Forefront | Forecast | 0
47 | 2022-02-01 | West | Forefront | Actual | 0
47 | 2022-02-01 | West | DPF | Budget
47 | 2022-02-01 | West | DPF | Forecast | 0
47 | 2022-02-01 | West | DPF | Actual | 0
47 | 2022-02-01 | West | OMJ | Budget
47 | 2022-02-01 | West | OMJ | Forecast | 0
47 | 2022-02-01 | West | OMJ | Actual | 0
47 | 2022-02-01 | West | DHB Utilities | Budget
47 | 2022-02-01 | West | DHB Utilities | Forecast | 0
47 | 2022-02-01 | West | DHB Utilities | Actual | 0
47 | 2022-02-01 | West | JDT | Budget
47 | 2022-02-01 | West | JDT | Forecast | 0
47 | 2022-02-01 | West | JDT | Actual | 0
47 | 2022-02-01 | West | MURRAY | Budget
47 | 2022-02-01 | West | MURRAY | Forecast | 0
47 | 2022-02-01 | West | MURRAY | Actual | 0
47 | 2022-02-01 | East | Terra Firma | Budget
47 | 2022-02-01 | East | Terra Firma | Forecast | 0
47 | 2022-02-01 | East | Terra Firma | Actual | 0
47 | 2022-02-01 | East | KLT | Budget
47 | 2022-02-01 | East | KLT | Forecast | 0
47 | 2022-02-01 | East | KLT | Actual | 0
47 | 2022-02-01 | East | Forefront | Budget
47 | 2022-02-01 | East | Forefront | Forecast | 0
47 | 2022-02-01 | East | Forefront | Actual | 0
47 | 2022-02-01 | East | DPF | Budget
47 | 2022-02-01 | East | DPF | Forecast | 0
47 | 2022-02-01 | East | DPF | Actual | 0
47 | 2022-02-01 | East | OMJ | Budget
47 | 2022-02-01 | East | OMJ | Forecast | 0
47 | 2022-02-01 | East | OMJ | Actual | 0
47 | 2022-02-01 | East | DHB Utilities | Budget
47 | 2022-02-01 | East | DHB Utilities | Forecast | 0
47 | 2022-02-01 | East | DHB Utilities | Actual | 0
47 | 2022-02-01 | East | JDT | Budget
47 | 2022-02-01 | East | JDT | Forecast | 0
47 | 2022-02-01 | East | JDT | Actual | 0
47 | 2022-02-01 | East | MURRAY | Budget
47 | 2022-02-01 | East | MURRAY | Forecast | 0
47 | 2022-02-01 | East | MURRAY | Actual | 0
47 | 2022-02-01 | Central | Terra Firma | Budget
47 | 2022-02-01 | Central | Terra Firma | Forecast | 0
47 | 2022-02-01 | Central | Terra Firma | Actual | 0
47 | 2022-02-01 | Central | KLT | Budget
47 | 2022-02-01 | Central | KLT | Forecast | 0
47 | 2022-02-01 | Central | KLT | Actual | 0
47 | 2022-02-01 | Central | Forefront | Budget
47 | 2022-02-01 | Central | Forefront | Forecast | 0
47 | 2022-02-01 | Central | Forefront | Actual | 0
47 | 2022-02-01 | Central | DPF | Budget
47 | 2022-02-01 | Central | DPF | Forecast | 0
47 | 2022-02-01 | Central | DPF | Actual | 0
47 | 2022-02-01 | Central | OMJ | Budget
47 | 2022-02-01 | Central | OMJ | Forecast | 0
47 | 2022-02-01 | Central | OMJ | Actual | 0
47 | 2022-02-01 | Central | DHB Utilities | Budget
47 | 2022-02-01 | Central | DHB Utilities | Forecast | 0
47 | 2022-02-01 | Central | DHB Utilities | Actual | 0
47 | 2022-02-01 | Central | JDT | Budget
47 | 2022-02-01 | Central | JDT | Forecast | 0
47 | 2022-02-01 | Central | JDT | Actual | 0
47 | 2022-02-01 | Central | MURRAY | Budget
47 | 2022-02-01 | Central | MURRAY | Forecast | 0
47 | 2022-02-01 | Central | MURRAY | Actual | 0
47 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Budget
47 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Budget
47 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Budget
47 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Budget
47 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | West | DIRECT MOLE | Budget
47 | 2022-02-01 | West | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | West | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | East | DIRECT MOLE | Budget
47 | 2022-02-01 | East | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | East | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | Central | DIRECT MOLE | Budget
47 | 2022-02-01 | Central | DIRECT MOLE | Forecast | 0
47 | 2022-02-01 | Central | DIRECT MOLE | Actual | 0
47 | 2022-02-01 | CMO West 1 | SQS | Budget
47 | 2022-02-01 | CMO West 1 | SQS | Forecast | 42.07
47 | 2022-02-01 | CMO West 1 | SQS | Actual | 0
47 | 2022-02-01 | CMO West 2 | SQS | Budget
47 | 2022-02-01 | CMO West 2 | SQS | Forecast | 194.5
47 | 2022-02-01 | CMO West 2 | SQS | Actual | 0
47 | 2022-02-01 | CMO East 1 | SQS | Budget
47 | 2022-02-01 | CMO East 1 | SQS | Forecast | 0
47 | 2022-02-01 | CMO East 1 | SQS | Actual | 0
47 | 2022-02-01 | CMO East 2 | SQS | Budget
47 | 2022-02-01 | CMO East 2 | SQS | Forecast | 0
47 | 2022-02-01 | CMO East 2 | SQS | Actual | 0
47 | 2022-02-01 | West | SQS | Budget
47 | 2022-02-01 | West | SQS | Forecast | 0
47 | 2022-02-01 | West | SQS | Actual | 0
47 | 2022-02-01 | East | SQS | Budget
47 | 2022-02-01 | East | SQS | Forecast | 0
48 | 2022-02-01 | East | SQS | Actual | 0
48 | 2022-02-01 | Central | SQS | Budget
48 | 2022-02-01 | Central | SQS | Forecast | 0
47 | 2022-02-01 | Central | SQS | Actual | 0
48 | 2022-02-01 | CMO West 1 | Terra Firma | Budget
48 | 2022-02-01 | CMO West 1 | Terra Firma | Forecast | 0
48 | 2022-02-01 | CMO West 1 | Terra Firma | Actual | 0
48 | 2022-02-01 | CMO West 1 | KLT | Budget
48 | 2022-02-01 | CMO West 1 | KLT | Forecast | 178.94
48 | 2022-02-01 | CMO West 1 | KLT | Actual | 0
48 | 2022-02-01 | CMO West 1 | Forefront | Budget
48 | 2022-02-01 | CMO West 1 | Forefront | Forecast | 0
48 | 2022-02-01 | CMO West 1 | Forefront | Actual | 0
48 | 2022-02-01 | CMO West 1 | DPF | Budget
48 | 2022-02-01 | CMO West 1 | DPF | Forecast | 0
48 | 2022-02-01 | CMO West 1 | DPF | Actual | 0
48 | 2022-02-01 | CMO West 1 | OMJ | Budget
48 | 2022-02-01 | CMO West 1 | OMJ | Forecast | 0
48 | 2022-02-01 | CMO West 1 | OMJ | Actual | 0
48 | 2022-02-01 | CMO West 1 | DHB Utilities | Budget
48 | 2022-02-01 | CMO West 1 | DHB Utilities | Forecast | 0
48 | 2022-02-01 | CMO West 1 | DHB Utilities | Actual | 0
48 | 2022-02-01 | CMO West 1 | JDT | Budget
48 | 2022-02-01 | CMO West 1 | JDT | Forecast | 0
48 | 2022-02-01 | CMO West 1 | JDT | Actual | 0
48 | 2022-02-01 | CMO West 1 | MURRAY | Budget
48 | 2022-02-01 | CMO West 1 | MURRAY | Forecast | 0
48 | 2022-02-01 | CMO West 1 | MURRAY | Actual | 0
48 | 2022-02-01 | CMO West 2 | Terra Firma | Budget
48 | 2022-02-01 | CMO West 2 | Terra Firma | Forecast | 0
48 | 2022-02-01 | CMO West 2 | Terra Firma | Actual | 0
48 | 2022-02-01 | CMO West 2 | KLT | Budget
48 | 2022-02-01 | CMO West 2 | KLT | Forecast | 501.7
48 | 2022-02-01 | CMO West 2 | KLT | Actual | 0
48 | 2022-02-01 | CMO West 2 | Forefront | Budget
48 | 2022-02-01 | CMO West 2 | Forefront | Forecast | 0
48 | 2022-02-01 | CMO West 2 | Forefront | Actual | 0
48 | 2022-02-01 | CMO West 2 | DPF | Budget
48 | 2022-02-01 | CMO West 2 | DPF | Forecast | 0
48 | 2022-02-01 | CMO West 2 | DPF | Actual | 0
48 | 2022-02-01 | CMO West 2 | OMJ | Budget
48 | 2022-02-01 | CMO West 2 | OMJ | Forecast | 514.06
48 | 2022-02-01 | CMO West 2 | OMJ | Actual | 0
48 | 2022-02-01 | CMO West 2 | DHB Utilities | Budget
48 | 2022-02-01 | CMO West 2 | DHB Utilities | Forecast | 269.14
48 | 2022-02-01 | CMO West 2 | DHB Utilities | Actual | 0
48 | 2022-02-01 | CMO West 2 | JDT | Budget
48 | 2022-02-01 | CMO West 2 | JDT | Forecast | 0
48 | 2022-02-01 | CMO West 2 | JDT | Actual | 0
48 | 2022-02-01 | CMO West 2 | MURRAY | Budget
48 | 2022-02-01 | CMO West 2 | MURRAY | Forecast | 0
48 | 2022-02-01 | CMO West 2 | MURRAY | Actual | 0
48 | 2022-02-01 | CMO East 1 | Terra Firma | Budget
48 | 2022-02-01 | CMO East 1 | Terra Firma | Forecast | 97.43
48 | 2022-02-01 | CMO East 1 | Terra Firma | Actual | 0
48 | 2022-02-01 | CMO East 1 | KLT | Budget
48 | 2022-02-01 | CMO East 1 | KLT | Forecast | 0
48 | 2022-02-01 | CMO East 1 | KLT | Actual | 0
48 | 2022-02-01 | CMO East 1 | Forefront | Budget
48 | 2022-02-01 | CMO East 1 | Forefront | Forecast | 213.85
48 | 2022-02-01 | CMO East 1 | Forefront | Actual | 0
48 | 2022-02-01 | CMO East 1 | DPF | Budget
48 | 2022-02-01 | CMO East 1 | DPF | Forecast | 262.75
48 | 2022-02-01 | CMO East 1 | DPF | Actual | 0
48 | 2022-02-01 | CMO East 1 | OMJ | Budget
48 | 2022-02-01 | CMO East 1 | OMJ | Forecast | 0
48 | 2022-02-01 | CMO East 1 | OMJ | Actual | 0
48 | 2022-02-01 | CMO East 1 | DHB Utilities | Budget
48 | 2022-02-01 | CMO East 1 | DHB Utilities | Forecast | 0
48 | 2022-02-01 | CMO East 1 | DHB Utilities | Actual | 0
48 | 2022-02-01 | CMO East 1 | JDT | Budget
48 | 2022-02-01 | CMO East 1 | JDT | Forecast | 0
48 | 2022-02-01 | CMO East 1 | JDT | Actual | 0
48 | 2022-02-01 | CMO East 1 | MURRAY | Budget
48 | 2022-02-01 | CMO East 1 | MURRAY | Forecast | 0
48 | 2022-02-01 | CMO East 1 | MURRAY | Actual | 0
48 | 2022-02-01 | CMO East 2 | Terra Firma | Budget
48 | 2022-02-01 | CMO East 2 | Terra Firma | Forecast | 506.99
48 | 2022-02-01 | CMO East 2 | Terra Firma | Actual | 0
48 | 2022-02-01 | CMO East 2 | KLT | Budget
48 | 2022-02-01 | CMO East 2 | KLT | Forecast | 0
48 | 2022-02-01 | CMO East 2 | KLT | Actual | 0
48 | 2022-02-01 | CMO East 2 | Forefront | Budget
48 | 2022-02-01 | CMO East 2 | Forefront | Forecast | 628.38
48 | 2022-02-01 | CMO East 2 | Forefront | Actual | 0
48 | 2022-02-01 | CMO East 2 | DPF | Budget
48 | 2022-02-01 | CMO East 2 | DPF | Forecast | 0
48 | 2022-02-01 | CMO East 2 | DPF | Actual | 0
48 | 2022-02-01 | CMO East 2 | OMJ | Budget
48 | 2022-02-01 | CMO East 2 | OMJ | Forecast | 0
48 | 2022-02-01 | CMO East 2 | OMJ | Actual | 0
48 | 2022-02-01 | CMO East 2 | DHB Utilities | Budget
48 | 2022-02-01 | CMO East 2 | DHB Utilities | Forecast | 0
48 | 2022-02-01 | CMO East 2 | DHB Utilities | Actual | 0
48 | 2022-02-01 | CMO East 2 | JDT | Budget
48 | 2022-02-01 | CMO East 2 | JDT | Forecast | 269.35
48 | 2022-02-01 | CMO East 2 | JDT | Actual | 0
48 | 2022-02-01 | CMO East 2 | MURRAY | Budget
48 | 2022-02-01 | CMO East 2 | MURRAY | Forecast | 0
48 | 2022-02-01 | CMO East 2 | MURRAY | Actual | 0
48 | 2022-02-01 | West | Terra Firma | Budget
48 | 2022-02-01 | West | Terra Firma | Forecast | 0
48 | 2022-02-01 | West | Terra Firma | Actual | 0
48 | 2022-02-01 | West | KLT | Budget
48 | 2022-02-01 | West | KLT | Forecast | 0
48 | 2022-02-01 | West | KLT | Actual | 0
48 | 2022-02-01 | West | Forefront | Budget
48 | 2022-02-01 | West | Forefront | Forecast | 0
48 | 2022-02-01 | West | Forefront | Actual | 0
48 | 2022-02-01 | West | DPF | Budget
48 | 2022-02-01 | West | DPF | Forecast | 0
48 | 2022-02-01 | West | DPF | Actual | 0
48 | 2022-02-01 | West | OMJ | Budget
48 | 2022-02-01 | West | OMJ | Forecast | 0
48 | 2022-02-01 | West | OMJ | Actual | 0
48 | 2022-02-01 | West | DHB Utilities | Budget
48 | 2022-02-01 | West | DHB Utilities | Forecast | 0
48 | 2022-02-01 | West | DHB Utilities | Actual | 0
48 | 2022-02-01 | West | JDT | Budget
48 | 2022-02-01 | West | JDT | Forecast | 0
48 | 2022-02-01 | West | JDT | Actual | 0
48 | 2022-02-01 | West | MURRAY | Budget
48 | 2022-02-01 | West | MURRAY | Forecast | 0
48 | 2022-02-01 | West | MURRAY | Actual | 0
48 | 2022-02-01 | East | Terra Firma | Budget
48 | 2022-02-01 | East | Terra Firma | Forecast | 0
48 | 2022-02-01 | East | Terra Firma | Actual | 0
48 | 2022-02-01 | East | KLT | Budget
48 | 2022-02-01 | East | KLT | Forecast | 0
48 | 2022-02-01 | East | KLT | Actual | 0
48 | 2022-02-01 | East | Forefront | Budget
48 | 2022-02-01 | East | Forefront | Forecast | 0
48 | 2022-02-01 | East | Forefront | Actual | 0
48 | 2022-02-01 | East | DPF | Budget
48 | 2022-02-01 | East | DPF | Forecast | 0
48 | 2022-02-01 | East | DPF | Actual | 0
48 | 2022-02-01 | East | OMJ | Budget
48 | 2022-02-01 | East | OMJ | Forecast | 0
48 | 2022-02-01 | East | OMJ | Actual | 0
48 | 2022-02-01 | East | DHB Utilities | Budget
48 | 2022-02-01 | East | DHB Utilities | Forecast | 0
48 | 2022-02-01 | East | DHB Utilities | Actual | 0
48 | 2022-02-01 | East | JDT | Budget
48 | 2022-02-01 | East | JDT | Forecast | 0
48 | 2022-02-01 | East | JDT | Actual | 0
48 | 2022-02-01 | East | MURRAY | Budget
48 | 2022-02-01 | East | MURRAY | Forecast | 0
48 | 2022-02-01 | East | MURRAY | Actual | 0
48 | 2022-02-01 | Central | Terra Firma | Budget
48 | 2022-02-01 | Central | Terra Firma | Forecast | 0
48 | 2022-02-01 | Central | Terra Firma | Actual | 0
48 | 2022-02-01 | Central | KLT | Budget
48 | 2022-02-01 | Central | KLT | Forecast | 0
48 | 2022-02-01 | Central | KLT | Actual | 0
48 | 2022-02-01 | Central | Forefront | Budget
48 | 2022-02-01 | Central | Forefront | Forecast | 0
48 | 2022-02-01 | Central | Forefront | Actual | 0
48 | 2022-02-01 | Central | DPF | Budget
48 | 2022-02-01 | Central | DPF | Forecast | 0
48 | 2022-02-01 | Central | DPF | Actual | 0
48 | 2022-02-01 | Central | OMJ | Budget
48 | 2022-02-01 | Central | OMJ | Forecast | 0
48 | 2022-02-01 | Central | OMJ | Actual | 0
48 | 2022-02-01 | Central | DHB Utilities | Budget
48 | 2022-02-01 | Central | DHB Utilities | Forecast | 0
48 | 2022-02-01 | Central | DHB Utilities | Actual | 0
48 | 2022-02-01 | Central | JDT | Budget
48 | 2022-02-01 | Central | JDT | Forecast | 0
48 | 2022-02-01 | Central | JDT | Actual | 0
48 | 2022-02-01 | Central | MURRAY | Budget
48 | 2022-02-01 | Central | MURRAY | Forecast | 0
48 | 2022-02-01 | Central | MURRAY | Actual | 0
48 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Budget
48 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | CMO West 1 | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Budget
48 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | CMO West 2 | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Budget
48 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | CMO East 1 | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Budget
48 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | CMO East 2 | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | West | DIRECT MOLE | Budget
48 | 2022-02-01 | West | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | West | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | East | DIRECT MOLE | Budget
48 | 2022-02-01 | East | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | East | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | Central | DIRECT MOLE | Budget
48 | 2022-02-01 | Central | DIRECT MOLE | Forecast | 0
48 | 2022-02-01 | Central | DIRECT MOLE | Actual | 0
48 | 2022-02-01 | CMO West 1 | SQS | Budget
48 | 2022-02-01 | CMO West 1 | SQS | Forecast | 42.07
48 | 2022-02-01 | CMO West 1 | SQS | Actual | 0
48 | 2022-02-01 | CMO West 2 | SQS | Budget
48 | 2022-02-01 | CMO West 2 | SQS | Forecast | 103.62
48 | 2022-02-01 | CMO West 2 | SQS | Actual | 0
48 | 2022-02-01 | CMO East 1 | SQS | Budget
48 | 2022-02-01 | CMO East 1 | SQS | Forecast | 0
48 | 2022-02-01 | CMO East 1 | SQS | Actual | 0
48 | 2022-02-01 | CMO East 2 | SQS | Budget
48 | 2022-02-01 | CMO East 2 | SQS | Forecast | 0
48 | 2022-02-01 | CMO East 2 | SQS | Actual | 0
48 | 2022-02-01 | West | SQS | Budget
48 | 2022-02-01 | West | SQS | Forecast | 0
48 | 2022-02-01 | West | SQS | Actual | 0
48 | 2022-02-01 | East | SQS | Budget
48 | 2022-02-01 | East | SQS | Forecast | 0
48 | 2022-02-01 | East | SQS | Actual | 0
48 | 2022-02-01 | Central | SQS | Budget
48 | 2022-02-01 | Central | SQS | Forecast | 0
48 | 2022-02-01 | Central | SQS | Actual | 0
49 | 2022-03-01 | CMO West 1 | Terra Firma | Budget
49 | 2022-03-01 | CMO West 1 | Terra Firma | Forecast | 0
49 | 2022-03-01 | CMO West 1 | Terra Firma | Actual | 0
49 | 2022-03-01 | CMO West 1 | KLT | Budget
49 | 2022-03-01 | CMO West 1 | KLT | Forecast | 178.94
49 | 2022-03-01 | CMO West 1 | KLT | Actual | 0
49 | 2022-03-01 | CMO West 1 | Forefront | Budget
49 | 2022-03-01 | CMO West 1 | Forefront | Forecast | 0
49 | 2022-03-01 | CMO West 1 | Forefront | Actual | 0
49 | 2022-03-01 | CMO West 1 | DPF | Budget
49 | 2022-03-01 | CMO West 1 | DPF | Forecast | 0
49 | 2022-03-01 | CMO West 1 | DPF | Actual | 0
49 | 2022-03-01 | CMO West 1 | OMJ | Budget
49 | 2022-03-01 | CMO West 1 | OMJ | Forecast | 0
49 | 2022-03-01 | CMO West 1 | OMJ | Actual | 0
49 | 2022-03-01 | CMO West 1 | DHB Utilities | Budget
49 | 2022-03-01 | CMO West 1 | DHB Utilities | Forecast | 0
49 | 2022-03-01 | CMO West 1 | DHB Utilities | Actual | 0
49 | 2022-03-01 | CMO West 1 | JDT | Budget
49 | 2022-03-01 | CMO West 1 | JDT | Forecast | 0
49 | 2022-03-01 | CMO West 1 | JDT | Actual | 0
49 | 2022-03-01 | CMO West 1 | MURRAY | Budget
49 | 2022-03-01 | CMO West 1 | MURRAY | Forecast | 0
49 | 2022-03-01 | CMO West 1 | MURRAY | Actual | 0
49 | 2022-03-01 | CMO West 2 | Terra Firma | Budget
49 | 2022-03-01 | CMO West 2 | Terra Firma | Forecast | 0
49 | 2022-03-01 | CMO West 2 | Terra Firma | Actual | 0
49 | 2022-03-01 | CMO West 2 | KLT | Budget
49 | 2022-03-01 | CMO West 2 | KLT | Forecast | 402.64
49 | 2022-03-01 | CMO West 2 | KLT | Actual | 0
49 | 2022-03-01 | CMO West 2 | Forefront | Budget
49 | 2022-03-01 | CMO West 2 | Forefront | Forecast | 0
49 | 2022-03-01 | CMO West 2 | Forefront | Actual | 0
49 | 2022-03-01 | CMO West 2 | DPF | Budget
49 | 2022-03-01 | CMO West 2 | DPF | Forecast | 0
49 | 2022-03-01 | CMO West 2 | DPF | Actual | 0
49 | 2022-03-01 | CMO West 2 | OMJ | Budget
49 | 2022-03-01 | CMO West 2 | OMJ | Forecast | 594.92
49 | 2022-03-01 | CMO West 2 | OMJ | Actual | 0
49 | 2022-03-01 | CMO West 2 | DHB Utilities | Budget
49 | 2022-03-01 | CMO West 2 | DHB Utilities | Forecast | 292.39
49 | 2022-03-01 | CMO West 2 | DHB Utilities | Actual | 0
49 | 2022-03-01 | CMO West 2 | JDT | Budget
49 | 2022-03-01 | CMO West 2 | JDT | Forecast | 0
49 | 2022-03-01 | CMO West 2 | JDT | Actual | 0
49 | 2022-03-01 | CMO West 2 | MURRAY | Budget
49 | 2022-03-01 | CMO West 2 | MURRAY | Forecast | 0
49 | 2022-03-01 | CMO West 2 | MURRAY | Actual | 0
49 | 2022-03-01 | CMO East 1 | Terra Firma | Budget
49 | 2022-03-01 | CMO East 1 | Terra Firma | Forecast | 97.43
49 | 2022-03-01 | CMO East 1 | Terra Firma | Actual | 0
49 | 2022-03-01 | CMO East 1 | KLT | Budget
49 | 2022-03-01 | CMO East 1 | KLT | Forecast | 0
49 | 2022-03-01 | CMO East 1 | KLT | Actual | 0
49 | 2022-03-01 | CMO East 1 | Forefront | Budget
49 | 2022-03-01 | CMO East 1 | Forefront | Forecast | 120.45
49 | 2022-03-01 | CMO East 1 | Forefront | Actual | 0
49 | 2022-03-01 | CMO East 1 | DPF | Budget
49 | 2022-03-01 | CMO East 1 | DPF | Forecast | 262.75
49 | 2022-03-01 | CMO East 1 | DPF | Actual | 0
49 | 2022-03-01 | CMO East 1 | OMJ | Budget
49 | 2022-03-01 | CMO East 1 | OMJ | Forecast | 0
49 | 2022-03-01 | CMO East 1 | OMJ | Actual | 0
49 | 2022-03-01 | CMO East 1 | DHB Utilities | Budget
49 | 2022-03-01 | CMO East 1 | DHB Utilities | Forecast | 0
49 | 2022-03-01 | CMO East 1 | DHB Utilities | Actual | 0
49 | 2022-03-01 | CMO East 1 | JDT | Budget
49 | 2022-03-01 | CMO East 1 | JDT | Forecast | 0
49 | 2022-03-01 | CMO East 1 | JDT | Actual | 0
49 | 2022-03-01 | CMO East 1 | MURRAY | Budget
49 | 2022-03-01 | CMO East 1 | MURRAY | Forecast | 0
49 | 2022-03-01 | CMO East 1 | MURRAY | Actual | 0
49 | 2022-03-01 | CMO East 2 | Terra Firma | Budget
49 | 2022-03-01 | CMO East 2 | Terra Firma | Forecast | 437.73
49 | 2022-03-01 | CMO East 2 | Terra Firma | Actual | 0
49 | 2022-03-01 | CMO East 2 | KLT | Budget
49 | 2022-03-01 | CMO East 2 | KLT | Forecast | 0
49 | 2022-03-01 | CMO East 2 | KLT | Actual | 0
49 | 2022-03-01 | CMO East 2 | Forefront | Budget
49 | 2022-03-01 | CMO East 2 | Forefront | Forecast | 432.93
49 | 2022-03-01 | CMO East 2 | Forefront | Actual | 0
49 | 2022-03-01 | CMO East 2 | DPF | Budget
49 | 2022-03-01 | CMO East 2 | DPF | Forecast | 0
49 | 2022-03-01 | CMO East 2 | DPF | Actual | 0
49 | 2022-03-01 | CMO East 2 | OMJ | Budget
49 | 2022-03-01 | CMO East 2 | OMJ | Forecast | 0
49 | 2022-03-01 | CMO East 2 | OMJ | Actual | 0
49 | 2022-03-01 | CMO East 2 | DHB Utilities | Budget
49 | 2022-03-01 | CMO East 2 | DHB Utilities | Forecast | 0
49 | 2022-03-01 | CMO East 2 | DHB Utilities | Actual | 0
49 | 2022-03-01 | CMO East 2 | JDT | Budget
49 | 2022-03-01 | CMO East 2 | JDT | Forecast | 269.35
49 | 2022-03-01 | CMO East 2 | JDT | Actual | 0
49 | 2022-03-01 | CMO East 2 | MURRAY | Budget
49 | 2022-03-01 | CMO East 2 | MURRAY | Forecast | 0
49 | 2022-03-01 | CMO East 2 | MURRAY | Actual | 0
49 | 2022-03-01 | West | Terra Firma | Budget
49 | 2022-03-01 | West | Terra Firma | Forecast | 0
49 | 2022-03-01 | West | Terra Firma | Actual | 0
49 | 2022-03-01 | West | KLT | Budget
49 | 2022-03-01 | West | KLT | Forecast | 0
49 | 2022-03-01 | West | KLT | Actual | 0
49 | 2022-03-01 | West | Forefront | Budget
49 | 2022-03-01 | West | Forefront | Forecast | 0
49 | 2022-03-01 | West | Forefront | Actual | 0
49 | 2022-03-01 | West | DPF | Budget
49 | 2022-03-01 | West | DPF | Forecast | 0
49 | 2022-03-01 | West | DPF | Actual | 0
49 | 2022-03-01 | West | OMJ | Budget
49 | 2022-03-01 | West | OMJ | Forecast | 0
49 | 2022-03-01 | West | OMJ | Actual | 0
49 | 2022-03-01 | West | DHB Utilities | Budget
49 | 2022-03-01 | West | DHB Utilities | Forecast | 0
49 | 2022-03-01 | West | DHB Utilities | Actual | 0
49 | 2022-03-01 | West | JDT | Budget
49 | 2022-03-01 | West | JDT | Forecast | 0
49 | 2022-03-01 | West | JDT | Actual | 0
49 | 2022-03-01 | West | MURRAY | Budget
49 | 2022-03-01 | West | MURRAY | Forecast | 0
49 | 2022-03-01 | West | MURRAY | Actual | 0
49 | 2022-03-01 | East | Terra Firma | Budget
49 | 2022-03-01 | East | Terra Firma | Forecast | 0
49 | 2022-03-01 | East | Terra Firma | Actual | 0
49 | 2022-03-01 | East | KLT | Budget
49 | 2022-03-01 | East | KLT | Forecast | 0
49 | 2022-03-01 | East | KLT | Actual | 0
49 | 2022-03-01 | East | Forefront | Budget
49 | 2022-03-01 | East | Forefront | Forecast | 0
49 | 2022-03-01 | East | Forefront | Actual | 0
49 | 2022-03-01 | East | DPF | Budget
49 | 2022-03-01 | East | DPF | Forecast | 0
49 | 2022-03-01 | East | DPF | Actual | 0
49 | 2022-03-01 | East | OMJ | Budget
49 | 2022-03-01 | East | OMJ | Forecast | 0
49 | 2022-03-01 | East | OMJ | Actual | 0
49 | 2022-03-01 | East | DHB Utilities | Budget
49 | 2022-03-01 | East | DHB Utilities | Forecast | 0
49 | 2022-03-01 | East | DHB Utilities | Actual | 0
49 | 2022-03-01 | East | JDT | Budget
49 | 2022-03-01 | East | JDT | Forecast | 0
49 | 2022-03-01 | East | JDT | Actual | 0
49 | 2022-03-01 | East | MURRAY | Budget
49 | 2022-03-01 | East | MURRAY | Forecast | 0
49 | 2022-03-01 | East | MURRAY | Actual | 0
49 | 2022-03-01 | Central | Terra Firma | Budget
49 | 2022-03-01 | Central | Terra Firma | Forecast | 0
49 | 2022-03-01 | Central | Terra Firma | Actual | 0
49 | 2022-03-01 | Central | KLT | Budget
49 | 2022-03-01 | Central | KLT | Forecast | 0
49 | 2022-03-01 | Central | KLT | Actual | 0
49 | 2022-03-01 | Central | Forefront | Budget
49 | 2022-03-01 | Central | Forefront | Forecast | 0
49 | 2022-03-01 | Central | Forefront | Actual | 0
49 | 2022-03-01 | Central | DPF | Budget
49 | 2022-03-01 | Central | DPF | Forecast | 0
49 | 2022-03-01 | Central | DPF | Actual | 0
49 | 2022-03-01 | Central | OMJ | Budget
49 | 2022-03-01 | Central | OMJ | Forecast | 0
49 | 2022-03-01 | Central | OMJ | Actual | 0
49 | 2022-03-01 | Central | DHB Utilities | Budget
49 | 2022-03-01 | Central | DHB Utilities | Forecast | 0
49 | 2022-03-01 | Central | DHB Utilities | Actual | 0
49 | 2022-03-01 | Central | JDT | Budget
49 | 2022-03-01 | Central | JDT | Forecast | 0
49 | 2022-03-01 | Central | JDT | Actual | 0
49 | 2022-03-01 | Central | MURRAY | Budget
49 | 2022-03-01 | Central | MURRAY | Forecast | 0
49 | 2022-03-01 | Central | MURRAY | Actual | 0
49 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Budget
49 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Budget
49 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Budget
49 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Budget
49 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | West | DIRECT MOLE | Budget
49 | 2022-03-01 | West | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | West | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | East | DIRECT MOLE | Budget
49 | 2022-03-01 | East | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | East | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | Central | DIRECT MOLE | Budget
49 | 2022-03-01 | Central | DIRECT MOLE | Forecast | 0
49 | 2022-03-01 | Central | DIRECT MOLE | Actual | 0
49 | 2022-03-01 | CMO West 1 | SQS | Budget
49 | 2022-03-01 | CMO West 1 | SQS | Forecast | 42.07
49 | 2022-03-01 | CMO West 1 | SQS | Actual | 0
49 | 2022-03-01 | CMO West 2 | SQS | Budget
49 | 2022-03-01 | CMO West 2 | SQS | Forecast | 177.63
49 | 2022-03-01 | CMO West 2 | SQS | Actual | 0
49 | 2022-03-01 | CMO East 1 | SQS | Budget
49 | 2022-03-01 | CMO East 1 | SQS | Forecast | 0
49 | 2022-03-01 | CMO East 1 | SQS | Actual | 0
49 | 2022-03-01 | CMO East 2 | SQS | Budget
49 | 2022-03-01 | CMO East 2 | SQS | Forecast | 0
49 | 2022-03-01 | CMO East 2 | SQS | Actual | 0
49 | 2022-03-01 | West | SQS | Budget
49 | 2022-03-01 | West | SQS | Forecast | 0
49 | 2022-03-01 | West | SQS | Actual | 0
49 | 2022-03-01 | East | SQS | Budget
49 | 2022-03-01 | East | SQS | Forecast | 0
49 | 2022-03-01 | East | SQS | Actual | 0
49 | 2022-03-01 | Central | SQS | Budget
49 | 2022-03-01 | Central | SQS | Forecast | 0
49 | 2022-03-01 | Central | SQS | Actual | 0
50 | 2022-03-01 | CMO West 1 | Terra Firma | Budget
50 | 2022-03-01 | CMO West 1 | Terra Firma | Forecast | 0
50 | 2022-03-01 | CMO West 1 | Terra Firma | Actual | 0
50 | 2022-03-01 | CMO West 1 | KLT | Budget
50 | 2022-03-01 | CMO West 1 | KLT | Forecast | 187.11
50 | 2022-03-01 | CMO West 1 | KLT | Actual | 0
50 | 2022-03-01 | CMO West 1 | Forefront | Budget
50 | 2022-03-01 | CMO West 1 | Forefront | Forecast | 0
50 | 2022-03-01 | CMO West 1 | Forefront | Actual | 0
50 | 2022-03-01 | CMO West 1 | DPF | Budget
50 | 2022-03-01 | CMO West 1 | DPF | Forecast | 0
50 | 2022-03-01 | CMO West 1 | DPF | Actual | 0
50 | 2022-03-01 | CMO West 1 | OMJ | Budget
50 | 2022-03-01 | CMO West 1 | OMJ | Forecast | 0
50 | 2022-03-01 | CMO West 1 | OMJ | Actual | 0
50 | 2022-03-01 | CMO West 1 | DHB Utilities | Budget
50 | 2022-03-01 | CMO West 1 | DHB Utilities | Forecast | 0
50 | 2022-03-01 | CMO West 1 | DHB Utilities | Actual | 0
50 | 2022-03-01 | CMO West 1 | JDT | Budget
50 | 2022-03-01 | CMO West 1 | JDT | Forecast | 0
50 | 2022-03-01 | CMO West 1 | JDT | Actual | 0
50 | 2022-03-01 | CMO West 1 | MURRAY | Budget
50 | 2022-03-01 | CMO West 1 | MURRAY | Forecast | 0
50 | 2022-03-01 | CMO West 1 | MURRAY | Actual | 0
50 | 2022-03-01 | CMO West 2 | Terra Firma | Budget
50 | 2022-03-01 | CMO West 2 | Terra Firma | Forecast | 0
50 | 2022-03-01 | CMO West 2 | Terra Firma | Actual | 0
50 | 2022-03-01 | CMO West 2 | KLT | Budget
50 | 2022-03-01 | CMO West 2 | KLT | Forecast | 464.72
50 | 2022-03-01 | CMO West 2 | KLT | Actual | 0
50 | 2022-03-01 | CMO West 2 | Forefront | Budget
50 | 2022-03-01 | CMO West 2 | Forefront | Forecast | 0
50 | 2022-03-01 | CMO West 2 | Forefront | Actual | 0
50 | 2022-03-01 | CMO West 2 | DPF | Budget
50 | 2022-03-01 | CMO West 2 | DPF | Forecast | 0
50 | 2022-03-01 | CMO West 2 | DPF | Actual | 0
50 | 2022-03-01 | CMO West 2 | OMJ | Budget
50 | 2022-03-01 | CMO West 2 | OMJ | Forecast | 332.71
50 | 2022-03-01 | CMO West 2 | OMJ | Actual | 0
50 | 2022-03-01 | CMO West 2 | DHB Utilities | Budget
50 | 2022-03-01 | CMO West 2 | DHB Utilities | Forecast | 283.11
50 | 2022-03-01 | CMO West 2 | DHB Utilities | Actual | 0
50 | 2022-03-01 | CMO West 2 | JDT | Budget
50 | 2022-03-01 | CMO West 2 | JDT | Forecast | 0
50 | 2022-03-01 | CMO West 2 | JDT | Actual | 0
50 | 2022-03-01 | CMO West 2 | MURRAY | Budget
50 | 2022-03-01 | CMO West 2 | MURRAY | Forecast | 0
50 | 2022-03-01 | CMO West 2 | MURRAY | Actual | 0
50 | 2022-03-01 | CMO East 1 | Terra Firma | Budget
50 | 2022-03-01 | CMO East 1 | Terra Firma | Forecast | 97.43
50 | 2022-03-01 | CMO East 1 | Terra Firma | Actual | 0
50 | 2022-03-01 | CMO East 1 | KLT | Budget
50 | 2022-03-01 | CMO East 1 | KLT | Forecast | 0
50 | 2022-03-01 | CMO East 1 | KLT | Actual | 0
50 | 2022-03-01 | CMO East 1 | Forefront | Budget
50 | 2022-03-01 | CMO East 1 | Forefront | Forecast | 120.45
50 | 2022-03-01 | CMO East 1 | Forefront | Actual | 0
50 | 2022-03-01 | CMO East 1 | DPF | Budget
50 | 2022-03-01 | CMO East 1 | DPF | Forecast | 224.03
50 | 2022-03-01 | CMO East 1 | DPF | Actual | 0
50 | 2022-03-01 | CMO East 1 | OMJ | Budget
50 | 2022-03-01 | CMO East 1 | OMJ | Forecast | 0
50 | 2022-03-01 | CMO East 1 | OMJ | Actual | 0
50 | 2022-03-01 | CMO East 1 | DHB Utilities | Budget
50 | 2022-03-01 | CMO East 1 | DHB Utilities | Forecast | 0
50 | 2022-03-01 | CMO East 1 | DHB Utilities | Actual | 0
50 | 2022-03-01 | CMO East 1 | JDT | Budget
50 | 2022-03-01 | CMO East 1 | JDT | Forecast | 0
50 | 2022-03-01 | CMO East 1 | JDT | Actual | 0
50 | 2022-03-01 | CMO East 1 | MURRAY | Budget
50 | 2022-03-01 | CMO East 1 | MURRAY | Forecast | 0
50 | 2022-03-01 | CMO East 1 | MURRAY | Actual | 0
50 | 2022-03-01 | CMO East 2 | Terra Firma | Budget
50 | 2022-03-01 | CMO East 2 | Terra Firma | Forecast | 360.3
50 | 2022-03-01 | CMO East 2 | Terra Firma | Actual | 0
50 | 2022-03-01 | CMO East 2 | KLT | Budget
50 | 2022-03-01 | CMO East 2 | KLT | Forecast | 0
50 | 2022-03-01 | CMO East 2 | KLT | Actual | 0
50 | 2022-03-01 | CMO East 2 | Forefront | Budget
50 | 2022-03-01 | CMO East 2 | Forefront | Forecast | 617.82
50 | 2022-03-01 | CMO East 2 | Forefront | Actual | 0
50 | 2022-03-01 | CMO East 2 | DPF | Budget
50 | 2022-03-01 | CMO East 2 | DPF | Forecast | 0
50 | 2022-03-01 | CMO East 2 | DPF | Actual | 0
50 | 2022-03-01 | CMO East 2 | OMJ | Budget
50 | 2022-03-01 | CMO East 2 | OMJ | Forecast | 0
50 | 2022-03-01 | CMO East 2 | OMJ | Actual | 0
50 | 2022-03-01 | CMO East 2 | DHB Utilities | Budget
50 | 2022-03-01 | CMO East 2 | DHB Utilities | Forecast | 0
50 | 2022-03-01 | CMO East 2 | DHB Utilities | Actual | 0
50 | 2022-03-01 | CMO East 2 | JDT | Budget
50 | 2022-03-01 | CMO East 2 | JDT | Forecast | 269.35
50 | 2022-03-01 | CMO East 2 | JDT | Actual | 0
50 | 2022-03-01 | CMO East 2 | MURRAY | Budget
50 | 2022-03-01 | CMO East 2 | MURRAY | Forecast | 0
50 | 2022-03-01 | CMO East 2 | MURRAY | Actual | 0
50 | 2022-03-01 | West | Terra Firma | Budget
50 | 2022-03-01 | West | Terra Firma | Forecast | 0
50 | 2022-03-01 | West | Terra Firma | Actual | 0
50 | 2022-03-01 | West | KLT | Budget
50 | 2022-03-01 | West | KLT | Forecast | 0
50 | 2022-03-01 | West | KLT | Actual | 0
50 | 2022-03-01 | West | Forefront | Budget
50 | 2022-03-01 | West | Forefront | Forecast | 0
50 | 2022-03-01 | West | Forefront | Actual | 0
50 | 2022-03-01 | West | DPF | Budget
50 | 2022-03-01 | West | DPF | Forecast | 0
50 | 2022-03-01 | West | DPF | Actual | 0
50 | 2022-03-01 | West | OMJ | Budget
50 | 2022-03-01 | West | OMJ | Forecast | 0
50 | 2022-03-01 | West | OMJ | Actual | 0
50 | 2022-03-01 | West | DHB Utilities | Budget
50 | 2022-03-01 | West | DHB Utilities | Forecast | 0
50 | 2022-03-01 | West | DHB Utilities | Actual | 0
50 | 2022-03-01 | West | JDT | Budget
50 | 2022-03-01 | West | JDT | Forecast | 0
50 | 2022-03-01 | West | JDT | Actual | 0
50 | 2022-03-01 | West | MURRAY | Budget
50 | 2022-03-01 | West | MURRAY | Forecast | 0
50 | 2022-03-01 | West | MURRAY | Actual | 0
50 | 2022-03-01 | East | Terra Firma | Budget
50 | 2022-03-01 | East | Terra Firma | Forecast | 0
50 | 2022-03-01 | East | Terra Firma | Actual | 0
50 | 2022-03-01 | East | KLT | Budget
50 | 2022-03-01 | East | KLT | Forecast | 0
50 | 2022-03-01 | East | KLT | Actual | 0
50 | 2022-03-01 | East | Forefront | Budget
50 | 2022-03-01 | East | Forefront | Forecast | 0
50 | 2022-03-01 | East | Forefront | Actual | 0
50 | 2022-03-01 | East | DPF | Budget
50 | 2022-03-01 | East | DPF | Forecast | 0
50 | 2022-03-01 | East | DPF | Actual | 0
50 | 2022-03-01 | East | OMJ | Budget
50 | 2022-03-01 | East | OMJ | Forecast | 0
50 | 2022-03-01 | East | OMJ | Actual | 0
50 | 2022-03-01 | East | DHB Utilities | Budget
50 | 2022-03-01 | East | DHB Utilities | Forecast | 0
50 | 2022-03-01 | East | DHB Utilities | Actual | 0
50 | 2022-03-01 | East | JDT | Budget
50 | 2022-03-01 | East | JDT | Forecast | 0
50 | 2022-03-01 | East | JDT | Actual | 0
50 | 2022-03-01 | East | MURRAY | Budget
50 | 2022-03-01 | East | MURRAY | Forecast | 0
50 | 2022-03-01 | East | MURRAY | Actual | 0
50 | 2022-03-01 | Central | Terra Firma | Budget
50 | 2022-03-01 | Central | Terra Firma | Forecast | 0
50 | 2022-03-01 | Central | Terra Firma | Actual | 0
50 | 2022-03-01 | Central | KLT | Budget
50 | 2022-03-01 | Central | KLT | Forecast | 0
50 | 2022-03-01 | Central | KLT | Actual | 0
50 | 2022-03-01 | Central | Forefront | Budget
50 | 2022-03-01 | Central | Forefront | Forecast | 0
50 | 2022-03-01 | Central | Forefront | Actual | 0
50 | 2022-03-01 | Central | DPF | Budget
50 | 2022-03-01 | Central | DPF | Forecast | 0
50 | 2022-03-01 | Central | DPF | Actual | 0
50 | 2022-03-01 | Central | OMJ | Budget
50 | 2022-03-01 | Central | OMJ | Forecast | 0
50 | 2022-03-01 | Central | OMJ | Actual | 0
50 | 2022-03-01 | Central | DHB Utilities | Budget
50 | 2022-03-01 | Central | DHB Utilities | Forecast | 0
50 | 2022-03-01 | Central | DHB Utilities | Actual | 0
50 | 2022-03-01 | Central | JDT | Budget
50 | 2022-03-01 | Central | JDT | Forecast | 0
50 | 2022-03-01 | Central | JDT | Actual | 0
50 | 2022-03-01 | Central | MURRAY | Budget
50 | 2022-03-01 | Central | MURRAY | Forecast | 0
50 | 2022-03-01 | Central | MURRAY | Actual | 0
50 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Budget
50 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Budget
50 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Budget
50 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Budget
50 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | West | DIRECT MOLE | Budget
50 | 2022-03-01 | West | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | West | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | East | DIRECT MOLE | Budget
50 | 2022-03-01 | East | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | East | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | Central | DIRECT MOLE | Budget
50 | 2022-03-01 | Central | DIRECT MOLE | Forecast | 0
50 | 2022-03-01 | Central | DIRECT MOLE | Actual | 0
50 | 2022-03-01 | CMO West 1 | SQS | Budget
50 | 2022-03-01 | CMO West 1 | SQS | Forecast | 42.07
50 | 2022-03-01 | CMO West 1 | SQS | Actual | 0
50 | 2022-03-01 | CMO West 2 | SQS | Budget
50 | 2022-03-01 | CMO West 2 | SQS | Forecast | 177.63
50 | 2022-03-01 | CMO West 2 | SQS | Actual | 0
50 | 2022-03-01 | CMO East 1 | SQS | Budget
50 | 2022-03-01 | CMO East 1 | SQS | Forecast | 0
50 | 2022-03-01 | CMO East 1 | SQS | Actual | 0
50 | 2022-03-01 | CMO East 2 | SQS | Budget
50 | 2022-03-01 | CMO East 2 | SQS | Forecast | 0
50 | 2022-03-01 | CMO East 2 | SQS | Actual | 0
50 | 2022-03-01 | West | SQS | Budget
50 | 2022-03-01 | West | SQS | Forecast | 0
50 | 2022-03-01 | West | SQS | Actual | 0
50 | 2022-03-01 | East | SQS | Budget
50 | 2022-03-01 | East | SQS | Forecast | 0
50 | 2022-03-01 | East | SQS | Actual | 0
50 | 2022-03-01 | Central | SQS | Budget
50 | 2022-03-01 | Central | SQS | Forecast | 0
50 | 2022-03-01 | Central | SQS | Actual | 0
51 | 2022-03-01 | CMO West 1 | Terra Firma | Budget
51 | 2022-03-01 | CMO West 1 | Terra Firma | Forecast | 0
51 | 2022-03-01 | CMO West 1 | Terra Firma | Actual | 0
51 | 2022-03-01 | CMO West 1 | KLT | Budget
51 | 2022-03-01 | CMO West 1 | KLT | Forecast | 221.49
51 | 2022-03-01 | CMO West 1 | KLT | Actual | 0
51 | 2022-03-01 | CMO West 1 | Forefront | Budget
51 | 2022-03-01 | CMO West 1 | Forefront | Forecast | 0
51 | 2022-03-01 | CMO West 1 | Forefront | Actual | 0
51 | 2022-03-01 | CMO West 1 | DPF | Budget
51 | 2022-03-01 | CMO West 1 | DPF | Forecast | 0
51 | 2022-03-01 | CMO West 1 | DPF | Actual | 0
51 | 2022-03-01 | CMO West 1 | OMJ | Budget
51 | 2022-03-01 | CMO West 1 | OMJ | Forecast | 0
51 | 2022-03-01 | CMO West 1 | OMJ | Actual | 0
51 | 2022-03-01 | CMO West 1 | DHB Utilities | Budget
51 | 2022-03-01 | CMO West 1 | DHB Utilities | Forecast | 0
51 | 2022-03-01 | CMO West 1 | DHB Utilities | Actual | 0
51 | 2022-03-01 | CMO West 1 | JDT | Budget
51 | 2022-03-01 | CMO West 1 | JDT | Forecast | 0
51 | 2022-03-01 | CMO West 1 | JDT | Actual | 0
51 | 2022-03-01 | CMO West 1 | MURRAY | Budget
51 | 2022-03-01 | CMO West 1 | MURRAY | Forecast | 0
51 | 2022-03-01 | CMO West 1 | MURRAY | Actual | 0
51 | 2022-03-01 | CMO West 2 | Terra Firma | Budget
51 | 2022-03-01 | CMO West 2 | Terra Firma | Forecast | 0
51 | 2022-03-01 | CMO West 2 | Terra Firma | Actual | 0
51 | 2022-03-01 | CMO West 2 | KLT | Budget
51 | 2022-03-01 | CMO West 2 | KLT | Forecast | 464.72
51 | 2022-03-01 | CMO West 2 | KLT | Actual | 0
51 | 2022-03-01 | CMO West 2 | Forefront | Budget
51 | 2022-03-01 | CMO West 2 | Forefront | Forecast | 0
51 | 2022-03-01 | CMO West 2 | Forefront | Actual | 0
51 | 2022-03-01 | CMO West 2 | DPF | Budget
51 | 2022-03-01 | CMO West 2 | DPF | Forecast | 0
51 | 2022-03-01 | CMO West 2 | DPF | Actual | 0
51 | 2022-03-01 | CMO West 2 | OMJ | Budget
51 | 2022-03-01 | CMO West 2 | OMJ | Forecast | 401.28
51 | 2022-03-01 | CMO West 2 | OMJ | Actual | 0
51 | 2022-03-01 | CMO West 2 | DHB Utilities | Budget
51 | 2022-03-01 | CMO West 2 | DHB Utilities | Forecast | 425.13
51 | 2022-03-01 | CMO West 2 | DHB Utilities | Actual | 0
51 | 2022-03-01 | CMO West 2 | JDT | Budget
51 | 2022-03-01 | CMO West 2 | JDT | Forecast | 0
51 | 2022-03-01 | CMO West 2 | JDT | Actual | 0
51 | 2022-03-01 | CMO West 2 | MURRAY | Budget
51 | 2022-03-01 | CMO West 2 | MURRAY | Forecast | 0
51 | 2022-03-01 | CMO West 2 | MURRAY | Actual | 0
51 | 2022-03-01 | CMO East 1 | Terra Firma | Budget
51 | 2022-03-01 | CMO East 1 | Terra Firma | Forecast | 33.68
51 | 2022-03-01 | CMO East 1 | Terra Firma | Actual | 0
51 | 2022-03-01 | CMO East 1 | KLT | Budget
51 | 2022-03-01 | CMO East 1 | KLT | Forecast | 0
51 | 2022-03-01 | CMO East 1 | KLT | Actual | 0
51 | 2022-03-01 | CMO East 1 | Forefront | Budget
51 | 2022-03-01 | CMO East 1 | Forefront | Forecast | 120.45
51 | 2022-03-01 | CMO East 1 | Forefront | Actual | 0
51 | 2022-03-01 | CMO East 1 | DPF | Budget
51 | 2022-03-01 | CMO East 1 | DPF | Forecast | 224.03
51 | 2022-03-01 | CMO East 1 | DPF | Actual | 0
51 | 2022-03-01 | CMO East 1 | OMJ | Budget
51 | 2022-03-01 | CMO East 1 | OMJ | Forecast | 0
51 | 2022-03-01 | CMO East 1 | OMJ | Actual | 0
51 | 2022-03-01 | CMO East 1 | DHB Utilities | Budget
51 | 2022-03-01 | CMO East 1 | DHB Utilities | Forecast | 0
51 | 2022-03-01 | CMO East 1 | DHB Utilities | Actual | 0
51 | 2022-03-01 | CMO East 1 | JDT | Budget
51 | 2022-03-01 | CMO East 1 | JDT | Forecast | 0
51 | 2022-03-01 | CMO East 1 | JDT | Actual | 0
51 | 2022-03-01 | CMO East 1 | MURRAY | Budget
51 | 2022-03-01 | CMO East 1 | MURRAY | Forecast | 0
51 | 2022-03-01 | CMO East 1 | MURRAY | Actual | 0
51 | 2022-03-01 | CMO East 2 | Terra Firma | Budget
51 | 2022-03-01 | CMO East 2 | Terra Firma | Forecast | 360.3
51 | 2022-03-01 | CMO East 2 | Terra Firma | Actual | 0
51 | 2022-03-01 | CMO East 2 | KLT | Budget
51 | 2022-03-01 | CMO East 2 | KLT | Forecast | 0
51 | 2022-03-01 | CMO East 2 | KLT | Actual | 0
51 | 2022-03-01 | CMO East 2 | Forefront | Budget
51 | 2022-03-01 | CMO East 2 | Forefront | Forecast | 436.06
51 | 2022-03-01 | CMO East 2 | Forefront | Actual | 0
51 | 2022-03-01 | CMO East 2 | DPF | Budget
51 | 2022-03-01 | CMO East 2 | DPF | Forecast | 0
51 | 2022-03-01 | CMO East 2 | DPF | Actual | 0
51 | 2022-03-01 | CMO East 2 | OMJ | Budget
51 | 2022-03-01 | CMO East 2 | OMJ | Forecast | 0
51 | 2022-03-01 | CMO East 2 | OMJ | Actual | 0
51 | 2022-03-01 | CMO East 2 | DHB Utilities | Budget
51 | 2022-03-01 | CMO East 2 | DHB Utilities | Forecast | 0
51 | 2022-03-01 | CMO East 2 | DHB Utilities | Actual | 0
51 | 2022-03-01 | CMO East 2 | JDT | Budget
51 | 2022-03-01 | CMO East 2 | JDT | Forecast | 269.35
51 | 2022-03-01 | CMO East 2 | JDT | Actual | 0
51 | 2022-03-01 | CMO East 2 | MURRAY | Budget
51 | 2022-03-01 | CMO East 2 | MURRAY | Forecast | 0
51 | 2022-03-01 | CMO East 2 | MURRAY | Actual | 0
51 | 2022-03-01 | West | Terra Firma | Budget
51 | 2022-03-01 | West | Terra Firma | Forecast | 0
51 | 2022-03-01 | West | Terra Firma | Actual | 0
51 | 2022-03-01 | West | KLT | Budget
51 | 2022-03-01 | West | KLT | Forecast | 0
51 | 2022-03-01 | West | KLT | Actual | 0
51 | 2022-03-01 | West | Forefront | Budget
51 | 2022-03-01 | West | Forefront | Forecast | 0
51 | 2022-03-01 | West | Forefront | Actual | 0
51 | 2022-03-01 | West | DPF | Budget
51 | 2022-03-01 | West | DPF | Forecast | 0
51 | 2022-03-01 | West | DPF | Actual | 0
51 | 2022-03-01 | West | OMJ | Budget
51 | 2022-03-01 | West | OMJ | Forecast | 0
51 | 2022-03-01 | West | OMJ | Actual | 0
51 | 2022-03-01 | West | DHB Utilities | Budget
51 | 2022-03-01 | West | DHB Utilities | Forecast | 0
51 | 2022-03-01 | West | DHB Utilities | Actual | 0
51 | 2022-03-01 | West | JDT | Budget
51 | 2022-03-01 | West | JDT | Forecast | 0
51 | 2022-03-01 | West | JDT | Actual | 0
51 | 2022-03-01 | West | MURRAY | Budget
51 | 2022-03-01 | West | MURRAY | Forecast | 0
51 | 2022-03-01 | West | MURRAY | Actual | 0
51 | 2022-03-01 | East | Terra Firma | Budget
51 | 2022-03-01 | East | Terra Firma | Forecast | 0
51 | 2022-03-01 | East | Terra Firma | Actual | 0
51 | 2022-03-01 | East | KLT | Budget
51 | 2022-03-01 | East | KLT | Forecast | 0
51 | 2022-03-01 | East | KLT | Actual | 0
51 | 2022-03-01 | East | Forefront | Budget
51 | 2022-03-01 | East | Forefront | Forecast | 0
51 | 2022-03-01 | East | Forefront | Actual | 0
51 | 2022-03-01 | East | DPF | Budget
51 | 2022-03-01 | East | DPF | Forecast | 0
51 | 2022-03-01 | East | DPF | Actual | 0
51 | 2022-03-01 | East | OMJ | Budget
51 | 2022-03-01 | East | OMJ | Forecast | 0
51 | 2022-03-01 | East | OMJ | Actual | 0
51 | 2022-03-01 | East | DHB Utilities | Budget
51 | 2022-03-01 | East | DHB Utilities | Forecast | 0
51 | 2022-03-01 | East | DHB Utilities | Actual | 0
51 | 2022-03-01 | East | JDT | Budget
51 | 2022-03-01 | East | JDT | Forecast | 0
51 | 2022-03-01 | East | JDT | Actual | 0
51 | 2022-03-01 | East | MURRAY | Budget
51 | 2022-03-01 | East | MURRAY | Forecast | 0
51 | 2022-03-01 | East | MURRAY | Actual | 0
51 | 2022-03-01 | Central | Terra Firma | Budget
51 | 2022-03-01 | Central | Terra Firma | Forecast | 0
51 | 2022-03-01 | Central | Terra Firma | Actual | 0
51 | 2022-03-01 | Central | KLT | Budget
51 | 2022-03-01 | Central | KLT | Forecast | 0
51 | 2022-03-01 | Central | KLT | Actual | 0
51 | 2022-03-01 | Central | Forefront | Budget
51 | 2022-03-01 | Central | Forefront | Forecast | 0
51 | 2022-03-01 | Central | Forefront | Actual | 0
51 | 2022-03-01 | Central | DPF | Budget
51 | 2022-03-01 | Central | DPF | Forecast | 0
51 | 2022-03-01 | Central | DPF | Actual | 0
51 | 2022-03-01 | Central | OMJ | Budget
51 | 2022-03-01 | Central | OMJ | Forecast | 0
51 | 2022-03-01 | Central | OMJ | Actual | 0
51 | 2022-03-01 | Central | DHB Utilities | Budget
51 | 2022-03-01 | Central | DHB Utilities | Forecast | 0
51 | 2022-03-01 | Central | DHB Utilities | Actual | 0
51 | 2022-03-01 | Central | JDT | Budget
51 | 2022-03-01 | Central | JDT | Forecast | 0
51 | 2022-03-01 | Central | JDT | Actual | 0
51 | 2022-03-01 | Central | MURRAY | Budget
51 | 2022-03-01 | Central | MURRAY | Forecast | 0
51 | 2022-03-01 | Central | MURRAY | Actual | 0
51 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Budget
51 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Budget
51 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Budget
51 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Budget
51 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | West | DIRECT MOLE | Budget
51 | 2022-03-01 | West | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | West | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | East | DIRECT MOLE | Budget
51 | 2022-03-01 | East | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | East | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | Central | DIRECT MOLE | Budget
51 | 2022-03-01 | Central | DIRECT MOLE | Forecast | 0
51 | 2022-03-01 | Central | DIRECT MOLE | Actual | 0
51 | 2022-03-01 | CMO West 1 | SQS | Budget
51 | 2022-03-01 | CMO West 1 | SQS | Forecast | 0
51 | 2022-03-01 | CMO West 1 | SQS | Actual | 0
51 | 2022-03-01 | CMO West 2 | SQS | Budget
51 | 2022-03-01 | CMO West 2 | SQS | Forecast | 177.63
51 | 2022-03-01 | CMO West 2 | SQS | Actual | 0
51 | 2022-03-01 | CMO East 1 | SQS | Budget
51 | 2022-03-01 | CMO East 1 | SQS | Forecast | 0
51 | 2022-03-01 | CMO East 1 | SQS | Actual | 0
51 | 2022-03-01 | CMO East 2 | SQS | Budget
51 | 2022-03-01 | CMO East 2 | SQS | Forecast | 0
51 | 2022-03-01 | CMO East 2 | SQS | Actual | 0
51 | 2022-03-01 | West | SQS | Budget
51 | 2022-03-01 | West | SQS | Forecast | 0
51 | 2022-03-01 | West | SQS | Actual | 0
51 | 2022-03-01 | East | SQS | Budget
51 | 2022-03-01 | East | SQS | Forecast | 0
51 | 2022-03-01 | East | SQS | Actual | 0
51 | 2022-03-01 | Central | SQS | Budget
51 | 2022-03-01 | Central | SQS | Forecast | 0
51 | 2022-03-01 | Central | SQS | Actual | 0
52 | 2022-03-01 | CMO West 1 | Terra Firma | Budget
52 | 2022-03-01 | CMO West 1 | Terra Firma | Forecast | 0
52 | 2022-03-01 | CMO West 1 | Terra Firma | Actual | 0
52 | 2022-03-01 | CMO West 1 | KLT | Budget
52 | 2022-03-01 | CMO West 1 | KLT | Forecast | 168.27
52 | 2022-03-01 | CMO West 1 | KLT | Actual | 0
52 | 2022-03-01 | CMO West 1 | Forefront | Budget
52 | 2022-03-01 | CMO West 1 | Forefront | Forecast | 0
52 | 2022-03-01 | CMO West 1 | Forefront | Actual | 0
52 | 2022-03-01 | CMO West 1 | DPF | Budget
52 | 2022-03-01 | CMO West 1 | DPF | Forecast | 0
52 | 2022-03-01 | CMO West 1 | DPF | Actual | 0
52 | 2022-03-01 | CMO West 1 | OMJ | Budget
52 | 2022-03-01 | CMO West 1 | OMJ | Forecast | 0
52 | 2022-03-01 | CMO West 1 | OMJ | Actual | 0
52 | 2022-03-01 | CMO West 1 | DHB Utilities | Budget
52 | 2022-03-01 | CMO West 1 | DHB Utilities | Forecast | 0
52 | 2022-03-01 | CMO West 1 | DHB Utilities | Actual | 0
52 | 2022-03-01 | CMO West 1 | JDT | Budget
52 | 2022-03-01 | CMO West 1 | JDT | Forecast | 0
52 | 2022-03-01 | CMO West 1 | JDT | Actual | 0
52 | 2022-03-01 | CMO West 1 | MURRAY | Budget
52 | 2022-03-01 | CMO West 1 | MURRAY | Forecast | 0
52 | 2022-03-01 | CMO West 1 | MURRAY | Actual | 0
52 | 2022-03-01 | CMO West 2 | Terra Firma | Budget
52 | 2022-03-01 | CMO West 2 | Terra Firma | Forecast | 0
52 | 2022-03-01 | CMO West 2 | Terra Firma | Actual | 0
52 | 2022-03-01 | CMO West 2 | KLT | Budget
52 | 2022-03-01 | CMO West 2 | KLT | Forecast | 440.44
52 | 2022-03-01 | CMO West 2 | KLT | Actual | 0
52 | 2022-03-01 | CMO West 2 | Forefront | Budget
52 | 2022-03-01 | CMO West 2 | Forefront | Forecast | 0
52 | 2022-03-01 | CMO West 2 | Forefront | Actual | 0
52 | 2022-03-01 | CMO West 2 | DPF | Budget
52 | 2022-03-01 | CMO West 2 | DPF | Forecast | 0
52 | 2022-03-01 | CMO West 2 | DPF | Actual | 0
52 | 2022-03-01 | CMO West 2 | OMJ | Budget
52 | 2022-03-01 | CMO West 2 | OMJ | Forecast | 348.94
52 | 2022-03-01 | CMO West 2 | OMJ | Actual | 0
52 | 2022-03-01 | CMO West 2 | DHB Utilities | Budget
52 | 2022-03-01 | CMO West 2 | DHB Utilities | Forecast | 522.2
52 | 2022-03-01 | CMO West 2 | DHB Utilities | Actual | 0
52 | 2022-03-01 | CMO West 2 | JDT | Budget
52 | 2022-03-01 | CMO West 2 | JDT | Forecast | 0
52 | 2022-03-01 | CMO West 2 | JDT | Actual | 0
52 | 2022-03-01 | CMO West 2 | MURRAY | Budget
52 | 2022-03-01 | CMO West 2 | MURRAY | Forecast | 0
52 | 2022-03-01 | CMO West 2 | MURRAY | Actual | 0
52 | 2022-03-01 | CMO East 1 | Terra Firma | Budget
52 | 2022-03-01 | CMO East 1 | Terra Firma | Forecast | 33.68
52 | 2022-03-01 | CMO East 1 | Terra Firma | Actual | 0
52 | 2022-03-01 | CMO East 1 | KLT | Budget
52 | 2022-03-01 | CMO East 1 | KLT | Forecast | 0
52 | 2022-03-01 | CMO East 1 | KLT | Actual | 0
52 | 2022-03-01 | CMO East 1 | Forefront | Budget
52 | 2022-03-01 | CMO East 1 | Forefront | Forecast | 120.45
52 | 2022-03-01 | CMO East 1 | Forefront | Actual | 0
52 | 2022-03-01 | CMO East 1 | DPF | Budget
52 | 2022-03-01 | CMO East 1 | DPF | Forecast | 224.03
52 | 2022-03-01 | CMO East 1 | DPF | Actual | 0
52 | 2022-03-01 | CMO East 1 | OMJ | Budget
52 | 2022-03-01 | CMO East 1 | OMJ | Forecast | 0
52 | 2022-03-01 | CMO East 1 | OMJ | Actual | 0
52 | 2022-03-01 | CMO East 1 | DHB Utilities | Budget
52 | 2022-03-01 | CMO East 1 | DHB Utilities | Forecast | 0
52 | 2022-03-01 | CMO East 1 | DHB Utilities | Actual | 0
52 | 2022-03-01 | CMO East 1 | JDT | Budget
52 | 2022-03-01 | CMO East 1 | JDT | Forecast | 0
52 | 2022-03-01 | CMO East 1 | JDT | Actual | 0
52 | 2022-03-01 | CMO East 1 | MURRAY | Budget
52 | 2022-03-01 | CMO East 1 | MURRAY | Forecast | 0
52 | 2022-03-01 | CMO East 1 | MURRAY | Actual | 0
52 | 2022-03-01 | CMO East 2 | Terra Firma | Budget
52 | 2022-03-01 | CMO East 2 | Terra Firma | Forecast | 360.3
52 | 2022-03-01 | CMO East 2 | Terra Firma | Actual | 0
52 | 2022-03-01 | CMO East 2 | KLT | Budget
52 | 2022-03-01 | CMO East 2 | KLT | Forecast | 0
52 | 2022-03-01 | CMO East 2 | KLT | Actual | 0
52 | 2022-03-01 | CMO East 2 | Forefront | Budget
52 | 2022-03-01 | CMO East 2 | Forefront | Forecast | 436.06
52 | 2022-03-01 | CMO East 2 | Forefront | Actual | 0
52 | 2022-03-01 | CMO East 2 | DPF | Budget
52 | 2022-03-01 | CMO East 2 | DPF | Forecast | 0
52 | 2022-03-01 | CMO East 2 | DPF | Actual | 0
52 | 2022-03-01 | CMO East 2 | OMJ | Budget
52 | 2022-03-01 | CMO East 2 | OMJ | Forecast | 0
52 | 2022-03-01 | CMO East 2 | OMJ | Actual | 0
52 | 2022-03-01 | CMO East 2 | DHB Utilities | Budget
52 | 2022-03-01 | CMO East 2 | DHB Utilities | Forecast | 0
52 | 2022-03-01 | CMO East 2 | DHB Utilities | Actual | 0
52 | 2022-03-01 | CMO East 2 | JDT | Budget
52 | 2022-03-01 | CMO East 2 | JDT | Forecast | 269.35
52 | 2022-03-01 | CMO East 2 | JDT | Actual | 0
52 | 2022-03-01 | CMO East 2 | MURRAY | Budget
52 | 2022-03-01 | CMO East 2 | MURRAY | Forecast | 0
52 | 2022-03-01 | CMO East 2 | MURRAY | Actual | 0
52 | 2022-03-01 | West | Terra Firma | Budget
52 | 2022-03-01 | West | Terra Firma | Forecast | 0
52 | 2022-03-01 | West | Terra Firma | Actual | 0
52 | 2022-03-01 | West | KLT | Budget
52 | 2022-03-01 | West | KLT | Forecast | 0
52 | 2022-03-01 | West | KLT | Actual | 0
52 | 2022-03-01 | West | Forefront | Budget
52 | 2022-03-01 | West | Forefront | Forecast | 0
52 | 2022-03-01 | West | Forefront | Actual | 0
52 | 2022-03-01 | West | DPF | Budget
52 | 2022-03-01 | West | DPF | Forecast | 0
52 | 2022-03-01 | West | DPF | Actual | 0
52 | 2022-03-01 | West | OMJ | Budget
52 | 2022-03-01 | West | OMJ | Forecast | 0
52 | 2022-03-01 | West | OMJ | Actual | 0
52 | 2022-03-01 | West | DHB Utilities | Budget
52 | 2022-03-01 | West | DHB Utilities | Forecast | 0
52 | 2022-03-01 | West | DHB Utilities | Actual | 0
52 | 2022-03-01 | West | JDT | Budget
52 | 2022-03-01 | West | JDT | Forecast | 0
52 | 2022-03-01 | West | JDT | Actual | 0
52 | 2022-03-01 | West | MURRAY | Budget
52 | 2022-03-01 | West | MURRAY | Forecast | 0
52 | 2022-03-01 | West | MURRAY | Actual | 0
52 | 2022-03-01 | East | Terra Firma | Budget
52 | 2022-03-01 | East | Terra Firma | Forecast | 0
52 | 2022-03-01 | East | Terra Firma | Actual | 0
52 | 2022-03-01 | East | KLT | Budget
52 | 2022-03-01 | East | KLT | Forecast | 0
52 | 2022-03-01 | East | KLT | Actual | 0
52 | 2022-03-01 | East | Forefront | Budget
52 | 2022-03-01 | East | Forefront | Forecast | 0
52 | 2022-03-01 | East | Forefront | Actual | 0
52 | 2022-03-01 | East | DPF | Budget
52 | 2022-03-01 | East | DPF | Forecast | 0
52 | 2022-03-01 | East | DPF | Actual | 0
52 | 2022-03-01 | East | OMJ | Budget
52 | 2022-03-01 | East | OMJ | Forecast | 0
52 | 2022-03-01 | East | OMJ | Actual | 0
52 | 2022-03-01 | East | DHB Utilities | Budget
52 | 2022-03-01 | East | DHB Utilities | Forecast | 0
52 | 2022-03-01 | East | DHB Utilities | Actual | 0
52 | 2022-03-01 | East | JDT | Budget
52 | 2022-03-01 | East | JDT | Forecast | 0
52 | 2022-03-01 | East | JDT | Actual | 0
52 | 2022-03-01 | East | MURRAY | Budget
52 | 2022-03-01 | East | MURRAY | Forecast | 0
52 | 2022-03-01 | East | MURRAY | Actual | 0
52 | 2022-03-01 | Central | Terra Firma | Budget
52 | 2022-03-01 | Central | Terra Firma | Forecast | 0
52 | 2022-03-01 | Central | Terra Firma | Actual | 0
52 | 2022-03-01 | Central | KLT | Budget
52 | 2022-03-01 | Central | KLT | Forecast | 0
52 | 2022-03-01 | Central | KLT | Actual | 0
52 | 2022-03-01 | Central | Forefront | Budget
52 | 2022-03-01 | Central | Forefront | Forecast | 0
52 | 2022-03-01 | Central | Forefront | Actual | 0
52 | 2022-03-01 | Central | DPF | Budget
52 | 2022-03-01 | Central | DPF | Forecast | 0
52 | 2022-03-01 | Central | DPF | Actual | 0
52 | 2022-03-01 | Central | OMJ | Budget
52 | 2022-03-01 | Central | OMJ | Forecast | 0
52 | 2022-03-01 | Central | OMJ | Actual | 0
52 | 2022-03-01 | Central | DHB Utilities | Budget
52 | 2022-03-01 | Central | DHB Utilities | Forecast | 0
52 | 2022-03-01 | Central | DHB Utilities | Actual | 0
52 | 2022-03-01 | Central | JDT | Budget
52 | 2022-03-01 | Central | JDT | Forecast | 0
52 | 2022-03-01 | Central | JDT | Actual | 0
52 | 2022-03-01 | Central | MURRAY | Budget
52 | 2022-03-01 | Central | MURRAY | Forecast | 0
52 | 2022-03-01 | Central | MURRAY | Actual | 0
52 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Budget
52 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Budget
52 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Budget
52 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Budget
52 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | West | DIRECT MOLE | Budget
52 | 2022-03-01 | West | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | West | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | East | DIRECT MOLE | Budget
52 | 2022-03-01 | East | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | East | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | Central | DIRECT MOLE | Budget
52 | 2022-03-01 | Central | DIRECT MOLE | Forecast | 0
52 | 2022-03-01 | Central | DIRECT MOLE | Actual | 0
52 | 2022-03-01 | CMO West 1 | SQS | Budget
52 | 2022-03-01 | CMO West 1 | SQS | Forecast | 0
52 | 2022-03-01 | CMO West 1 | SQS | Actual | 0
52 | 2022-03-01 | CMO West 2 | SQS | Budget
52 | 2022-03-01 | CMO West 2 | SQS | Forecast | 77.45
52 | 2022-03-01 | CMO West 2 | SQS | Actual | 0
52 | 2022-03-01 | CMO East 1 | SQS | Budget
52 | 2022-03-01 | CMO East 1 | SQS | Forecast | 0
52 | 2022-03-01 | CMO East 1 | SQS | Actual | 0
52 | 2022-03-01 | CMO East 2 | SQS | Budget
52 | 2022-03-01 | CMO East 2 | SQS | Forecast | 0
52 | 2022-03-01 | CMO East 2 | SQS | Actual | 0
52 | 2022-03-01 | West | SQS | Budget
52 | 2022-03-01 | West | SQS | Forecast | 0
52 | 2022-03-01 | West | SQS | Actual | 0
52 | 2022-03-01 | East | SQS | Budget
52 | 2022-03-01 | East | SQS | Forecast | 0
52 | 2022-03-01 | East | SQS | Actual | 0
52 | 2022-03-01 | Central | SQS | Budget
52 | 2022-03-01 | Central | SQS | Forecast | 0
52 | 2022-03-01 | Central | SQS | Actual | 0
53 | 2022-03-01 | CMO West 1 | Terra Firma | Budget
53 | 2022-03-01 | CMO West 1 | Terra Firma | Forecast | 0
53 | 2022-03-01 | CMO West 1 | Terra Firma | Actual | 0
53 | 2022-03-01 | CMO West 1 | KLT | Budget
53 | 2022-03-01 | CMO West 1 | KLT | Forecast | 286.08
53 | 2022-03-01 | CMO West 1 | KLT | Actual | 0
53 | 2022-03-01 | CMO West 1 | Forefront | Budget
53 | 2022-03-01 | CMO West 1 | Forefront | Forecast | 0
53 | 2022-03-01 | CMO West 1 | Forefront | Actual | 0
53 | 2022-03-01 | CMO West 1 | DPF | Budget
53 | 2022-03-01 | CMO West 1 | DPF | Forecast | 0
53 | 2022-03-01 | CMO West 1 | DPF | Actual | 0
53 | 2022-03-01 | CMO West 1 | OMJ | Budget
53 | 2022-03-01 | CMO West 1 | OMJ | Forecast | 0
53 | 2022-03-01 | CMO West 1 | OMJ | Actual | 0
53 | 2022-03-01 | CMO West 1 | DHB Utilities | Budget
53 | 2022-03-01 | CMO West 1 | DHB Utilities | Forecast | 0
53 | 2022-03-01 | CMO West 1 | DHB Utilities | Actual | 0
53 | 2022-03-01 | CMO West 1 | JDT | Budget
53 | 2022-03-01 | CMO West 1 | JDT | Forecast | 0
53 | 2022-03-01 | CMO West 1 | JDT | Actual | 0
53 | 2022-03-01 | CMO West 1 | MURRAY | Budget
53 | 2022-03-01 | CMO West 1 | MURRAY | Forecast | 0
53 | 2022-03-01 | CMO West 1 | MURRAY | Actual | 0
53 | 2022-03-01 | CMO West 2 | Terra Firma | Budget
53 | 2022-03-01 | CMO West 2 | Terra Firma | Forecast | 0
53 | 2022-03-01 | CMO West 2 | Terra Firma | Actual | 0
53 | 2022-03-01 | CMO West 2 | KLT | Budget
53 | 2022-03-01 | CMO West 2 | KLT | Forecast | 392.69
53 | 2022-03-01 | CMO West 2 | KLT | Actual | 0
53 | 2022-03-01 | CMO West 2 | Forefront | Budget
53 | 2022-03-01 | CMO West 2 | Forefront | Forecast | 0
53 | 2022-03-01 | CMO West 2 | Forefront | Actual | 0
53 | 2022-03-01 | CMO West 2 | DPF | Budget
53 | 2022-03-01 | CMO West 2 | DPF | Forecast | 0
53 | 2022-03-01 | CMO West 2 | DPF | Actual | 0
53 | 2022-03-01 | CMO West 2 | OMJ | Budget
53 | 2022-03-01 | CMO West 2 | OMJ | Forecast | 148.75
53 | 2022-03-01 | CMO West 2 | OMJ | Actual | 0
53 | 2022-03-01 | CMO West 2 | DHB Utilities | Budget
53 | 2022-03-01 | CMO West 2 | DHB Utilities | Forecast | 709.13
53 | 2022-03-01 | CMO West 2 | DHB Utilities | Actual | 0
53 | 2022-03-01 | CMO West 2 | JDT | Budget
53 | 2022-03-01 | CMO West 2 | JDT | Forecast | 0
53 | 2022-03-01 | CMO West 2 | JDT | Actual | 0
53 | 2022-03-01 | CMO West 2 | MURRAY | Budget
53 | 2022-03-01 | CMO West 2 | MURRAY | Forecast | 0
53 | 2022-03-01 | CMO West 2 | MURRAY | Actual | 0
53 | 2022-03-01 | CMO East 1 | Terra Firma | Budget
53 | 2022-03-01 | CMO East 1 | Terra Firma | Forecast | 0
53 | 2022-03-01 | CMO East 1 | Terra Firma | Actual | 0
53 | 2022-03-01 | CMO East 1 | KLT | Budget
53 | 2022-03-01 | CMO East 1 | KLT | Forecast | 0
53 | 2022-03-01 | CMO East 1 | KLT | Actual | 0
53 | 2022-03-01 | CMO East 1 | Forefront | Budget
53 | 2022-03-01 | CMO East 1 | Forefront | Forecast | 120.45
53 | 2022-03-01 | CMO East 1 | Forefront | Actual | 0
53 | 2022-03-01 | CMO East 1 | DPF | Budget
53 | 2022-03-01 | CMO East 1 | DPF | Forecast | 224.03
53 | 2022-03-01 | CMO East 1 | DPF | Actual | 0
53 | 2022-03-01 | CMO East 1 | OMJ | Budget
53 | 2022-03-01 | CMO East 1 | OMJ | Forecast | 0
53 | 2022-03-01 | CMO East 1 | OMJ | Actual | 0
53 | 2022-03-01 | CMO East 1 | DHB Utilities | Budget
53 | 2022-03-01 | CMO East 1 | DHB Utilities | Forecast | 0
53 | 2022-03-01 | CMO East 1 | DHB Utilities | Actual | 0
53 | 2022-03-01 | CMO East 1 | JDT | Budget
53 | 2022-03-01 | CMO East 1 | JDT | Forecast | 0
53 | 2022-03-01 | CMO East 1 | JDT | Actual | 0
53 | 2022-03-01 | CMO East 1 | MURRAY | Budget
53 | 2022-03-01 | CMO East 1 | MURRAY | Forecast | 0
53 | 2022-03-01 | CMO East 1 | MURRAY | Actual | 0
53 | 2022-03-01 | CMO East 2 | Terra Firma | Budget
53 | 2022-03-01 | CMO East 2 | Terra Firma | Forecast | 276.42
53 | 2022-03-01 | CMO East 2 | Terra Firma | Actual | 0
53 | 2022-03-01 | CMO East 2 | KLT | Budget
53 | 2022-03-01 | CMO East 2 | KLT | Forecast | 0
53 | 2022-03-01 | CMO East 2 | KLT | Actual | 0
53 | 2022-03-01 | CMO East 2 | Forefront | Budget
53 | 2022-03-01 | CMO East 2 | Forefront | Forecast | 436.06
53 | 2022-03-01 | CMO East 2 | Forefront | Actual | 0
53 | 2022-03-01 | CMO East 2 | DPF | Budget
53 | 2022-03-01 | CMO East 2 | DPF | Forecast | 0
53 | 2022-03-01 | CMO East 2 | DPF | Actual | 0
53 | 2022-03-01 | CMO East 2 | OMJ | Budget
53 | 2022-03-01 | CMO East 2 | OMJ | Forecast | 0
53 | 2022-03-01 | CMO East 2 | OMJ | Actual | 0
53 | 2022-03-01 | CMO East 2 | DHB Utilities | Budget
53 | 2022-03-01 | CMO East 2 | DHB Utilities | Forecast | 0
53 | 2022-03-01 | CMO East 2 | DHB Utilities | Actual | 0
53 | 2022-03-01 | CMO East 2 | JDT | Budget
53 | 2022-03-01 | CMO East 2 | JDT | Forecast | 269.35
53 | 2022-03-01 | CMO East 2 | JDT | Actual | 0
53 | 2022-03-01 | CMO East 2 | MURRAY | Budget
53 | 2022-03-01 | CMO East 2 | MURRAY | Forecast | 0
53 | 2022-03-01 | CMO East 2 | MURRAY | Actual | 0
53 | 2022-03-01 | West | Terra Firma | Budget
53 | 2022-03-01 | West | Terra Firma | Forecast | 0
53 | 2022-03-01 | West | Terra Firma | Actual | 0
53 | 2022-03-01 | West | KLT | Budget
53 | 2022-03-01 | West | KLT | Forecast | 0
53 | 2022-03-01 | West | KLT | Actual | 0
53 | 2022-03-01 | West | Forefront | Budget
53 | 2022-03-01 | West | Forefront | Forecast | 0
53 | 2022-03-01 | West | Forefront | Actual | 0
53 | 2022-03-01 | West | DPF | Budget
53 | 2022-03-01 | West | DPF | Forecast | 0
53 | 2022-03-01 | West | DPF | Actual | 0
53 | 2022-03-01 | West | OMJ | Budget
53 | 2022-03-01 | West | OMJ | Forecast | 0
53 | 2022-03-01 | West | OMJ | Actual | 0
53 | 2022-03-01 | West | DHB Utilities | Budget
53 | 2022-03-01 | West | DHB Utilities | Forecast | 0
53 | 2022-03-01 | West | DHB Utilities | Actual | 0
53 | 2022-03-01 | West | JDT | Budget
53 | 2022-03-01 | West | JDT | Forecast | 0
53 | 2022-03-01 | West | JDT | Actual | 0
53 | 2022-03-01 | West | MURRAY | Budget
53 | 2022-03-01 | West | MURRAY | Forecast | 0
53 | 2022-03-01 | West | MURRAY | Actual | 0
53 | 2022-03-01 | East | Terra Firma | Budget
53 | 2022-03-01 | East | Terra Firma | Forecast | 0
53 | 2022-03-01 | East | Terra Firma | Actual | 0
53 | 2022-03-01 | East | KLT | Budget
53 | 2022-03-01 | East | KLT | Forecast | 0
53 | 2022-03-01 | East | KLT | Actual | 0
53 | 2022-03-01 | East | Forefront | Budget
53 | 2022-03-01 | East | Forefront | Forecast | 0
53 | 2022-03-01 | East | Forefront | Actual | 0
53 | 2022-03-01 | East | DPF | Budget
53 | 2022-03-01 | East | DPF | Forecast | 0
53 | 2022-03-01 | East | DPF | Actual | 0
53 | 2022-03-01 | East | OMJ | Budget
53 | 2022-03-01 | East | OMJ | Forecast | 0
53 | 2022-03-01 | East | OMJ | Actual | 0
53 | 2022-03-01 | East | DHB Utilities | Budget
53 | 2022-03-01 | East | DHB Utilities | Forecast | 0
53 | 2022-03-01 | East | DHB Utilities | Actual | 0
53 | 2022-03-01 | East | JDT | Budget
53 | 2022-03-01 | East | JDT | Forecast | 0
53 | 2022-03-01 | East | JDT | Actual | 0
53 | 2022-03-01 | East | MURRAY | Budget
53 | 2022-03-01 | East | MURRAY | Forecast | 0
53 | 2022-03-01 | East | MURRAY | Actual | 0
53 | 2022-03-01 | Central | Terra Firma | Budget
53 | 2022-03-01 | Central | Terra Firma | Forecast | 0
53 | 2022-03-01 | Central | Terra Firma | Actual | 0
53 | 2022-03-01 | Central | KLT | Budget
53 | 2022-03-01 | Central | KLT | Forecast | 0
53 | 2022-03-01 | Central | KLT | Actual | 0
53 | 2022-03-01 | Central | Forefront | Budget
53 | 2022-03-01 | Central | Forefront | Forecast | 0
53 | 2022-03-01 | Central | Forefront | Actual | 0
53 | 2022-03-01 | Central | DPF | Budget
53 | 2022-03-01 | Central | DPF | Forecast | 0
53 | 2022-03-01 | Central | DPF | Actual | 0
53 | 2022-03-01 | Central | OMJ | Budget
53 | 2022-03-01 | Central | OMJ | Forecast | 0
53 | 2022-03-01 | Central | OMJ | Actual | 0
53 | 2022-03-01 | Central | DHB Utilities | Budget
53 | 2022-03-01 | Central | DHB Utilities | Forecast | 0
53 | 2022-03-01 | Central | DHB Utilities | Actual | 0
53 | 2022-03-01 | Central | JDT | Budget
53 | 2022-03-01 | Central | JDT | Forecast | 0
53 | 2022-03-01 | Central | JDT | Actual | 0
53 | 2022-03-01 | Central | MURRAY | Budget
53 | 2022-03-01 | Central | MURRAY | Forecast | 0
53 | 2022-03-01 | Central | MURRAY | Actual | 0
53 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Budget
53 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | CMO West 1 | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Budget
53 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | CMO West 2 | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Budget
53 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | CMO East 1 | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Budget
53 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | CMO East 2 | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | West | DIRECT MOLE | Budget
53 | 2022-03-01 | West | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | West | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | East | DIRECT MOLE | Budget
53 | 2022-03-01 | East | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | East | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | Central | DIRECT MOLE | Budget
53 | 2022-03-01 | Central | DIRECT MOLE | Forecast | 0
53 | 2022-03-01 | Central | DIRECT MOLE | Actual | 0
53 | 2022-03-01 | CMO West 1 | SQS | Budget
53 | 2022-03-01 | CMO West 1 | SQS | Forecast | 0
53 | 2022-03-01 | CMO West 1 | SQS | Actual | 0
53 | 2022-03-01 | CMO West 2 | SQS | Budget
53 | 2022-03-01 | CMO West 2 | SQS | Forecast | 374.98
53 | 2022-03-01 | CMO West 2 | SQS | Actual | 0
53 | 2022-03-01 | CMO East 1 | SQS | Budget
53 | 2022-03-01 | CMO East 1 | SQS | Forecast | 0
53 | 2022-03-01 | CMO East 1 | SQS | Actual | 0
53 | 2022-03-01 | CMO East 2 | SQS | Budget
53 | 2022-03-01 | CMO East 2 | SQS | Forecast | 0
53 | 2022-03-01 | CMO East 2 | SQS | Actual | 0
53 | 2022-03-01 | West | SQS | Budget
53 | 2022-03-01 | West | SQS | Forecast | 0
53 | 2022-03-01 | West | SQS | Actual | 0
53 | 2022-03-01 | East | SQS | Budget
53 | 2022-03-01 | East | SQS | Forecast | 0
53 | 2022-03-01 | East | SQS | Actual | 0
53 | 2022-03-01 | Central | SQS | Budget
53 | 2022-03-01 | Central | SQS | Forecast | 0
53 | 2022-03-01 | Central | SQS | Actual | 0
|  | CMO East 2 | MURRAY | Actual
|  | West | Terra Firma | Budget
|  | West | Terra Firma | Forecast
|  | West | Terra Firma | Actual
|  | West | KLT | Budget
|  | West | KLT | Forecast
|  | West | KLT | Actual
|  | West | Forefront | Budget
|  | West | Forefront | Forecast
|  | West | Forefront | Actual
|  | West | DPF | Budget
|  | West | DPF | Forecast
|  | West | DPF | Actual
|  | West | OMJ | Budget
|  | West | OMJ | Forecast
|  | West | OMJ | Actual
|  | West | DHB UTILITIES | Budget
|  | West | DHB UTILITIES | Forecast
|  | West | DHB UTILITIES | Actual
|  | West | JDT | Budget
|  | West | JDT | Forecast
|  | West | JDT | Actual
|  | West | MURRAY | Budget
|  | West | MURRAY | Forecast
|  | West | MURRAY | Actual
|  | East | Terra Firma | Budget
|  | East | Terra Firma | Forecast
|  | East | Terra Firma | Actual
|  | East | KLT | Budget
|  | East | KLT | Forecast
|  | East | KLT | Actual
|  | East | Forefront | Budget
|  | East | Forefront | Forecast
|  | East | Forefront | Actual
|  | East | DPF | Budget
|  | East | DPF | Forecast
|  | East | DPF | Actual
|  | East | OMJ | Budget
|  | East | OMJ | Forecast
|  | East | OMJ | Actual
|  | East | DHB UTILITIES | Budget
|  | East | DHB UTILITIES | Forecast
|  | East | DHB UTILITIES | Actual
|  | East | JDT | Budget
|  | East | JDT | Forecast
|  | East | JDT | Actual
|  | East | MURRAY | Budget
|  | East | MURRAY | Forecast
|  | East | MURRAY | Actual
|  | Central | Terra Firma | Budget
|  | Central | Terra Firma | Forecast
|  | Central | Terra Firma | Actual
|  | Central | KLT | Budget
|  | Central | KLT | Forecast
|  | Central | KLT | Actual
|  | Central | Forefront | Budget
|  | Central | Forefront | Forecast
|  | Central | Forefront | Actual
|  | Central | DPF | Budget
|  | Central | DPF | Forecast
|  | Central | DPF | Actual
|  | Central | OMJ | Budget
|  | Central | OMJ | Forecast
|  | Central | OMJ | Actual
|  | Central | DHB UTILITIES | Budget
|  | Central | DHB UTILITIES | Forecast
|  | Central | DHB UTILITIES | Actual
|  | Central | JDT | Budget
|  | Central | JDT | Forecast
|  | Central | JDT | Actual
|  | Central | MURRAY | Budget
|  | Central | MURRAY | Forecast
|  | Central | MURRAY | Actual
|  | CMO West 1 | DIRECT MOLE | Budget
|  | CMO West 1 | DIRECT MOLE | Forecast
|  | CMO West 1 | DIRECT MOLE | Actual
|  | CMO West 2 | DIRECT MOLE | Budget
|  | CMO West 2 | DIRECT MOLE | Forecast
|  | CMO West 2 | DIRECT MOLE | Actual
|  | CMO East 1 | DIRECT MOLE | Budget
|  | CMO East 1 | DIRECT MOLE | Forecast
|  | CMO East 1 | DIRECT MOLE | Actual
|  | CMO East 2 | DIRECT MOLE | Budget
|  | CMO East 2 | DIRECT MOLE | Forecast
|  | CMO East 2 | DIRECT MOLE | Actual
|  | West | DIRECT MOLE | Budget
|  | West | DIRECT MOLE | Forecast
|  | West | DIRECT MOLE | Actual
|  | East | DIRECT MOLE | Budget
|  | East | DIRECT MOLE | Forecast
|  | East | DIRECT MOLE | Actual
|  | Central | DIRECT MOLE | Budget
|  | Central | DIRECT MOLE | Forecast
|  | Central | DIRECT MOLE | Actual
|  | CMO West 1 | SQS | Budget
|  | CMO West 1 | SQS | Forecast
|  | CMO West 1 | SQS | Actual
|  | CMO West 2 | SQS | Budget
|  | CMO West 2 | SQS | Forecast
|  | CMO West 2 | SQS | Actual
|  | CMO East 1 | SQS | Budget
|  | CMO East 1 | SQS | Forecast
|  | CMO East 1 | SQS | Actual
|  | CMO East 2 | SQS | Budget
|  | CMO East 2 | SQS | Forecast
|  | CMO East 2 | SQS | Actual
|  | West | SQS | Budget
|  | West | SQS | Forecast
|  | West | SQS | Actual
|  | East | SQS | Budget
|  | East | SQS | Forecast
|  | East | SQS | Actual
|  | Central | SQS | Budget
|  | Central | SQS | Forecast
|  | Central | SQS | Actual