## Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
|  |  | 2024-01-02 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2024-03-26 |  |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Not Started |  | 2024-01-02 | 2024-02-09 | 39 |  | Not Started
1.1 | – Project Charter | Complete |  | 2024-01-02 | 2024-01-11 | 10 |  | In Progress
1.1.1 | –– Project Charter Revisions | Complete |  | 2024-01-07 | 2024-01-11 | 5 |  | Complete
1.2 | – Research | Complete |  | 2024-01-10 | 2024-02-23 | 45 |  | On Hold
1.3 | – Projections | Complete |  | 2024-01-10 | 2024-01-20 | 11
1.4 | – Stakeholders | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 | – Guidelines | In Progress |  | 2024-01-19 | 2024-02-01 | 14
1.6 | – Project Initiation | In Progress |  | 2024-01-22 | 2024-02-09 | 19
2 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting | On Hold |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Communication Plan | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Risk Management | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – KPIs | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Monitoring | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Forecasts | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Project Updates | Not Started |  | 2024-02-22 | 2024-02-23 | 2
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4 | PROJECT PERFORMANCE / MONITORING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Quality Deliverables | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Effort & Cost Tracking | Not Started |  | 2024-02-25 | 2024-03-06 | 11
4.4 | – Project Performance | Not Started |  | 2024-03-03 | 2024-03-26 | 24
CLICK HERE TO CREATE IN SMARTSHEET

## Mursion SA
MURSION REPORTING STRETCH ASSIGNMENT
| PROJECT TITLE |  |  | START DATE
| Mursion Reporting Stretch Assignment Q1 2022 |  |  | 2022-01-01 |  | PROJECT DURATION
|  |  |  | END DATE |  | in days
| Noël Linden |  |  | 2022-04-01 |  | 91
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT INITIATION AND PLANNING | Complete |  | 2022-01-01 | 2022-01-27 | 27 |  | Not Started
1.1 | – Project initial meeting | Complete |  | 2022-01-03 | 2022-01-03 | 1 | with Victoria, Shonta and Josh | In Progress
1.1.1 | –– New Year Sync and second meeting with VM | Complete |  | 2022-01-07 | 2022-01-07 | 1 |  | Complete
1.2 | – Review current reporting and data | Complete |  | 2022-01-11 | 2022-01-11 | 1 | meeting with Josh | On Hold
1.3 | – Project initiation meeting | Complete |  | 2022-01-13 | 2022-01-13 | 1 | meeting with Victoria and Shonta
1.4 | – Obtain data source access | Complete |  | 2022-01-11 | 2022-01-21 | 11
1.5 | –Create Work Back Schedule for SA | Complete |  | 2022-01-17 | 2022-01-27 | 11 | send to VM and SPP by 1/31 for review
2 | PROJECT LAUNCH & EXECUTION | In Progress |  | 2022-01-27 | 2022-03-03 | 36
2.1 | –Connect data sources in PBI successfully | In Progress |  | 2022-02-02 | 2022-02-03 | 2 | requested access to SHMS, imported SP data
2.1.1 | –– Test joining sources | Not Started |  | 2022-02-02 | 2022-02-03 | 2 | troubleshoot if needed
2.1.2 | –– Touchbase with Josh | Not Started |  | 2022-02-03 | 2022-02-03 | 1 | 30 min meeting
2.1.3 | –– WBS review meeting | Not Started |  | 2022-02-03 | 2022-02-03 | 1 | meeting with VM and SPP
2.2 | –Build Individual view | Not Started |  | 2022-02-09 | 2022-02-10 | 2
2.3 | –Build Class, Region & Director view | Not Started |  | 2022-02-16 | 2022-02-22 | 7 | possible layer with Sr Mgr
2.3.1 | –– Touchbase with Josh | Not Started |  | 2022-02-17 | 2022-02-17 | 1
2.3.2 | –– Progress review with Shonta | Not Started |  | 2022-02-17 | 2022-02-17 | 1
2.4 | –Finalize first draft | Not Started |  | 2022-03-02 | 2022-03-03 | 2 | meet with VM and SPP
3 | PROJECT REFINEMENT & COMPLETION | In Progress |  | 2022-03-03 | 2022-04-01 | 30
3.1 | – Edit first draft | In Progress |  | 2022-03-09 | 2022-03-10 | 2
3.1.1 | –– Review first draft with Josh and SPP | Not Started |  | 2022-03-09 | 2022-03-09 | 1
3.1.2 | –– Review first draft with Nick, Isabel, Josh, VM | Not Started |  | 2022-03-10 | 2022-03-10 | 1 | send draft to Granmaison & DiNatale
3.2 | – Edit/revise dashboard | Not Started |  | 2022-03-16 | 2022-03-17 | 2
3.2.1 | –– Meet w. Grandmaison, DiNatale, SPP | Not Started |  | 2022-03-17 | 2022-03-17 | 1
3.2.2 | –– Meet with Michelle Hall (ID) | Not Started |  | 2022-03-17 | 2022-03-17 | 1
3.3 | – Edit/revise dashboard | Not Started |  | 2022-03-23 | 2022-03-24 | 2
3.3.1 | –– Review first draft with Nick, Josh, SPP | Not Started |  | 2022-03-24 | 2022-03-24 | 1
4 | Capstone | Not Started |  | 2022-03-30 | 2022-04-08 | 10
4.1 | – Edit/revise dashboard | Not Started |  | 2022-03-30 | 2022-03-31 | 2
4.2 | – Capstone Readout | Not Started |  | 2022-04-04 | 2022-04-08 | 5
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*