## Chart
REACTIVE MAINTENANCE
Total Number of Reactive Maintenance |  |  | 151
OPEN |  |  | 0
CLOSE |  |  | 151
REACTIVE MAINTENANCE - DEPARTMENT / SECTION
DEPARTMENT / SECTION | STATUS
| OPEN | CLOSE | TOTAL
HVA | 0 | 1 | 1
HYD | 0 | 10 | 10
GEN | 0 | 0 | 0
LV | 0 | 1 | 1
VER | 0 | 4 | 4
LC | 0 | 0 | 0
TEL | 0 | 0 | 0
KLE | 0 | 0 | 0
SAF | 0 | 0 | 0
CIVIL | 0 | 90 | 90
L-N-D | 0 | 23 | 23
H-H-C | 0 | 13 | 13
P-S-C | 0 | 7 | 7
OTHERS | 0 | 2 | 2

## RM
Work Order | Description | Project | Location | Asset | Section | Department | Status | Target Start | Target Finish | Scheduled Start | Scheduled Finish | Actual Start | Actual Finish
WO1441271 | painting on wall outside bld no 001 | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-15 08:15 | 2018-04-15 16:15 | 2018-04-15 09:17 | 2018-04-15 15:54 | #VALUE!
WO1433777 | Repair tiles in kitchen | M185 | M1851ZN4041100__0011 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-14 08:00 | 2018-04-14 16:00 | 2018-04-14 09:28 | 2018-04-14 15:48
WO1433790 | Check and Repair of doors , curtains and wardrobes | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-14 08:15 | 2018-04-14 16:15 | 2018-04-14 09:35 | 2018-04-14 15:49
WO1444999 | Apply Pest Control Outside and Inside Building | M185 | M1851ZN4 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-04-15 08:00 | 2018-04-15 16:00 | 2018-04-15 09:55 | 2018-04-15 15:59
WO1445837 | Cut Grass Outside Villa Garden | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-04-15 08:45 | 2018-04-15 16:00 | 2018-04-15 10:00 | 2018-04-15 15:58
WO1442215 | Servicing and checking of doors , windows , hinges ,curtains. | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-15 08:15 | 2018-04-15 15:45 | 2018-04-15 09:27 | 2018-04-15 15:57
WO1442244 | Check & Repair of Doors and Windows | NULL | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-15 08:15 | 2018-04-15 15:30 | 2018-04-15 09:27 | 2018-04-15 15:47
WO1443383 | Fix Electrical Pole inside building 001 | M185 | M1851VIP000100__0035 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-15 08:30 | 2018-04-15 16:30 | 2018-04-15 09:40 | 2018-04-15 15:53
WO1443403 | Fix Electrical Pole. | NULL | M1851VIP000100__0035 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-15 08:15 | 2018-04-15 16:00 | 2018-04-15 09:40 | 2018-04-15 15:52
WO1433561 | TEST ONLY | M185 | M1851VIP0XXX | NULL | NULL | NULL | CLOSE | NULL | NULL | 2018-04-10 09:00 | 2018-04-10 09:15 | 2018-04-11 09:11 | 2018-04-11 09:21
WO1433562 | Test Only Abdul Hakim Khan | M185 | M1851ZN2022101__ | 11502697 | NULL | NULL | CLOSE | NULL | NULL | 2018-04-11 08:00 | 2018-04-11 16:00 | 2018-04-11 09:32 | 2018-04-11 09:37
WO1433587 | cleaning the road | M185 | M1851VIP | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-11 23:53 | 2018-04-12 14:00 | 2018-04-11 10:02 | 2018-04-11 10:05
WO1433590 | painting coloum of balcony | M185 | M1851VIP000101__0148 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-11 10:00 | 2018-04-15 14:00 | 2018-04-11 10:25 | 2018-04-11 10:26
WO1433595 | painting balcony | M185 | M1851VIP000101__0108 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-11 08:00 | 2018-04-19 16:00 | 2018-04-11 11:04 | 2018-04-14 14:21
WO1433597 | repair lecking pipe | M185 | M1851VIP000100__0006 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-04-11 09:00 | 2018-04-12 14:45 | 2018-04-11 11:40 | 2018-04-12 15:34
WO1433598 | replace busted bulbs | M185 | M1851VIP000100__0028 | NULL | LV | ELEC | CLOSE | NULL | NULL | 2018-04-12 08:30 | 2018-04-14 15:00 | 2018-04-11 11:34 | 2018-04-14 14:19
WO1433603 | need to replace the capacitor | M185 | M1851VIP000101__0105 | NULL | HVA | MECH | CLOSE | NULL | NULL | 2018-04-11 13:15 | 2018-04-12 15:30 | 2018-04-11 11:28 | 2018-04-12 15:27
WO1433615 | cut the grass around main villa 001 | M185 | M1851VIP0XXX | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-04-11 07:45 | 2018-04-14 15:30 | 2018-04-11 12:01 | 2018-04-14 14:20
WO1490264 | Cleaning External Road | M185 | M1851VIP | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-16 07:45 | 2018-04-16 16:00 | 2018-04-16 12:09 | 2018-04-16 15:40
WO1444310 | Cleaning Outside Zone | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-15 08:00 | 2018-04-15 15:30 | 2018-04-15 09:47 | 2018-04-15 15:58
WO1491035 | Clean , inspect irrigations Valves | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-04-16 08:00 | 2018-04-16 16:00 | 2018-04-16 12:10 | 2018-04-16 15:32
WO1492746 | Apply Pest Control Inside and Outside Building | M185 | M185 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-04-16 11:00 | 2018-04-18 14:30 | 2018-04-16 12:42 | 2018-04-16 15:56
WO1492792 | Retouch bathroom , Ceiling near building 015 | M185 | M1851VIP0015 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-17 08:00 | 2018-04-17 15:45 | 2018-04-17 08:34 | 2018-04-17 14:54
WO1489116 | Service and Repair doors, hinges , curtains and wardrobes etc. | M185 | M1851ZN40411 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-16 08:15 | 2018-04-16 15:00 | 2018-04-16 12:30 | 2018-04-16 15:28
WO1489117 | Servicing | NULL | M1851ZN40411 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-16 08:15 | 2018-04-16 15:00 | 2018-04-16 12:29 | 2018-04-16 15:28
WO1489118 | Repair and refix manholes around the building # 001 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-16 12:15 | 2018-04-16 15:30 | 2018-04-16 12:31 | 2018-04-16 15:57
WO1489120 | Painting Outside wall near building # 332 | M185 | M1851ZN30332 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-16 08:15 | 2018-04-16 16:00 | 2018-04-16 12:08 | 2018-04-16 15:26
WO1492806 | Servicing all Hinges , windows etc in building # 432 | M185 | M1851ZN40432 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-17 08:45 | 2018-04-17 16:00 | 2018-04-17 08:54 | 2018-04-17 14:55
WO1492814 | Servicing and Checking Building # 461 ( Furniture , Accessories) | M185 | M1851ZN40461 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-17 09:00 | 2018-04-17 15:45 | 2018-04-17 09:00 | 2018-04-17 15:40
WO1492823 | Cleaning inside and outside building | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-17 10:30 | 2018-04-17 15:45 | 2018-04-17 09:09 | 2018-04-17 15:40
WO1545971 | Hedge clipping | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-04-22 09:30 | 2018-04-24 14:00 | 2018-04-22 08:12 | 2018-04-24 10:17
WO1545974 | Housekeeping (Inside and Outside) | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-22 09:15 | 2018-04-29 15:30 | 2018-04-22 08:18 | 2018-04-30 15:23
WO1536868 | painting one meter electrical pools | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-21 08:30 | 2018-04-22 16:30 | 2018-04-21 09:26 | 2018-04-22 15:12
WO1492910 | applying Paint to Manhole System Near Zone VIP | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-18 08:30 | 2018-04-19 14:00 | 2018-04-18 09:26 | 2018-04-19 15:23
WO1492912 | Repair and apply plaster outside wall Building # 411 | M185 | M1851ZN40411 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-18 11:30 | 2018-04-19 15:00 | 2018-04-18 09:30 | 2018-04-19 15:25
WO1492917 | Check doors, curtains,windows and unstability of furniture | M185 | M1851ZN1 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-18 10:30 | 2018-04-21 15:30 | 2018-04-18 09:34 | 2018-04-19 15:54
WO1492918 | Perform general cleaning of the external hardscrap and green areas | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-18 08:45 | 2018-04-18 15:45 | 2018-04-18 09:41 | 2018-04-18 15:52
WO1492946 | Flower and Shrub Bed Maintenance. | M185 | M1851 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-04-18 08:00 | 2018-04-18 15:30 | 2018-04-18 12:05 | 2018-04-18 15:53
WO1492960 | Cleaning External Road Outside Villa | M185 | M1851 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-04-18 13:00 | 2018-04-18 15:15 | 2018-04-18 14:46 | 2018-04-18 14:48
WO1572216 | Painting manhole cover black & green (ZN 1) | M185 | M1851ZN1 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-26 08:00 | 2018-04-28 15:45 | 2018-04-26 08:18 | 2018-04-28 14:47
WO1572217 | Remove and Refix Ceramic tiles building # 001 Room # 013 | M185 | M1851VIP000100__0013 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-26 08:30 | 2018-04-26 16:00 | 2018-04-26 08:25 | 2018-04-28 14:57
WO1572218 | Servicing and Oiling channel gate all zone | M185 | M1851 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-26 09:00 | 2018-04-26 15:00 | 2018-04-26 08:34 | 2018-04-26 15:46
WO1572361 | Retouch Ceiling in Building # 411 Room # 008,011,021,024 | M185 | M1851ZN4 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-29 08:30 | 2018-04-29 16:00 | 2018-04-29 08:46 | 2018-04-29 15:55
WO1572372 | Remove and Refix tiles in Building # 001 Balcony | M185 | M1851VIP000101__0148 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-29 08:00 | 2018-04-30 15:45 | 2018-04-29 09:05 | 2018-04-30 15:21
WO1552956 | Polishing and finishing door | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-23 10:00 | 2018-04-24 15:30 | 2018-04-23 11:09 | 2018-04-24 15:30
WO1552963 | Remove and Refix concrete tiles near building # 153 Outside | M185 | M1851ZN10153 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-23 08:30 | 2018-04-24 15:49 | 2018-04-23 11:21 | 2018-04-24 15:31
WO1552968 | Repair and servicing doors , windows , curtains etc. | M185 | M1851ZN2 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-23 09:30 | 2018-04-23 15:00 | 2018-04-23 11:27 | 2018-04-23 16:09
WO1539668 | Repair Manholes near Zone # 4. | M185 | M1851ZN4 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-21 09:00 | 2018-04-22 15:30 | 2018-04-21 09:45 | 2018-04-22 15:15
WO1572639 | Retouch wall and ceillng building 461 room no 002,006,009,012 | M185 | M1851ZN40461 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-01 08:30 | 2018-05-02 16:15 | 2018-05-01 11:13 | 2018-05-02 16:06
WO1572640 | plastering of wall inside building 461 room no 005 | M185 | M1851ZN3034100__0005 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-01 08:45 | 2018-05-02 16:30 | 2018-05-01 11:16 | 2018-05-02 16:07
WO1553124 | Refix Kerbstone near zone VIP | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-25 08:00 | 2018-04-25 16:00 | 2018-04-25 10:10 | 2018-04-25 15:00
WO1553127 | Apply Paint & Retouch | M185 | M1851VIP0012 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-25 08:30 | 2018-04-25 15:30 | 2018-04-25 10:15 | 2018-04-25 15:00
WO1553128 | Servicing and Repairs curtains and hinges and unstability of furniture | M185 | M1851ZN4 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-04-25 09:00 | 2018-04-25 15:00 | 2018-04-25 10:29 | 2018-04-25 15:01
WO1580449 | Retouch the ceiling in building no 001 room no 009,039,028,027 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-03 09:45 | 2018-05-04 15:00 | 2018-05-03 10:54 | 2018-05-03 15:30
WO1580450 | General interior checking doors,windows,hinges and unstably furnitures | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-03 08:15 | 2018-05-03 16:30 | 2018-05-03 10:52 | 2018-05-03 11:11
WO1580455 | Remove and refix marble inside the building 001 room 009 | M185 | M1851VIP000100__0009 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-03 09:00 | 2018-05-03 15:30 | 2018-05-03 10:54 | 2018-05-03 11:11
WO1580810 | Broken Sanitary Pipe Line G.I 1 1/4 " Outside Building 334 | M185 | M1851ZN30334 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-05-05 09:00 | 2018-05-05 09:00 | 2018-05-05 09:04 | 2018-05-06 11:00
WO1652640 | Retouch wall in Main Palace in 009,027,028,039 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-08 08:00 | 2018-05-09 16:00 | 2018-05-08 08:51 | 2018-05-09 16:43
WO1652645 | Perform General cleaning of the external hardscrap and green areas | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-05-01 07:30 | 2018-05-31 16:15 | 2018-05-08 08:58 | 2018-05-24 07:18
WO1652647 | Dusting furniture and correctly arrange vaccum , carpet , clean and sanitize bathrooms , public area | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-05-01 08:00 | 2018-05-31 16:30 | 2018-05-08 09:06 | 2018-05-24 07:19
WO1652656 | Irrigation System Inspection - Regular | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-05-01 08:00 | 2018-05-31 16:30 | 2018-05-08 09:33 | 2018-05-23 12:51
WO1652681 | Flower and shrub bed maintenance | M185 | M1851 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-05-01 08:00 | 2018-05-28 16:30 | 2018-05-08 09:41 | 2018-05-24 12:09
WO1652693 | Hedge Clipping | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-05-01 08:00 | 2018-05-31 16:00 | 2018-05-08 09:49 | 2018-05-24 07:19
WO1652700 | Grass cutting in entire palace garden | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-05-01 08:00 | 2018-05-31 16:00 | 2018-05-08 09:58 | 2018-05-24 12:10
WO1652708 | Pest Control entire palace - inside and outside | M185 | M185 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-05-01 08:00 | 2018-05-31 16:30 | 2018-05-08 10:11 | 2018-05-17 12:17
WO1680255 | Repair and Refix flooring tiles outside main villa | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-09 08:00 | 2018-05-11 17:00 | 2018-05-10 09:23 | 2018-05-13 09:37
WO1685922 | Asset: Lift Hoistway Mechanical maintenance_ZNVIP001_LF002 | M185 | M1851VIP0001 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-05-13 08:30 | 2018-05-14 16:30 | 2018-05-13 10:06 | 2018-05-14 08:23
WO1685932 | Repair flooring tiles outside main villa 001 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-12 08:00 | 2018-05-13 16:30 | 2018-05-13 10:16 | 2018-05-13 16:23
WO1685937 | Repair Manholes Outside Main Palace Build # 001 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-13 08:00 | 2018-05-16 16:30 | 2018-05-13 10:25 | 2018-05-15 15:38
WO1685944 | Refix Ceramic Tiles Build # 411 , RM # 008 | M185 | M1851ZN4041100__0008 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-13 08:00 | 2018-05-16 16:30 | 2018-05-13 10:52 | 2018-05-15 15:37
WO1581002 | Check and clean Lifts Hoistway , Panels etc. | M185 | M185 | NULL | VER | ELEC | CLOSE | NULL | NULL | 2018-05-05 08:00 | 2018-05-05 16:21 | 2018-05-05 15:22 | 2018-05-05 16:20
WO1581044 | Cut grass from garden and dispose | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-05-05 08:00 | 2018-05-05 16:00 | 2018-05-05 16:25 | 2018-05-05 16:25
WO1581046 | Cut grass from garden and dispose | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-05-05 08:00 | 2018-05-05 16:00 | 2018-05-05 16:26 | 2018-05-05 16:26
WO1680690 | Check furniture, doors , hinges , curtains inside building | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-09 08:00 | 2018-05-11 16:00 | 2018-05-10 09:32 | 2018-05-13 16:24
WO1720566 | Applying Polish in Main Door Bldg # 411 | M185 | M1851ZN40411 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-14 08:00 | 2018-05-17 11:45 | 2018-05-16 08:14 | 2018-05-19 10:00
WO1721708 | Making a plaster for curb behind of main palace bldg 001 | M185 | M1851VIP0XXX | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-16 08:15 | 2018-05-16 16:30 | 2018-05-16 10:24 | 2018-05-16 16:20
WO1720788 | Apply metal coatings to diesel tank in Generator Room ZN4 | M185 | M1851ZN40ER5 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-14 08:00 | 2018-05-16 16:30 | 2018-05-16 08:25 | 2018-05-16 16:15
WO1720953 | Fix net on window from outside Bldg # 001 Main Palace | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-14 08:00 | 2018-05-28 07:40 | 2018-05-16 08:41 | 2018-05-28 07:39
WO1721875 | Repair Curbstone Outside ZN 1 , Garden Area | M185 | M1851ZN1 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-16 08:00 | 2018-05-16 16:00 | 2018-05-16 10:46 | 2018-05-16 16:06
WO1732159 | Apply masonary work main villa 001 around for one fountain outside | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-17 06:30 | 2018-05-25 12:00 | 2018-05-20 09:27 | 2018-05-21 12:46
WO1732163 | Retouch electrical building ER2 , ZN1 and apply metal coating to diesel tank. | M185 | M1851ZN10ER2 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-17 08:00 | 2018-05-19 12:00 | 2018-05-17 09:35 | 2018-05-19 12:07
WO1732254 | Pest control apply inside building # 411 ,115 ,001 | M185 | M1851 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-05-17 06:00 | 2018-05-17 12:00 | 2018-05-17 06:00 | 2018-05-17 12:00
WO1760709 | Scarap and apply white cement in outside Fountain #2 near main palace 001 | M185 | M1851VIP0XXX00__FT02 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-24 06:30 | 2018-07-21 10:41 | 2018-07-21 08:01 | 2018-07-21 10:34
WO1776455 | Refix Marble tiles in Fountain # 2 Outside Zone VIP | M185 | M1851VIP0XXX00__FT02 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-26 06:30 | 2018-05-28 19:43 | 2018-05-26 06:54 | 2018-05-28 07:43
WO1760743 | Add chlorine to sanitary water tank ( Location - 012 water tank ) | M185 | M1851VIP0012-1__ | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-05-24 06:00 | 2018-05-24 12:00 | 2018-05-24 08:45 | 2018-05-24 11:44
WO1760506 | Repair Kerbstone aroound the road near zone vip 001 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-23 06:00 | 2018-05-23 13:00 | 2018-05-23 06:57 | 2018-05-23 12:49
WO1760509 | Apply polish to door frame and retouch door | M185 | M1851ZN3033500__0002 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-23 06:30 | 2018-05-24 20:11 | 2018-05-23 08:00 | 2018-05-24 12:10
WO1760565 | Fix Door locks in building # 335 | M185 | M1851ZN30335 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-13 08:00 | 2018-05-13 16:00 | 2018-05-23 10:23 | 2018-05-23 10:24
WO1777211 | Broken Sanitary Pipe Line G.I 1 1/4" | M185 | M1851ZN30332 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-05-04 08:00 | 2018-05-30 10:13 | 2018-05-04 08:00 | 2018-05-04 10:30
WO1777283 | Broken Sanitary Pipe Line G.I 1 1/4" | M185 | M1851ZN30332 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-05-30 11:03 | 2018-05-30 11:03 | 2018-05-30 11:04 | 2018-05-30 11:33
WO1777448 | General interior checking , doors, windows , hinges and unstability bldg # 432 | M185 | M1851ZN40432 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-30 06:30 | 2018-05-31 13:03 | 2018-05-30 06:30 | 2018-05-31 12:30
WO1777450 | Refix tiles , Scrap , and apply retouch in FT# 3 | M185 | M1851 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-30 06:00 | 2018-06-02 | 2018-05-31 07:47 | 2018-06-04 12:41
WO1777451 | Remove tiles scrap and retouch FT#1 | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-05-30 06:00 | 2018-06-03 13:00 | 2018-06-04 07:53 | 2018-07-03 11:17
WO1777453 | Door / Window Rolling shutter Inspection All Zone | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-01 06:00 | 2018-06-13 13:00 | 2018-06-01 06:00 | 2018-06-23 11:08
WO1777454 | To check door locks, hinges , curtain and furniture unstability in the Bldg # 152,153,154, 432,461 | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-02 08:00 | 2018-06-04 13:00 | 2018-06-02 08:00 | 2018-06-23 11:08
WO1821790 | To check door , locks hinges and perform other related task in bldg # 331,332,333,334,335,351,341 | M185 | M1851ZN3 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-06 06:30 | 2018-06-13 13:00 | 2018-06-06 06:30 | 2018-06-23 11:11
WO1821791 | To check door locks , hinges , curtain and unstability of furniture in bldg # 411,016,432,461 | M185 | M1851ZN4 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-19 08:00 | 2018-06-24 17:00 | 2018-06-19 09:30 | 2018-06-23 11:30
WO1819456 | Perform general cleaning of external hardscrap and green areas | M185 | M1851 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 17:00 | 2018-06-02 08:51 | 2018-06-28 16:12
WO1819485 | Dusting Furniture and correctly arrange , vaccum , carpet , clean and sanitize bathrooms | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 17:00 | 2018-06-02 08:52 | 2018-06-28 16:13
WO1822641 | Scrap tiles surface preparation and retouch fountain # 4 | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-06 10:59 | 2018-06-06 10:59 | 2018-06-06 11:30 | 2018-07-25 10:46
WO1821537 | Irrigation System Inspection & Maintenance | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 16:30 | 2018-06-02 08:59 | 2018-06-26 08:13
WO1821538 | Irrigation Valve Boxes | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 16:30 | 2018-06-02 09:07 | 2018-06-26 08:14
WO1821542 | Flower and shrub bed maintenance | M185 | M1851 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 16:30 | 2018-06-02 09:17 | 2018-06-28 16:13
WO1821545 | Hedge Clipping | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 17:00 | 2018-06-02 06:00 | 2018-06-28 16:13
WO1821547 | Grass cutting in entire palace garden | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-06-02 06:00 | 2018-06-30 16:30 | 2018-06-02 06:00 | 2018-06-28 16:14
WO1821552 | To check door locks , hinges , curtain , and unstability of furniture 001 ,015,GH1 | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-02 06:30 | 2018-06-30 17:00 | 2018-06-02 10:02 | 2018-06-26 08:59
WO1852516 | Scrap , refix and retouch inside in fountain # 4 | M185 | M1851 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-05 06:00 | 2018-06-12 | 2018-06-11 10:04 | 2018-06-23 10:28
WO1934413 | Apply pest control in Bldg # 151,152,153,154,331,332,333,334,335,341,351 | M185 | M185 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-06-27 08:30 | 2018-06-28 16:30 | 2018-06-27 08:30 | 2018-06-30 10:27
WO1934527 | Repair Marble Grounting in Bldg # 001 , 015 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-27 08:30 | 2018-06-30 16:00 | 2018-06-27 08:30 | 2018-06-30 10:28
WO1852815 | Remove and Refix pavement cement tiles | M185 | M1851VIP0XXX | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-07 06:30 | 2018-06-13 17:03 | 2018-06-07 06:30 | NULL
WO2039698 | Repair and Refix Cement pavement tiles and curbstone near Bldg #143 Parking | M185 | M1851ZN1014300__PK02 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-25 09:00 | 2018-07-26 16:00 | 2018-07-25 09:00 | 2018-07-25 16:00
WO1884521 | Removing rust stains from marble inside building # 411 | M185 | M1851ZN4041100__0002 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-19 08:00 | 2018-06-19 18:29 | 2018-06-19 08:00 | 2018-06-20 08:06
WO2031267 | To replace the grounting of tiles in Bldg # 411 , 432 , 461 | M185 | M1851ZN40411 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-02 10:00 | 2018-07-03 16:00 | 2018-07-02 10:10 | 2018-07-03 11:48
WO1931382 | Rusting stains marble inside building 001 garden outside area | M185 | M1851VIP000100__0035 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-26 08:00 | 2018-06-26 16:30 | 2018-06-23 09:59 | 2018-06-23 15:40
WO2031276 | Perform general cleaning of external hardscrap and green area | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-07-01 07:30 | 2018-07-31 14:30 | 2018-07-02 10:30 | 2018-07-30 15:43
WO2031277 | Dusting Furniture and correctly arrange , vaccum , carpet , clean and sanitize bathroom | M185 | M185 | NULL | H-H-C | HHC | CLOSE | NULL | NULL | 2018-07-01 07:30 | 2018-07-31 16:30 | 2018-07-01 07:35 | 2018-07-30 15:43
WO2031279 | Irrigation System Inspection and Maintenance | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-01 | 2018-07-31 00:40 | 2018-07-01 10:43 | 2018-07-29 15:41
WO1885070 | Refix facade marble outside Bldg # 015 | M185 | M1851VIP0015 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-20 10:00 | 2018-06-20 16:49 | 2018-06-20 10:49 | 2018-06-20 16:08
WO2031481 | Check - Irrigation Valve Boxes - Maintenance ( 4 - VALVE BOXES) | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-01 08:30 | 2018-07-31 16:00 | 2018-07-02 15:31 | 2018-07-24 15:51
WO2031492 | Flower and shrub bed maintenance | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-01 08:00 | 2018-07-31 16:30 | 2018-07-02 15:39 | 2018-07-29 15:43
WO2031494 | Hedge Clipping | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-01 09:00 | 2018-07-31 16:00 | 2018-07-07 09:15 | 2018-07-29 15:45
WO2031738 | Hedge trimming and dispose | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-01 08:00 | 2018-07-31 16:14 | 2018-07-03 14:17 | 2018-07-29 15:44
WO2031741 | Ficus Cutting | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-01 07:45 | 2018-07-01 15:45 | 2018-07-03 14:23 | 2018-07-29 15:42
WO2031900 | Plaster work of pavement slope near ZN1 - GARAGE | M185 | M1851ZN10142 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-04 08:30 | 2018-07-04 16:45 | 2018-07-04 09:00 | 2018-07-04 15:59
WO2031917 | To check doors , locks and hinges and unstability of furniture in bldg # 411,016,432,461 | M185 | M1851ZN4 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-01 08:00 | 2018-07-31 16:00 | 2018-07-04 10:01 | 2018-07-29 15:39
WO2031925 | To check doors, locks and hinges in Bldg # 001 , 015 | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-01 08:00 | 2018-07-31 12:06 | 2018-07-01 08:00 | 2018-07-25 15:30
WO2031931 | To check doors , locks , hinges and unstability of furniture in Bldg # 131,132,133,134 | M185 | M1851ZN1 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-01 08:00 | 2018-07-31 16:30 | 2018-07-04 10:19 | 2018-07-29 15:40
WO2031938 | To check doors , locks , hinges and unstability of furniture in Bldg # 331,332,333,334,335,351,341 | M185 | M1851ZN3 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-01 00:15 | 2018-07-31 16:30 | 2018-07-01 00:15 | 2018-07-25 16:00
WO2031943 | Door / Windows Rolling shutter inspection all zones | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-01 08:00 | 2018-07-31 12:29 | 2018-07-04 10:32 | 2018-07-29 15:39
WO2031947 | Change New Locks and cylinder in Bldg # 152 Room # 17 | M185 | M1851ZN1015200__0017 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-03 10:35 | 2018-07-04 11:37 | 2018-07-03 10:35 | 2018-07-03 11:35
WO1933098 | Repair Wood skirting in buildg # 015 | M185 | M1851VIP001500__0003 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-24 09:00 | 2018-06-24 16:00 | 2018-06-24 09:00 | 2018-06-25 08:42
WO2032209 | Change cylinder In Bldg # 001 Main Gate 2 | M185 | M1851VIP0001 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-05 09:10 | 2018-07-06 17:13 | 2018-07-05 09:10 | 2018-07-05 09:50
WO1933127 | Repair Wood skirting in buildg # 015 | M185 | M1851VIP001500__0003 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-24 09:00 | 2018-06-24 16:00 | 2018-06-24 09:49 | 2018-06-25 08:43
WO1933344 | Lift Hoistway Mechanical Maintenance_ZNVIP001_LF002 | M185 | M1851VIP0001GN__LF02 | NULL | VER | ELEC | CLOSE | NULL | NULL | 2018-06-25 08:30 | 2018-06-25 17:05 | 2018-06-25 08:30 | 2018-06-25 10:20
WO1933402 | Apply Herbicide Outside Grass and Garden Area | M185 | M185 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-06-25 08:15 | 2018-06-25 15:45 | 2018-06-25 08:30 | NULL
WO1933460 | Lift Standard Hswy & Lndg Dumb Waiter (DUMB WAITER-RELAY) FOODS LIFT | M185 | M1851VIP0001GN__LF02 | NULL | VER | ELEC | CLOSE | NULL | NULL | 2018-06-25 10:15 | 2018-06-25 16:00 | 2018-06-25 10:15 | 2018-06-26 08:16
WO1933464 | Repair Civil works near Building # 016 | M185 | M1851ZN40XXX | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-25 08:30 | 2018-06-25 18:46 | 2018-06-25 10:47 | 2018-06-26 08:19
WO2032550 | Grounting Ceramic tiles in bldg # 152,153,154 Location - Bathroom | M185 | M1851ZN1 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-07 08:01 | 2018-07-07 16:30 | 2018-07-07 13:03 | 2018-07-07 16:00
WO1933670 | Apply pest control inside and outside bldg # 001,015,411 | M185 | M185 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-06-26 08:00 | 2018-06-26 16:27 | 2018-06-26 08:28 | 2018-06-26 16:33
WO2032739 | Broken G.I PIPE 1" NEAR GATE # 01 | M185 | M1851VIP0XXX00__GA01 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-07-07 08:00 | 2018-07-08 16:00 | 2018-07-08 08:00 | 2018-07-08 12:00
WO2033118 | G.I Pipe broken 3/4" outside Building # 152 | M185 | M1851ZN10152 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-07-09 08:00 | 2018-07-10 16:00 | 2018-07-09 08:45 | 2018-07-10 15:45
WO2033634 | Ceramic Tiles Refix and Grounting in Bldg 341 | M185 | M1851ZN3034100__ | 11502691 | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-11 08:30 | 2018-07-11 17:46 | 2018-07-11 08:30 | 2018-07-11 12:00
WO2033789 | Refix ceramic Tiles in Bldg 001 Room # 148 Balcony | M185 | M1851VIP000101__0148 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-12 08:30 | 2018-07-12 12:00 | 2018-07-12 08:30 | 2018-07-12 11:30
WO2034027 | Broken GI Pipe 3/4" near Garden Area Gate # 01 | M185 | M185 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-07-12 09:00 | 2018-07-14 16:15 | 2018-07-12 08:15 | 2018-07-14 15:30
WO2034241 | Repair of Pavement Cement Tile in ZNVIP Outside | M185 | M1851VIP | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-15 09:00 | 2018-07-21 04:00 | 2018-07-15 11:18 | 2018-07-21 16:25
WO2034809 | Lift Standard Hswy & Lndg Dumb Waiter (DUMB WAITER-RELAY) FOODS LIFT | M185 | M1851VIP0001GN__LF02 | NULL | VER | ELEC | CLOSE | NULL | NULL | 2018-07-17 08:00 | 2018-07-17 16:00 | 2018-07-17 13:17 | 2018-07-17 16:10
WO2035202 | G.I Pipe 3/4" broken inside Bldg # 152 | M185 | M1851ZN1015200__0001 | NULL | HYD | MECH | CLOSE | NULL | NULL | 2018-07-18 10:00 | 2018-07-20 00:14 | 2018-07-19 08:15 | 2018-07-19 16:00
WO2035210 | Repair Plain Cement Concrete Near Bldg # 143 Outside | M185 | M1851ZN1014300__ | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-19 08:30 | 2018-07-19 16:00 | 2018-07-19 08:24 | 2018-07-19 16:04
WO2035806 | Apply Vertebrae Pests in Bldg # 001,015,411 | M185 | M185 | NULL | L-N-D | LND | CLOSE | NULL | NULL | 2018-07-22 08:00 | 2018-07-22 16:30 | 2018-07-22 08:00 | 2018-07-22 16:01
WO2035933 | Remove and Refix cement Tiles and Repair Sanitary Pipe Line in Bldg # 152 _ Kitchen and Outside | M185 | M1851ZN1015200__0009 | NULL | CIVIL | CIV | CLOSE | NULL | NULL | 2018-07-25 08:00 | 2018-07-31 17:00 | 2018-07-22 08:35 | 2018-07-22 16:02
WO2036250 | Apply Pest Control inside and outside building all zone | M185 | M185 | NULL | P-S-C | PSC | CLOSE | NULL | NULL | 2018-07-23 08:30 | 2018-07-23 16:30 | 2018-07-23 08:00 | 2018-07-26 16:15