## Sheet1
[12 empty] | 1 |  | 2 |  |  | 4 | 5 |  |  | 7 | 8 |  |  | 10 | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69
Type (EC, PCR, New Product) | Tool Builder | Project Owner | -Project Status | - Job award date | - First Parts Due | - First Assembly Trial | - Start of Production | -Tool Completion Date |  | -Tool Delivery Date |  | - Project Development Kickoff Date (job award +10 days) |  | - Pre Launch Control Plan (tool delivery -7) |  | - Control Plan Completion Date (PPAP Submission -7) |  | - PFMEA Completion Date (planned sample completion +7) |  | - Sub-Supplier PPAP Completion Date (First Assembly Trial - 10) |  | - Check Fixture / Gage Delivery Due Date (First Parts -7) |  | - MSA Completion Date (first parts due +14) |  | - Process Capability Study Due Date (first parts due +21) |  | - PV testing completion date (SOP -45) |  | - Grain Completion Date (SOP -70) |  | - Grain and Color Approval (SOP - 60) |  | - PPAP Submission Date (SOP-45) |  | - PPAP Approval Date (SOP-7) |  | - SORF Request (Tool delivery +2 days) |  | - Sample completed (Tool delivery +7 days) |  | - Work Instruction Completion Date (sample completed +7) |  | - Inspection Standard / Key Feature Diagram (Kickoff +14) |  | - Job Instruction Manual / Process parameters (First Sample +14) | [5 empty] | -Tool Completion Date | - Project Development Kickoff Date (job award +10 days) | - Pre Launch Control Plan | - Control Plan Completion Date | - PFMEA Completion Date | - Sub-Supplier PPAP Completion Date (First Parts Due - 10) | - Check Fixture / Gage Delivery Due Date | - MSA Completion Date | - Process Capability Study Due Date | - PV testing completion date | - Grain Completion Date | - Grain and Color Approval | - PPAP Submission Date | - PPAP Approval Date | - SORF Request (Tool delivery +2 days) | - Sample completed (Tool delivery +7 days) | - Work Instruction Completion Date (sample completed +7) | -Number of items delivered late | -Items Delivered |  |  |  | -Project Development rating | -Date | -Items Delivered | -Items Due | -Items due not completed
|  |  | On Hold | Actual | Actual | Actual | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
New | TBD | Engineering |  | 2018-09-13 | 2019-01-25 | 2019-01-25 | 2020-01-06 | 2019-01-05 |  | 2019-01-06 |  | 2018-09-23 | 2018-09-24 | 2018-12-29 | 2018-01-31 | 2019-11-15 |  | 2019-01-20 |  | 2019-01-15 | N/A | 2019-01-18 | N/A | 2019-02-08 |  | 2019-02-15 |  | 2019-11-22 | N/A | 2019-10-28 | N/A | 2019-11-07 | N/A | 2019-11-22 |  | 2019-12-30 |  | 2019-01-08 |  | 2019-01-13 |  | 2019-01-20 |  | 2018-10-07 |  | 2019-01-27 | [5 empty] | Schedule | 1 | -332 | Schedule | Schedule | N/A | N/A | Schedule | Schedule | N/A | N/A | N/A | Schedule | Schedule | Schedule | Schedule | Schedule | 1 | 2 |  |  |  | 50% | 2018-10-18 | 20 | 25
New | Across Mold | Engineering |  | 2017-12-12 | 2018-02-26 | 2018-02-28 | 2019-04-01 | 2018-03-03 | 2018-03-08 | 2018-06-08 | 2018-06-06 | 2017-12-22 | 2017-12-18 | 2018-02-24 |  | 2019-02-08 |  | 2018-06-22 |  | 2018-02-18 | N/A | 2018-02-19 | 2018-02-19 | 2018-03-12 |  | 2018-03-19 | N/A | 2019-02-15 | N/A | 2019-01-21 | N/A | 2019-01-31 | N/A | 2019-02-15 |  | 2019-03-25 |  | 2018-06-10 | 2018-06-07 | 2018-06-15 | 2018-06-14 | 2018-06-22 |  | 2018-01-05 | N/A | 2018-06-29 | [5 empty] | 5 | -4 | Incomplete | Schedule | Incomplete | N/A | 0 | Incomplete | N/A | N/A | N/A | N/A | Schedule | Schedule | -3 | -1 | Incomplete | 1 | 5 |  |  |  | 80% | 2018-11-18 | 0 | 13
New | Across Mold | Engineering |  | 2017-12-12 | 2018-02-26 | 2018-02-28 | 2019-04-01 | 2018-03-03 | 2018-03-05 | 2018-06-08 | 2018-06-06 | 2017-12-22 | 2017-12-18 | 2018-02-24 |  | 2019-02-08 |  | 2018-06-22 |  | 2018-02-18 | N/A | 2018-02-19 | 2018-02-19 | 2018-03-12 |  | 2018-03-19 | N/A | 2019-02-15 | N/A | 2019-01-21 | N/A | 2019-01-31 | N/A | 2019-02-15 |  | 2019-03-25 |  | 2018-06-10 | 2018-06-07 | 2018-06-15 | 2018-07-03 | 2018-06-22 |  | 2018-01-05 | N/A | 2018-06-29 | [5 empty] | 2 | -4 | Incomplete | Schedule | Incomplete | N/A | 0 | Incomplete | N/A | N/A | N/A | N/A | Schedule | Schedule | -3 | 18 | Incomplete | 2 | 5 |  |  |  | 60% | 2018-12-18 | 0 | 15
EC | Kuhns | Engineering |  | 2018-05-08 | 2018-05-29 | 2018-05-29 | 2018-02-10 | 2018-06-04 | 2018-06-01 | 2018-06-08 | 2018-06-01 | 2018-05-18 |  | 2018-05-28 | 2016-12-12 | 2018-04-02 | 2017-12-12 | 2018-06-22 | 2016-12-12 | 2018-05-19 | 2017-01-31 | 2018-05-22 | 2017-02-10 | 2018-06-12 |  | 2018-06-19 | N/A | 2017-12-27 | N/A | 2017-12-02 | N/A | 2017-12-12 | N/A | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-06-10 | 2018-06-10 | 2018-06-15 | 2018-06-15 | 2018-03-07 | 2018-02-20 | 2018-06-01 | N/A | 2018-03-14 | 2017-03-08 |  |  |  |  | -3 | Incomplete | -532 | -111 | -557 | -473 | -466 | Incomplete | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | -15 | 0 | 7 |  |  |  | 100%
New | R&M | Engineering |  | 2016-10-20 | 2018-02-19 | 2018-02-20 | 2018-07-13 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2016-10-30 | 2016-10-25 | 2017-02-09 | N/A | 2018-06-14 | 2018-04-11 | 2017-03-02 | 2018-03-15 | 2018-02-10 | 2018-02-10 | 2018-05-18 | 2018-05-31 | 2018-06-08 | 2018-07-13 | 2018-03-12 | 2018-07-19 | 2018-05-29 | N/A | 2018-05-04 | N/A | 2018-05-14 | N/A | 2018-06-21 | 2018-07-19 | 2018-07-06 |  | 2017-02-18 | 2017-01-23 | 2017-02-23 | 2017-01-30 | 2017-03-02 | 2018-07-13 | 2016-11-13 | N/A | 2017-03-09 | 2017-01-31 |  |  |  |  | 0 | -5 | N/A | -64 | 378 | 0 | 13 | 35 | 129 | N/A | N/A | N/A | 28 | Incomplete | -26 | -24 | 498 | 6 | 12 |  |  |  | 50%
New | R&M | Engineering |  | 2016-10-20 | 2018-02-19 | 2018-02-20 | 2018-07-13 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2016-10-30 | 2016-10-25 | 2017-02-09 | N/A | 2018-06-25 | 2018-04-15 | 2017-03-02 | 2018-04-15 | 2018-02-10 | 2018-02-10 | 2018-05-18 | 2018-05-31 | 2018-06-08 | 2018-06-22 | 2018-06-29 | 2018-06-29 | 2018-05-29 | 2018-02-02 | 2018-05-04 | N/A | 2018-05-14 | N/A | 2018-07-02 | 2018-07-02 | 2018-07-06 |  | 2017-02-18 | 2017-01-17 | 2017-02-23 | 2017-01-27 | 2018-06-21 | 2018-06-20 | 2016-11-13 | N/A | 2017-03-09 | 2017-01-30 |  |  |  |  | 0 | -5 | N/A | -71 | 409 | 0 | 13 | 14 | 0 | -116 | N/A | N/A | 0 | Incomplete | -32 | -27 | -1 | 3 | 13 |  |  |  | 76.92%
New | R&M | Engineering |  | 2016-10-20 | 2018-02-19 | 2018-02-20 | 2018-07-13 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2016-10-30 | 2016-10-25 | 2017-02-09 | N/A | 2018-06-14 | 2018-05-01 | 2017-03-02 | 2018-05-01 | 2018-02-10 | 2018-02-10 | 2018-07-19 | 2018-07-13 | 2018-06-08 | 2018-07-26 | 2018-03-12 | 2018-08-14 | 2018-05-29 | 2018-02-02 | 2018-05-04 | N/A | 2018-05-14 | N/A | 2018-06-21 | 2018-08-14 | 2018-07-06 |  | 2017-02-18 | 2017-01-23 | 2017-02-23 | 2017-01-31 | 2017-03-02 | 2018-07-31 | 2016-11-13 | N/A | 2017-03-09 | 2017-02-28 |  |  |  |  | 0 | -5 | N/A | -44 | 425 | 0 | -6 | 48 | 155 | -116 | N/A | N/A | 54 | Incomplete | -26 | -23 | 516 | 5 | 13 |  |  |  | 61.54%
New | R&M | Engineering |  | 2016-10-20 | 2018-02-19 | 2018-02-20 | 2018-07-13 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2016-10-30 | 2016-10-25 | 2017-02-09 | N/A | 2018-06-14 | 2018-05-01 | 2017-03-02 | 2018-05-01 | 2018-02-10 | 2018-02-10 | 2018-07-19 | 2018-07-13 | 2018-06-08 | 2018-07-26 | 2018-03-12 | 2018-08-08 | 2018-05-29 | 2018-02-02 | 2018-05-04 | N/A | 2018-05-14 | N/A | 2018-06-21 | 2018-08-08 | 2018-07-06 |  | 2017-02-18 | 2017-01-23 | 2017-02-23 | 2017-01-30 | 2017-03-02 | 2018-07-31 | 2016-11-13 | N/A | 2017-03-09 | 2017-01-31 |  |  |  |  | 0 | -5 | N/A | -44 | 425 | 0 | -6 | 48 | 149 | -116 | N/A | N/A | 48 | Incomplete | -26 | -24 | 516 | 5 | 13 |  |  |  | 61.54%
EC | Trifecta | Engineering |  | 2018-05-10 | 2018-06-07 | 2018-06-07 | 2018-08-06 | 2018-06-01 | 2018-05-31 | 2018-06-03 | 2018-05-31 | 2018-05-20 | 2018-05-10 | 2018-05-25 | 2016-12-12 | 2017-09-29 | 2017-09-07 | 2017-03-02 | 2017-03-15 | 2017-09-30 | 2017-09-30 | 2017-10-03 | 2017-02-11 | 2017-10-24 | 2017-05-17 | 2017-10-31 | 2017-10-31 | 2017-10-06 | 2017-09-23 | 2018-05-28 | N/A | 2018-06-07 | N/A | 2018-07-13 | 2018-07-11 | 2018-07-30 |  | 2018-06-05 | 2018-05-31 | 2018-06-10 | 2018-06-21 | 2017-03-02 | 2017-03-02 | 2018-06-03 | N/A | 2017-03-09 | 2017-03-09 |  |  |  |  | -1 | -10 | -529 | -22 | 13 | 0 | -234 | -160 | 0 | -13 | N/A | N/A | -2 | Incomplete | -5 | 11 | 0 | 2 | 13 |  |  |  | 84.62%
New | R&M | Engineering |  | 2018-08-09 | 2018-10-11 | 2018-11-02 | 2018-11-02 | 2018-10-11 | 2018-10-05 | 2018-10-08 | 2018-10-10 | 2018-08-19 | 2018-08-21 | 2018-10-04 | 2018-10-04 | 2018-11-23 | 2018-10-08 | 2018-10-22 | 2018-10-08 | 2018-10-23 | 2018-10-23 | 2018-10-04 | 2018-10-04 | 2018-10-25 |  | 2018-11-01 |  | 2018-10-30 | 2018-10-22 | 2018-11-01 |  | 2018-11-15 |  | 2018-11-30 |  | 2018-11-30 |  | 2018-10-10 | 2018-10-03 | 2018-10-15 | 2018-10-10 | 2018-10-22 |  | 2018-09-02 | 2018-09-02 | 2018-10-29 | [5 empty] | -6 | 2 | 0 | -46 | -14 | 0 | 0 | Incomplete | Incomplete | -8 | Incomplete | Coming Due | Coming Due | Coming Due | -7 | -5 | Incomplete | 1 | 10 |  |  |  | 90%
New | R&M | Engineering |  | 2018-06-28 | 2018-12-17 | 2018-05-20 | 2019-11-11 | 2018-09-30 | 2018-10-15 | 2019-03-01 |  | 2018-07-08 | 2018-07-17 | 2018-09-23 |  | 2019-09-20 |  | 2019-03-15 |  | 2018-05-10 | N/A | 2018-12-10 |  | 2018-12-31 |  | 2019-01-07 |  | 2019-09-27 |  | 2019-09-02 | N/A | 2019-09-12 | N/A | 2019-09-27 |  | 2019-11-04 |  | 2019-03-03 |  | 2019-03-08 |  | 2019-03-15 |  | 2018-07-22 |  | 2019-03-22 | [5 empty] | 15 | 9 | Incomplete | Schedule | Schedule | N/A | Schedule | Schedule | Schedule | Schedule | N/A | N/A | Schedule | Schedule | Schedule | Schedule | Schedule | 2 | 2 |  |  |  | 0%
New | OMC | Engineering |  | 2017-08-28 | 2017-11-29 | 2018-04-24 | 2018-10-30 | 2017-11-03 | 2017-11-03 | 2017-12-12 | 2017-12-12 | 2017-09-07 | 2017-10-30 | 2017-10-27 | 2017-09-26 | 2018-10-08 | 2017-09-26 | 2017-12-26 | 2017-09-26 | 2018-04-14 |  | 2017-11-22 | 2017-11-28 | 2017-12-13 |  | 2017-12-20 |  | 2018-10-01 | 2018-08-27 | 2018-08-21 | 2018-04-09 | 2018-08-31 | 2018-09-19 | 2018-10-15 | 2018-10-15 | 2018-10-23 | 2018-10-19 | 2017-12-14 | 2017-12-12 | 2017-12-19 | 2017-12-14 | 2017-12-26 | 2018-10-19 | 2017-09-21 | 2017-09-15 | 2018-01-02 | 2018-01-29 |  |  |  |  | 0 | 53 | -31 | -377 | -91 | Incomplete | 6 | Incomplete | Incomplete | -35 | -134 | 19 | 0 | -4 | -2 | -5 | 297 | 4 | 13 |  |  |  | 69.23%
New | R&M | Engineering |  | 2017-08-11 | 2017-11-29 | 2018-04-24 | 2018-10-30 | 2017-10-25 | 2017-10-26 | 2017-12-19 | 2017-12-19 | 2017-08-21 | 2017-08-16 | 2017-10-18 | 2018-01-15 | 2018-09-08 | 2018-01-15 | 2018-01-02 | 2018-07-12 | 2018-04-14 | 2014-03-28 | 2017-11-22 | 2017-11-27 | 2017-12-13 |  | 2017-12-20 | N/A | 2018-10-08 | 2018-08-27 | 2018-08-21 | 2018-07-12 | 2018-08-31 | 2018-09-19 | 2018-09-15 | 2018-10-03 | 2018-10-23 | 2018-10-09 | 2017-12-21 | 2018-01-24 | 2017-12-26 | 2018-02-15 | 2018-01-02 | 2018-10-15 | 2017-09-04 | 2017-10-10 | 2018-01-09 | [5 empty] | 1 | -5 | 89 | -236 | 191 | -1478 | 5 | Incomplete | N/A | -42 | -40 | 19 | 18 | -14 | 34 | 51 | 286 | 9 | 14 |  |  |  | 35.71%
New | R&M | Engineering |  | 2017-08-11 | 2017-11-29 | 2018-04-24 | 2018-10-30 | 2017-10-25 | 2017-10-26 | 2017-12-19 | 2017-12-19 | 2017-08-21 | 2017-08-16 | 2017-10-18 | 2018-01-15 | 2018-09-08 | 2018-01-15 | 2018-01-02 | 2018-07-12 | 2018-04-14 | 2016-02-24 | 2017-11-22 | 2017-11-27 | 2017-12-13 |  | 2017-12-20 | N/A | 2018-10-08 | 2018-08-27 | 2018-08-21 | 2018-07-12 | 2018-08-31 | 2018-09-19 | 2018-09-15 | 2018-10-08 | 2018-10-23 | 2018-10-16 | 2017-12-21 | 2018-01-24 | 2017-12-26 | 2018-02-15 | 2018-01-02 | 2018-10-15 | 2017-09-04 | 2017-10-10 | 2018-01-09 | [5 empty] | 1 | -5 | 89 | -236 | 191 | -780 | 5 | Incomplete | N/A | -42 | -40 | 19 | 23 | -7 | 34 | 51 | 286 | 9 | 14 |  |  |  | 35.71%
New | R&M | Engineering |  | 2017-08-11 | 2017-11-29 | 2018-04-24 | 2018-10-30 | 2017-10-25 | 2017-10-26 | 2017-12-19 | 2017-12-19 | 2017-08-21 | 2017-08-16 | 2017-10-18 | 2018-01-15 | 2018-09-08 | 2018-01-15 | 2018-01-02 | 2018-07-12 | 2018-04-14 | 2016-02-24 | 2017-11-22 | 2017-11-27 | 2017-12-13 |  | 2017-12-20 | N/A | 2018-10-08 | 2018-08-27 | 2018-08-21 | 2018-07-12 | 2018-08-31 | 2018-09-19 | 2018-09-15 | 2018-10-08 | 2018-10-23 | 2018-10-16 | 2017-12-21 | 2018-01-24 | 2017-12-26 | 2018-02-15 | 2018-01-02 | 2018-10-15 | 2017-09-04 | 2017-10-10 | 2018-01-09 | [5 empty] | 1 | -5 | 89 | -236 | 191 | -780 | 5 | Incomplete | N/A | -42 | -40 | 19 | 23 | -7 | 34 | 51 | 286 | 9 | 14 |  |  |  | 35.71%
New | R&M | Engineering |  | 2018-09-15 | 2018-12-17 | 2018-12-17 | 2019-11-25 | 2018-11-26 |  |  |  | 2018-09-25 | 2018-09-24 | 2018-11-19 |  | 2019-10-04 |  |  |  | 2018-12-07 |  | 2018-12-10 |  | 2018-12-31 |  | 2019-01-07 | N/A | 2019-10-11 |  | 2019-09-16 |  | 2019-09-26 |  | 2019-10-11 |  | 2019-11-18 | [7 empty] | 2018-10-09 |  |  |  | 47: Coming Due; 48: -1; 49: Coming Due; 50: Schedule; 52: Schedule; 53: Schedule; 54: Schedule; 55: N/A; 56: Schedule; 57: Schedule; 58: Schedule; 59: Schedule; 60: Schedule; 64: 0; 65: 1; 69: 100%
New | R&M | Engineering |  | 2018-09-15 | 2018-12-17 | 2018-12-17 | 2019-11-25 | 2018-11-26 |  |  |  | 2018-09-25 | 2018-09-24 | 2018-11-19 |  | 2019-10-04 |  |  |  | 2018-12-07 |  | 2018-12-10 |  | 2018-12-31 |  | 2019-01-07 | N/A | 2019-10-11 |  | 2019-09-16 |  | 2019-09-26 |  | 2019-10-11 |  | 2019-11-18 | [7 empty] | 2018-10-09 |  |  |  | 47: Coming Due; 48: -1; 49: Coming Due; 50: Schedule; 52: Schedule; 53: Schedule; 54: Schedule; 55: N/A; 56: Schedule; 57: Schedule; 58: Schedule; 59: Schedule; 60: Schedule; 64: 0; 65: 1; 69: 100%
New | R&M | Engineering |  | 2018-09-15 | 2018-12-17 | 2018-12-17 | 2019-11-25 | 2018-11-26 |  |  |  | 2018-09-25 | 2018-09-24 | 2018-11-19 |  | 2019-10-04 |  |  |  | 2018-12-07 |  | 2018-12-10 |  | 2018-12-31 |  | 2019-01-07 | N/A | 2019-10-11 |  | 2019-09-16 |  | 2019-09-26 |  | 2019-10-11 |  | 2019-11-18 | [7 empty] | 2018-10-09 |  |  |  | 47: Coming Due; 48: -1; 49: Coming Due; 50: Schedule; 52: Schedule; 53: Schedule; 54: Schedule; 55: N/A; 56: Schedule; 57: Schedule; 58: Schedule; 59: Schedule; 60: Schedule; 64: 0; 65: 1; 69: 100%
New | R&M | Engineering |  | 2018-09-15 | 2018-12-17 | 2018-12-17 | 2019-11-25 | 2018-11-26 |  |  |  | 2018-09-25 | 2018-09-24 | 2018-11-19 |  | 2019-10-04 |  |  |  | 2018-12-07 |  | 2018-12-10 |  | 2018-12-31 |  | 2019-01-07 | N/A | 2019-10-11 |  | 2019-09-16 |  | 2019-09-26 |  | 2019-10-11 |  | 2019-11-18 | [7 empty] | 2018-10-09 |  |  |  | 47: Coming Due; 48: -1; 49: Coming Due; 50: Schedule; 52: Schedule; 53: Schedule; 54: Schedule; 55: N/A; 56: Schedule; 57: Schedule; 58: Schedule; 59: Schedule; 60: Schedule; 64: 0; 65: 1; 69: 100%
New | R&M | Engineering |  | 2017-07-06 | 2017-12-14 | 2017-12-14 | 2018-10-01 | 2017-10-15 | 2017-10-17 | 2017-12-19 | 2017-12-19 | 2017-07-16 | 2017-09-28 | 2017-10-08 | 2018-01-16 | 2018-08-10 | 2018-01-16 | 2018-01-02 | 2018-01-16 | 2017-12-04 | 2014-03-28 | 2017-12-07 | 2017-11-16 | 2017-12-28 |  | 2018-01-04 | N/A | 2018-11-09 | 2018-08-27 | 2018-07-23 | 2018-08-24 | 2018-08-02 |  | 2018-08-17 |  | 2018-09-24 |  | 2017-12-21 | 2017-12-19 | 2017-12-26 | 2018-01-17 | 2018-01-02 |  | 2017-07-30 | 2017-10-10 | 2018-01-09 | 2018-01-17 |  |  |  |  | 2 | 74 | 100 | -206 | 14 | -1347 | -21 | Incomplete | N/A | -74 | 32 | Incomplete | Incomplete | Incomplete | -2 | 22 | Incomplete | 6 | 10 |  |  |  | 40%
New | R&M | Engineering |  | 2017-07-06 | 2017-12-14 | 2017-12-14 | 2018-10-01 | 2017-10-15 | 2017-10-17 | 2017-12-19 | 2017-12-19 | 2017-07-16 | 2017-09-28 | 2017-10-08 | 2018-01-16 | 2018-08-10 | 2018-01-16 | 2018-01-02 | 2018-01-16 | 2017-12-04 | 2016-02-24 | 2017-12-07 | 2017-11-16 | 2017-12-28 |  | 2018-01-04 | N/A | 2018-11-09 | 2018-08-27 | 2018-07-23 | 2018-08-24 | 2018-08-02 |  | 2018-08-17 |  | 2018-09-24 |  | 2017-12-21 | 2018-01-24 | 2017-12-26 | 2018-02-15 | 2018-01-02 |  | 2017-07-30 | 2017-10-10 | 2018-01-09 | 2018-01-17 |  |  |  |  | 2 | 74 | 100 | -206 | 14 | -649 | -21 | Incomplete | N/A | -74 | 32 | Incomplete | Incomplete | Incomplete | 34 | 51 | Incomplete | 7 | 10 |  |  |  | 30%
New | R&M | Engineering |  | 2017-07-06 | 2017-12-14 | 2017-12-14 | 2018-10-01 | 2017-10-15 | 2017-10-17 | 2017-12-19 | 2017-12-19 | 2017-07-16 | 2017-09-28 | 2017-10-08 | 2018-01-16 | 2018-08-10 | 2018-01-16 | 2018-01-02 | 2018-01-16 | 2017-12-04 | 2016-02-24 | 2017-12-07 | 2017-11-16 | 2017-12-28 |  | 2018-01-04 | N/A | 2018-11-09 | 2018-08-27 | 2018-07-23 | 2018-08-24 | 2018-08-02 |  | 2018-08-17 |  | 2018-09-24 |  | 2017-12-21 | 2018-01-24 | 2017-12-26 | 2018-02-15 | 2018-01-02 |  | 2017-07-30 | 2017-10-10 | 2018-01-09 | 2018-01-17 |  |  |  |  | 2 | 74 | 100 | -206 | 14 | -649 | -21 | Incomplete | N/A | -74 | 32 | Incomplete | Incomplete | Incomplete | 34 | 51 | Incomplete | 7 | 10 |  |  |  | 30%
[69 empty] | 0 | 0
[69 empty] | 0 | 0
[69 empty] | 0 | 0
[69 empty] | 0 | 0
#DIV/0! | [47 empty] | 64: 0; 65: 0
| 0 | [46 empty] | 64: 0; 65: 0
[69 empty] | 0 | 0
[69 empty] | 0 | 0
[69 empty] | 0 | 0
[69 empty] | 79 | 122 | 35.25%
Formulas:
Plan = IFS([Actual]="","",ISNUMBER([Actual]),[Actual]+10)
Plan = IFS([Plan]="","",ISNUMBER([Plan]),[Plan]-7)
Note on K5: tgsmith: Tool late due to Chinese new year
Note on AA5: tgsmith: Not Required
Note on K6: tgsmith: Tool late due to Chinese new year
Note on AA6: tgsmith: Not Required
Note on AH13: tgsmith: testing for 20% GF
Note on BY35: Tyler Smith: Percent of items delivered on time