## Sheet1
Job Status | Sched Resource | Mtl Status | Floor Seq | Job Priority | Job Number | Plt Prep | Job Promise By | # OCRs | Job OD By | Job Req By | 1st Ship Date | Op Start Time | Op End Date | Part | Rem Hrs | Rem Qty | Rem Qty (M) | OH Qty | Dmd Qty | MinPlusSafety | Op Prod. Std | Dimensions | Operation Comments | Print Name | Job Created | Paper Color | Basis Wt | Size# | Ink % | Ink1 | Ink2 | Ink3 | Ink4 | Prev Opr % Cmplt | Carton Number | Avail Qty | Rush | Rev | Side Seam | Op Run Qty | Run Qty (M) | Traveler Printed | Carton Pack | Description | Sched Est Hrs | Ink Prep | OpSeq | Custom Part | Job End | Op Qty Cmplt | Part Comments | Company | UOM | Year Job Req Due | Month Job Req Due | Week Job Req Due | WhatIfRecord | Job Code
STARTED ¦ OVERDUE | B1 | OK | 10 | IMMED | 160777-1-1 | TRUE |  | 0 | 16 | 2024-08-22 | 2024-08-22 | 07:00 AM | 2024-09-03 | 15706 | 6.08 | 38 | 76 | 0 | 0 | 0 | 6.25 | 2 3/4 x 10 | Plate Damaged 8/14 - ETA is 8/16 for Plate to be in house 9/6 given as B/O date 53 cases part shipped 8/16 | Parker John's | 2024-07-18 | Recycled Natural | 30 |  | 25 | Black 39999 |  |  |  | 0 | CTN101_52 | 0 | FALSE | A | FALSE | 100 | 200 | 2024-07-29 | 2000 | 2 3/4 x 10 Recycled Natural Merchandise Prtd *Parker John's* 1c/1s Black 39999, CN17192. | 8.52 | TRUE | 10 | TRUE | 2024-09-07 | 62 | Make sure sample room gets plenty of samples | WCI | CS | 2024 | 8 | 34 | FALSE
STARTED | 250 | OK | 10 | IMMED | 161140-1-1 | TRUE |  | 0 | -7 | 2024-09-16 | 2024-09-16 | 07:00 AM | 2024-09-05 | 15695 | 27.8 | 556 | 111.2 | 0 | 0 | 0 | 20 | 10 1/2 x 3 3/4 x 16 |  | Reformation (word only) | 2024-08-02 | Recycled Natural | 78 |  | 25 | White 30305 |  |  |  | 0 | CTN15_59 | 0 | FALSE | B | FALSE | 650 | 130 | 2024-08-09 | 200 | 10 1/2 x 3 3/4 x 16 Recycled Natural Eco-Natural Lite P/S Prtd *Reformation (word only)* 1c/1s White 30305, CN12263. | 28.3 | TRUE | 10 | TRUE | 2024-09-09 | 94 |  | WCI | CS | 2024 | 9 | 38 | FALSE | SP
READY ¦ PLATES NOT READY ¦ INK NOT READY ¦ CUS CREDIT HOLD | 650 | OK | 10 | IMMED | 161478-1-1 | FALSE |  | 0 | -4 | 2024-09-06 | 2024-09-06 | 08:00 AM | 2024-08-29 | 15931 | 0.5 | 2 | 1 | 0 | 0 | 0 | 4 | 5 x 3 1/8 x 9 5/8 |  | Go Mustangs! (State Farm Steve Kropp) | 2024-08-23 | White | 35 | 4# | 25 | CMYK - Digital |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 2 | 1 | 2024-08-26 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Prtd *Go Mustangs! (State Farm Steve Kropp)* 1c/1s CMYK - Digital, CN17342. | 0.75 | FALSE | 10 | TRUE | 2024-09-02 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ CUS CREDIT HOLD | 405 | OK | 11 | IMMED | 160213-2-1 | TRUE |  | 0 | -3 | 2024-09-03 | 2024-09-03 | 09:55 AM | 2024-08-29 | 12936 | 2.11 | 20 | 10 | 0 | 0 | 0 | 9.5 | 6 x 3 5/8 x 11 1/16 | Use New Grease paper Only - Roll Lot# MUST start with a T | Central Pastry Shop | 2024-06-25 | White Grease Resistant | 35 | 6# | 25 | Ruby Red 199u |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 20 | 10 | 2024-08-13 | 500 | 6 x 3 5/8 x 11 1/16 White Grease Resistant SOS 6# Prtd *Central Pastry Shop* 1c/1s Ruby Red 199u CN15526 . | 2.61 | TRUE | 10 | TRUE | 2024-08-31 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ OVERDUE | 405 | OK | 13 | IMMED | 160239-2-1 | TRUE |  | 0 | 1 | 2024-09-04 | 2024-09-04 | 05:31 PM | 2024-09-03 | 14250 | 2.11 | 20 | 10 | 0 | 0 | 0 | 9.5 | 6 x 3 5/8 x 11 1/16 |  | Soda Station | 2024-06-26 | Natural Grease Resistant | 35 | 6# | 25 | Black 39999 |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 20 | 10 | 2024-08-01 | 500 | 6 x 3 5/8 x 11 1/16 Natural Grease Resistant SOS 6# Prtd *Soda Station* 1c/1s Black 39999 CN16201 . | 2.61 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
MAINT JOB | 250 |  | 15 | IMMED | MNT029350 | FALSE |  | 0 | -8 | 2024-09-06 |  | 12:00 AM | 2024-08-29 | <250> | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 1/2 x 3 3/4 x 16->12 1/2 x 4 x 20 |  |  | 2024-08-26 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 1 | 0 |  |  | 10 1/2 x 3 3/4 x 16->12 1/2 x 4 x 20 | 0 | FALSE | 10 | FALSE | 2024-08-29 | 0 |  | WCI | M | 2024 | 9 | 36 | FALSE
MAINT JOB | B2 |  | 15 | IMMED | MNT029170 | FALSE |  | 0 | -13 | 2024-09-11 |  | 06:00 AM | 2024-08-29 | <B2> | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 8 3/8 x 9 -> 3 x 2 x 9 | Change Over 4.50 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-05 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 8 3/8 x 9 -> 3 x 2 x 9 | 5 | FALSE | 10 | FALSE | 2024-08-29 | 0 |  | WCI | M | 2024 | 9 | 37 | FALSE
READY ¦ PLATES NOT READY ¦ INK NOT READY | 405 | OK | 15 | IMMED | 028528 | FALSE |  | 0 | -9 | 2024-09-14 |  | 12:08 AM | 2024-09-03 | SOGN6 | 6 | 48 | 24 | 125 | 0 | 185 | 8 | 6 x 3 5/8 x 11 1/16 | Do not get over 192 on hand unless order exceeds that |  | 2024-05-20 | Natural Grease Resistant | 35 | 6# | [5 empty] | 0 | CTN51_54 | 125 | FALSE | B | FALSE | 48 | 24 | 2024-06-12 | 500 | 6 x 3 5/8 x 11 1/16 Natural Grease Resistant SOS 6# Unprinted . | 6.25 | FALSE | 10 | FALSE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ PLATES NOT READY ¦ INK NOT READY | 405 | OK | 17 | IMMED | 028944 | FALSE |  | 0 | -7 | 2024-09-13 | 2024-08-30 | 09:23 AM | 2024-09-04 | SOWH6 | 22.4 | 224 | 112 | 263 | 110 | 712 | 10 | 6 x 3 5/8 x 11 1/16 | Do not get over 500 on hand unless order exceeds that |  | 2024-07-10 | White | 35 | 6# | [5 empty] | 0 | CTN51_54 | 153 | FALSE | A | FALSE | 224 | 112 | 2024-08-15 | 500 | 6 x 3 5/8 x 11 1/16 White SOS 6# Unprinted . | 23.4 | FALSE | 10 | FALSE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ CUS CREDIT HOLD | 405 | OK | 19 | IMMED | 160193-1-1 | TRUE |  | 0 | 2 | 2024-09-04 | 2024-09-04 | 06:47 PM | 2024-09-04 | 08491 | 2 | 20 | 10 | 0 | 0 | 0 | 10 | 6 x 3 5/8 x 11 1/16 |  | Avera Txt - RX | 2024-06-24 | White | 35 | 6# | 25 | Green (spl) 341u | Black 39999 |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 20 | 10 | 2024-08-15 | 500 | 6 x 3 5/8 x 11 1/16 White SOS 6# Prtd *Avera Txt - RX* 2c/2s Green (spl) 341u , Black 39999 CN12924 . | 3 | TRUE | 10 | TRUE | 2024-09-06 | 0 | No WCI markings on cartons or paperwork | WCI | CS | 2024 | 9 | 36 | FALSE
STARTED ¦ BELOW 0 | 102 | OK | 20 | IMMED | 028368 | TRUE |  | 0 | -10 | 2024-09-10 | 2024-09-03 | 05:00 AM | 2024-08-29 | 15068 | 1.89 | 51 | 51 | 160 | 21120 | 0 | 27 | 6 1/8 x 2 1/2 x 15 1/2 | 18" Paper - Needs to have Green Pallet Tags | Subway | 2024-05-01 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-07-08 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 2.39 | TRUE | 10 | TRUE | 2024-08-31 | 909 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 37 | FALSE
STARTED ¦ PLATES NOT READY ¦ INK NOT READY | 104 | OK | 20 | IMMED | 029097 | FALSE |  | 0 | -1 | 2024-09-06 |  | 05:00 AM | 2024-09-03 | SLWS1717 | 2.88 | 46 | 11.5 | 313 | 0 | 357 | 16 | 17 x 9 x 17 |  |  | 2024-07-25 | Sani-Liner Specialty Paper | 40 | [6 empty] | 0 | CTN11_55 | 313 | FALSE | A | FALSE | 96 | 24 | 2024-07-26 | 250 | 17 x 9 x 17 Sani-Liner Specialty Paper Sani-Liner Unprinted . | 3.13 | FALSE | 10 | FALSE | 2024-09-05 | 50 | Use Wet Stregth glue on bottom (ADH-BS-4) and seam (ADH-SM-2)!!! | WCI | CS | 2024 | 9 | 36 | FALSE
STARTED | 302 | OK | 20 | IMMED | 029311 | TRUE |  | 0 | -13 | 2024-09-13 |  | 06:00 AM | 2024-08-29 | EPNA12G | 0.6 | 12 | 2.4 | 260 | 10 | 278 | 20 | 12 1/2 x 4 x 20 |  |  | 2024-08-22 | Recycled Natural | 105 | 12G | [5 empty] | 100 | CTN34_50 | 250 | FALSE | B | FALSE | 80 | 16 | 2024-08-23 | 200 | 12 1/2 x 4 x 20 Recycled Natural Eco-Shipper P/S 12G Stock Printed With Recycled Logo. | 1.25 | TRUE | 20 | FALSE | 2024-08-31 | 68 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE | B2 | OK | 20 | IMMED | 160955-1-1 | TRUE |  | 0 | 2 | 2024-09-04 | 2024-09-04 | 07:00 PM | 2024-09-02 | 15882 | 1.2 | 3 | 30 | 0 | 0 | 0 | 2.5 | 3 x 2 x 9 |  | Alohaaa | 2024-07-30 | White Grease Resistant | 20 |  | 25 | Red (spl) 2347u |  |  |  | 0 | CTN72_46 | 0 | FALSE | A | FALSE | 3 | 30 | 2024-07-31 | 10000 | 3 x 2 x 9 White Grease Resistant Merchandise Prtd *Alohaaa* 1c/1s Red (spl) 2347u, CN17312 Packed 10/1000. | 1.7 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ PLATES NOT READY | 250 | OK | 20 | IMMED | 161565-1-1 | FALSE |  | 0 | -22 | 2024-10-01 | 2024-10-01 | 10:18 AM | 2024-09-05 | 15943 | 2 | 40 | 8 | 0 | 0 | 0 | 20 | 12 1/2 x 4 x 20 | Job is short 688#s - Run paper call complete |  | 2024-08-22 | Natural | 78 | 12G | [5 empty] | 0 |  | 0 | FALSE | A | FALSE | 40 | 8 | 2024-08-27 | 200 | 12 1/2 x 4 x 20 Natural Eco-Natural Lite P/S 12G Stock Printed. | 2.5 | TRUE | 10 | TRUE | 2024-09-09 | 0 | Paper Part # TEST48 34.00" Virgin Linerboard - 78# - IP - Test Roll Run on machine 250 For all test parts: 25 samples and Test Report to Laura Gerbers - Purchasing upon completion. Total qty will be monitored by Production; This is a test to see how paper runs on machine, tests for glue, etc. Fill our paper test results form Run up all the test paper | WCI | CS | 2024 | 10 | 40 | FALSE
READY | 405 | OK | 20 | IMMED | 160452-3-1 | TRUE |  | 0 | -5 | 2024-09-16 | 2024-09-16 | 08:23 PM | 2024-09-09 | 01919 | 5.26 | 50 | 25 | 0 | 0 | 0 | 9.5 | 6 x 3 5/8 x 11 1/16 |  | Tufts Medical Center | 2024-07-05 | White | 35 | 6# | 25 | Pantone Process Blue 50 | Blue Dk 289u |  |  | 0 | CTN51_74 | 0 | FALSE | B | FALSE | 50 | 25 | 2024-08-26 | 500 | 6 x 3 5/8 x 11 1/16 White SOS 6# Prtd *Tufts Medical Center* 2c/1s Pantone Process Blue 50 , Blue Dk 289u CN7548 . | 5.76 | TRUE | 10 | TRUE | 2024-09-11 | 0 | Show DS PO# on cartons. | WCI | CS | 2024 | 9 | 38 | FALSE
STARTED ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | 401 | OK | 25 | IMMED | 029306 | FALSE |  | 0 | 1 | 2024-08-30 | 2024-09-13 | 04:00 AM | 2024-08-29 | SOWH4 | 0.78 | 9 | 4.5 | 222 | 131 | 504 | 11.5 | 5 x 3 1/8 x 9 5/8 | Do not get over 504 on hand unless order exceeds that |  | 2024-08-21 | White | 35 | 4# | [5 empty] | 0 | CTN51_54 | 91 | FALSE | A | FALSE | 224 | 112 | 2024-08-22 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Unprinted . | 1.28 | FALSE | 10 | FALSE | 2024-08-31 | 215 |  | WCI | CS | 2024 | 8 | 35 | FALSE
STARTED ¦ PLATES NOT READY ¦ INK NOT READY | 108 | OK | 25 | IMMED | 029275 | FALSE |  | 0 | -1 | 2024-09-06 | 2024-09-13 | 07:00 AM | 2024-09-03 | GRWH46 | 6.15 | 83 | 83 | 82 | 80 | 111 | 13.5 | 4 3/4 x 6 3/4 |  |  | 2024-08-15 | White | 30 | [6 empty] | 0 | CTN29_51 | 2 | FALSE | A | FALSE | 160 | 160 | 2024-08-19 | 1000 | 4 3/4 x 6 3/4 White/Glassine Gourmet Unprinted . | 7.61 | FALSE | 10 | FALSE | 2024-09-05 | 77 |  | WCI | CS | 2024 | 9 | 36 | FALSE
!! MTL ISSUE | 102 | SUBRN-1800-35 PO 34460 Due 08/30/24 | 25 | IMMED | 028370 | TRUE |  | 0 | 3 | 2024-09-03 | 2024-09-03 | 07:23 AM | 2024-09-04 | 15068 | 35.56 | 960 | 960 | 160 | 21120 | 0 | 27 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-05-01 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-05-23 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 36.06 | TRUE | 10 | TRUE | 2024-09-06 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 36 | FALSE
MAINT JOB | B2 |  | 25 | IMMED | MNT029225 | FALSE |  | 0 | -8 | 2024-09-12 |  | 12:42 AM | 2024-09-04 | <B2> | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 3 x 2 x 9 -> 6 1/4 x 9 1/4 | Change Over 6.50 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-12 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 3 x 2 x 9 -> 6 1/4 x 9 1/4 | 7 | FALSE | 10 | FALSE | 2024-09-04 | 0 |  | WCI | M | 2024 | 9 | 37 | FALSE
MAINT JOB | 250 |  | 25 | IMMED | MNT029351 | FALSE |  | 0 | -1 | 2024-09-12 |  | 03:48 PM | 2024-09-11 | <250> | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 12 1/2 x 4 x 20-> 12 1/2 x 4 x 18 |  |  | 2024-08-26 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 1 | 0 |  |  | 12 1/2 x 4 x 20-> 12 1/2 x 4 x 18 | 12 | FALSE | 10 | FALSE | 2024-09-11 | 0 |  | WCI | M | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | 401 | OK | 27 | IMMED | 029340 | FALSE |  | 0 | 9 | 2024-09-03 | 2024-09-13 | 05:16 AM | 2024-09-10 | SOWH4 | 41.74 | 480 | 240 | 222 | 131 | 504 | 11.5 | 5 x 3 1/8 x 9 5/8 | Do not get over 504 on hand unless order exceeds that |  | 2024-08-23 | White | 35 | 4# | [5 empty] | 0 | CTN51_54 | 91 | FALSE | A | FALSE | 480 | 240 | 2024-08-27 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Unprinted . | 42.24 | FALSE | 10 | FALSE | 2024-09-12 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
MAINT JOB | 108 |  | 30 | IMMED | MNT029352 | FALSE |  | 0 | 9 | 2024-08-25 |  | 08:36 AM | 2024-09-03 | <108> | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 4 3/4 x 6 3/4 -> 6 1/4 x 9 1/4 | Change Over 2.75 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-26 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 4 3/4 x 6 3/4 -> 6 1/4 x 9 1/4 | 3.25 | FALSE | 10 | FALSE | 2024-09-03 | 0 |  | WCI | M | 2024 | 8 | 35 | FALSE
READY ¦ OVERDUE | B2 | OK | 30 | IMMED | 160831-1-1 | TRUE |  | 1 | 3 | 2024-09-03 | 2024-09-03 | 06:42 AM | 2024-09-04 | 14751 | 0.48 | 10 | 10 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Edgewood Warrenville | 2024-07-22 | White | 30 |  | 25 | Green Dk (spl) 3308u |  |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 10 | 10 | 2024-07-22 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *Edgewood Warrenville* 1c/1s Green Dk (spl) 3308u CN16526 . | 0.98 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 30 | IMMED | 028366 | TRUE |  | 0 | -5 | 2024-09-12 | 2024-09-03 | 11:27 AM | 2024-09-05 | 15068 | 10.5 | 504 | 504 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-05-01 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-07-01 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 11 | TRUE | 10 | TRUE | 2024-09-07 | 456 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ PLATES NOT READY | 401 | OK | 30 | IMMED | 029245 | FALSE |  | 0 | 9 | 2024-09-04 |  | 06:31 AM | 2024-09-11 | HWRN4 | 9.74 | 224 | 56 | 220 | 12 | 332 | 23 | 5 x 3 1/8 x 9 5/8 |  |  | 2024-08-14 | Recycled Natural | 50 | 4# | [5 empty] | 0 | CTN51_54 | 208 | FALSE | A | FALSE | 224 | 56 | 2024-08-15 | 250 | 5 x 3 1/8 x 9 5/8 Recycled Natural Hardware 4# Stock Printed With Recycled Logo. | 9.97 | TRUE | 10 | FALSE | 2024-09-13 | 0 | Recycled Logo printed with Black 39999. Case pack 250 | WCI | CS | 2024 | 9 | 36 | FALSE
STARTED ¦ OVERDUE ¦ INK NOT READY | 801 | OK | 40 | IMMED | 161387-2-1 | TRUE |  | 0 | 22 | 2024-09-24 | 2024-09-24 | 05:00 AM | 2024-10-14 | 10686 | 22.27 | 24 | 6.125 | 0 | 0 | 0 | 1.1 | 10 x 5 x 13 |  | Seroogy's | 2024-08-14 | Recycled Natural | 63 |  | 25 | Metallic Gold 07hs |  |  |  | 0 | CTN85_96 | 0 | FALSE | A | FALSE | 30 | 7.5 | 2024-08-15 | 250 | 10 x 5 x 13 Recycled Natural Handled Shopper Hot Stamp *Seroogy's* 1c/1s Metallic Gold 07hs CN14380 . | 24.13 | FALSE | 10 | TRUE | 2024-10-16 | 5.5 |  | WCI | CS | 2024 | 9 | 39 | FALSE
RUNNING ¦ OVERDUE | 407 | OK | 40 | IMMED | 160457-1-1 | TRUE |  | 1 | 13 | 2024-08-29 | 2024-08-29 | 06:00 AM | 2024-09-09 | 14863 | 22.67 | 170 | 85 | 0 | 0 | 0 | 7.5 | 8 1/4 x 5 1/4 x 13 3/8 | Must start by 8/16 to make ship date | Bobby's Burgers | 2024-07-05 | Recycled Natural | 40 | 20# Shorty | 25 | Blue (spl) 282u |  |  |  | 0 | CTN20_64 | 0 | FALSE | A | FALSE | 400 | 200 | 2024-08-14 | 500 | 8 1/4 x 5 1/4 x 13 3/8 Recycled Natural SOS 20# Shorty Prtd *Bobby's Burgers* 1c/2s Blue (spl) 282u CN16622 . | 25.3 | TRUE | 10 | TRUE | 2024-09-11 | 230 |  | WCI | CS | 2024 | 8 | 35 | FALSE | LP
RUNNING | 403 | OK | 40 | IMMED | 160471-1-1 | TRUE |  | 0 | -13 | 2024-09-13 | 2024-09-13 | 10:19 AM | 2024-08-29 | 14580 | 5.57 | 64 | 32 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 |  | Saroki's | 2024-07-08 | White | 35 | 4# | 25 | Black 39999 | Red (spl) 3517u |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 64 | 32 | 2024-08-21 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Prtd *Saroki's* 2c/2s Black 39999 , Red (spl) 3517u CN16413 . | 6.57 | TRUE | 10 | TRUE | 2024-08-31 | 0 | Apply one customer supplied label to case in addition to our standard case label | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ PLATES NOT READY ¦ INK NOT READY | 104 | OK | 40 | IMMED | 029033 | FALSE |  | 0 | -11 | 2024-09-18 |  | 05:07 AM | 2024-09-05 | SLWS1717GRA | 6 | 96 | 24 | 419 | 0 | 480 | 16 | 17 x 9 x 17 |  |  | 2024-07-18 | Sani-Liner Specialty Paper | 40 | [6 empty] | 0 | CTN11_55 | 419 | FALSE | A | FALSE | 96 | 24 | 2024-08-08 | 250 | 17 x 9 x 17 Sani-Liner Specialty Paper Merchandise Unprinted . | 7 | FALSE | 10 | FALSE | 2024-09-07 | 0 | Use Wet Stregth glue on bottom (ADH-BS-4) and seam (ADH-SM-2)!!! Use 27Qt Tough Guy Labels | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE | B2 | OK | 40 | IMMED | 160859-2-1 | TRUE |  | 1 | 3 | 2024-09-03 | 2024-09-03 | 07:40 AM | 2024-09-04 | 10228 | 1.19 | 25 | 25 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | See Rock City (High Atop Lookout Mountain) | 2024-07-23 | White | 30 |  | 25 | Black 39999 | Red (spl) 34621 |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 25 | 25 | 2024-07-25 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *See Rock City (High Atop Lookout Mountain)* 2c/1s Black 39999 , Red (spl) 34621 CN14085 . | 1.69 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ INK NOT READY | 401 | OK | 40 | IMMED | 160537-2-1 | TRUE |  | 0 | -5 | 2024-09-18 | 2024-09-18 | 06:29 AM | 2024-09-11 | 11988 | 1.74 | 20 | 10 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 |  | Cousin's Candy Shop (Old Town San Diego) | 2024-07-10 | Recycled Natural | 35 | 4# | 25 | Black 39999 |  |  |  | 0 | CTN51_74 | 0 | FALSE | B | FALSE | 20 | 10 | 2024-08-05 | 500 | 5 x 3 1/8 x 9 5/8 Recycled Natural SOS 4# Prtd *Cousin's Candy Shop (Old Town San Diego)* 1c/1s Black 39999 CN14942 . | 2.24 | FALSE | 10 | TRUE | 2024-09-13 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
RUNNING ¦ OVERDUE | 107 | OK | 50 | IMMED | 160912-1-1 | TRUE |  | 0 | 5 | 2024-08-28 | 2024-08-28 | 07:00 AM | 2024-08-29 | 15396 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 8 1/2 x 11 | 3 Colors | Posman Books | 2024-07-24 | White | 30 |  | 25 | Green (spl) 375u | Green (spl) 7479u | Pink (spl) 212u |  | 0 | CTN23_64 | 0 | FALSE | B | TRUE | 15 | 15 | 2024-08-15 | 1000 | 8 1/2 x 11 White Merchandise Prtd *Posman Books* 3c/2s Green (spl) 375u, Green (spl) 7479u, Pink (spl) 212u, CN16997. | 2.65 | TRUE | 10 | TRUE | 2024-09-02 | 15 | Past complaint with crushed cases - make sure they are packed well | WCI | CS | 2024 | 8 | 35 | FALSE
READY ¦ OVERDUE | B2 | OK | 50 | IMMED | 160808-1-1 | TRUE |  | 0 | 1 | 2024-09-05 | 2024-09-05 | 05:22 PM | 2024-09-04 | 10568 | 0.48 | 10 | 10 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Mammoth Shirt Co. | 2024-07-26 | White | 30 |  | 25 | Black 39999 | Ruby Red 199u |  |  | 0 | CTN25_68 | 0 | FALSE | B | FALSE | 10 | 10 | 2024-07-31 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *Mammoth Shirt Co.* 2c/1s Black 39999 , Ruby Red 199u CN14311 . | 1.48 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 50 | IMMED | 028839 | TRUE |  | 0 | 6 | 2024-09-05 | 2024-09-03 | 06:27 AM | 2024-09-09 | 15068 | 20 | 960 | 960 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-06-28 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-08-13 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 20.5 | TRUE | 10 | TRUE | 2024-09-11 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ INK NOT READY | 407 | OK | 50 | IMMED | 160852-1-1 | TRUE |  | 0 | -5 | 2024-09-17 | 2024-09-17 | 06:18 AM | 2024-09-10 | 13089 | 10 | 75 | 37.5 | 0 | 0 | 0 | 7.5 | 8 1/4 x 5 1/4 x 13 3/8 |  | Edith's | 2024-07-22 | Recycled Natural | 40 | 20# Shorty | 75 | Blue Dk (spl) 37731 |  |  |  | 0 | CTN20_64 | 0 | FALSE | B | FALSE | 75 | 37.5 | 2024-08-15 | 500 | 8 1/4 x 5 1/4 x 13 3/8 Recycled Natural SOS 20# Shorty Prtd *Edith's* 1c/4s Blue Dk (spl) 37731 CN15623 . | 10.5 | FALSE | 10 | TRUE | 2024-09-12 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ INK NOT READY | 401 | OK | 50 | IMMED | 160490-1-1 | TRUE |  | 0 | -6 | 2024-09-20 | 2024-09-20 | 09:43 AM | 2024-09-12 | 13670 | 8.7 | 100 | 50 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 |  | Olive's | 2024-07-08 | Recycled Natural | 35 | 4# | 25 | Black 39999 |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 100 | 50 | 2024-08-15 | 500 | 5 x 3 1/8 x 9 5/8 Recycled Natural SOS 4# Prtd *Olive's* 1c/2s Black 39999 CN15858 . | 9.2 | FALSE | 10 | TRUE | 2024-09-14 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | 801 | OK | 50 | IMMED | 161387-1-1 | FALSE |  | 0 | 52 | 2024-09-24 | 2024-09-24 | 05:07 AM | 2024-11-13 | 10685 | 18.18 | 20 | 5 | 0 | 0 | 0 | 1.1 | 5 1/2 x 3 1/4 x 8 3/8 |  | Seroogy's | 2024-08-14 | Recycled Natural | 63 |  | 25 | Metallic Gold 07hs |  |  |  | 0 | CTN81_45 | 0 | FALSE | A | FALSE | 20 | 5 | 2024-08-27 | 250 | 5 1/2 x 3 1/4 x 8 3/8 Recycled Natural Handled Shopper Hot Stamp *Seroogy's* 1c/1s Metallic Gold 07hs CN14380 . | 18.68 | FALSE | 10 | TRUE | 2024-11-15 | 0 |  | WCI | CS | 2024 | 9 | 39 | FALSE
READY ¦ CUS CREDIT HOLD | 403 | OK | 52 | IMMED | 160610-1-1 | TRUE |  | 0 | -20 | 2024-09-20 | 2024-09-20 | 04:54 PM | 2024-08-29 | 03138 | 1.74 | 20 | 10 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 |  | Kid's Meal (Fernbank) | 2024-07-12 | White | 35 | 4# | 25 | Black 39999 |  |  |  | 0 | CTN51_74 | 0 | FALSE | C | FALSE | 20 | 10 | 2024-08-26 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Prtd *Kid's Meal (Fernbank)* 1c/2s Black 39999 CN9789 . | 2.24 | TRUE | 10 | TRUE | 2024-08-31 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
MAINT JOB | 407 |  | 55 | IMMED | MNT029354 | FALSE |  | 0 | -1 | 2024-09-12 |  | 06:48 PM | 2024-09-11 | <407> | 4.25 | 2 | 0 | 0 | 0 | 0 | 0 | 8 1/4 x 5 1/4 x 13 3/8 -> 8 1/4 x 5 1/4 x 16 1/8 | Change Over 3.75 Hours (Combined 3), Fine Tune 0.50 Hours |  | 2024-08-26 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 8 1/4 x 5 1/4 x 13 3/8 -> 8 1/4 x 5 1/4 x 16 1/8 | 4.25 | FALSE | 10 | FALSE | 2024-09-11 | 0 |  | WCI | M | 2024 | 9 | 37 | FALSE
MAINT JOB | 401 |  | 55 | IMMED | MNT029341 | FALSE |  | 0 | 19 | 2024-08-29 |  | 07:55 AM | 2024-09-17 | <401> | 8.5 | 2 | 0 | 0 | 0 | 0 | 0 | 5 x 3 1/8 x 9 5/8 -> 3 1/2 x 2 3/8 x 7 1/8 | MUST C/O by 9/6 to make 1# & 3# Ship Dates. Change Over 8.00 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-23 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 5 x 3 1/8 x 9 5/8 -> 3 1/2 x 2 3/8 x 7 1/8 | 8.5 | FALSE | 10 | FALSE | 2024-09-17 | 0 |  | WCI | M | 2024 | 8 | 35 | FALSE
READY | 406 | OK | 60 | IMMED | 160506-1-1 | TRUE |  | 0 | -1 | 2024-09-03 | 2024-09-03 | 06:00 AM | 2024-08-29 | 15520 | 1.05 | 10 | 5 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 |  | GG's Kid's Meal | 2024-07-09 | White | 35 | 8# | 50 | Red 185u |  |  |  | 0 | CTN50_69 | 0 | FALSE | A | FALSE | 10 | 5 | 2024-08-08 | 500 | 6 1/4 x 3 13/16 x 12 1/2 White SOS 8# Prtd *GG's Kid's Meal* 1c/4s Red 185u, CN17068. | 1.55 | TRUE | 10 | TRUE | 2024-09-02 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ OVERDUE | 107 | OK | 60 | IMMED | 161722-1-1 | TRUE |  | 0 | 1 | 2024-09-04 | 2024-09-04 | 09:39 AM | 2024-09-03 | 08909 | 1.57 | 22 | 22 | 0 | 0 | 0 | 14 | 8 1/2 x 11 | 3 Colors | Derm SA (Dermatology Assoc. of San Antonio) | 2024-08-29 | White | 30 |  | 25 | Gray Dk (spl) 7545u | Blue (spl) 306u | Green (spl) 390u |  | 0 | CTN23_64 | 0 | FALSE | A | FALSE | 22 | 22 | 2024-08-29 | 1000 | 8 1/2 x 11 White Merchandise Prtd *Derm SA (Dermatology Assoc. of San Antonio)* 3c/1s Gray Dk (spl) 7545u, Blue (spl) 306u, Green (spl) 390u, CN13209. | 3.07 | TRUE | 10 | TRUE | 2024-09-05 | 0 | No WCI markings on cartons or paperwork Please make sure this is ran with 3 colors last run was only done with 2 colors the green was missing. 8/27/24 | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ PLATES NOT READY | 403 | OK | 60 | IMMED | 161454-1-1 | FALSE |  | 0 | -14 | 2024-09-19 | 2024-09-19 | 07:08 PM | 2024-09-03 | 01850 | 4.35 | 50 | 25 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 | RUSH OCR: The customer signed the rush agreement to have this done in 4 weeks 9/19/24. | Grand Island Physical Therapy | 2024-08-22 | White | 35 | 4# | 25 | Pantone Process Blue 50 | Blue Dk 289u |  |  | 0 | CTN51_74 | 0 | TRUE | E | FALSE | 50 | 25 | 2024-08-26 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Prtd *Grand Island Physical Therapy* 2c/1s Pantone Process Blue 50, Blue Dk 289u, CN9286. | 5.35 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE | RU
READY ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | B2 | OK | 60 | IMMED | 160995-5-1 | FALSE |  | 0 | 3 | 2024-09-06 | 2024-09-06 | 06:51 PM | 2024-09-09 | 00737 | 7.62 | 160 | 160 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. |  | 2024-07-29 | Natural | 30 | [6 empty] | 0 | CTN166U_48 | 0 | FALSE | A | FALSE | 160 | 160 | 2024-08-21 | 1000 | 6 1/4 x 9 1/4 Natural Merchandise Unprinted . | 8.62 | FALSE | 10 | TRUE | 2024-09-09 | 0 | Use exact pallet configuration per instruction guide. Max Pallet Height of 56" Do not use brown tape - only use clear tape Use Uline cartons - check box for Natural Use Uline Pallet (Part #PLT-48-40-5-GA) | WCI | CS | 2024 | 9 | 36 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 60 | IMMED | 028838 | TRUE |  | 0 | 7 | 2024-09-05 | 2024-09-03 | 10:57 AM | 2024-09-10 | 15068 | 20 | 960 | 960 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-06-28 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-08-14 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 20.5 | TRUE | 10 | TRUE | 2024-09-12 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ OVERDUE | 250 | OK | 60 | IMMED | 161420-1-1 | TRUE |  | 0 | 11 | 2024-09-12 | 2024-09-19 | 08:48 AM | 2024-09-19 | 15696 | 37.5 | 750 | 150 | 0 | 0 | 0 | 20 | 12 1/2 x 4 x 18 |  | Reformation (word only) | 2024-08-14 | Recycled Natural | 78 |  | 25 | White 30305 |  |  |  | 0 | CTN49_53 | 0 | FALSE | B | FALSE | 750 | 150 | 2024-08-15 | 200 | 12 1/2 x 4 x 18 Recycled Natural Eco-Natural Lite P/S Prtd *Reformation (word only)* 1c/1s White 30305, CN12263. | 38 | TRUE | 10 | TRUE | 2024-09-23 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE | SP
READY ¦ INK NOT READY | 407 | OK | 60 | IMMED | 029353 | TRUE |  | 0 | -3 | 2024-09-17 |  | 09:03 AM | 2024-09-12 | HWRN20 | 3.87 | 60 | 15 | 3 | 0 | 35 | 15.5 | 8 1/4 x 5 1/4 x 16 1/8 |  |  | 2024-08-26 | Recycled Natural | 57 | 20# | [5 empty] | 0 | CTN20_57 | 3 | FALSE | A | FALSE | 60 | 15 | 2024-08-28 | 250 | 8 1/4 x 5 1/4 x 16 1/8 Recycled Natural Hardware 20# Stock Printed With Recycled Logo. | 4.12 | FALSE | 10 | FALSE | 2024-09-14 | 0 | Recycled Logo printed with Black 39999. Case pack 250 | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE ¦ BELOW 0 ¦ INK NOT READY | 401 | OK | 60 | IMMED | 028859 | TRUE |  | 0 | 10 | 2024-09-16 | 2024-08-02 | 06:25 AM | 2024-09-24 | SORN1 | 32 | 240 | 240 | 0 | 97 | 75 | 7.5 | 3 1/2 x 2 3/8 x 7 1/8 | This job made to cover stock and custom Recycled Natural that come in from 7/1 to 9/10. |  | 2024-07-01 | Recycled Natural | 35 | 1# | [5 empty] | 0 | CTN12_57 | -97 | FALSE | A | FALSE | 240 | 240 | 2024-08-21 | 1000 | 3 1/2 x 2 3/8 x 7 1/8 Recycled Natural SOS 1# Stock Printed With Recycled Logo. | 33 | FALSE | 10 | FALSE | 2024-09-26 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE | 406 | OK | 65 | IMMED | 160121-1-1 | TRUE |  | 0 | 1 | 2024-08-30 | 2024-08-30 | 07:33 AM | 2024-08-29 | 14581 | 2.53 | 24 | 12 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 | OCR: DO NOT SHIP THIS UNTIL 8/30/24. SNL 6/19/2024 | Saroki's | 2024-06-20 | White | 35 | 8# | 25 | Black 39999 | Red (spl) 3517u |  |  | 0 | CTN50_69 | 0 | FALSE | A | FALSE | 24 | 12 | 2024-08-08 | 500 | 6 1/4 x 3 13/16 x 12 1/2 White SOS 8# Prtd *Saroki's* 2c/2s Black 39999 , Red (spl) 3517u CN16413 . | 3.53 | TRUE | 10 | TRUE | 2024-08-31 | 0 | Apply customer supplied labels to cases (in addition to WCI's standard label) | WCI | CS | 2024 | 8 | 35 | FALSE
READY | 108 | OK | 65 | IMMED | 160952-2-1 | TRUE |  | 0 | -4 | 2024-09-09 | 2024-09-09 | 06:51 PM | 2024-09-03 | 09337 | 0.29 | 6 | 6 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Kartchner Caverns | 2024-07-26 | Recycled Natural | 30 |  | 25 | Teal 327u |  |  |  | 0 | CTN25_68 | 0 | FALSE | B | FALSE | 6 | 6 | 2024-07-31 | 1000 | 6 1/4 x 9 1/4 Recycled Natural Merchandise Prtd *Kartchner Caverns* 1c/1s Teal 327u CN13412 . | 0.79 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
MAINT JOB | 401 |  | 65 | IMMED | MNT029342 | FALSE |  | 0 | 27 | 2024-08-29 |  | 10:25 AM | 2024-09-25 | <401> | 8.5 | 2 | 0 | 0 | 0 | 0 | 0 | 3 1/2 x 2 3/8 x 7 1/8 -> 4 3/4 x 2 7/8 x 8 13/16 | Change Over 8.00 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-23 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 3 1/2 x 2 3/8 x 7 1/8 -> 4 3/4 x 2 7/8 x 8 13/16 | 8.5 | FALSE | 10 | FALSE | 2024-09-25 | 0 |  | WCI | M | 2024 | 8 | 35 | FALSE
READY | 406 | OK | 70 | IMMED | 160448-1-1 | TRUE |  | 0 | -3 | 2024-09-05 | 2024-09-05 | 11:04 AM | 2024-08-29 | 15844 | 2.11 | 20 | 10 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 |  | Melton's Deli | 2024-07-12 | White | 35 | 8# | 25 | Black 39999 |  |  |  | 0 | CTN50_69 | 0 | FALSE | A | FALSE | 20 | 10 | 2024-07-18 | 500 | 6 1/4 x 3 13/16 x 12 1/2 White SOS 8# Prtd *Melton's Deli* 1c/1s Black 39999, CN17285. | 2.61 | TRUE | 10 | TRUE | 2024-09-02 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY | 403 | OK | 70 | IMMED | 160594-1-1 | TRUE |  | 0 | -14 | 2024-09-19 | 2024-09-19 | 06:29 AM | 2024-09-03 | 09546 | 4.35 | 50 | 25 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 |  | ESS (Every Day Counts) | 2024-08-09 | White | 35 | 4# | 25 | Blue Dk (spl) 2768u |  |  |  | 0 | CTN51_74 | 0 | FALSE | B | FALSE | 50 | 25 | 2024-08-26 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Prtd *ESS (Every Day Counts)* 1c/1s Blue Dk (spl) 2768u, CN13645. | 4.85 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY | 108 | OK | 70 | IMMED | 160972-1-1 | TRUE |  | 0 | 0 | 2024-09-06 | 2024-09-06 | 07:39 PM | 2024-09-04 | 13568 | 0.48 | 10 | 10 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | I Support Public Land (BlackHillsParks.org) | 2024-07-26 | Recycled Natural | 30 |  | 25 | Green Dk 342u |  |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 10 | 10 | 2024-07-31 | 1000 | 6 1/4 x 9 1/4 Recycled Natural Merchandise Prtd *I Support Public Land (BlackHillsParks.org)* 1c/1s Green Dk 342u CN15559 . | 0.98 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 70 | IMMED | 028967 | TRUE |  | 0 | 4 | 2024-09-09 | 2024-09-03 | 03:27 PM | 2024-09-11 | 15068 | 20 | 960 | 960 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-07-15 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-08-15 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 20.5 | FALSE | 10 | TRUE | 2024-09-13 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 37 | FALSE
MAINT JOB | 407 |  | 70 | IMMED | MNT029355 | FALSE |  | 0 | -4 | 2024-09-16 |  | 06:10 AM | 2024-09-12 | <407> | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 8 1/4 x 5 1/4 x 16 1/8 -> 8 1/4 x 5 1/4 x 18 | Change Over 2.50 Hours, Fine Tune 0.50 Hours |  | 2024-08-26 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 8 1/4 x 5 1/4 x 16 1/8 -> 8 1/4 x 5 1/4 x 18 | 3 | FALSE | 10 | FALSE | 2024-09-12 | 0 |  | WCI | M | 2024 | 9 | 38 | FALSE
MAINT JOB | 250 |  | 70 | IMMED | MNT029337 | FALSE |  | 0 | 20 | 2024-09-05 |  | 05:48 PM | 2024-09-25 | <250> | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 12 1/2 x 4 x 18->18 1/2 x 6 1/4 x 24 3/4 |  |  | 2024-08-22 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 1 | 0 |  |  | 12 1/2 x 4 x 18->18 1/2 x 6 1/4 x 24 3/4 | 12 | FALSE | 10 | FALSE | 2024-09-25 | 0 |  | WCI | M | 2024 | 9 | 36 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 401 | OK | 70 | IMMED | 161173-1-1 | TRUE |  | 0 | 7 | 2024-09-20 | 2024-09-20 | 07:55 AM | 2024-09-25 | 13790 | 3.33 | 50 | 25 | 0 | 0 | 0 | 15 | 4 3/4 x 2 7/8 x 8 13/16 | 3# SOS | Bank of Pontiac | 2024-08-05 | White | 35 | 3# | 25 | Blue Dk (spl) 281u |  |  |  | 0 | CTN51_74 | 0 | FALSE | B | FALSE | 50 | 25 | 2024-08-15 | 500 | 4 3/4 x 2 7/8 x 8 13/16 White SOS 3# Prtd *Bank of Pontiac* 1c/1s Blue Dk (spl) 281u CN15915 . | 3.83 | FALSE | 10 | TRUE | 2024-09-27 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 801 | OK | 70 | IMMED | 161506-2-1 | TRUE |  | 0 | 56 | 2024-09-27 | 2024-09-27 | 05:48 AM | 2024-11-20 | 06808 | 3.33 | 1 | 1 | 0 | 0 | 0 | 0.3 | 5 3/4 x 7 1/2 |  | Beerntsen's | 2024-08-19 | White | 30 |  | 25 | Metallic Silver 01hs |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 1 | 1 | 2024-08-27 | 1000 | 5 3/4 x 7 1/2 White/Glassine Gourmet Hot Stamp *Beerntsen's* 1c/1s Metallic Silver 01hs, CN8232. | 3.83 | FALSE | 10 | TRUE | 2024-11-22 | 0 | No WCI markings on cartons or paperwork | WCI | CS | 2024 | 9 | 39 | FALSE
READY | 406 | OK | 75 | IMMED | 160354-1-1 | TRUE |  | 0 | -21 | 2024-09-26 | 2024-09-26 | 01:41 PM | 2024-09-03 | 02805 | 15 | 150 | 75 | 0 | 0 | 0 | 10 | 6 1/4 x 3 13/16 x 12 1/2 | OCR: Customer does not want this to ship before 8/30; order has been marked accordingly. 7/1/24 fb | Taste The Pioneer Spirit Of Fruita | 2024-07-01 | Recycled Natural | 35 | 8# | 25 | Black 39999 | Red 185u |  |  | 0 | CTN50_69 | 0 | FALSE | C | FALSE | 150 | 75 | 2024-08-08 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural SOS 8# Prtd *Taste The Pioneer Spirit Of Fruita* 2c/1s Black 39999 , Red 185u CN7924 . | 16 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 39 | FALSE
MAINT JOB | 107 |  | 75 | IMMED | MNT029378 | FALSE |  | 0 | 0 | 2024-09-03 |  | 07:43 AM | 2024-09-03 | <107> | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 8 1/2 x 11 -> 5 x 7 1/2 | Change Over 3.50 Hours (Combined 5), Fine Tune 0.50 Hours |  | 2024-08-27 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 8 1/2 x 11 -> 5 x 7 1/2 | 4 | FALSE | 10 | FALSE | 2024-09-03 | 0 |  | WCI | M | 2024 | 9 | 36 | FALSE
READY ¦ BELOW 0 | 108 | OK | 77 | IMMED | 029267 | TRUE |  | 0 | -2 | 2024-09-13 | 2024-09-13 | 07:37 AM | 2024-09-09 | MRRN69 | 15.24 | 320 | 320 | 188 | 307 | 720 | 21 | 6 1/4 x 9 1/4 |  |  | 2024-08-15 | Recycled Natural | 30 | [6 empty] | 0 | CTN25_55 | -119 | FALSE | A | FALSE | 320 | 320 | 2024-08-21 | 1000 | 6 1/4 x 9 1/4 Recycled Natural Merchandise Stock Printed With Recycled Logo. | 15.74 | TRUE | 10 | FALSE | 2024-09-11 | 0 | Rec. logo printed with Black 39999 | WCI | CS | 2024 | 9 | 37 | FALSE
READY | 403 | OK | 80 | IMMED | 160625-1-1 | TRUE |  | 0 | -15 | 2024-09-20 | 2024-09-20 | 11:20 AM | 2024-09-03 | 13551 | 2.09 | 24 | 12 | 0 | 0 | 0 | 11.5 | 5 x 3 1/8 x 9 5/8 |  | Farm Bureau Insurance (Pope County) | 2024-07-12 | White | 35 | 4# | 25 | Maroon 207u |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 24 | 12 | 2024-08-26 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Prtd *Farm Bureau Insurance (Pope County)* 1c/1s Maroon 207u CN14736 . | 2.59 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE | 406 | OK | 80 | IMMED | 160584-1-1 | TRUE |  | 0 | 2 | 2024-09-04 | 2024-09-04 | 04:41 PM | 2024-09-04 | 14911 | 4.21 | 40 | 20 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 | OCR: do not ship before 8/23. JT 7-17-24 | Windy City Dispensary | 2024-07-11 | Recycled Natural | 35 | 8# | 25 | Black 39999 |  |  |  | 0 | CTN50_69 | 0 | FALSE | A | FALSE | 40 | 20 | 2024-07-17 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural SOS 8# Prtd *Windy City Dispensary* 1c/1s Black 39999 CN16158 . | 4.71 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 108 | OK | 80 | IMMED | 160973-1-1 | TRUE |  | 0 | 11 | 2024-09-10 | 2024-09-10 | 06:22 PM | 2024-09-17 | 15881 | 26.19 | 550 | 550 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 | **Customer contacted WCI and is very concerned about their job being late** | AYEYA | 2024-07-30 | Recycled Natural | 30 |  | 25 | Black 39999 |  |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 550 | 550 | 2024-08-05 | 1000 | 6 1/4 x 9 1/4 Recycled Natural Merchandise Prtd *AYEYA* 1c/1s Black 39999, CN17311. | 26.69 | FALSE | 10 | TRUE | 2024-09-21 | 0 | max pallet height 54" Apply customer supplied case labels in addition to WCI's standard case label. | WCI | CS | 2024 | 9 | 37 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 80 | IMMED | 028842 | TRUE |  | 0 | 6 | 2024-09-12 | 2024-09-03 | 07:57 PM | 2024-09-16 | 15068 | 20 | 960 | 960 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-06-28 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-08-15 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 20.5 | FALSE | 10 | TRUE | 2024-09-18 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 250 | OK | 80 | IMMED | 029234 | TRUE |  | 0 | 20 | 2024-09-09 |  | 10:48 AM | 2024-09-25 | EPLT18G-R | 0.38 | 8 | 1.6 | 2 | 0 | 10 | 21 | 18 1/2 x 6 1/4 x 24 3/4 |  |  | 2024-08-13 | Recycled Natural | 78 | 18G | [5 empty] | 0 | CTN180_60 | 2 | FALSE | A | FALSE | 8 | 1.6 | 2024-08-16 | 200 | 18 1/2 x 6 1/4 x 24 3/4 Recycled Natural Eco-Natural Lite P/S Resendable 18G Stock Printed With Recycled Logo. | 0.88 | FALSE | 10 | FALSE | 2024-09-29 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 401 | OK | 80 | IMMED | 161293-1-1 | TRUE |  | 0 | 8 | 2024-09-20 | 2024-09-20 | 12:45 PM | 2024-09-26 | 00707 | 4.21 | 60 | 30 | 0 | 0 | 0 | 14.25 | 4 3/4 x 2 7/8 x 8 13/16 |  | South Bend Chocolate Company | 2024-08-09 | White | 35 | 3# | 25 | Brown Dk (spl) 4625u |  |  |  | 0 | CTN51_74 | 0 | FALSE | B | FALSE | 60 | 30 | 2024-08-15 | 500 | 4 3/4 x 2 7/8 x 8 13/16 White SOS 3# Prtd *South Bend Chocolate Company* 1c/1s Brown Dk (spl) 4625u CN5711 . | 5.46 | FALSE | 10 | TRUE | 2024-09-28 | 0 | No WCI Markings on Cartons or ANY paperwork | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 801 | OK | 80 | IMMED | 161506-3-1 | TRUE |  | 0 | 63 | 2024-09-27 | 2024-09-27 | 05:38 AM | 2024-11-27 | 06809 | 3.33 | 1 | 1 | 0 | 0 | 0 | 0.3 | 6 3/4 x 9 1/4 |  | Beerntsen's | 2024-08-19 | White | 30 |  | 25 | Metallic Silver 01hs |  |  |  | 0 | CTN30_81 | 0 | FALSE | A | FALSE | 1 | 1 | 2024-08-27 | 1000 | 6 3/4 x 9 1/4 White/Glassine Gourmet Hot Stamp *Beerntsen's* 1c/1s Metallic Silver 01hs, CN8232. | 3.83 | FALSE | 10 | TRUE | 2024-11-29 | 0 | No WCI markings on cartons or paperwork | WCI | CS | 2024 | 9 | 39 | FALSE
READY ¦ OVERDUE | 406 | OK | 85 | IMMED | 160585-1-1 | TRUE |  | 0 | 2 | 2024-09-04 | 2024-09-04 | 08:24 AM | 2024-09-04 | 14910 | 6.32 | 60 | 30 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 | OCR: do not ship before 8/23. JT 7-17-24 | Windy City Cannabis | 2024-07-11 | Recycled Natural | 35 | 8# | 25 | Black 39999 |  |  |  | 0 | CTN50_69 | 0 | FALSE | B | FALSE | 60 | 30 | 2024-07-16 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural SOS 8# Prtd *Windy City Cannabis* 1c/1s Black 39999 CN13938 . | 6.82 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY | 406 | OK | 87 | IMMED | 160537-3-1 | TRUE |  | 0 | -12 | 2024-09-18 | 2024-09-18 | 03:13 PM | 2024-09-04 | 11989 | 1.05 | 10 | 5 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 | Customer concerned about this job being late | Cousin's Candy Shop (Old Town San Diego) | 2024-07-10 | Recycled Natural | 35 | 8# | 25 | Black 39999 |  |  |  | 0 | CTN50_69 | 0 | FALSE | B | FALSE | 10 | 5 | 2024-08-05 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural SOS 8# Prtd *Cousin's Candy Shop (Old Town San Diego)* 1c/1s Black 39999 CN14942 . | 1.55 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE | 406 | OK | 90 | IMMED | 160573-1-1 | TRUE |  | 0 | 1 | 2024-09-05 | 2024-09-05 | 04:46 PM | 2024-09-04 | 03659 | 1.05 | 20 | 5 | 0 | 0 | 0 | 19 | 6 1/4 x 3 13/16 x 12 1/2 | Hardware | CoxHealth (Meals on Wheels) | 2024-07-10 | Recycled Natural | 57 | 8# | 25 | Blue (spl) 301u |  |  |  | 0 | CTN50_69 | 0 | FALSE | B | FALSE | 20 | 5 | 2024-07-17 | 250 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural Hardware 8# Prtd *CoxHealth (Meals on Wheels)* 1c/1s Blue (spl) 301u CN10037 . | 1.55 | TRUE | 10 | TRUE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ INK NOT READY | 407 | OK | 90 | IMMED | 029250 | TRUE |  | 0 | 0 | 2024-09-18 |  | 09:10 AM | 2024-09-16 | SORN25 | 5 | 40 | 20 | 64 | 0 | 74 | 8 | 8 1/4 x 5 1/4 x 18 |  |  | 2024-08-14 | Recycled Natural | 40 | 25# | [5 empty] | 0 | CTN20_57 | 64 | FALSE | A | FALSE | 40 | 20 | 2024-08-29 | 500 | 8 1/4 x 5 1/4 x 18 Recycled Natural SOS 25# Stock Printed With Recycled Logo. | 5.23 | FALSE | 10 | FALSE | 2024-09-18 | 0 | Black Ink 39999 bottom turnover recy. logo | WCI | CS | 2024 | 9 | 38 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 90 | IMMED | 028965 | TRUE |  | 0 | 7 | 2024-09-12 | 2024-09-03 | 08:27 AM | 2024-09-17 | 15068 | 20 | 960 | 960 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-07-15 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-08-12 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 20.5 | FALSE | 10 | TRUE | 2024-09-19 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ INK NOT READY | 108 | OK | 90 | IMMED | 161012-1-1 | TRUE |  | 0 | 10 | 2024-09-09 | 2024-09-09 | 08:03 AM | 2024-09-17 | 10464 | 1.19 | 25 | 25 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Museum Store | 2024-07-29 | Recycled Natural | 30 |  | 25 | Black 39999 |  |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 25 | 25 | 2024-07-29 | 1000 | 6 1/4 x 9 1/4 Recycled Natural Merchandise Prtd *Museum Store* 1c/2s Black 39999 CN14241 . | 1.69 | FALSE | 10 | TRUE | 2024-09-19 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | 401 | OK | 90 | IMMED | 028860 | FALSE |  | 0 | 13 | 2024-09-20 |  | 07:13 AM | 2024-10-01 | SOWH3 | 7.47 | 112 | 56 | 119 | 0 | 112 | 15 | 4 3/4 x 2 7/8 x 8 13/16 | This job made to cover any stock and customer orders that come in from 7/1 to 9/10. |  | 2024-07-01 | White | 35 | 3# | [5 empty] | 0 | CTN51_54 | 119 | FALSE | A | FALSE | 112 | 56 | 2024-08-20 | 500 | 4 3/4 x 2 7/8 x 8 13/16 White SOS 3# Unprinted . | 15.97 | FALSE | 10 | FALSE | 2024-10-03 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY | 406 | OK | 95 | IMMED | 160740-1-1 | TRUE |  | 0 | -4 | 2024-09-11 | 2024-09-11 | 06:19 PM | 2024-09-05 | 12159 | 5.26 | 50 | 25 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 |  | Baggby's Gourmet Sandwiches | 2024-07-17 | Recycled Natural | 35 | 8# | 25 | Pantone Reflex Blue 13 |  |  |  | 0 | CTN50_69 | 0 | FALSE | C | FALSE | 50 | 25 | 2024-07-24 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural SOS 8# Prtd *Baggby's Gourmet Sandwiches* 1c/2s Pantone Reflex Blue 13 CN5902 . | 5.76 | TRUE | 10 | TRUE | 2024-09-07 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
MAINT JOB | 103 |  | 97 | IMMED | MNT029294 | FALSE |  | 0 | -26 | 2024-09-24 |  | 08:47 AM | 2024-08-29 | <103> | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 12 x 15 -> 10 x 2 x 15 | Change Over 2.00 Hours (Combined 3), Fine Tune 0.50 Hours |  | 2024-08-19 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 12 x 15 -> 10 x 2 x 15 | 2.5 | FALSE | 10 | FALSE | 2024-08-29 | 0 |  | WCI | M | 2024 | 9 | 39 | FALSE
!! MTL ISSUE | 404 | WHGR-1425-35 | 100 | IMMED | 161321-1-1 | TRUE |  | 0 | -11 | 2024-09-13 | 2024-09-13 | 05:00 AM | 2024-08-29 | 15916 | 0.25 | 15 | 7.5 | 0 | 0 | 0 | 60 | 4 1/8 x 2 1/2 x 7 7/8 | 14.25" Paper - Let supervisor know 1/4" wider paper | Donita's | 2024-08-16 | White Grease Resistant | 35 | 2# | 50 | Pink (spl) 225u |  |  |  | 0 | CTN29_74 | 0 | FALSE | A | FALSE | 36 | 18 | 2024-08-21 | 500 | 4 1/8 x 2 1/2 x 7 7/8 White Grease Resistant SOS 2# Prtd *Donita's* 1c/2s Pink (spl) 225u, CN17128. | 1.02 | TRUE | 10 | TRUE | 2024-09-02 | 21 | Must run up full roll of paper | WCI | CS | 2024 | 9 | 37 | FALSE
READY | 601 | OK | 100 | IMMED | 161262-1-1 | TRUE |  | 0 | -11 | 2024-09-11 | 2024-09-11 | 06:00 AM | 2024-08-29 | 14433 | 1.33 | 2 | 1 | 0 | 0 | 0 | 1.5 | 12 x 2 3/4 x 18 |  | The House of Guitars | 2024-08-13 | Recycled Natural | 35 |  | 25 | Black 39999 |  |  |  | 0 | CTN13_68 | 0 | FALSE | A | FALSE | 2 | 1 | 2024-08-15 | 500 | 12 x 2 3/4 x 18 Recycled Natural Merchandise Prtd *The House of Guitars* 1c/1s Black 39999 CN16325 . | 1.83 | TRUE | 10 | TRUE | 2024-08-31 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
RUNNING ¦ OVERDUE ¦ BELOW 0 ¦ PLATES NOT READY | 106 | OK | 100 | IMMED | 029265 | FALSE |  | 0 | 2 | 2024-09-04 | 2024-08-30 | 08:00 AM | 2024-09-04 | MRRN811 | 9.86 | 138 | 138 | 176 | 250 | 420 | 14 | 8 1/2 x 11 |  |  | 2024-08-15 | Recycled Natural | 30 | [6 empty] | 0 | CTN23_55 | -74 | FALSE | A | FALSE | 240 | 240 | 2024-08-20 | 1000 | 8 1/2 x 11 Recycled Natural Merchandise Stock Printed With Recycled Logo. | 13.57 | TRUE | 10 | FALSE | 2024-09-06 | 102 | Rec. logo printed Black 39999. | WCI | CS | 2024 | 9 | 36 | FALSE
RUNNING | 103 | OK | 100 | IMMED | 161312-1-1 | TRUE |  | 0 | -25 | 2024-09-25 | 2024-09-25 | 11:17 AM | 2024-08-29 | 13195 | 2.78 | 25 | 25 | 0 | 0 | 0 | 9 | 10 x 2 x 15 |  | Zia Records | 2024-08-16 | Recycled Natural | 30 |  | 25 | Black 39999 |  |  |  | 0 | CTN5_67 | 0 | FALSE | B | FALSE | 25 | 25 | 2024-08-21 | 1000 | 10 x 2 x 15 Recycled Natural Merchandise Prtd *Zia Records* 1c/1s Black 39999 CN15688 . | 3.28 | TRUE | 10 | TRUE | 2024-08-31 | 0 | At least 20 samples to sample room. | WCI | CS | 2024 | 9 | 39 | FALSE
READY ¦ OVERDUE ¦ BELOW 0 ¦ PLATES NOT READY ¦ INK NOT READY | 107 | OK | 100 | IMMED | 160995-12-1 | FALSE |  | 0 | 11 | 2024-09-06 | 2024-09-06 | 06:43 PM | 2024-09-17 | 00569 | 35 | 455 | 455 | 0 | 637 | 0 | 13 | 5 x 7 1/2 | **Uline** (This job may move to machine 107) |  | 2024-07-29 | Natural | 30 | [6 empty] | 0 | CTN28U_54 | -637 | FALSE | A | FALSE | 455 | 455 | 2024-08-08 | 1000 | 5 x 7 1/2 Natural Merchandise Unprinted . | 36 | FALSE | 10 | TRUE | 2024-09-17 | 0 | Use pallet configuration per instruction guide. Maximum pallet height of 56" Use Uline Cartons Do not use brown tape - only use clear tape If using Pre-printed Boxes use Check Box for Natural &/ White If not using pre-print cartons - Apply Labels In the upper left hand corner on the short side of the box. Customer Part# S-12491 Use Uline Pallet (Part #PLT-48-40-5-GA) | WCI | CS | 2024 | 9 | 36 | FALSE | LP
READY ¦ OVERDUE ¦ CUS CREDIT HOLD | 406 | OK | 100 | IMMED | 160571-1-1 | TRUE |  | 0 | 7 | 2024-09-06 | 2024-09-06 | 11:04 AM | 2024-09-09 | 15847 | 10.53 | 100 | 50 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 |  | Little Red Hen Bakery Sourdough | 2024-07-15 | Recycled Natural | 35 | 8# | 25 | Red 185u | Black 39999 |  |  | 0 | CTN50_69 | 0 | FALSE | A | FALSE | 100 | 50 | 2024-07-19 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Recycled Natural SOS 8# Prtd *Little Red Hen Bakery Sourdough* 2c/1s Red 185u, Black 39999, CN17287. | 11.53 | TRUE | 10 | TRUE | 2024-09-13 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
READY ¦ NO TRAVELER ¦ PLATES NOT READY ¦ INK NOT READY | 407 | OK | 100 | IMMED | 160889-1-1 | FALSE |  | 0 | 0 | 2024-09-18 | 2024-09-18 | 08:24 AM | 2024-09-16 | 12509 | 2.67 | 20 | 10 | 0 | 0 | 0 | 7.5 | 8 1/4 x 5 1/4 x 18 |  | Your Meds, Your Way (Essentia Health Pharmacy) | 2024-07-24 | White | 40 | 25# | 25 | Blue Dk 289u |  |  |  | 0 | CTN20_64 | 0 | FALSE | B | FALSE | 20 | 10 |  | 500 | 8 1/4 x 5 1/4 x 18 White SOS 25# Prtd *Your Meds, Your Way (Essentia Health Pharmacy)* 1c/2s Blue Dk 289u, CN15260. | 3.17 | FALSE | 10 | TRUE | 2024-09-18 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
!! MTL ISSUE | 102 | SUBRN-3600-35 PO 34456 Due 08/30/24 | 100 | IMMED | 028843 | TRUE |  | 0 | 4 | 2024-09-16 | 2024-09-03 | 12:57 PM | 2024-09-18 | 15068 | 20 | 960 | 960 | 160 | 21120 | 0 | 48 | 6 1/8 x 2 1/2 x 15 1/2 | Date of production and operator number must be stamped on the bottom of each carton near the carton logo, see supervisor for stamper at beginning of production run. | Subway | 2024-06-28 | Recycled Natural | 35 |  | 25 | Subway Green Dk (spl) 38719 |  |  |  | 0 | CTN80N_53 | -20960 | FALSE | A | FALSE | 960 | 960 | 2024-08-21 | 1000 | 6 1/8 x 2 1/2 x 15 1/2 Recycled Natural Merchandise Prtd *Subway* 1c/2s Subway Green Dk (spl) 38719, CN16768. | 20.5 | FALSE | 10 | TRUE | 2024-09-20 | 0 | Should be 32 cases per pallet Subway Quality Retain Labels needed for this job. 1) Pull 1 bag sample every 6 cases (5 bag samples per pallet). 2) Place the Quality label on the top center of the bag sample. 3) Fill out the 4 items on the Quality label. 4) Place all bag samples in a box at the machine. | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE ¦ NO TRAVELER ¦ PLATES NOT READY ¦ INK NOT READY | 401 | OK | 100 | IMMED | 029305 | FALSE |  | 0 | 14 | 2024-09-20 | 2024-09-13 | 02:11 PM | 2024-10-02 | SORN4 | 9.74 | 112 | 56 | 485 | 30 | 336 | 11.5 | 5 x 3 1/8 x 9 5/8 |  |  | 2024-08-21 | Recycled Natural | 35 | 4# | [5 empty] | 0 | CTN51_54 | 455 | FALSE | A | FALSE | 112 | 56 |  | 500 | 5 x 3 1/8 x 9 5/8 Recycled Natural SOS 4# Stock Printed With Recycled Logo. | 10.24 | FALSE | 10 | FALSE | 2024-10-04 | 0 | Black Ink 39999 bottom turnover recy. logo | WCI | CS | 2024 | 9 | 38 | FALSE
MAINT JOB | 100 |  | 110 | IMMED | MNT029232 | FALSE |  | 0 | -7 | 2024-09-05 |  | 06:00 AM | 2024-08-29 | <100> | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 14 3/4 x 18 -> 16 x 3 3/4 x 24 | Change Over 2.75 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-13 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 14 3/4 x 18 -> 16 x 3 3/4 x 24 | 3.25 | FALSE | 10 | FALSE | 2024-08-29 | 0 |  | WCI | M | 2024 | 9 | 36 | FALSE
STARTED | 601 | OK | 110 | IMMED | 161427-1-1 | TRUE |  | 0 | -12 | 2024-09-12 | 2024-09-12 | 07:49 AM | 2024-08-29 | 07853 | 2 | 3 | 1.5 | 0 | 0 | 0 | 1.5 | 5 x 3 1/8 x 9 5/8 |  | Go Bulldogs (Harrisonville Telephone Co.) | 2024-08-15 | White | 35 | 4 | 25 | Black 39999 |  |  |  | 0 | CTN51_74 | 0 | FALSE | A | FALSE | 4 | 2 | 2024-08-15 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4 Prtd *Go Bulldogs (Harrisonville Telephone Co.)* 1c/1s Black 39999 CN12496 . | 2.25 | TRUE | 10 | TRUE | 2024-08-31 | 1 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY | 103 | OK | 110 | IMMED | 161639-1-1 | TRUE |  | 0 | -34 | 2024-10-04 | 2024-10-04 | 02:34 PM | 2024-08-29 | 13086 | 1.79 | 25 | 25 | 0 | 0 | 0 | 14 | 10 x 2 x 15 |  | Bit of Swiss | 2024-08-23 | White | 30 |  | 25 | Black 39999 | Red (spl) 186u |  |  | 0 | CTN5_67 | 0 | FALSE | B | TRUE | 25 | 25 | 2024-08-26 | 1000 | 10 x 2 x 15 White Merchandise Prtd *Bit of Swiss* 2c/4s Black 39999 , Red (spl) 186u CN14463 . | 2.79 | TRUE | 10 | TRUE | 2024-08-31 | 0 |  | WCI | CS | 2024 | 10 | 40 | FALSE
READY ¦ PLATES NOT READY ¦ INK NOT READY | 403 | OK | 110 | IMMED | 029258 | FALSE |  | 0 | -15 | 2024-09-20 | 2024-09-13 | 01:55 PM | 2024-09-03 | SOWH4 | 4.87 | 56 | 28 | 222 | 131 | 504 | 11.5 | 5 x 3 1/8 x 9 5/8 | Do not get over 504 on hand unless order exceeds that |  | 2024-08-15 | White | 35 | 4# | [5 empty] | 0 | CTN51_54 | 91 | FALSE | A | FALSE | 56 | 28 | 2024-08-26 | 500 | 5 x 3 1/8 x 9 5/8 White SOS 4# Unprinted . | 5.37 | FALSE | 10 | FALSE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | B2 | OK | 110 | IMMED | 160780-1-1 | FALSE |  | 0 | 1 | 2024-09-12 | 2024-09-12 | 07:28 AM | 2024-09-09 | 15867 | 0.24 | 5 | 5 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Twice Pediatric Dentistry | 2024-08-01 | White | 30 |  | 25 | Teal 327u |  |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 5 | 5 | 2024-08-28 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *Twice Pediatric Dentistry* 1c/1s Teal 327u, CN17303. | 0.74 | FALSE | 10 | TRUE | 2024-09-13 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE | 406 | OK | 110 | IMMED | 160707-1-1 | TRUE |  | 0 | 1 | 2024-09-10 | 2024-09-10 | 09:36 AM | 2024-09-09 | 12518 | 5.26 | 50 | 25 | 0 | 0 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 | Use New Grease paper Only - Roll Lot# MUST start with a T | Leo's Bread | 2024-07-16 | White Grease Resistant | 35 | 8# | 25 | Brown (spl) 718u |  |  |  | 0 | CTN50_69 | 0 | FALSE | A | FALSE | 50 | 25 | 2024-07-24 | 500 | 6 1/4 x 3 13/16 x 12 1/2 White Grease Resistant SOS 8# Prtd *Leo's Bread* 1c/1s Brown (spl) 718u CN15267 . | 5.76 | TRUE | 10 | TRUE | 2024-09-11 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE | 107 | OK | 110 | IMMED | 161401-1-1 | TRUE |  | 0 | 8 | 2024-09-11 | 2024-09-11 | 07:43 AM | 2024-09-17 | 04198 | 0.89 | 12 | 12 | 0 | 0 | 0 | 13.5 | 5 x 7 1/2 |  | Skylift Gift Shop | 2024-08-14 | White | 30 |  | 25 | Green Dk 342u |  |  |  | 0 | CTN28_68 | 0 | FALSE | C | FALSE | 12 | 12 | 2024-08-15 | 1000 | 5 x 7 1/2 White Merchandise Prtd *Skylift Gift Shop* 1c/1s Green Dk 342u CN5989 . | 1.39 | TRUE | 10 | TRUE | 2024-09-19 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
MAINT JOB | 107 |  | 115 | IMMED | MNT029349 | FALSE |  | 0 | 21 | 2024-08-28 |  | 09:06 AM | 2024-09-18 | <107> | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 5 x 7 1/2 -> 10 x 13 | Change Over 2.50 Hours (Combined 3), Fine Tune 0.50 Hours |  | 2024-08-26 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 5 x 7 1/2 -> 10 x 13 | 3 | FALSE | 10 | FALSE | 2024-09-18 | 0 |  | WCI | M | 2024 | 8 | 35 | FALSE
READY ¦ OVERDUE | 100 | OK | 120 | IMMED | 029119 | TRUE |  | 0 | 1 | 2024-09-04 | 2024-08-30 | 09:15 AM | 2024-09-03 | MRRN1624 | 4 | 96 | 48 | 75 | 40 | 180 | 24 | 16 x 3 3/4 x 24 |  |  | 2024-07-30 | Recycled Natural | 40 | [6 empty] | 0 | CTN9_55 | 35 | FALSE | A | FALSE | 96 | 48 | 2024-08-08 | 500 | 16 x 3 3/4 x 24 Recycled Natural Merchandise Stock Printed With Recycled Logo. | 4.25 | TRUE | 10 | FALSE | 2024-09-05 | 0 | Prtd Black 39999 | WCI | CS | 2024 | 9 | 36 | FALSE
READY | 601 | OK | 120 | IMMED | 161400-3-1 | TRUE |  | 0 | -12 | 2024-09-12 | 2024-09-12 | 05:04 PM | 2024-08-29 | 13876 | 1.33 | 1 | 1 | 0 | 0 | 0 | 0.75 | 10 x 13 |  | Polk | 2024-08-14 | Recycled Natural | 30 |  | 25 | Black 39999 |  |  |  | 0 | CTN31_68 | 0 | FALSE | A | FALSE | 1 | 1 | 2024-08-16 | 1000 | 10 x 13 Recycled Natural Merchandise Prtd *Polk* 1c/1s Black 39999 CN15966 . | 1.83 | TRUE | 10 | TRUE | 2024-08-31 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ BELOW 0 ¦ PLATES NOT READY ¦ INK NOT READY | 106 | OK | 120 | IMMED | 029157 | FALSE |  | 0 | -6 | 2024-09-13 | 2024-09-13 | 05:34 PM | 2024-09-05 | 01001 | 4.29 | 60 | 60 | 0 | 60 | 0 | 14 | 8 1/2 x 11 | **Uline** This job was made for SO# 161148 Ship date is 9/13 |  | 2024-08-02 | Black | 32 | [6 empty] | 0 | CTN164U_44 | -60 | FALSE | A | FALSE | 60 | 60 | 2024-08-23 | 1000 | 8 1/2 x 11 Black Merchandise Unprinted . | 5.29 | FALSE | 10 | TRUE | 2024-09-07 | 0 | Traveler Team - No Uline labels Use pallet configuration per instruction guide. Maximum pallet height of 56" Customer part# S-14252 must appear on all labels Must use clear tape. Only run full pallet qty. for Uline Use Uline Pallet (Part #PLT-48-40-5-GA) | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ INK NOT READY | B2 | OK | 120 | IMMED | 161109-1-1 | TRUE |  | 0 | -5 | 2024-09-16 | 2024-09-16 | 08:12 AM | 2024-09-09 | 15097 | 0.24 | 5 | 5 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Clifton & Mauney Orthodontics & Pediatric Dentistry | 2024-08-02 | White | 30 |  | 25 | Pantone Process Blue 50 | Green Lt 354u |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 5 | 5 | 2024-08-28 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *Clifton & Mauney Orthodontics & Pediatric Dentistry* 2c/1s Pantone Process Blue 50, Green Lt 354u, CN16785 . | 1.24 | FALSE | 10 | TRUE | 2024-09-11 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ BELOW 0 ¦ PLATES NOT READY ¦ INK NOT READY | 406 | OK | 120 | IMMED | 029155 | FALSE |  | 0 | -1 | 2024-09-13 | 2024-08-30 | 03:22 PM | 2024-09-10 | 00735 | 11.37 | 108 | 54 | 36 | 180 | 0 | 9.5 | 6 1/4 x 3 13/16 x 12 1/2 | **Uline** This job was made for SO# 161148 Ship date is 9/13 |  | 2024-08-02 | Black | 32 | 8# | [5 empty] | 0 | CTN50_53 | -144 | FALSE | A | FALSE | 108 | 54 | 2024-08-22 | 500 | 6 1/4 x 3 13/16 x 12 1/2 Black SOS 8# Unprinted . | 12.37 | FALSE | 10 | TRUE | 2024-09-12 | 0 | Traveler Team - print Uline labels Use pallet configuration per instruction guide. Maximum pallet height of 56" Apply Labels in the upper left hand corner on the short side of the box. Customer part# S-11568BL must appear on all labels Must use clear tape. Only run full pallet qty. for Uline Use Uline Pallet (Part #PLT-48-40-5-GA) | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ OVERDUE ¦ PLATES NOT READY ¦ INK NOT READY | 107 | OK | 120 | IMMED | 029150 | FALSE |  | 0 | 16 | 2024-09-04 |  | 07:06 AM | 2024-09-18 | MRWH1013 | 2.96 | 40 | 40 | 39 | 0 | 47 | 13.5 | 10 x 13 |  |  | 2024-08-01 | White | 30 | [6 empty] | 0 | CTN31_55 | 39 | FALSE | A | FALSE | 40 | 40 | 2024-08-06 | 1000 | 10 x 13 White Merchandise Unprinted . | 3.21 | FALSE | 10 | FALSE | 2024-09-20 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE
MAINT JOB | 103 |  | 125 | IMMED | MNT029295 | FALSE |  | 0 | 14 | 2024-08-20 |  | 06:21 PM | 2024-09-03 | <103> | 3.25 | 2 | 0 | 0 | 0 | 0 | 0 | 10 x 2 x 15 -> 6 1/8 x 2 1/2 x 15 1/2 | Change Over 2.75 Hours (Combined 4), Fine Tune 0.50 Hours |  | 2024-08-19 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 10 x 2 x 15 -> 6 1/8 x 2 1/2 x 15 1/2 | 3.25 | FALSE | 10 | FALSE | 2024-09-03 | 0 |  | WCI | M | 2024 | 8 | 34 | FALSE
READY ¦ CUS CREDIT HOLD | B2 | OK | 125 | IMMED | 161139-1-1 | TRUE |  | 0 | -6 | 2024-09-17 | 2024-09-17 | 05:27 PM | 2024-09-09 | 01648 | 0.71 | 15 | 15 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Chicago Sports | 2024-08-05 | White | 30 |  | 25 | Blue Dk 289u | Ruby Red 199u |  |  | 0 | CTN25_68 | 0 | FALSE | C | FALSE | 15 | 15 | 2024-08-28 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *Chicago Sports * 2c/2s Blue Dk 289u , Ruby Red 199u CN6605 . | 1.71 | TRUE | 10 | TRUE | 2024-09-11 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
READY ¦ INK NOT READY | B2 | OK | 127 | IMMED | 161210-1-1 | TRUE |  | 0 | -6 | 2024-09-18 | 2024-09-18 | 07:09 PM | 2024-09-10 | 09685 | 0.48 | 10 | 10 | 0 | 0 | 0 | 21 | 6 1/4 x 9 1/4 |  | Tenement Museum NYC | 2024-08-06 | White | 30 |  | 25 | Red (spl) 1795u | Brown (spl) 1817u |  |  | 0 | CTN25_68 | 0 | FALSE | A | FALSE | 10 | 10 | 2024-08-28 | 1000 | 6 1/4 x 9 1/4 White Merchandise Prtd *Tenement Museum NYC* 2c/1s Red (spl) 1795u , Brown (spl) 1817u CN13739 . | 1.48 | FALSE | 10 | TRUE | 2024-09-12 | 0 |  | WCI | CS | 2024 | 9 | 38 | FALSE
MAINT JOB | 101 |  | 128 | IMMED | MNT029164 | FALSE |  | 0 | 7 | 2024-08-22 |  | 08:45 PM | 2024-08-29 | <101> | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 5 x 2 x 16 -> 12 x 8 x 14 | Change Over 3.25 Hours (Combined 5), Fine Tune 0.50 Hours |  | 2024-08-05 | [8 empty] | 0 |  | 0 | FALSE |  | FALSE | 2 | 0 |  |  | 5 x 2 x 16 -> 12 x 8 x 14 | 3.75 | FALSE | 10 | FALSE | 2024-08-29 | 0 |  | WCI | M | 2024 | 8 | 34 | FALSE
READY ¦ PLATES NOT READY ¦ INK NOT READY | 101 | OK | 130 | IMMED | 029025 | FALSE |  | 0 | -5 | 2024-09-05 |  | 06:30 AM | 2024-08-29 | SLWS1214GRA | 2.57 | 72 | 18 | 26 | 0 | 89 | 28 | 12 x 8 x 14 |  |  | 2024-07-18 | Sani-Liner Specialty Paper | 40 | [6 empty] | 0 | CTN50_53 | 26 | FALSE | A | FALSE | 72 | 18 | 2024-08-06 | 250 | 12 x 8 x 14 Sani-Liner Specialty Paper Sani-Liner Unprinted . | 2.82 | FALSE | 10 | FALSE | 2024-08-31 | 0 | Use Wet Stregth glue on bottom (ADH-BS-4) and seam (ADH-SM-2)!!! Use 14Qt Tough Guy Labels | WCI | CS | 2024 | 9 | 36 | FALSE
READY | 601 | OK | 130 | IMMED | 161400-2-1 | TRUE |  | 0 | -7 | 2024-09-12 | 2024-09-12 | 06:54 PM | 2024-09-03 | 13875 | 1.33 | 1 | 1 | 0 | 0 | 0 | 0.75 | 8 1/2 x 11 |  | Polk | 2024-08-14 | Recycled Natural | 30 |  | 25 | Black 39999 |  |  |  | 0 | CTN23_64 | 0 | FALSE | A | FALSE | 1 | 1 | 2024-08-16 | 1000 | 8 1/2 x 11 Recycled Natural Merchandise Prtd *Polk* 1c/1s Black 39999, CN15966. | 1.83 | TRUE | 10 | TRUE | 2024-09-05 | 0 |  | WCI | CS | 2024 | 9 | 37 | FALSE
READY ¦ PLATES NOT READY ¦ INK NOT READY | 100 | OK | 130 | IMMED | 029247 | FALSE |  | 0 | 0 | 2024-09-06 | 2024-09-13 | 09:30 AM | 2024-09-04 | MRWH1624 | 1.5 | 36 | 18 | 48 | 5 | 57 | 24 | 16 x 3 3/4 x 24 |  |  | 2024-08-14 | White | 40 | [6 empty] | 0 | CTN9_55 | 43 | FALSE | A | FALSE | 36 | 18 | 2024-08-15 | 500 | 16 x 3 3/4 x 24 White Merchandise Unprinted . | 2 | FALSE | 10 | FALSE | 2024-09-06 | 0 |  | WCI | CS | 2024 | 9 | 36 | FALSE