## 12 MO. Road
Project | [8 empty] | Instructions:
County | [8 empty] | 1.Enter Date for Time Charges Began
Descritpion | [8 empty] | 2.Enter Date for Contract Completion Date (Never change this) The new contract completion date will be figured in blue.
Notice to Proceed: | 2019-06-01 | [7 empty] | 3.Data in Yellow should be all zeros when starting project. Update at the end of each month.
Time Charges Began: | 2019-06-12
Contract Completion Date: | 2019-11-30 | [7 empty] | 4.Data in green will populate automatically.
New Contract Completion Date | 2020-01-28
If less months are needed, add numbers in yellow table to make numbers in green table equal 0
Work Began:
Time Charges Stopped: | [9 empty] | Project Weather Data |  | Extra Days for Supplemental Agreements | Calculations
[10 empty] | Not including |  |  | Actual weather days minus inclimate weather days as shown on the weather zone chart plus Extra days for Supplemental Agreements.
Weather Zone Chart Data | [9 empty] | holidays or weekends:
Zone 3 - Roadway | [8 empty] | Actual | Actual | Actual
| Calendar | Weekend | Rain | Cold | Wet |  | Available |  | Rain | Cold | Wet
Month | Days | Days | Days | Days | Days | Holidays | Work Days |  | Days | Days | Days |  | Days
2019-06-12 | 18 | 6 | 2 | 0 | -1 | 0 | 11 |  | 5 | 0 | 0 | 9 | 13
2019-07-01 | 31 | 8 | 4 | 0 | -1 | 1 | 19 |  | 4 | 0 | 0 | 15 | 16
2019-08-01 | 31 | 9 | 3 | 0 | -2 | 0 | 21 |  | 3 | 0 | 0 | 0 | 2
2019-09-01 | 30 | 9 | 3 | 0 | 0 | 1 | 17 |  | 1 | 0 | 0 | 0 | -2
2019-10-01 | 31 | 8 | 2 | 0 | 0 | 1 | 20 |  | 2 | 0 | 0 | 0 | 0
2019-11-01 | 30 | 9 | 2 | 0 | 0 | 3 | 16 |  | 3 | 0 | 2 | 0 | 3
2019-12-01 | 31 | 9 | 2 | 1 | 1 | 2 | 16 |  | 1 | 0 | 2 | 0 | -1
2020-01-01 | 31 | 8 | 3 | 2 | 1 | 2 | 15 |  | 3 | 0 | 0 | 0 | -3
2020-02-01 | 28 | 9 | 3 | 1 | 1 | 0 | 14 |  | 2 | 0 | 0 | 0 | -3
2020-03-01 | 31 | 9 | 3 | 0 | 1 | 0 | 18 |  | 4 | 0 | 0 | 0 | 0 | ONLY EVALUATE
2020-04-01 | 30 | 8 | 2 | 0 | 1 | 1 | 18 |  | 2 | 0 | 0 | 0 | -1 | THRU ORIGINAL
2020-05-01 | 31 | 10 | 2 | 0 | -1 | 1 | 19 |  | 4 | 0 | 0 | 0 | 3 | COMPLETION DATE*
2020-06-01 | 30 | 8 | 3 | 0 | -1 | 0 | 20 |  | 5 | 0 | 0 | 0 | 3
2020-07-01 | 31 | 8 | 4 | 0 | -1 | 1 | 19 |  | 3 | 0 | 0 | 0 | 0
2020-08-01 | 31 | 10 | 3 | 0 | -2 | 0 | 20 |  | 1 | 0 | 0 | 0 | 0
2020-09-01 | 30 | 8 | 3 | 0 | 0 | 1 | 18 |  | 3 | 0 | 0 | 0 | 0
=========
[13 empty] | 30 | if a positive number =
work days owed
*Unless engineering judgement
suggests carrying thru to the
Revised completion date.
2019-11-01
| 2019-11-01 | 30 | owed work days |  |  |  | 14 | owed work days
| 2019-12-01 | 16 | available work days
| 2020-01-01 | 15 | available work days
|  |  | available work days | [6 empty] | 2020-01-28 |  |  |  |  | 43872
available work days
available work days
available work days
| 2020-01-01 | 14 | owed work days
|  | 15 | available work days
|  | 28 | owed calendar days
|  | 28 | calendar days
Formulas:
Time Charges Stopped: = IF(LEN([Time Charges Stopped:, row above])=0, "",EOMONTH([Time Charges Stopped:, row above], 0)+1)
Calendar = IF(LEN([Time Charges Stopped:])=0,"",EOMONTH([Time Charges Stopped:],0)-[Time Charges Stopped:])
Calendar = IFERROR(IF(C49>0,EOMONTH([Calendar, row above],0)+1,""),"")
Weekend = IF(LEN([Time Charges Stopped:])=0,"",(EOMONTH([Time Charges Stopped:],0)-[Time Charges Stopped:])-NETWORKDAYS([Time Charges Stopped:],EOMONTH([Time Charges Stopped:],0)))+1

## Holidays
|  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
New Year Day | C2 | 2015-01-01 | 2016-01-01 | 2017-01-01 | 2018-01-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 | 2022-01-01 | 2023-01-01 | 2024-01-01 | 2025-01-01 | 2026-01-01 | 2027-01-01 | 2028-01-01
Martin Luther King Jr. Day | C3 | 2015-01-19 | 2016-01-18 | 2017-01-16 | 2018-01-15 | 2019-01-21 | 2020-01-20 | 2021-01-18 | 2022-01-17 | 2023-01-16 | 2024-01-15 | 2025-01-20 | 2026-01-19 | 2027-01-18 | 2028-01-17
State Holiday | C4 | 2015-04-27 | 2016-04-25 | 2017-04-24 | 2018-04-23 | 2019-04-22 | 2020-04-27 | 2021-04-26 | 2022-04-25 | 2023-04-24 | 2024-04-22 | 2025-04-28 | 2026-04-27 | 2027-04-26 | 2028-04-24
Memorial Day | C5 | 2015-05-25 | 2016-05-30 | 2017-05-29 | 2018-05-28 | 2019-05-27 | 2020-05-25 | 2021-05-31 | 2022-05-30 | 2023-05-29 | 2024-05-27 | 2025-05-26 | 2026-05-25 | 2027-05-31 | 2028-05-29
Independence Day | C6 | 2015-07-04 | 2016-07-04 | 2017-07-04 | 2018-07-04 | 2019-07-04 | 2020-07-04 | 2021-07-04 | 2022-07-04 | 2023-07-04 | 2024-07-04 | 2025-07-04 | 2026-07-04 | 2027-07-04 | 2028-07-04
Labor Day | C7 | 2015-09-07 | 2016-09-05 | 2017-09-04 | 2018-09-03 | 2019-09-02 | 2020-09-07 | 2021-09-06 | 2022-09-05 | 2023-09-04 | 2024-09-02 | 2025-09-01 | 2026-09-07 | 2027-09-06 | 2028-09-04
Columbus Day | C8 | 2015-10-12 | 2016-10-10 | 2017-10-09 | 2018-10-08 | 2019-10-14 | 2020-10-12 | 2021-10-11 | 2022-10-10 | 2023-10-09 | 2024-10-14 | 2025-10-13 | 2026-10-12 | 2027-10-11 | 2028-10-09
Veterans Day | C9 | 2015-11-11 | 2016-11-11 | 2017-11-11 | 2018-11-11 | 2019-11-11 | 2020-11-11 | 2021-11-11 | 2022-11-11 | 2023-11-11 | 2024-11-11 | 2025-11-11 | 2026-11-11 | 2027-11-11 | 2028-11-11
Thanksgiving Day | C10 | 2015-11-26 | 2016-11-24 | 2017-11-23 | 2018-11-22 | 2019-11-28 | 2020-11-26 | 2021-11-25 | 2022-11-24 | 2023-11-23 | 2024-11-28 | 2025-11-27 | 2026-11-26 | 2027-11-25 | 2028-11-23
State Holiday | C11 | 2015-11-27 | 2016-11-25 | 2017-11-24 | 2018-11-23 | 2019-11-29 | 2020-11-27 | 2021-11-26 | 2022-11-25 | 2023-11-24 | 2024-11-29 | 2025-11-28 | 2026-11-27 | 2027-11-26 | 2028-11-24
Christmas Eve | C12 | 2015-12-24 | 2016-12-24 | 2017-12-24 | 2018-12-24 | 2019-12-24 | 2020-12-24 | 2021-12-24 | 2022-12-24 | 2023-12-24 | 2024-12-24 | 2025-12-24 | 2026-12-24 | 2027-12-24 | 2028-12-24
Christmas Day | C13 | 2015-12-25 | 2016-12-25 | 2017-12-25 | 2018-12-25 | 2019-12-25 | 2020-12-25 | 2021-12-25 | 2022-12-25 | 2023-12-25 | 2024-12-25 | 2025-12-25 | 2026-12-25 | 2027-12-25 | 2028-12-25

## DO NOT TOUCH
|  | Calendar | Weekend | Rain | Cold | Wet |  | Available
|  | Days | Days | Days | Days | Days | Holidays | Work Days
1 | January | 31 | 9 | 3 | 2 | 1 | 2 | 14
2 | February | 28 | 8 | 3 | 1 | 1 | 0 | 15
3 | March | 31 | 9 | 3 | 0 | 1 | 0 | 18
4 | April | 30 | 9 | 2 | 0 | 1 | 1 | 17
5 | May | 31 | 9 | 2 | 0 | -1 | 1 | 20
6 | June | 30 | 9 | 3 | 0 | -1 | 0 | 19
7 | July | 31 | 9 | 4 | 0 | -1 | 1 | 18
8 | August | 31 | 9 | 3 | 0 | -2 | 0 | 21
9 | September | 30 | 9 | 3 | 0 | 0 | 1 | 17
10 | October | 31 | 9 | 2 | 0 | 0 | 1 | 19
11 | November | 30 | 9 | 2 | 0 | 0 | 3 | 16
12 | December | 31 | 9 | 2 | 1 | 1 | 2 | 16
30 | 3 | 0 | -1
31 | 4 | 0 | -1
31 | 3 | 0 | -2
30 | 3 | 0 | 0
31 | 2 | 0 | 0
30 | 2 | 0 | 0
31 | 2 | 1 | 1
31 | 3 | 2 | 1
28 | 3 | 1 | 1
31 | 3 | 0 | 1
30 | 2 | 0 | 1
31 | 2 | 0 | -1
30 | 3 | 0 | -1
31 | 4 | 0 | -1
31 | 3 | 0 | -2
30 | 3 | 0 | 0
-1