## Budget
Category | Type | Estimate | Date | Labor Cost | Vendor | Vendor Invoice# | Material Cost | Variance | Description
Administrative
Design & Development | Services | 3500
| Services |  | 05/31-06/09 | 90 | BRC |  |  |  | admin Labor
| Services |  | 06/07-06/13 | 225 | BRC |  |  |  | admin Labor
| Services |  | 08/09-08/15 | 92.25 | BRC |  |  |  | admin Labor
Blueprints | Services | 150 | 2020-03-06 |  | Henco | 109166 | 83.46 |  | 24x36 Bond Copies
| Services |  | 2020-03-19 |  | Henco | 1093161 | 41.73 |  | 24x36 Bond Copies
Permit- Development Services | Services | 2000 | 2020-01-28 |  | Buncombe County |  | 750 |  | Well app/permit fee Buncombe county
| Services |  | 2020-03-09 |  | Buncombe County | 165078 | 1122 |  | Residential permit fee receipt#165078 buncombe county
Survey | Services |  | 2020-03-22 |  | Brooks | 9020 | 587.5 |  | Stake Bldg. For Footers
| Services |  | 2020-04-03 |  | Mady | 200030 | 350 |  | Structural Engineering
| Services |  | 2020-04-26 |  | Brooks | 9070 | 312.5 |  | Stake Bldg.
Lein Agent Notice | Services | 30 | 2020-03-06 |  |  |  | 30
Builders Risk Insurance | Services | 1200 | 2020-04-06 |  | Builders Mutual |  | 1270
Administrative Subtotal |  | 6880 |  | 407.25 |  |  | 4547.19 | 1925.56
Site Prep
| Materials |  | 2020-02-14 |  | Home depot | 19853 | 14.93 |  | stake flags
| Materials |  | 2020-03-18 |  | Home depot | 51580 | 47.85 |  | Permit Box, RedWkGlvs,gorilla grip.MKE l Red Nitrile-dip
Dumpster & Toilet | Services |  | 2020-03-24 |  | Griffin | 240403 | 74.9 |  | Portable Toilet
| Materials |  | 2020-03-24 |  | QP | 9052174 | 26.84 |  | Fuel
|  |  | 2020-04-16 |  | Griffin | 243989 | 74.9 |  | Portable Toilet
| Services |  | 2020-05-14 |  | Griffin | 248402 | 74.9 |  | Portable Toilet
| Services |  | 2020-06-11 |  | Griffin | 252863 | 74.9 |  | Portable Toilet
| Services |  | 2020-06-30 |  | Griffin | 255558 | 478.4 |  | 10 yard/haul
| Services |  | 2020-07-09 |  | Griffin | 257470 | 74.9 |  | Inv#257470
| Services |  | 2020-07-31 |  | Griffin | 25711 | 287.8 |  | Container rental 29days & landfill haul
| Services |  | 2020-08-06 |  | Griffin | 262135 | 74.9 |  | Portable Toilet
| Services |  | 2020-08-31 |  | Griffin | 262287 | 298.4 |  | Container Rental, Landfill, 10yard/Haul
| Services |  | 2020-09-03 |  | Griffin | 266916 | 74.9 |  | Portable Toilet
| Services |  | 2020-09-16 |  | Griffin | 267650 | 505.8 |  | Container Rental, Landfill, 10yard/Haul
|  |  | 2020-09-30 |  | Griffin | 270092 | 285 |  | Container Rental, Landfill, 10yard/Haul
| Services |  | 2020-10-01 |  | Griffin | 271535 | 74.9 |  | Portable Toilet
|  |  | 2020-10-29 |  | Griffin | 276366 | 74.9 |  | Portable Toilet
|  |  | 2020-10-29 |  | Griffin | 276581 | 62 |  | Container Rental, Landfill, 10yard/Haul
|  |  | 2020-11-11 |  | Griffin | 278758 | 480.8 |  | Container Rental, Landfill, 10yard/Haul
|  |  | 2020-11-26 |  | Griffin | 281156 | 74.9 |  | Portable Toilet
|  |  | 09/13-09/19 | 168 | BRC |  |  |  | Site Clean up
|  |  | 11/08-11/14 | 382.5 | BRC |  |  |  | Site Clean up
Site Prep Subtotal |  | 0 |  | 550.5 |  |  | 3236.82 | -3787.32
Water& Sewer
Septic System Installation |  | 7000 | 2020-09-04 | 5000 | Burnette Excavating |  |  |  | New Septic Tank
Well Drilling & Development |  | 7000
Water& Sewer Subtotal |  | 14000 |  | 5000 |  |  | 0 | 9000
Excavation, Lot Clear, Backfill
BRC Labor | Labor | 9000 | 03/09-03/15 | 2340 | BRC |  |  |  | Machine Labor @ 52 hours
| Labor |  | 03/09-03/15 | 180 | BRC |  |  |  | Grading @ 4 hours
| Labor |  | 03/16-03/21 | 4050 | BRC |  |  |  | Machine op @ 45 hours
| Labor |  | 04/13-04/17 | 3060 | BRC |  |  |  | Machine op @ 34 hours
| Labor |  | 06/21-06/27 | 810 | BRC |  |  |  | Machine Labor
| Labor |  | 06/21-06/27 | 540 | BRC |  |  |  | Driveway labor
Excavation, Lot Clear, Backfill Subtotal |  | 9000 |  | 10980 |  |  | 0 | -1980
Foundation
Footers & Slabs | Materials | 14797.5 | 2020-03-19 |  | Home depot | 60760 | 19.01 |  | 2x12-12ft #2 prime KD SYP
Foundation Materials | Materials | 3800 | 2020-03-19 |  | Home depot | 58897 | 34.4 |  | 2x12-8 SYP,12/32 OSB Subfloor
| Materials |  | 2020-03-19 |  | Lowes | 7080 | 163.84 |  | 1/2-2 #4 Steel Rebar Pin, 3/8-2#3 Steel Rebar Pin
| Materials |  | 2020-03-20 |  | Southern | 557838 | 3545.87 |  | 5.00 W753ONS
| Materials |  | 2020-03-20 |  | Southern | 557713 | 2738.29 |  | 9.00 W753ONS
| Materials |  | 2020-03-27 |  | Old Castle | 1016010744 | 433.2 |  | Drainage J-Drain 200 4'x50' roll
| Materials |  | 2020-03-27 |  | Home depot | 68819 | 71.01 |  | Loctite Pl Premium Max
| Materials |  | 2020-03-28 |  | Hipps ston | 43918 | 69.55 |  | 1 ton bag of mortar sand
| Materials |  | 2020-03-28 |  | Home depot | 81170 | 712.62 |  | 8x8x16 Concrete HW block
| Materials |  | 2020-03-31 |  | Old Castle | 302075759 | 174.46 |  | Amerimix TypesS Reg 75# CEMEX
| Materials |  | 2020-03-31 |  | Home depot | 642 | 158.57 |  | 8x8x16 Block
| Materials |  | 2020-04-01 |  | Home depot | 3091 | 26.48 |  | 8x8x16 Block
| Materials |  | 2020-04-03 |  | Southern | 563170 | 1737.95 |  | 2.00 W753ONS
| Materials |  | 2020-04-13 |  | Grove Stone | 492724 | 474.98 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492757 | 463.22 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492645 | 453.77 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492770 | 476.45 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492693 | 487.37 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492700 | 499.34 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492592 | 466.58 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492791 | 478.55 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492764 | 482.33 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-13 |  | Grove Stone | 492704 | 459.23 |  | #57 Coarse Aggregate
| Materials |  | 2020-04-14 |  | Home depot | 3169 | 49.17 |  | 25' WBBLD tape,Tapcom 1/4x1-3/4 hex head
| Materials |  | 2020-04-15 |  | Old Castle | 302086489 | 189.93 |  | Wire Mesh 10ga 6x6 5x10 sheet
| Materials |  | 2020-04-16 |  | Home depot | 32020 | 76.56 |  | 10"x1/2 Hot Galv Anchor Bolys
| Materials |  | 2020-04-17 |  | Southern | 568555 | 1387.25 |  | 9.00 W753ONS
| Materials |  | 2020-04-17 |  | Southern | 568673 | 2160.32 |  | 5.00 W753ONS
| Materials |  | 2020-04-21 |  | Home depot | 13504 | 62.86 |  | 5/8"x10' #5 Rebar
| Materials |  | 2020-04-21 |  | Old Castle | 1016137523 | 152.71 |  | Wire Mesh 10ga 6x6 5x10 sheet
| Materials |  | 2020-09-22 |  | Carolina Ready Mix | 28105 | 2524.67 |  | 14 yd 3000 Blend Residential Fiber Env
| Materials |  | 2020-09-23 |  | Home depot | 52163 | 41.66 |  | Sledge Hammer, Blades,Utility Knife
|  |  | 2020-09-23 |  | Home depot | 21270 | 350 |  | Pro Small Breaker rental
|  |  | 2020-09-23 |  | Home depot | 21411 | -257.28 |  | Credit fpr Inv#21270
|  |  | 2020-09-28 |  | Carolina Ready Mix | 5301520 | 739.37 |  | Concrete Repair
|  |  | 2020-09-28 |  | Home depot | 71106 | 4.6 |  | 5" expansion joint
|  |  | 2020-10-05 | 650 | Melrose | 5016 |  |  | Pumping Concrete in Barn
|  |  | 2020-10-06 |  | Carolina Ready Mix | 100620 | 2148.56 |  | Concrete
Termite Control | Services | 600
Waterproofing | Services | 3000 | 2020-04-03 | 2464 | Sealing Agent | 5436576 |  |  | Waterproofing Foundation
| Services |  | 2020-07-31 | 4677 | Sealing Agent | 3521254 |  |  | Sealed crawl
Foundation Labor | Labor | 1662.5 | 2020-04-04 | 5170 | Lopez | 2008 |  |  | Subcontractor Labor
| Labor |  | 2020-04-03 | 605 | Melrose | 4546 |  |  | Concrete Pumping
| Labor |  | 03/16-03/21 | 1080 | BRC |  |  |  | FF labor @ 24 hours
| Labor |  | 03/30-04/04 | 337.5 | BRC |  |  |  | FF labor @ 7.5
| Labor |  | 04/06-04/12 | 202.5 | BRC |  |  |  | FF labor @ 4.5
| Labor |  | 04/13-04/17 | 1000 | BRC |  |  |  | Machine Labor
| Labor |  | 04/13-04/17 | 495 | BRC |  |  |  | Garage Labor @ 11 hours
| Labor |  | 04/13-04/17 | 360 | BRC |  |  |  | Concrete Labor @ 8 hours
| Labor |  | 04/27-05/01 | 855 | BRC |  |  |  | Machine Labor @ 9.5 hrs
| Labor |  | 2020-03-20 | 1015 | Melrose |  |  |  | Concrete Pumping
| Labor |  | 08/02-08/08 | 231.75 | BRC |  |  |  | Labor Concrete work
|  |  | 09/20-09/26 | 720 | BRC |  |  |  | Concrete Form
|  |  | 09/20-09/26 | 1552.5 | BRC |  |  |  | Concrete Work
Foundation Subtotal |  | 23860 |  | 21415.25 |  |  | 24257.45 | -21812.7
Other Masonry
Fireplaces/Hearths | Materials |  | 2020-06-15 |  | Glob Marble | 8986 | 799.27 |  | Wood Planks Stamped Con. Mats 9"
|  |  | 2020-08-24 |  | fireplace Store | 183501 | 1774.06 |  | Fireplace
|  |  | 2020-10-14 |  | Clear Creek Wood | 120664 | 50 |  | Sanding Mantle
Other Masonry Subtotal |  | 0 |  | 0 |  |  | 2623.33 | -2623.33
Framing
Framing Materials | Materials | 51687.5 | 2020-04-07 |  | Builders First Source | 46973971 | 1349.87 |  | 2x8-16',2x10-14',2x10-16'
| Materials |  | 2020-04-07 |  | Builders First Source | 46973835 | 1710.72 |  | 2x10-14',4x8-3/4
| Materials |  | 2020-04-09 |  | Builders First Source | 47007757 | 804.43 |  | 2x1-14'
| Materials |  | 2020-04-13 |  | Builders First Source | 47051291 | 1397.42 |  | 2x6-105",2x6-16'
| Materials |  | 2020-04-09 |  | Builders First Source | 47005120 | 52.28 |  | BFS Sub Flr Glue
| Materials |  | 2020-04-14 |  | Builders First Source | 47086270 | 317.43 |  | 2x6-16',2x6-105"
| Materials |  | 2020-04-21 |  | Builders First Source | 47194819 | 274.99 |  | BC LVL 1-3/4"x9, 2x6-16'
| Materials |  | 2020-04-30 |  | Builders First Source | 47365527 | 374.53 |  | 2x4-12,2x6-12,2x6-105",2x4-105"
| Materials |  | 2020-04-28 |  | Builders First Source | 47333842 | 1020.87 |  | 6x6,2x10,2x8,3x9
| Materials |  | 2020-04-29 |  | Builders First Source | 47359148 | 699.78 |  | 5/4x6-16
| Materials |  | 2020-04-14 |  | Builders First Source | 47071378 | 2360.85 |  | 4x8-7/16,2x4-16',2x4-105"
| Materials |  | 2020-04-15 |  | Builders First Source | 47097027 | 470.93 |  | 2x6-105",2x6-16', BC Lvl 1-3/4"x9
| Materials |  | 2020-04-17 |  | Builders First Source | 47157270 | 820.16 |  | 2x6-12',2x4-12',2x6-16'
| Materials |  | 2020-04-30 |  | Builders First Source | 47384567 | 835.56 |  | 2x10-16,2x10-12,2x8-16,2x8-12
| Materials |  | 2020-05-11 |  | Builders First Source | 47544483 | 59.75 |  | BFS Sub Flr Glue
| Materials |  | 2020-05-11 |  | Builders First Source | 47543562 | 2345.32 |  | 23/32" 4x8 T&G, BC LVL1-3/4"x16"x22"
| Materials |  | 2020-05-11 |  | Builders First Source | 47548835 | 3789.64 |  | 2x6-93",2x4-93,2x6-16',2x4-16',7/16" 4x8,4" zip
| Materials |  | 2020-05-14 |  | Builders First Source | 47627941 | 60.75 |  | BC LVL 1-3/4"x9-1/4"x12'
| Materials |  | 2020-05-12 |  | Builders First Source | 47569977 | 232.65 |  | 4x10-10',2x4-16',1x4-16&-12
| Materials |  | 2020-05-26 |  | Builders First Source | 47803677 | 1069.3 |  | 2x8-16',2x4-16',2x6-16'
| Materials |  | 2020-05-28 |  | Builders First Source | 47855618 | 3703.83 |  | 1/2"4x8,7/16"4x8,23/32 4x8,2x4-16',2x6-12&-16,4" zip
| Materials |  | 2020-05-26 |  | Builders First Source | 47807561 | 1177 |  | 1x6-16 T&G Joint
| Materials |  | 2020-04-20 |  | Home depot | 28070 | 150.54 |  | 80Lb Quickrete,2x4-16,2x4-12,DckGlovexl,23/32 4x8 subfloor
| Materials |  | 2020-05-23 |  | Home depot | 34260 | 169.5 |  | 2x12-16Ft #2 prime KD SYP
| Materials |  | 2020-06-11 |  | Lowes | 6010 | 93.37 |  | whitewood kD and #2 BTR KD
| Materials |  | 2020-06-23 |  | Old Castle | 302138751 | 65.14 |  | Poly 6mil 20'x100' blk
| Materials |  | 2020-05-08 |  | Builders First Source | 46007673 | 577.16 |  | 2x6-16 #2, 2x4-16' and 2x6-105"
| Materials |  | 2020-05-11 |  | Builders First Source | 45603970 | 6855.29 |  | Floor Truss
| Materials |  | 2020-05-12 |  | Builders First Source | 46061579 | 429.11 |  | 2x8-16' &2x10-16'
| Materials |  | 2020-05-12 |  | Builders First Source | 46065817 | 20.68 |  | 3x9 PGP Star DR Tan
| Materials |  | 2020-05-22 |  | Builders First Source | 46150039 | 741.72 |  | 7/16"4x8 OSB ZIP ST1W/R
| Materials |  | 2020-05-22 |  | Builders First Source | 46148841 | 4258.88 |  | 2x10,2x6,2x8 Lumber
| Materials |  | 2020-06-02 |  | Builders First Source | 47917140 | 562.17 |  | 2x12,2x10 &1/2"4x8OSB ZIP
| Materials |  | 2020-06-02 |  | Builders First Source | 46359999 | 271.88 |  | 2x12-16 &2x12-12
| Materials |  | 2020-06-04 |  | Builders First Source | 46474094 | 363.76 |  | 4" ZIP Sheathing Tape
| Materials |  | 2020-06-04 |  | Builders First Source | 46463659 | 1191.77 |  | 1x6 joint,1/2"4x8 OSB&2x8-16
| Materials |  | 2020-06-09 |  | Builders First Source | 46541551 | 363.76 |  | 4" ZIP Sheathing Tape
| Materials |  | 2020-06-09 |  | Builders First Source | 46541333 | 87.49 |  | 23/32"4x8&2x6-16'
|  |  | 2020-08-24 |  | Log Homes Of America | 11947 | 2303.39 |  | Timber for porch Framing
|  |  | 2020-08-31 |  | Home depot | 97780 | 83.25 |  | 2x4-12,2x6-12,2x6-105",2x4-105"
|  |  | 2020-09-28 |  | Builders First Source | 50192664 | 523.85 |  | Porch Framing Materials
|  |  | 2020-09-28 |  | Home depot | 22715 | 61.4 |  | Framing Consumables
|  |  | 2020-09-30 |  | Home depot | 26344 | 126.16 |  | Timbers for Framing
|  |  | 2020-10-27 |  | Builders First Source | C47993044 | -1090.59 |  | Credit for Inv#47993044
|  |  | 2020-10-28 |  | Builders First Source | C49145182 | -108.71 |  | Credit for Inv#45589459
|  |  | 2020-11-02 |  | Home depot | 74635 | 44.34 |  | 1/2x8,1/2 Fender Washer,screws,crayon, pencil
|  |  | 2020-11-02 |  | Log Homes Of America | 12019 | 479.9 |  | White Pine timbers
|  |  | 2020-11-03 |  | Home depot | 92858 | 62.04 |  | Nails
|  |  | 2020-11-03 |  | Builders First Source |  | 1729.16 |  | T&G for Porch roof
|  |  | 2020-11-05 |  | Builders First Source | 49264158 | 1175.61 |  | 7/16" 4X8,1/2"4x8 OSB Zip
|  |  | 2020-11-06 |  | Builders First Source |  | 3021
|  |  | 2020-11-06 |  | Home depot | 33692 | 212.89 |  | Nutrile Coated gloves,AA bateries, Zip system seam tape
|  |  | 2020-11-09 |  | Home depot | 70907 | 192.57 |  | weatherwatch roofing material
|  |  | 2020-11-09 |  | Home Depot | 71277 | 192.54 |  | Weatherwatch 1.5 SQ
Framing Labor |  | 51687.5
| Labor |  | 08/02-08/08 | 382.5 | BRC |  |  |  | Labor Framing
| Labor |  | 2020-04-12 | 5000 | Binuelos Framing |  |  |  | Framing deposit
| Labor |  | 2020-05-12 | 6000 | Binuelos Framing |  |  |  | Framing Labor
| Labor |  | 2020-05-29 | 7000 | Binuelos Framing |  |  |  | Framing Labor
| Labor |  | 2020-06-10 | 6000 | Binuelos Framing |  |  |  | Framing Labor
| Labor |  | 2020-06-10 | 4000 | Binuelos Framing |  |  |  | Framing Labor
| Labor |  | 2020-07-22 | 2000 | Binuelos Framing |  |  |  | Framing Labor
| Labor |  | 2020-07-22 | 1000 | Binuelos Framing |  |  |  | windows
|  |  | 08/30-09/05 | 360 | BRC |  |  |  | Framing Labor
|  |  | 09/20-09/26 | 405 | BRC |  |  |  | Framing Labor
|  |  | 10/18-10/24 | 180 | BRC |  |  |  | Framing Labor
|  |  | 10/25-10/31 | 697.5 | BRC |  |  |  | Porches & Decks
|  |  | 11/01-11/07 | 1147.5 | BRC |  |  |  | Porches & Decks
|  |  | 11/01-1107 | 4027.5 | BRC |  |  |  | Roof Framing
|  |  | 2020-11-11 | 2500 | Binuelos Framing |  |  |  | Framing Labor
|  |  | 11/08-11/14 | 798.75 | BRC |  |  |  | Interior Framing
Framing Subtotal |  | 103375 |  | 41498.75 |  |  | 50139.08 | 11737.17
Roofing
Per Square Foot Cost | L&M | 8270 | 2020-07-16 | 6906 | Consolidated Roofing | 6906 |  |  | Roof Install
Gutters & Downspouts |  | 2821 | 11/08-11/14 | 1417.5 | BRC |  |  |  | Roof Labor
Roofing Subtotal |  | 11091 |  | 8323.5 |  |  | 0 | 2767.5
Exterior
Vinyl or Composite Siding |  | 6000 | 2020-10-14 |  | 84 Lumber | 499871 | 136.27 |  | Trim 1x12x16
|  |  | 2020-10-29 |  | 84 Lumber | 501101 | 282.48 |  | 1x4x16 PRMD FJ RADIATA
|  |  | 2020-11-03 |  | 84 Lumber | 501503 | 312.85 |  | Trim 1x6x16,1x4x16
|  |  | 2020-11-10 |  | Home depot | 7252 | 16.26 |  | Sel-centering hing bit,scotchblue,Latch strike
Stucco |  | 3000
Exterior Paint, Stain, Caulk |  | 6500 | 2020-10-28 | 1720 | Adrian Zambrano | 3478 |  |  | Trim Labor
Exterior, Labor-Only |  | 12000 | 10/25-10/31 | 180 | BRC |  |  |  | Trim Labor
|  |  | 2020-11-12 | 2340 | Adrian Zambrano |  |  |  | Trim Labor
Exterior Subtotal |  | 27500 |  | 4240 |  |  | 747.86 | 22512.14
Windows/Exterior Doors
Entry Door, Prehung |  | 8850
| Materials |  | 2020-06-24 |  | Builders First Source | 48370903 | 228.79 |  | 6"x75' TYVEK Windows Mant'ls
|  |  | 2020-06-24 |  | Home Depot | 38141 | 124.03 |  | Caulk for Windows
|  |  | 2020-06-24 |  | Builders First Source | 46823093 | 228.79 |  | 6"x75" TYVEK Flex wrap tape
|  |  | 09/13-09/19 | 540 | BRC |  |  |  | Doors
|  |  | 11/08-11/14 | 1125 | BRC |  |  |  | Window Labor
Windows/Exterior Doors Subtotal |  | 8850 |  | 1665 |  |  | 581.61 | 6603.39
Plumbing
Per Drop Cost |  | 12275 | 2020-06-19 |  | Hajoca |  | 558.19 |  | Moen 1/2 crimp,Left hand tub,Watco pol chrome
Kitchen Sinks |  | 250 | 2020-08-25 |  | Prosource | S2244139 | 1167.49 |  | Moen "U" Four- Outlet, Moen Body Spray
Plumbing Subtotal |  | 12525 |  | 0 |  |  | 1725.68 | 10799.32
Electrical
Per Square Foot Cost |  | 20054.75
Electrical Subtotal |  | 20054.75 |  | 0 |  |  | 0 | 20054.75
HVAC
Per SF Estimate |  | 13791.96
HVAC Subtotal |  | 13791.96 |  | 0 |  |  | 0 | 13791.96
Insulation & Air Sealing
Insulation & Material Labor | L&M | 9500 | 2020-08-05 | 10207 | Sealing Agent |  |  |  | Spray Foam
Insulation & Air Sealing Subtotal |  | 9500 |  | 10207 |  |  | 0 | -707
Drywall/Plaster
Drywall Labor Only |  | 9599 | 2020-08-25 |  | Trejos Drywall |  |  |  | $11,200 Estimate
|  |  | 2020-08-28 |  | Tucker Materials |  | 7079.64 |  | Drywall Materials
|  |  | 2020-09-22 | 4000 | Trejos Drywall |  |  |  | Britt Drywall
|  |  | 2020-09-29 | 7200 | Trejos Drywall |  |  |  | Britt Drywall
Drywall/Plaster Subtotal |  | 9599 |  | 11200 |  |  | 7079.64 | -8680.64
Interior Finish
Interior Doors, Prehung |  | 4405
|  |  | 2020-10-13 |  | Home depot | 33734 | 42.51 |  | Interior Trim
Interior Trim |  | 2947 | 2020-10-14 |  | Lowes | 6840 | 224.42 |  | Trim for Stairs
|  |  | 2020-10-15 |  | Home depot | 60179 | 15.26 |  | Interior Trim
|  |  | 2020-10-16 |  | Lowes | 42454 | 99.34 |  | Interior Trim
|  |  | 2020-11-16 |  | Home Depot | 53818 | 70.56 |  | Interior Trim Materials
|  |  | 2020-11-17 |  | Home depot |  | 181.64 |  | Interior Trim
|  |  | 2020-11-19 |  | 84 Lumber | 502558 | 4404.39 |  | Britt Doors
|  |  | 2020-11-19 |  | 84 Lumber | 502565 | 88.79 |  | Interior Trim
|  |  | 2020-11-19 |  | Home depot |  | 58.82 |  | Interior Trim
|  |  | 2020-11-20 |  | Home depot |  | 281.55 |  | Interior Trim
|  |  | 2020-11-24 |  | 84 Lumber | 502980 | 342.89 |  | Interior Trim
|  |  | 2020-11-24 |  | 84 Lumber | 503024 | 1865.9 |  | Interior Trim
Interior Carpentry Labor Only |  | 2885.4
Interior Painting |  | 8000 | 2020-10-05 | 3200 | Lake Norman Color | 375 |  |  | prime ceiling& walls,prep& paint
Wood Flooring |  | 3683.75 | 2020-11-09 |  | Gennett Lumber | 61442 | 140.17 |  | Flooring Materials
|  |  | 2020-11-18 | 6024 | Carolina Wood Floor | 99 |  |  | Install and sanding 1,680 sqft
Carpeting |  | 3683.75
Interior Trim Labor |  | 8841 | 11/08-11/14 | 720 | BRC |  |  |  | Punchout
|  |  | 11/15-11/21 | 1372.5 | BRC |  |  |  | Interior Trim Labor
Interior Finish Subtotal |  | 34445.9 |  | 11316.5 |  |  | 7816.24 | 15313.16
Kitchen & Bath Cabinets & Finishes
Cabinet Package Estimate |  | 20294.06 | 2020-09-24 |  | Crystal Cabinet | 717908 | 3700 |  | Kitchen Cabinets
Kit. Cabinet Hardware & Accessories |  | 600 | 2020-09-24 |  | Crystal Cabinet | 717909 | 1050 |  | Master Bath
Kit. Countertops |  | 6000 | 2020-09-24 |  | Crystal Cabinet | 717910 | 1400 |  | Guest Bath
Tile Installation Labor |  | 6300 | 2020-09-24 |  | Crystal Cabinet | 717911 | 375 |  | Kids Bath
Finish Labor & Materials |  | 9000 | 2020-09-30 |  | Crystal Cabinet | 717908 | 3605.91 |  | Kitchen Cabinets
|  |  | 2020-09-30 |  | Crystal Cabinet | 717909 | 1092.24 |  | Master Bath
|  |  | 2020-09-30 |  | Crystal Cabinet | 717910 | 1339.43 |  | Guest Bath
|  |  | 2020-09-30 |  | Crystal Cabinet | 717911 | 364.79 |  | Kids Bath
|  |  | 2020-10-13 |  | Crystal Cabinet | 720028 | 22.19 |  | Touch Up Paint
|  |  | 2020-10-14 |  | WNC Ceramic Tile | 176178A | 338.11 |  | Bathroom Tile for Drains
|  |  | 2020-10-14 |  | Home depot | 50361 | 114.73 |  | Bathroom Tile Materials
|  |  | 2020-10-14 |  | WNC Ceramic Tile |  | 761.83 |  | Bathroom Tile Materials
|  |  | 2020-10-20 |  | WNC Ceramic Tile | 176483 | 397.24 |  | Bathroom Tile
|  |  | 2020-10-20 |  | Home depot | 33277 | 216.39 |  | Bathroom Thinset
|  |  | 2020-10-20 |  | Lowes | 12320 | 157.2 |  | Shower Niche,dur edgeguard
|  |  | 2020-10-26 |  | Home depot | 655344 | 8.53 |  | Wood Biscuits
|  |  | 2020-10-29 |  | Crystal Cabinet | 3588271 | 95.87 |  | Kids Bath
|  |  | 2020-10-30 |  | Home depot | 52152 | 18.59 |  | Cabinet repair materials
|  |  | 2020-11-02 |  | Home depot | 74304 | 10.67 |  | Sanding disk
|  |  | 2020-11-03 |  | Crystal Cabinet | 3588569 | 50.81 |  | Tall Vanity Filler
|  |  | 2020-11-03 |  | Crystal Cabinet | 3588337 | 72.97 |  | Touch Up Paint
|  |  | 2020-11-18 |  | Crystal Cabinet | 3589704 | 298.29 |  | Kitchen Cabinets
|  |  | 2020-11-18 |  | Crystal Cabinet | 3589759 | 33.96 |  | Moulding for guest bath
|  |  | 10/11-10/17 | 360 | BRC |  |  |  | Cabinet Labor
Kitchen & Bath Cabinets & Finishes Subtotal |  | 42194.06 |  | 360 |  |  | 15524.75 | 26309.31 | Project Total Cost
TOTAL CONSTRUCTION COSTS |  | 346666.67 |  | 127163.75 |  |  | 118279.65 | 101223.27 | 245443.4
CONTRACTORS FEE @ 20% |  | 69333.334 | [6 empty] | 49088.68
TOTAL |  | 416000.004 | [6 empty] | 294532.08
COST PER SQUARE FOOT
RAW COST
Conditioned Square Footage | [5 empty] | Date | Billed |  | Paid
Lower Level Square Footage | [5 empty] | 2020-05-08 | 41386.73 |  | 41386.73
Main Level Square Footage | [5 empty] | 2020-05-12 | 28170.9 |  | 28170.9
Loft Square | [5 empty] | 2020-07-03 | 43908.67 |  | 43908.67
[6 empty] | 2020-08-07 | 55454.89 |  | 55454.89
Total SF | [5 empty] | 2020-09-30 | 41105.832 |  | 41105.83
[6 empty] | 2020-10-27 | 26637.156 |  | 26637.16
Non-Conditioned SF
Roof Covered SF | [6 empty] | 236664.178 |  | 236664.18
Additional Porch SF - Back Porch & Ramp
Total Conditioned & Non-Conditioned
BRC Estimate @ 165 sf
17236.25

## Budget Summary
Category | Estimate | Labor Cost | Material Cost | Variance
Administrative
3500
Design & Development | 3500
| 150 |  | 83.46
Blueprints | 150 |  | 83.46
| 2000 |  | 750
Permit- Development Services | 2000 |  | 750
587.5
Survey |  |  | 587.5
| 30 |  | 30
Lein Agent Notice | 30 |  | 30
| 1200 |  | 1270
Builders Risk Insurance | 1200 |  | 1270
| 6880 | 407.25 | 4547.19 | 1925.56
Administrative Subtotal | 6880 | 407.25 | 4547.19 | 1925.56
Site Prep
74.9
Dumpster & Toilet |  |  | 74.9
| 0 | 550.5 | 3236.82 | -3787.32
Site Prep Subtotal | 0 | 550.5 | 3236.82 | -3787.32
Water& Sewer
| 7000 | 5000
Septic System Installation | 7000 | 5000
7000
Well Drilling & Development | 7000
| 14000 | 5000 | 0 | 9000
Water& Sewer Subtotal | 14000 | 5000 | 0 | 9000
Excavation, Lot Clear, Backfill
| 9000 | 2340
BRC Labor | 9000 | 2340
| 9000 | 10980 | 0 | -1980
Excavation, Lot Clear, Backfill Subtotal | 9000 | 10980 | 0 | -1980
Foundation
| 14797.5 |  | 19.01
Footers & Slabs | 14797.5 |  | 19.01
| 3800 |  | 34.4
Foundation Materials | 3800 |  | 34.4
600
Termite Control | 600
| 3000 | 2464
Waterproofing | 3000 | 2464
| 1662.5 | 5170
Foundation Labor | 1662.5 | 5170
| 23860 | 21415.25 | 24257.45 | -21812.7
Foundation Subtotal | 23860 | 21415.25 | 24257.45 | -21812.7
Other Masonry
799.27
Fireplaces/Hearths |  |  | 799.27
| 0 | 0 | 2623.33 | -2623.33
Other Masonry Subtotal | 0 | 0 | 2623.33 | -2623.33
Framing
| 51687.5 |  | 1349.87
Framing Materials | 51687.5 |  | 1349.87
51687.5
Framing Labor | 51687.5
| 103375 | 41498.75 | 50139.08 | 11737.17
Framing Subtotal | 103375 | 41498.75 | 50139.08 | 11737.17
Roofing
| 8270 | 6906
20054.75
Per Square Foot Cost | 28324.75 | 6906
2821
Gutters & Downspouts | 2821
| 11091 | 8323.5 | 0 | 2767.5
Roofing Subtotal | 11091 | 8323.5 | 0 | 2767.5
Exterior
| 6000 |  | 136.27
Vinyl or Composite Siding | 6000 |  | 136.27
3000
Stucco | 3000
| 6500 | 1720
Exterior Paint, Stain, Caulk | 6500 | 1720
| 12000 | 180
Exterior, Labor-Only | 12000 | 180
| 27500 | 4240 | 747.86 | 22512.14
Exterior Subtotal | 27500 | 4240 | 747.86 | 22512.14
Windows/Exterior Doors
8850
Entry Door, Prehung | 8850
| 8850 | 1665 | 581.61 | 6603.39
Windows/Exterior Doors Subtotal | 8850 | 1665 | 581.61 | 6603.39
Plumbing
| 12275 |  | 558.19
Per Drop Cost | 12275 |  | 558.19
| 250 |  | 1167.49
Kitchen Sinks | 250 |  | 1167.49
| 12525 | 0 | 1725.68 | 10799.32
Plumbing Subtotal | 12525 | 0 | 1725.68 | 10799.32
Electrical
| 20054.75 | 0 | 0 | 20054.75
Electrical Subtotal | 20054.75 | 0 | 0 | 20054.75
HVAC
13791.96
Per SF Estimate | 13791.96
| 13791.96 | 0 | 0 | 13791.96
HVAC Subtotal | 13791.96 | 0 | 0 | 13791.96
Insulation & Air Sealing
| 9500 | 10207
Insulation & Material Labor | 9500 | 10207
| 9500 | 10207 | 0 | -707
Insulation & Air Sealing Subtotal | 9500 | 10207 | 0 | -707
Drywall/Plaster
9599
Drywall Labor Only | 9599
| 9599 | 11200 | 7079.64 | -8680.64
Drywall/Plaster Subtotal | 9599 | 11200 | 7079.64 | -8680.64
Interior Finish
4405
Interior Doors, Prehung | 4405
| 2947 |  | 224.42
Interior Trim | 2947 |  | 224.42
2885.4
Interior Carpentry Labor Only | 2885.4
| 8000 | 3200
Interior Painting | 8000 | 3200
| 3683.75 |  | 140.17
Wood Flooring | 3683.75 |  | 140.17
3683.75
Carpeting | 3683.75
8841
Interior Trim Labor | 8841
| 34445.9 | 11316.5 | 7816.24 | 15313.16
Interior Finish Subtotal | 34445.9 | 11316.5 | 7816.24 | 15313.16
Kitchen & Bath Cabinets & Finishes
| 20294.06 |  | 3700
Cabinet Package Estimate | 20294.06 |  | 3700
| 600 |  | 1050
Kit. Cabinet Hardware & Accessories | 600 |  | 1050
| 6000 |  | 1400
Kit. Countertops | 6000 |  | 1400
| 6300 |  | 375
Tile Installation Labor | 6300 |  | 375
| 9000 |  | 3605.91
Finish Labor & Materials | 9000 |  | 3605.91
| 42194.06 | 360 | 15524.75 | 26309.31
Kitchen & Bath Cabinets & Finishes Subtotal | 42194.06 | 360 | 15524.75 | 26309.31 | Total Project Cost to Date
| 346666.67 | 127163.75 | 118279.65 | 101223.27
TOTAL CONSTRUCTION COSTS | 346666.67 | 127163.75 | 118279.65 | 101223.27 | 245443.4

## Inv#1 (hidden)
INVOICE
Blue Ridge Concepts, LLC
WNC’s Premier Building Professionals/ Lic. No. 77121
231 Merchant St, Asheville, NC 28803
828-367-8368 – Scott Brown, Owner
828-713-0910 – Todd Claussen, Project Manager
Funds dispursed TO: | SITE ADDRESS:
Blue Ridge Concepts LLC | 382 Old Fort Rd
802 Fairview Road Suite #4000 | Fairview, NC 28730
Asheville, NC 28803
DESCRIPTION | AMOUNT
#1- Admin: Builders Risk Insurance | 1270
Admin: Design & Development Coordination | 3500
Plans/Survey: Prints | 125.19
Permit Fees | 1872
#2-Survey and Staking | 937.5
Lot clear/Excavation/Backfill | 7245
#3- Footing/Slab: Labor- | 1620
Footing/Foundation: Labor- Melrose/Lopez masonry | 5775
Gravel | 3391.26
Footing/Slab: Materials | 16771.78
Framing: Materials- | 7993
Framing labor- Deposit- Binuelos Framing | 5000
Waterproofing-Sealing Agents | 2464
57964.73
Contractor Fee @ 20% | 11593
INVOICE TOTAL | 69557.63
Paid | 41386.73
Due | 28170.9
Make all checks payable to Blue Ridge Concepts, LLC and mail to 231 Merchant Street, Asheville, NC 28803.
If you have any questions concerning this invoice, contact Catherine DeWitt, (828) 273-8919, Cat@brcdesignbuild.com
Thank you for your business!
Draw request #1
April 21, 2020

## Inv#2 (hidden)
Blue Ridge Concepts , LLC
#02 | 802 Fairview Road Suite 4000 Asheville NC, 28803 Owner: Scott Brown (828) 367-8368 Project Manager:Todd Claussen (828) 273-8919
Bill To:
INVOICE | William & Andrea Britt
382 Old Fort Road
Fairview NC 28730
2020-06-30
DESCRIPTION
| Permit - Development Services |  |  | 312.5
| Dumpster Fees |  |  | 299.6
| Foundation labor |  |  | 1015
| Foundation materials |  |  | 1167.48
| Framing Package |  |  | 21856.06
| Framing labor-Binuelos |  |  | 13000
|  | Subtotal |  | 37650.64
|  | 20% Contractor fee |  | 7530.128
|  |  | Balance Due | 45180.768 | 5.77 | 45186.538

## Inv#3 (hidden)
Blue Ridge Concepts , LLC
#03 | 802 Fairview Road Suite 4000 Asheville NC, 28803 Owner: Scott Brown (828) 367-8368 Project Manager: Todd Claussen (828) 273-8919
Bill To:
INVOICE | William & Andrea Britt
382 Old Fort Road
Fairview NC 28730
2020-08-18
DESCRIPTION
| Site Prep- Griffin Waste Services |  | Dumpster and Portable Toilet |  | 916
| Excavation - Blue Ridge Concepts |  | Grading Labor |  | 1350
| Roofing-Consolidated Roofing |  | Installed Shingles |  | 6906
| Foundation Waterproofing & Materials |  | Sealed Crawlspace |  | 4677
| Sealing Agents |  | Spray foam Insulation |  | 9934
| Framing- Subcontractor Labor |  | Binuelos |  | 13614.25
| Framing Materials |  | Builders First Source |  | 12577.82
|  |  | Subtotal |  | 49975.07
|  |  | Contractor fee |  | 9995.014
|  |  |  | Balance Due | 59970.084
Make all checks payable to Blue Ridge Concepts, LLC If you have any questions concerning this invoice contact Gloria Diaz (828) 273-8919 Gloria@brcdesignbuild.com
Thank you for your business

## Inv#4 (hidden)
Blue Ridge Concepts , LLC 802 Fairview Road Suite 4000 Asheville NC, 28803 Owner: Scott Brown (828) 367-8368 Project Manager: Todd Claussen (828) 273-8919
#04
Bill To:
INVOICE | William & Andrea Britt
382 Old Fort Road
Fairview NC 28730
2020-09-30
| Date | Description | Vendor |  | Amount
| 2020-08-31 | Dumpster | Griffin |  | 879.1
| 2020-09-04 | Septic | Burnette Excavation |  | 5000
| 2020-08-24 | Fire Place | fireplace Store |  | 1774.06
| 2020-08-31 | Framing Materials | Log Homes Of America |  | 3098.05
| 08/30-09/05 | Framing Labor | Blue Ridge Concepts |  | 900
| 2020-08-25 | Plumbing Materials | Prosource & Hajoca |  | 1725.68
| 2020-08-28 | Drywall Materials | Tucker Materials |  | 7079.64
| 2020-08-05 | Insulation | Sealing Agent |  | 707
| 2020-09-22 | Subcontractor Labor | Trejos Drywall |  | 4000
| 2020-09-24 | Cabinets | Crystal Cabinet |  | 6525
| 2020-09-22 | Foundation Materials | Carolina Ready Mix |  | 2566.33 | -10333.158
|  |  | Subtotal |  | 34254.86
|  |  | Contractor fee |  | 6850.972
|  |  |  | Balance Due | 41105.832
Make all checks payable to Blue Ridge Concepts, LLC If you have any questions concerning this invoice contact Gloria Diaz (828) 273-8919 Gloria@brcdesignbuild.com
Thank you for your business

## Inv#5
Blue Ridge Concepts , LLC 802 Fairview Road Suite 4000 Asheville NC, 28803 Owner: Scott Brown (828) 367-8368 Project Manager: Todd Claussen (828) 273-8919
#05
Bill To:
INVOICE | William & Andrea Britt
382 Old Fort Road
Fairview NC 28730
2020-10-27
| Date | Description | Vendor |  | Amount
| 2020-09-30 | Container Rental | Griffin |  | 285
| 2020-10-01 | Portable Toilet | Griffin |  | 74.9
| 09/13-09/19 | Site Labor | Blue Ridge Concepts |  | 528
| 2020-09-29 | Subcontractor Drywall | Trejos Drywall |  | 7200
| 2020-10-05 | Subcontractor Paint | Lake Norman Color |  | 3200
| 2020-09-30 | Cabinets | Crystal Cabinet |  | 6424.56
| 2020-10-05 | Pumping Concrete in Barn | Melrose |  | 650
| 2020-10-06 | Concrete | Carolina Ready Mix |  | 2148.56
| 09/20-09/26 | Framing Labor | Blue Ridge Concepts |  | 405
| 2020-10-14 | Interior Trim | Lowes, Home Depot |  | 381.53
| 2020-10-14 | Bathroom Tile | WNC Ceramic Tile |  | 850.08
| 2020-10-14 | Sanding Mantle | Clear Creek Wood |  | 50
|  |  | Subtotal |  | 22197.63
|  |  | Contractor fee |  | 4439.526
|  |  |  | Balance Due | 26637.156
Make all checks payable to Blue Ridge Concepts, LLC If you have any questions concerning this invoice contact Gloria Diaz (828) 273-8919 Gloria@brcdesignbuild.com
Thank you for your business

## Inv#6
Blue Ridge Concepts , LLC 802 Fairview Road Suite 4000 Asheville NC, 28803 Owner: Scott Brown (828) 367-8368 Project Manager: Todd Claussen (828) 273-8919
#06
Bill To:
INVOICE | William & Andrea Britt
382 Old Fort Road
Fairview NC 28730
2020-11-25
| Date | Description | Vendor |  | Amount
| 10/18-10/24 | Framing Labor | Blue Ridge Concepts |  | 6851.25
| 2020-10-29 | Portable Toilet | Griffin Waste |  | 136.9
| 2020-10-29 | Kitchen & Bathroom Cabinets | Crystal Cabinet |  | 551.9
| 2020-10-14 | Subcontractor Trim Labor | Adrian Zambrano |  | 4060
| 10/25-10/31 | Exterior Trim Labor | Blue Ridge Concepts |  | 1900
| 2020-10-27 | Framing Materials | Builders First Source & Log Homes of America |  | 5910.75
| 2020-10-20 | Bathroom Tile Materials | Home Depot & Lowes |  | 1173.21
| 2020-11-09 | Flooring Materials | Gennett Lumber |  | 140.17
| 2020-11-03 | Exterior Trim Materials | 84 Lumber |  | 747.86
| 2020-11-11 | Subcontractor Framing Labor | Binuelos Framing |  | 2500
| 11/08-11/14 | Site Clean up | Blue Ridge Concepts |  | 382.5
| 11/08-11/14 | Window Installation Labor | Blue Ridge Concepts |  | 1125
| 11/08-11/14 | Interior Finish Labor | Blue Ridge Concepts |  | 3510
| 2020-11-18 | Install and sanding 1,680 sqft | Carolina Wood Floor |  | 6024
| 2020-11-16 | Interior Trim Materials | Home Depot |  | 592.57
| 2020-11-19 | Interior Trim & Doors | 84 Lumber |  | 6701.97
|  |  | Subtotal |  | 42308.08
|  |  | Contractor fee |  | 8461.616
|  |  |  | Balance Due | 50769.696
Make all checks payable to Blue Ridge Concepts, LLC If you have any questions concerning this invoice contact Gloria Diaz (828) 273-8919 Gloria@brcdesignbuild.com
Thank you for your business

## Draw Sheet 2 (hidden)
| DRAW # 1 | DATE:______________
DRAW STATEMENT FOR UNITED FEDERAL CREDIT UNION
| OWNER: | Britt | CONTRACTOR NAME: | Blue Ridge Concepts |  |  | TELEPHONE: | (828) 273-8919
|  |  | PERSON SUBMITTING: | Scott Brown |  |  | CELL/PHONE:
FAX:
|  |  | PROPERTY ADDRESS | 382 Old Fort Road Fairview, NC 28803
| SUBCONTRACTOR/SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
| OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
1 |  | Builders Risk Insurance | 1200 | 0 | 1200 | 1270 | 0 | 0 | -70
2 |  | Design & Development | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0
3 |  | Blueprints | 150 | 0 | 150 | 125.19 | 0 | 0 | 24.81
4 |  | Lien agent Notice | 30 | 0 | 30 | 1872 | 0 | 0 | -1842
5 |  | Permit - Development Services | 2000 | 0 | 2000 | 937.5 | 312.5 | 0 | 750
6 |  | Permit - Water Availability | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | New Well | 7000 | 0 | 7000 | 0 | 0 | 0 | 7000
8 |  | New Septic System | 7000 | 0 | 7000 | 0 | 0 | 0 | 7000
9 |  | Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Lot Clearing/Excavation | 9000 | 0 | 9000 | 10636.26 | 0 | 0 | -1636.26
11 |  | Footings & Slabs | 14797.5 | 0 | 14797.5 | 14797.5 | 0 | 0 | 0
12 |  | Foundation Materials | 3800 | 0 | 3800 | 0 | 1167.48 | 0 | 2632.52
13 |  | Foundation labor | 1662.5 | 0 | 1662.5 | 1620 | 1015 | 0 | -972.5
14 |  | Exterior water proofing | 3000 | 0 | 3000 | 2464 | 0 | 0 | 536
15 |  | Stucco | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000
16 |  | Termite control | 600 | 0 | 600 | 0 | 0 | 0 | 600
17 |  | Framing Package | 51687.5 | 0 | 51687.5 | 15742.28 | 21856.06 | 0 | 14089.16
18 |  | Framing Labor | 51687.5 | 0 | 51687.5 | 5000 | 13000 | 0 | 33687.5
19 |  | Roof | 8270 | 0 | 8270 | 0 | 0 | 0 | 8270
20 |  | Gutters & Downspouts | 2821 | 0 | 2821 | 0 | 0 | 0 | 2821
21 |  | Siding Materials | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
22 |  | Siding Labor | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000
23 |  | Exterior Paint/Wood Treatment | 6500 | 0 | 6500 | 0 | 0 | 0 | 6500
24 |  | Insulation | 9500 | 0 | 9500 | 0 | 0 | 0 | 9500
25 |  | Flooting Materials | 7367.5 | 0 | 7367.5 | 0 | 0 | 0 | 7367.5
26 |  | Flooring labor | 2885.4 | 0 | 2885.4 | 0 | 0 | 0 | 2885.4
27 |  | Drywall | 9599 | 0 | 9599 | 0 | 0 | 0 | 9599
28 |  | Interior Paint | 8000 | 0 | 8000 | 0 | 0 | 0 | 8000
29 |  | Interior Trim - Materials | 2947 | 0 | 2947 | 0 | 0 | 0 | 2947
30 |  | Interior Trim - labor | 8841 | 0 | 8841 | 0 | 0 | 0 | 8841
31 |  | Exterior Doors | 8850 | 0 | 8850 | 0 | 0 | 0 | 8850
32 |  | Interior Doors | 4405 | 0 | 4405 | 0 | 0 | 0 | 4405
33 |  | Windows/Sliders/Skylights | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL PAGE 1: |  | 258100.9 | 0 | 258100.9 | 57964.73 | 37351.04 | 0 | 162785.13
SWORN STATEMENT (PAGE 2)
| SUBCONTRACTOR SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
| OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
34 |  | Gas Fireplace | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  | HVAC | 13791.96 | 0 | 13791.96 | 0 | 0 | 0 | 13791.96
36 |  | Electrical Wiring & Installation | 20054.75 | 0 | 20054.75 | 0 | 0 | 0 | 20054.75
37 |  | Light Fixture Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  | Rough-In Plumbing | 12275 | 0 | 12275 | 0 | 0 | 0 | 12275
39 |  | Plumbing Fixtures | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  | Kitchen Sink/Faucet | 250 | 0 | 250 | 0 | 0 | 0 | 250
41 |  | Hot Water Heater | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 |  | Tile & Backsplash labor | 6300 | 0 | 6300 | 0 | 0 | 0 | 6300
43 |  | Tile Showers | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  | Glass Shower Doors | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  | Toilets | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  | Cabinet Package | 20294.06 | 0 | 20294.06 | 0 | 0 | 0 | 20294.06
47 |  | Kitchen Bath Countertops | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
48 |  | Appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 |  | Finish hardware | 600 | 0 | 600 | 0 | 0 | 0 | 600
50 |  | Finish labor | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000
51 |  | Dumpster Fees | 0 | 0 | 0 | 0 | 299.6 | 0 | -299.6
52 |  | Portable restroom | 0 | 0 | 0 | 0 |  | 0 | 0
53 |  |  |  | 0 | 0 | 0 |  | 0 | 0
54 |  | Contractor Fee | 69333.33 | 0 | 69333.33 | 11593 | 7530.13 | 0 | 50210.2
55 |  | Contingency Allowance |  | 0 | 0 | 0 |  | 0 | 0
56 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
57 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL PAGE 2: |  | 157899.1 | 0 | 157899.1 | 11593 | 7829.73 | 0 | 138476.37
| PAGE 2 SUB TOTAL |  | 416000 | 0 | 416000 | 69557.73 | 45180.77 | 0 | 301261.5
SWORN STATEMENT (PAGE 3)
| SUBCONTRACTOR SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
| OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
67 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL PAGE 3: |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GRAND TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Draw Sheet 3 (hidden)
DRAW # 3 | Date: 8/17/2020
DRAW STATEMENT FOR UNITED FEDERAL CREDIT UNION
OWNER: | Britt | CONTRACTOR NAME: | Blue Ridge Concepts |  |  | TELEPHONE: | (828) 273-8919
|  | PERSON SUBMITTING: | Scott Brown |  |  | CELL/PHONE:
FAX:
|  | PROPERTY ADDRESS | 382 Old Fort Road Fairview, NC 28803
SUBCONTRACTOR/SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Builders Risk Insurance | 1200 | 0 | 1200 | 1270 | 0 | 0 | -70
| Design & Development | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0
| Blueprints | 150 | 0 | 150 | 125.19 | 0 | 0 | 24.81
| Lien agent Notice | 30 | 0 | 30 | 1872 | 0 | 0 | -1842
| Permit - Development Services | 2000 | 0 | 2000 | 1250 | 0 | 0 | 750
| Permit - Water Availability | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Well | 7000 | 0 | 7000 | 0 | 0 | 0 | 7000
| New Septic System | 7000 | 0 | 7000 | 0 | 0 | 0 | 7000
| Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lot Clearing/Excavation | 9000 | 0 | 9000 | 10636.26 | 1350 | 0 | -2986.26
| Footers & Slabs | 14797.5 | 0 | 14797.5 | 14797.5 | 4677 | 0 | -4677
| Foundation Materials | 3800 | 0 | 3800 | 1167.48 | 0 | 0 | 2632.52
| Foundation labor | 1662.5 | 0 | 1662.5 | 2635 | 0 | 0 | -972.5
| Exterior water proofing | 3000 | 0 | 3000 | 2464 | 0 | 0 | 536
| Stucco | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000
| Termite control | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Framing Package | 51687.5 | 0 | 51687.5 | 37598.34 | 12577.82 | 0 | 1511.34
| Framing Labor | 51687.5 | 0 | 51687.5 | 18000 | 13614.25 | 0 | 20073.25
| Roof | 8270 | 0 | 8270 | 0 | 6906 | 0 | 1364
| Gutters & Downspouts | 2821 | 0 | 2821 | 0 | 0 | 0 | 2821
| Siding Materials | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Siding Labor | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000
| Exterior Paint/Wood Treatment | 6500 | 0 | 6500 | 0 | 0 | 0 | 6500
| Insulation | 9500 | 0 | 9500 | 0 | 9934 | 0 | -434
| Flooting Materials | 7367.5 | 0 | 7367.5 | 0 | 0 | 0 | 7367.5
| Flooring labor | 2885.4 | 0 | 2885.4 | 0 | 0 | 0 | 2885.4
| Drywall | 9599 | 0 | 9599 | 0 | 0 | 0 | 9599
| Interior Paint | 8000 | 0 | 8000 | 0 | 0 | 0 | 8000
| Interior Trim - Materials | 2947 | 0 | 2947 | 0 | 0 | 0 | 2947
| Interior Trim - labor | 8841 | 0 | 8841 | 0 | 0 | 0 | 8841
| Exterior Doors | 8850 | 0 | 8850 | 0 | 0 | 0 | 8850
| Interior Doors | 4405 | 0 | 4405 | 0 | 0 | 0 | 4405
| Windows/Sliders/Skylights | 12175 | -12175 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 1: |  | 270275.9 | -12175 | 258100.9 | 95315.77 | 49059.07 | 0 | 113726.06
SWORN STATEMENT (PAGE 2)
SUBCONTRACTOR SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Gas Fireplace | 1100 | -1100 | 0 | 0 | 0 | 0 | 0
| HVAC | 13791.96 | 0 | 13791.96 | 0 | 0 | 0 | 13791.96
| Electrical Wiring & Installation | 20054.75 | 0 | 20054.75 | 0 | 0 | 0 | 20054.75
| Light Fixture Budget | 2000 | -2000 | 0 | 0 | 0 | 0 | 0
| Rough-In Plumbing | 12275 | 0 | 12275 | 0 | 0 | 0 | 12275
| Plumbing Fixtures | 2850 | -2850 | 0 | 0 | 0 | 0 | 0
| Kitchen Sink/Faucet | 250 | 0 | 250 | 0 | 0 | 0 | 250
| Hot Water Heater | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile & Backsplash labor | 6300 | 0 | 6300 | 0 | 0 | 0 | 6300
| Tile Showers |  | 0 | 0 | 0 | 0 | 0 | 0
| Glass Shower Doors | 2400 | -2400 | 0 | 0 | 0 | 0 | 0
| Toilets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cabinet Package | 21258 | -963.94 | 20294.06 | 0 | 0 | 0 | 20294.06
| Kitchen Bath Countertops | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Appliances | 4500 | -4500 | 0 | 0 | 0 | 0 | 0
| Finish hardware | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Finish labor | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000
| Dumpster Fees | 5000 | -5000 | 0 | 299.6 | 916 | 0 | -1215.6
| Portable restroom | 3000 | -3000 | 0 | 0 | 0 | 0 | 0
| Driveway/Curb | 500 | -500 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Contractor Fee | 76231.12 | -6897.79 | 69333.33 | 19123.13 | 9995.014 | 0 | 40215.186
| Contingency Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 2: |  | 187110.83 | -29211.73 | 157899.1 | 19422.73 | 10911.014 | 0 | 127565.356
PAGE 2 SUB TOTAL |  | 457386.73 | -41386.73 | 416000 | 114738.5 | 59970.084 | 0 | 241291.416
SWORN STATEMENT (PAGE 3)

## Draw Sheet 4 (hidden)
DRAW # 4 | Date: 09/30/2020
DRAW STATEMENT FOR UNITED FEDERAL CREDIT UNION
OWNER: | Britt | CONTRACTOR NAME: | Blue Ridge Concepts |  |  | TELEPHONE: | (828) 273-8919
|  | PERSON SUBMITTING: | Scott Brown |  |  | CELL/PHONE:
FAX:
|  | PROPERTY ADDRESS | 382 Old Fort Road Fairview, NC 28803
SUBCONTRACTOR/SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Builders Risk Insurance | 1200 | 70 | 1270 | 1270 | 0 | 0 | 0
| Design & Development | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0
| Blueprints | 150 | -24.81 | 125.19 | 125.19 | 0 | 0 | 0
| Lien agent Notice | 30 | 1842 | 1872 | 1872 | 0 | 0 | 0
| Permit - Development Services | 2000 | -750 | 1250 | 1250 | 0 | 0 | 0
| Permit - Water Availability | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Well | 7000 | -1184.9 | 5815.1 | 0 | 0 | 0 | 5815.1
| New Septic System | 7000 | -2000 | 5000 | 0 | 5000 | 0 | 0
| Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lot Clearing/Excavation | 9000 | 2986.26 | 11986.26 | 11986.26 | 0 | 0 | 0
| Footers & Slabs | 14797.5 | 4677 | 19474.5 | 19474.5 | 0 | 0 | 0
| Foundation Materials | 3800 | 44.86 | 3844.86 | 1167.48 | 2566.33 | 0 | 111.05
| Foundation labor | 1662.5 | 972.5 | 2635 | 2635 | 0 | 0 | 0
| Exterior water proofing | 3000 | 0 | 3000 | 2464 | 0 | 0 | 536
| Stucco | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000
| Termite control | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Framing Package | 51687.5 | -1320.05 | 50367.45 | 50176.16 | 3098.05 | 0 | -2906.76
| Framing Labor | 51687.5 | -7608.76 | 44078.74 | 31614.25 | 900 | 0 | 11564.49
| Roof | 8270 | 0 | 8270 | 6906 | 0 | 0 | 1364
| Gutters & Downspouts | 2821 | 0 | 2821 | 0 | 0 | 0 | 2821
| Siding Materials | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Siding Labor | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000
| Exterior Paint/Wood Treatment | 6500 | 0 | 6500 | 0 | 0 | 0 | 6500
| Insulation | 9500 | 707 | 10207 | 9934 | 707 | 0 | -434
| Flooting Materials | 7367.5 | 0 | 7367.5 | 0 | 0 | 0 | 7367.5
| Flooring labor | 2885.4 | 0 | 2885.4 | 0 | 0 | 0 | 2885.4
| Drywall | 9599 | 0 | 9599 | 0 | 11079.64 | 0 | -1480.64
| Interior Paint | 8000 | 0 | 8000 | 0 | 0 | 0 | 8000
| Interior Trim - Materials | 2947 | 0 | 2947 | 0 | 0 | 0 | 2947
| Interior Trim - labor | 8841 | 0 | 8841 | 0 | 0 | 0 | 8841
| Exterior Doors | 8850 | 0 | 8850 | 0 | 0 | 0 | 8850
| Interior Doors | 4405 | 0 | 4405 | 0 | 0 | 0 | 4405
| Windows/Sliders/Skylights | 12175 | -12175 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 1: |  | 270275.9 | -13763.9 | 256512 | 144374.84 | 23351.02 | 0 | 88786.14
SWORN STATEMENT (PAGE 2)
SUBCONTRACTOR SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Gas Fireplace | 1100 | 674.06 | 1774.06 | 0 | 1774.06 | 0 | 0
| HVAC | 13791.96 | 0 | 13791.96 | 0 | 0 | 0 | 13791.96
| Electrical Wiring & Installation | 20054.75 | -1774.06 | 18280.69 | 0 | 0 | 0 | 18280.69
| Light Fixture Budget | 2000 | -2000 | 0 | 0 | 0 | 0 | 0
| Rough-In Plumbing | 12275 | 0 | 12275 | 0 | 0 | 0 | 12275
| Plumbing Fixtures | 2850 | -2850 | 0 | 0 | 1725.68 | 0 | -1725.68
| Kitchen Sink/Faucet | 250 | 0 | 250 | 0 | 0 | 0 | 250
| Hot Water Heater | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile & Backsplash labor | 6300 | 0 | 6300 | 0 | 0 | 0 | 6300
| Tile Showers |  | 0 | 0 | 0 | 0 | 0 | 0
| Glass Shower Doors | 2400 | -2400 | 0 | 0 | 0 | 0 | 0
| Toilets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cabinet Package | 21258 | -963.94 | 20294.06 | 0 | 6525 | 0 | 13769.06
| Kitchen Bath Countertops | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Appliances | 4500 | -4500 | 0 | 0 | 0 | 0 | 0
| Finish hardware | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Finish labor | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000
| Dumpster Fees | 5000 | -3411.1 | 1588.9 | 1215.6 | 879.1 | 0 | -505.8
| Portable restroom | 3000 | -3000 | 0 | 0 | 0 | 0 | 0
| Driveway/Curb | 500 | -500 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Contractor Fee | 76231.12 | -6897.79 | 69333.33 | 29118.144 | 6850.972 | 0 | 33364.214
| Contingency Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 2: |  | 187110.83 | -27622.83 | 159488 | 30333.744 | 17754.812 | 0 | 111399.444
PAGE 2 SUB TOTAL |  | 457386.73 | -41386.73 | 416000 | 174708.584 | 41105.832 | 0 | 200185.584
SWORN STATEMENT (PAGE 3)

## Draw Sheet 5
DRAW # 5 | Date: 10/27/2020
DRAW STATEMENT FOR UNITED FEDERAL CREDIT UNION
OWNER: | Britt | CONTRACTOR NAME: | Blue Ridge Concepts |  |  | TELEPHONE: | (828) 273-8919
|  | PERSON SUBMITTING: | Scott Brown |  |  | CELL/PHONE:
FAX:
|  | PROPERTY ADDRESS | 382 Old Fort Road Fairview, NC 28803
SUBCONTRACTOR/SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Builders Risk Insurance | 1200 | 70 | 1270 | 1270 | 0 | 0 | 0
| Design & Development | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0
| Blueprints | 150 | -24.81 | 125.19 | 125.19 | 0 | 0 | 0
| Lien agent Notice | 30 | 1842 | 1872 | 1872 | 0 | 0 | 0
| Permit - Development Services | 2000 | -750 | 1250 | 1250 | 0 | 0 | 0
| Permit - Water Availability | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Well | 7000 | -7000 | -9.0949e-13 | 0 | 0 | 0 | -9.0949e-13
| New Septic System | 7000 | -2000 | 5000 | 5000 | 0 | 0 | 0
| Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lot Clearing/Excavation | 9000 | 2986.26 | 11986.26 | 11986.26 | 0 | 0 | 0
| Footers & Slabs | 14797.5 | 4677 | 19474.5 | 19474.5 | 0 | 0 | 0
| Foundation Materials | 3800 | -66.19 | 3733.81 | 3733.81 | 0 | 0 | 0
| Foundation labor | 1662.5 | 972.5 | 2635 | 2635 | 0 | 0 | 0
| Exterior water proofing | 3000 | -536 | 2464 | 2464 | 0 | 0 | 0
| Stucco | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000
| Termite control | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Framing Package | 51687.5 | 1586.71 | 53274.21 | 53274.21 | 0 | 0 | 0
| Framing Labor | 51687.5 | -15441.69 | 36245.81 | 32514.25 | 3731.56 | 0 | -2.2737e-12
| Roof | 8270 | 0 | 8270 | 6906 | 0 | 0 | 1364
| Gutters & Downspouts | 2821 | 0 | 2821 | 0 | 0 | 0 | 2821
| Siding Materials | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Siding Labor | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000
| Exterior Paint/Wood Treatment | 6500 | 0 | 6500 | 0 | 0 | 0 | 6500
| Insulation | 9500 | 1141 | 10641 | 10641 | 0 | 0 | 0
| Flooting Materials | 7367.5 | 0 | 7367.5 | 0 | 0 | 0 | 7367.5
| Flooring labor | 2885.4 | 0 | 2885.4 | 0 | 0 | 0 | 2885.4
| Drywall | 9599 | 8680.64 | 18279.64 | 11079.64 | 7200 | 0 | 0
| Interior Paint | 8000 | -143.34 | 7856.66 | 0 | 3200 | 0 | 4656.66
| Interior Trim - Materials | 2947 | 0 | 2947 | 0 | 431.53 | 0 | 2515.47
| Interior Trim - labor | 8841 | 0 | 8841 | 0 | 0 | 0 | 8841
| Exterior Doors | 8850 | 0 | 8850 | 0 | 0 | 0 | 8850
| Interior Doors | 4405 | 0 | 4405 | 0 | 0 | 0 | 4405
| Windows/Sliders/Skylights | 12175 | -12175 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 1: |  | 270275.9 | -16180.92 | 254094.98 | 167725.86 | 14563.09 | 0 | 71806.03
SWORN STATEMENT (PAGE 2)
SUBCONTRACTOR SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Gas Fireplace | 1100 | 674.06 | 1774.06 | 1774.06 | 0 | 0 | 0
| HVAC | 13791.96 | 0 | 13791.96 | 0 | 0 | 0 | 13791.96
| Electrical Wiring & Installation | 20054.75 | -2401.26 | 17653.49 | 0 | 0 | 0 | 17653.49
| Light Fixture Budget | 2000 | -2000 | 0 | 0 | 0 | 0 | 0
| Rough-In Plumbing | 12275 | 0 | 12275 | 0 | 0 | 0 | 12275
| Plumbing Fixtures | 2850 | -1124.32 | 1725.68 | 1725.68 | 0 | 0 | 0
| Kitchen Sink/Faucet | 250 | 0 | 250 | 0 | 0 | 0 | 250
| Hot Water Heater | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile & Backsplash labor | 6300 | 0 | 6300 | 0 | 0 | 0 | 6300
| Tile Showers |  | 452.84 | 452.84 | 0 | 850.08 | 0 | -397.24
| Glass Shower Doors | 2400 | -2400 | 0 | 0 | 0 | 0 | 0
| Toilets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cabinet Package | 21258 | -963.94 | 20294.06 | 6525 | 6424.56 | 0 | 7344.5
| Kitchen Bath Countertops | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Appliances | 4500 | -4500 | 0 | 0 | 0 | 0 | 0
| Finish hardware | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Finish labor | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000
| Dumpster Fees | 5000 | -2545.4 | 2454.6 | 2094.7 | 359.9 | 0 | 5.6843e-13
| Portable restroom | 3000 | -3000 | 0 | 0 | 0 | 0 | 0
| Driveway/Curb | 500 | -500 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Contractor Fee | 76231.12 | -6897.79 | 69333.33 | 35969.116 | 4439.526 | 0 | 28924.688
| Contingency Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 2: |  | 187110.83 | -25205.81 | 161905.02 | 48088.556 | 12074.066 | 0 | 101742.398
PAGE 2 SUB TOTAL |  | 457386.73 | -41386.73 | 416000 | 215814.416 | 26637.156 | 0 | 173548.428
SWORN STATEMENT (PAGE 3)

## Draw Sheet 6
DRAW # 6 | Date: 11/25/2020
DRAW STATEMENT FOR UNITED FEDERAL CREDIT UNION
OWNER: | Britt | CONTRACTOR NAME: | Blue Ridge Concepts |  |  | TELEPHONE: | (828) 273-8919
|  | PERSON SUBMITTING: | Scott Brown |  |  | CELL/PHONE:
|  | PROPERTY ADDRESS | 382 Old Fort Road Fairview, NC 28803
SUBCONTRACTOR/SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Builders Risk Insurance | 1200 | 70 | 1270 | 1270 | 0 | 0 | 0
| Design & Development | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0
| Blueprints | 150 | -24.81 | 125.19 | 125.19 | 0 | 0 | 0
| Lien agent Notice | 30 | 1842 | 1872 | 1872 | 0 | 0 | 0
| Permit - Development Services | 2000 | -750 | 1250 | 1250 | 0 | 0 | 0
| Permit - Water Availability | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New Well | 7000 | -7000 | 0 | 0 | 0 | 0 | 0
| New Septic System | 7000 | -2000 | 5000 | 5000 | 0 | 0 | 0
| Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lot Clearing/Excavation | 9000 | 2986.26 | 11986.26 | 11986.26 | 0 | 0 | 0
| Footers & Slabs | 14797.5 | 4677 | 19474.5 | 19474.5 | 0 | 0 | 0
| Foundation Materials | 3800 | -66.19 | 3733.81 | 3733.81 | 0 | 0 | 0
| Foundation labor | 1662.5 | 972.5 | 2635 | 2635 | 0 | 0 | 0
| Exterior water proofing | 3000 | -536 | 2464 | 2464 | 0 | 0 | 0
| Stucco | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000
| Termite control | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Framing Package | 51687.5 | 1586.71 | 53274.21 | 53274.21 | 0 | 0 | 0
| Framing Labor | 51687.5 | -15441.69 | 36245.81 | 36245.81 | 9351.25 | 0 | -9351.25
| Roof | 8270 | 0 | 8270 | 6906 | 0 | 0 | 1364
| Gutters & Downspouts | 2821 | 0 | 2821 | 0 | 0 | 0 | 2821
| Siding Materials | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Siding Labor | 12000 | 0 | 12000 | 0 | 0 | 0 | 12000
| Exterior Paint/Wood Treatment | 6500 | 0 | 6500 | 0 | 6658.61 | 0 | -158.61
| Insulation | 9500 | 1141 | 10641 | 10641 | 0 | 0 | 0
| Flooting Materials | 7367.5 | 0 | 7367.5 | 0 | 140.17 | 0 | 7227.33
| Flooring labor | 2885.4 | 0 | 2885.4 | 0 | 6024 | 0 | -3138.6
| Drywall | 9599 | 8680.64 | 18279.64 | 18279.64 | 0 | 0 | 0
| Interior Paint | 8000 | -143.34 | 7856.66 | 3200 | 0 | 0 | 4656.66
| Interior Trim - Materials | 2947 | 0 | 2947 | 431.53 | 592.57 | 0 | 1922.9
| Interior Trim - labor | 8841 | 0 | 8841 | 0 | 9470 | 0 | -629
| Exterior Doors | 8850 | 0 | 8850 | 0 | 0 | 0 | 8850
| Interior Doors | 4405 | 0 | 4405 | 0 | 6701.97 | 0 | -2296.97
| Windows/Sliders/Skylights | 12175 | -12175 | 0 | 0 | 1125 | 0 | -1125
TOTAL PAGE 1: |  | 270275.9 | -16180.92 | 254094.98 | 182288.95 | 40063.57 | 0 | 31742.46
SWORN STATEMENT (PAGE 2)
SUBCONTRACTOR SUPPLIER | DESCRIPTION OF WORK OR | ORIGINAL CONTRACT | CHANGE ORDERS | ADJUSTED | PREVIOUS PAYMENTS | AMOUNT OF THIS | RETAINAGE | BALANCE TO
OR LABORER | MATERIAL | AMOUNT | (IF ANY) | CONTRACT AMOUNT | AND/OR DRAWS | REQUEST | (IF ANY) | COMPLETE
| Gas Fireplace | 1100 | 674.06 | 1774.06 | 1774.06 | 0 | 0 | 0
| HVAC | 13791.96 | 0 | 13791.96 | 0 | 0 | 0 | 13791.96
| Electrical Wiring & Installation | 20054.75 | -2401.26 | 17653.49 | 0 | 0 | 0 | 17653.49
| Light Fixture Budget | 2000 | -2000 | 0 | 0 | 0 | 0 | 0
| Rough-In Plumbing | 12275 | 0 | 12275 | 0 | 0 | 0 | 12275
| Plumbing Fixtures | 2850 | -1124.32 | 1725.68 | 1725.68 | 0 | 0 | 0
| Kitchen Sink/Faucet | 250 | 0 | 250 | 0 | 0 | 0 | 250
| Hot Water Heater | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tile & Backsplash labor | 6300 | 0 | 6300 | 0 | 0 | 0 | 6300
| Tile Showers |  | 452.84 | 452.84 | 850.08 | 1173.21 | 0 | -1570.45
| Glass Shower Doors | 2400 | -2400 | 0 | 0 | 0 | 0 | 0
| Toilets | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cabinet Package | 21258 | -963.94 | 20294.06 | 12949.56 | 551.9 | 0 | 6792.6
| Kitchen Bath Countertops | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000
| Appliances | 4500 | -4500 | 0 | 0 | 0 | 0 | 0
| Finish hardware | 600 | 0 | 600 | 0 | 0 | 0 | 600
| Finish labor | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000
| Dumpster Fees | 5000 | -2545.4 | 2454.6 | 2454.6 | 382.5 | 0 | -382.5
| Portable restroom | 3000 | -3000 | 0 | 0 | 136.9 | 0 | -136.9
| Driveway/Curb | 500 | -500 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
| Contractor Fee | 76231.12 | -6897.79 | 69333.33 | 40408.642 | 8461.616 | 0 | 20463.072
| Contingency Allowance |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL PAGE 2: |  | 187110.83 | -25205.81 | 161905.02 | 60162.622 | 10706.126 | 0 | 91036.272
PAGE 2 SUB TOTAL |  | 457386.73 | -41386.73 | 416000 | 242451.572 | 50769.696 | 0 | 122778.732
SWORN STATEMENT (PAGE 3)

## Gantt
Britt
Blue Ridge Concepts
802 Fairview Rd Asheville, NC 28803 |  | Project Start: | 2020-03-24
|  | Display Week: | 0 |  | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11
 | time axis 2020-03-16 to 2020-05-17
Task | Assigned To | Progress | Start | End | time axis 2020-03-16 to 2020-05-17
Administrative
Design & Development |  | 100% | 2020-03-24 | 2020-03-31
Permit- Development |  | 100% | 2020-04-01 | 2020-04-08
Plan/survey/Engineering |  | 100% | 2020-04-09 | 2020-04-16
Lien Agent |  | 100% | 2020-04-17 | 2020-04-24
Builders Risk Insurance |  | 100% | 2020-04-25 | 2020-05-02
Site Prep & Excavation
Lot Clear |  | 100% | 2020-05-03 | 2020-05-10
Rough Grading |  | 100% | 2020-05-11 | 2020-05-18
Foundation Excavation |  | 100% | 2020-05-19 | 2020-05-26
Finish Grading |  | 0% | 2020-05-27 | 2020-06-03
Dumpster & Toilet |  | 50% | 2020-06-04 | 2020-06-11
Foundation
Footers& Piers |  | 100% | 2020-06-12 | 2020-06-19
Foundation Wall |  | 100% | 2020-06-20 | 2020-06-27
Steel Reinforcing |  | 100% | 2020-06-28 | 2020-07-05
Radon Venting |  | 0% | 2020-07-06 | 2020-07-13
Concrete Finish |  | 100% | 2020-07-14 | 2020-07-21
Waterproofing
Termite Control |  | 0% | 2020-07-22 | 2020-07-29
Concrete Pumping |  | 100% | 2020-07-30 | 2020-08-06
Framing
Floor |  | 100% | 2020-08-07 | 2020-08-14
Exterior Walls |  | 100% | 2020-08-15 | 2020-08-22
Interior walls |  | 100% | 2020-08-23 | 2020-08-30
Sub Floor |  | 100% | 2020-08-31 | 2020-09-07
Roof Framing |  | 100% | 2020-09-08 | 2020-09-15
Deck & Porch Framing |  | 0% | 2020-09-16 | 2020-09-23
Exterior
Roofing |  | 0% | 2020-09-24 | 2020-10-01
Gutter & Downspouts |  | 0% | 2020-10-02 | 2020-10-09
Stucco |  | 0% | 2020-10-10 | 2020-10-17
Siding |  | 0% | 2020-10-18 | 2020-10-25
Exterior Trim |  | 0% | 2020-10-26 | 2020-11-02
Windows & doors
Exterior Door Install |  | 0% | 2020-11-03 | 2020-11-10
Window Install |  | 0% | 2020-11-11 | 2020-11-18
Garage Door install |  | 0% | 2020-11-19 | 2020-11-26
Plumbing
Rough In Plumbing |  | 100% | 2020-11-27 | 2020-12-04
Fridge Connection |  | 100% | 2020-12-05 | 2020-12-12
Gas Piping |  | 0% | 2020-12-13 | 2020-12-20
Dishwasher |  | 0% | 2020-12-21 | 2020-12-28
Hose Bib |  | 0% | 2020-12-29 | 2021-01-05
Water Heater |  | 0% | 2021-01-06 | 2021-01-13
Toilets |  | 0% | 2021-01-14 | 2021-01-21
Disposal |  | 0% | 2021-01-22 | 2021-01-29
Electrical
Rough Wiring |  | 100% | 2021-01-30 | 2021-02-06
Light Fixtures |  | 100% | 2021-02-07 | 2021-02-14
Service Panel |  | 100% | 2021-02-15 | 2021-02-22
Phone,Cable,Internet |  | 0% | 2021-02-23 | 2021-03-02
HVAC
ERV Unit Install |  | 0% | 2021-03-03 | 2021-03-10
Interior
Drywall |  | 100% | 2021-03-11 | 2021-03-18
Doors |  | 100% | 2021-03-19 | 2021-03-26
Interior Trim |  | 100% | 2021-03-27 | 2021-04-03
Paint |  | 0% | 2021-04-04 | 2021-04-11
Flooring Installation |  | 0% | 2021-04-12 | 2021-04-19
Kitchen Backsplash |  | 0% | 2021-04-20 | 2021-04-27
Tile Installation |  | 0% | 2021-04-28 | 2021-05-05