Contents

Project Phases	2

Phase 1: Planning and Assessment	2

Phase 2: DR Site Upgrade	5

Phase 3: Production Site Upgrade	5

Phase 4: Post-Upgrade Monitoring and Maintenance	6

Configuration Summary	6

Detailed plan to upgrade infrastructure's Windows Server 2016 Active Directory servers to Windows Server 2022 with best practices, risk assessment, mitigation, and change management incorporated.

### Project Phases

1. Planning and Assessment

2. DR Site Upgrade

3. Production Site Upgrade

4. Post-Upgrade Monitoring and Maintenance

### Phase 1: Planning and Assessment

#### I. Inventory & Documentation

#### Existing AD Structure:

- Number of domain controllers, their locations (physical and site topology within AD).

- Domain and forest functional levels.

- FSMO role placement.

- Trust relationships (if any).

#### Application Dependencies:

- Create a comprehensive list of all core banking applications and other critical services relying on Active Directory.

- Document authentication/authorization methods (LDAP, Kerberos, etc.).

- Identify any applications with specific domain/forest functional level requirements.

#### Hardware and Virtualization:

- Document specifications of existing DC servers (CPU, RAM, storage).

- Inventory your virtualization platform (Hyper-V, VMware, etc.) and its version.

#### Network & DNS:

- Map network subnets used by domain controllers.

- Thoroughly document DNS configuration, including zones, records, and any DNS forwarding or delegation.

#### II. Compatibility Assessment

#### Applications:

- Contact each core banking application vendor to determine:

- Official support statements for Windows Server 2022.

- Any known compatibility issues or required updates.

- Specific domain/forest level requirements, if applicable.

#### Hardware & Hypervisor:

- Verify your hypervisor's compatibility with Windows Server 2022. Check vendor HCLs (Hardware Compatibility Lists).

- Ensure existing server hardware meets minimum requirements for Windows Server 2022 if they are physical hosts.

#### III. Risk Assessment

#### Expanded Risk Identification

- Downtime: Assess the impact of potential downtime during upgrades on services and banking operations.

- Data Loss: Consider risks from potential replication issues, demotion failures, and configuration errors.

- Security Vulnerabilities: During the transition period, there might be a mixed environment of Server 2016 and 2022; address any known vulnerabilities.

- Operational Overhead: Estimate the resources (time, personnel) required for the project.

#### Risk Mitigation Strategies

- Lab Testing: Create a replica of your production AD environment for extensive upgrade testing.

- Thorough Backups: Have verified backups of all DCs before any changes.

- Snapshot Capability: Utilize VM snapshots for quick rollback if needed.

- Change Control: Rigorous change management process with approvals and communication plans.

- Phased Rollout: Upgrade DR first to minimize the risk to production.

- Skills and Resources: Ensure your IT team has expertise for Windows Server 2022 or arrange training/external support if needed.

#### IV. Capacity Planning

- New DCs: Determine if need to provision additional virtual machines (or physical servers if applicable).

- Resource Requirements: Estimate the CPU, RAM, and storage needed for the new Windows Server 2022 DCs based on your AD load.

#### V. Change Management

#### Stakeholder Identification: List everyone impacted by the upgrade:

- Banking application users and owners

- IT operations teams

- Network and security teams.

- Management for approvals

#### Communication Plan:

- Scheduled downtime notifications with ample notice.

- Updates on project progress.

- Clear instructions for users in case reconfiguration is needed on their side.

Approval Process: Outline the steps required for obtaining the necessary approvals at each stage of the project.

Rollback Plan: Create a detailed process for reverting changes if major problems occur.

### Phase 2: DR Site Upgrade

#### Build New 2022 AD Servers (DR):

Create new VMs with Windows Server 2022.

Install the Active Directory Domain Services role.

#### Promote to Domain Controllers:

Promote the new VMs to domain controllers in the existing 2016 domain.

Ensure thorough replication of Active Directory data.

#### Application Testing (DR):

Work with application owners to rigorously test core banking applications against the new 2022 AD servers in the DR environment.

#### Configure DNS (DR):

Update DNS records to point clients and applications to the new 2022 AD servers in the DR site.

#### Demote Old 2016 AD Servers (DR):

Gracefully demote the old Windows Server 2016 domain controllers.

Thoroughly monitor replication and DNS functionality post-demotion.

### Phase 3: Production Site Upgrade

#### Build New 2022 AD Servers (Production):(Replicate steps from DR)

- Promote to Domain Controllers

- Application Testing (Production)

- Configure DNS (Production)

- Demote Old 2016 AD Servers (Production)

### Phase 4: Post-Upgrade Monitoring and Maintenance

#### Monitoring:

- Ensure replication health between all domain controllers.

- Monitor application performance and user experience.

#### Maintenance:

- Implement a patch management strategy for the new Windows Server 2022 environment.

#### Best Practices - FSMO Roles

FSMO Transfer: Before demoting old servers, transfer FSMO roles gracefully to the new Windows Server 2022 DCs.

Placement: Ensure careful distribution of FSMO roles across multiple 2022 DCs for redundancy. Consider site affinity for roles based on physical site locations.

#### Key Considerations

Lab Environment: Always test the entire upgrade process in a non-production lab environment first. (If necessary)

Backups: Have comprehensive, tested backups of all Active Directory servers before starting.

Downtime: Schedule the upgrade during planned maintenance windows.

### Configuration Summary

- Move FSMO role to another domain controller.

- Demote domain controller on old server.

- Migrate certificate service.

- Switch IP between old and new server.

- promote domain controller on new server.

Configuration steps for each task along with the relevant Microsoft documentation.

#### 1. Move FSMO Roles to Another Domain Controller

- Identifying Existing FSMO Role Holders: Use the netdom query fsmo command to list the current FSMO role holders.

- Transferring Roles (GUI):

  - Open "Active Directory Users and Computers" or other relevant AD management tool.

  - Right-click on the domain, select "Operations Masters".

  - For each role (RID, PDC Emulator, Infrastructure, Domain Naming, Schema), click "Change" and select the target domain controller.

- Transferring Roles (PowerShell): Use the Move-ADDirectoryServerOperationMasterRole cmdlet.

  - Example: Move-ADDirectoryServerOperationMasterRole -Identity TargetDC -OperationMasterRole SchemaMaster

Microsoft Documentation:

- GUI Method: https://learn.microsoft.com/en-us/troubleshoot/windows-server/active-directory/view-transfer-fsmo-roles

- PowerShell Method: https://learn.microsoft.com/en-us/powershell/module/activedirectory/move-addirectoryserveroperationmasterrole

#### 2. Demote Domain Controller on Old Server

- Prerequisites:

  - FSMO roles must be transferred.

  - Ensure no critical services are solely reliant on this DC.

- GUI Method:

  - Server Manager -> Manage -> "Remove Roles and Features".

  - Uncheck "Active Directory Domain Services". Follow wizard.

- PowerShell: Uninstall-ADDSDomainController

  - Parameters allow for cleanup of metadata, forced removal, etc.

Microsoft Documentation:

- Demoting a Domain Controller: [Need to add the Microsoft URL]

#### 3. Migrate Certificate Services

- Complexity Varies: Process complexity depends on Certificate Authority (CA) type (Standalone vs. Enterprise) and security needs.

- General Outline:

  - Backup: Thoroughly backup CA database, keys, and configuration.

  - Install CA Role: Install the "Active Directory Certificate Services" role on the new server.

  - Restore/Configure: Restore CA database and configuration or follow steps for a new CA setup, potentially reissuing certificates depending on the configuration.

Microsoft Documentation:

- Backup/Restore: [Need to add the Microsoft URL]

- CA Migration (General guidance): [Need to add the Microsoft URL]

4. Switch IP Between Old and New Server

- Prerequisites: Verify that no other devices are using the IP Address you intend to assign.

- Methods:

  - Network Interface Configuration: Change the IP address settings directly on each server through the network adapter properties.

5. Promote Domain Controller on New Server

- Prerequisites:

  - Windows Server 2022 installed.

  - Network connectivity to existing domain.

  - Proper DNS configuration.

- GUI Method:

  - Server Manager -> Manage -> "Add Roles and Features".

  - Select "Active Directory Domain Services". Follow wizard.

- PowerShell: Install-ADDSForest

  - Include parameters for domain name, database paths, etc.

Microsoft Documentation:

- Promoting a Domain Controller: [Need to add the Microsoft URL]

| Category | Detail | Notes |
| --- | --- | --- |
| Metadata | Date/Time of Data Collection | Essential for pre/post upgrade distinction |
| Forest/Domain | Forest Functional Level, Domain Functional Level | Compatibility with Server 2022 |
| Domain Controllers | Hostname, OS version (Pre-Upgrade), Site, OS Version (Post-Upgrade) | Track pre/post states |
| FSMO Roles | Role, Server Holding Role (Pre-Upgrade), Server Holding Role (Post-Upgrade) | Verify successful FSMO transfer |
| DNS | DNS Server IPs, Zones, A/AAAA Records (ensure records are gathered both pre and post-upgrade) | Ensure post-upgrade resolution |
| Group Policies | GPO Names, Settings (focus on critical policies) | Policy backup location |
| AD Sites and Replication | Site Names, Subnets, Site Links, Schedules | Replication topology design for Server 2022 |
| Organizational Units | OU Names, Nested OU Structure, Purpose | Group Policy and delegation mapping |
| User/Computer Accounts | Key User Accounts, Group Memberships, Computer OUs | Permissions considerations |
| Trust Relationships | Domains/Forests Involved, Trust Type, Direction | Impact on external resource access |

# Get Forest Functional Level

(Get-ADForest).ForestMode

# Get Domain Functional Levels for all domains

Get-ADDomain | Select-Object DomainMode

# General replication status

repadmin /showrepl * /csv > replication_status.csv

# Comprehensive DC diagnostics (long-running)

dcdiag /v /c /e > dcdiag_report.txt

Get-ADForest | Select-Object SchemaMaster, DomainNamingMaster

Get-ADDomain | Select-Object RIDMaster, PDCEmulator, InfrastructureMaster

# List AD Sites

Get-ADReplicationSite -Filter *

# List Site Links

Get-ADReplicationSiteLink -Filter *

# Check replication health between sites (adjust site names)

Get-ADReplicationPartnerMetadata -Target "Default-First-Site-Name" -Partner "Another-Site"

# Check DNS SRV records for DCs

Resolve-DnsName -Type SRV _ldap._tcp.dc._msdcs.contoso.local

# Check DNS Server settings on each DC

Get-DnsServerSetting -ComputerName <DCName>

# List all GPOs in the domain

Get-GPO -All

# Get detailed report on a specific GPO

Get-GPOReport -Name "GPO Name" -ReportType Html -Path C:\GPO_Report.html

# Get Schema version

(Get-ADForest).SchemaMaster | Get-ADObject -Properties objectVersion

# Look for recent Schema modifications (if applicable)

Get-ADObject -SearchBase (Get-ADRootDSE).schemaNamingContext -LDAPFilter "(whenChanged>=<start-date>)" -Properties whenChanged

# Find stale user accounts (adjust inactivity period)

Search-ADAccount -AccountInactive -TimeSpan 90.00:00:00 | Select-Object Name, LastLogonDate

# Find stale computer accounts (adjust inactivity period)

Search-ADAccount -ComputersOnly -AccountInactive -TimeSpan 60.00:00:00 | Select-Object Name, LastLogonDate

# Sample script - needs refinement based on your environment

# Get list of domain joined computers (assuming apps run on these)

$computers = Get-ADComputer -Filter *

foreach($computer in $computers){

# Check for listening ports related to LDAP

$listeningLDAP =  -LocalPort 389,636 -OwningProcess (Get-Process -ComputerName $computer.Name)

if($listeningLDAP){

Write-Host "Potential LDAP-based app found on: " $computer.Name

# Further investigate process details in $listeningLDAP

}

}

# Basic health check

Get-ADDomainController -Filter * | ForEach-Object{

Test-ADReplication -Server $_.Name

}

# More in-depth using repadmin (https://docs.microsoft.com/en-us/windows-server/administration/windows-commands/repadmin)

repadmin /showrepl *

Get-GPO -All | Select-Object DisplayName, GPOStatus

Get-GPOReport -Name <GPO_Name> -ReportType HTML -Path C:\mygporeport.html

Get-ADDomainController -Filter * | Select-Object Hostname, OperatingSystem, Site

Get-DnsServerResourceRecord -ZoneName contoso.local | Where-Object RecordType -EQ 'A' -or RecordType -EQ 'AAAA'

Get-DnsServerResourceRecord -ZoneName contoso.local | Where-Object RecordType -in 'A', 'AAAA'